## Priorities table
0 | Pack | Pack name | L3 Due date | Hub | Expected File count* | JSON Requested File Count | Completed file count | Status | Remaining works | Commentary | Delivery Manager | L3 Date - 1 week (7 days) | * This data is taken from MPDT Detailed Design tracker PowerBi. This may not be relevent as this would contain the list of all files ever assinged to the IDR, some of which may have been completed pre 2024?
1 | 238.02 | Ladbroke Cutting Phase 3 - Remainder​ | 2024-11-27 | G2S | 13 | 13 | 13 | Complete | 0 |  |  | 2024-11-20
2 | UFDR 229.D | Banbury Road Main Works | 2024-12-04 | G2S | 7 | 7 | 7 | Complete | 0 |  |  | 2024-11-27
3 | 212.5 | Fencing, Landscaping and MAS (Southern L1 Packages) | 2024-12-09 | NC2A | 85 | 85 | 85 | Complete | 0 |  |  | 2024-12-02
4 | 202.1-3 | Small Dean Viaduct Network Rail Cutting Reinstatement | 2025-01-08 | NC2A | 4 | 4 | 4 | Complete | 0 |  |  | 2025-01-01
5 | 201.0-1 | South Heath Cutting and C2.T.3 | 2024-12-11 | NC2A | 22 | 22 | 22 | Complete | 0 |  |  | 2024-12-04
6 | UFDR 209.A | Thame Valley Oxford Road (Thames Water Main 6209/6210) | 2024-12-11 | NC2A | 3 | 3 | 3 | Complete | 0 |  |  | 2024-12-04
7 | 215.03 | Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | 2024-12-11 | CA | 44 | 44 | 44 | Complete | 0 |  |  | 2024-12-04
8 | 224.7 | Turweston Cutting Additional Landscape and Earthworks (New bunds) | 2024-12-11 | T2G | 10 | 9 | 9 | Complete | 0 | Correct as per MIDP |  | 2024-12-04
9 | UFDR 223.A | Featherbed Lane - Permanent Diversions | 2024-12-11 | T2G | 1 | 1 | 1 | Complete | 0 |  |  | 2024-12-04
10 | 233.01-3 | Chipping Warden Green Tunnel - Associated Assets South - Part 3 | 2024-12-11 | G2S | 32 | 32 | 32 | Complete | 0 |  |  | 2024-12-04
11 | 214.06 | Sheephouse Wood Bat Mitigation Structure - Full - Mesh panels | 2024-12-12 | CA | 7 | 2 | 2 | Incomplete | 0 | Awaiting 5 to be requested |  | 2024-12-05
12 | UFDR 211.A | Waddesdon (UKPN) | 2024-12-16 | NC2A | 6 | 6 | 6 | Complete | 0 |  |  | 2024-12-09
13 | 213.07-1 | Quainton Cutting Ancillary Civils Fencing and Planting | 2024-12-18 | CA | 34 | 33 | 33 | Complete | 0 | Correct as per MIDP |  | 2024-12-11
14 | UFDR 214.A | FCC Sidings | 2024-12-18 | CA | 7 | 7 | 7 | Complete | 0 |  |  | 2024-12-11
15 | UFDR 216.I | West St IP Gas Permanent diversion | 2024-12-18 | CA | 2 | 2 | 2 | Complete | 0 |  |  | 2024-12-11
16 | 202.5-2 | Small Dean North Embankment ( Remainder) | 2025-01-08 | NC2A | 1 | 1 | 1 | Complete | 0 |  |  | 2025-01-01
17 | 229.01-2 | Greatworth Green Tunnel Portal North | 2025-01-22 | G2S | 30 | 28 | 28 | Complete | 0 | Correct as per MIDP |  | 2025-01-15
19 | 202.5-2_2 | Small Dean North Embankment - Grove Farm Accommodation Underbridge and track drainage | Mar | NC2A | 1 | 1 | 1 | Complete | 0 |  |  | 2025-01-01
20 | 219.1 | Noise Barriers | Mar | T2G | 10 | 1 | 1 | Complete | 0 | Expecting JSON requests. |  | 2025-01-08
18 | 222.9 | Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | 2025-01-22 | T2G | 102 | 74 | 74 | Incomplete | 0 | Awaiting 29 to be requested |  | 2025-01-15
21 | 214.07 | Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | Feb |  | 43 | 21 | 21 | Incomplete | 0 | Awaiting 20 to be requested |  | Date not clear
22 | UFDR 202.B | ​Rocky Lane (UKPN 1203, Thames Water Main 6200, BT Openreach 3101)​ | Feb |  | 5 | 5 | 5 | Complete | 0 |  |  | Date not clear
23 | 204.1-1 | Wendover North Cutting re-submission (to include Wendover North Cutting Portal Access Road​ | Mar |  | 9 | 6 | 6 | Incomplete | 0 | Awaiting 3 to be requested |  | Date not clear
24 | 214.08 | Greatmoor (FCC) Sidings (structure & drainage) ​ | Mar |  | 8 | 1 | 1 | Complete | 0 | Correct as per MIDP |  | Date not clear
Formulas:
L3 Date - 1 week (7 days) = Table3[[#This Row],[[Delivery Manager, row below] Due date]]-7
L3 Date - 1 week (7 days) = Table3[[#This Row],[[Delivery Manager] Due date]]-7

## Analysis
Run rate | Total | Lee | Supriyan | Rakesh
2024-04-01 | 35 | 16 | 19 | 0
2024-04-08 | 26 | 19 | 7 | 0
2024-04-15 | 27 | 12 | 14 | 0
2024-04-22 | 58 | 38 | 20 | 0
2024-04-29 | 57 | 22 | 35 | 0
2024-05-06 | 37 | 4 | 16 | 12
2024-05-13 | 21 | 6 | 9 | 6
2024-05-20 | 27 | 17 | 2 | 8
2024-05-27 | 51 | 2 | 20 | 27
2024-06-03 | 66 | 15 | 22 | 29
2024-06-10 | 51 | 16 | 12 | 23
2024-06-17 | 22 | 19 | 0 | 3
2024-06-24 | 12 | 4 | 3 | 5
2024-07-01 | 17 | 3 | 11 | 3
2024-07-08 | 42 | 13 | 16 | 13
2024-07-15 | 19 | 10 | 7 | 2
2024-07-22 | 52 | 30 | 7 | 15
2024-07-29 | 60 | 26 | 19 | 15
2024-08-05 | 41 | 21 | 11 | 9
2024-08-12 | 27 | 15 | 7 | 5
2024-08-19 | 48 | 23 | 18 | 7
2024-08-26 | 21 | 0 | 9 | 12
2024-09-02 | 10 | 1 | 7 | 2
2024-09-09 | 15 | 8 | 5 | 2
2024-09-16 | 61 | 39 | 16 | 6
2024-09-23 | 22 | 9 | 6 | 7
2024-09-30 | 20 | 7 | 10 | 3
2024-10-07 | 11 | 4 | 5 | 2
2024-10-14 | 16 | 5 | 5 | 6
2024-10-21 | 32 | 9 | 7 | 16
2024-10-28 | 30 | 13 | 8 | 9
2024-11-04 | 52 | 30 | 11 | 11
2024-11-11 | 61 | 22 | 11 | 28
2024-11-18 | 45 | 21 | 11 | 13
2024-11-25 | 37 | 16 | 11 | 10
2024-12-02 | 36 | 21 | 9 | 6
2024-12-09 | 35 | 25 | 10 | 0
Total | 55 | 24.7 | 11 | 15

## Central_Team
PRIORITY R.A.G. | IDR / UFDR | UAID_2 | L2 Asset Name | ACBOS/MPDT Link | Revision Submitted for JSON Works | Request sent on (Date) | Compliant source file received on (Date) | Completion date. | Immediate process requested. | JSON Path | Coordinate Check CE | Comments Issued 1 (include Date) | Response Date1 | Comments 2 (include Date) | Response Date2 | Comment 3 (include Date) | Response Date3 | Comment 4 (include Date) | Response Date4 | Status | Action by | Requester Name / Email | *KPI - Measure1* | *KPI - Measure2* | *KPI - Measure3*
| 233.01-2 | HS2-00002NJ06 | Chipping Warden Green Tunnel North Portal | 1MC07-CEK-TN-FRM-CS07_CL14-000001 | P02 | 2023-10-31 | 2023-11-07 | 2023-11-08 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600042 |  | update rcvd 3/11/23 - CM_ISCI set to YES |  | edited in house liaising with DT to get them to update MPDT on PW. |  | DT can update PW file post JSON creation |  |  |  | 10 - Complete | Lee | Matthew Smith <MWSH@cowi.com> | 1 | 3 | 7
| 236.01 | HS2-00002XCBC | Oxford Canal South Embankment Ditch Crossing 1 | 1MC07-ASC-CV-FRM-CS07_CL23-000068-ACBOS | P01 | 2023-10-31 | 2023-11-03 | 2023-11-10 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600109 |  | StrctrlT |  | updated in house into SQL / Json |  | PW file to follow sync |  |  |  | 10 - Complete | Lee | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 5 | 3 | 3
| 216.01 | HS2-00002CT9B | Charndon Lodge Pumping Station (ME) | 1MC06-CEK-ME-FRM-CS06_CL09-600001 | P05 | 2023-10-31 |  | 2024-12-13 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600197 | No issues | rvsd chacks 19-nov-24 - ZZ-ZZ class issues | 2024-12-11 | 92 assts - loading |  | LOADED - 92 |  | 92 |  | 10 - Complete | Lee | Stafford, Quincy <quincy.stafford@arcadis.com> | 282 | 4
| 216.01 | HS2-00002CT9B | Charndon Lodge Pumping Station (EL) Telecomms | 1MC06-CEK-EL-FRM-CS06_CL09-600002 | P06 | 2023-10-31 |  | 2024-12-13 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600197 | No issues | rvsd chacks 19-nov-24 - ZZ-ZZ class issues | 2024-12-11 | 7 loadinn g |  | LOADED - 7 |  | 99 |  | 10 - Complete | Lee | Stafford, Quincy <quincy.stafford@arcadis.com> | 282 | 4
| 216.01 | HS2-00002CT9B | Charndon Lodge Pumping Station (EL) | 1MC06-CEK-EL-FRM-CS06_CL09-600001 | P01 | 2023-10-31 |  | 2024-12-13 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600197 | No issues | rvsd chacks 19-nov-24 - ZZ-ZZ class issues | 2024-12-11 | 13 loading |  | LOADED 13 |  | 112 |  | 10 - Complete | Lee | Stafford, Quincy <quincy.stafford@arcadis.com> | 282 | 4
| 216.01 | HS2-00002CT9B | Charndon Lodge Pumping Station (CV) | 1MC06-CEK-CV-FRM-CS06_CL09-000014 | P01 | 2023-10-31 |  | 2024-12-13 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600197 | No issues | rvsd chacks 19-nov-24 - ZZ-ZZ class issues | 2024-12-11 | 59 loading |  | LOADED 59 |  | 171 |  | 10 - Complete | Lee | Stafford, Quincy <quincy.stafford@arcadis.com> | 282 | 4
| 204.3-1 | HS2-00002BJS0 | Nash Lee Orchard (ELL-20) Footpath Realignment | 1MC06-ASC-HW-FRM-CS03_CL17-000006-ACBOS | P01 | 2023-11-01 | 2023-11-03 | 2023-11-03 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600011 |  | some items set As None All AssetDescription_2 incorrect | [7 empty] | 10 - Complete | Lee | Thompson, Stephen <stephen.thompson@arcadis.com> | 0 | 1 | 2
| 236.01 | HS2-00003B585 | Oxford Canal South Embankment Ditch Crossing 2 | 1MC07-ASC-CV-FRM-CS07_CL23-000069-ACBOS | P01 | 2023-11-01 | 2023-11-03 | 2023-11-10 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600110 |  | StrctrlT |  | updated in house into SQL / Json |  | PW file to follow sync |  |  |  | 10 - Complete | Lee | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 5 | 3 | 2
| 216.01-2 | HS2-00002CT8U | HS2-00002C5T4-West Street Drainage System | 1MC06-ASC-DR-FRM-CS06_CL09-000029-ACBOS | P01 | 2023-11-02 | 2023-11-03 | 2023-11-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600255 |  | 2 DsgnFlw att set to 0 - DT to fix | [7 empty] | 10 - Complete | Lee | Rai C, Keerthan <keerthan.raic@arcadis.com> | 1 | 1 | 1
| 230.01 | HS2-00002PRWV | Lower Thorpe Viaduct Group | 1MC07-ASC-CV-FRM-CS07_CL26-000069-ACBOS | P01 | 2023-11-02 |  | 2023-11-07 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600131 | [9 empty] | 10 - Complete | Supriyan | PATIL, APOORVA <apoorva.patil@arcadis.com> | 3 | 0
| 223.4 | HS2-00002BJV0 | Bridleway 303/4 and 303/22 Diversions | 1MC06-ASC-HW-FRM-CS06_CL22-000015-ACBOS | P01 | 2023-11-02 | 2023-11-07 | 2023-11-09 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600110 |  | Send Queries to Team on 07-Nov-23 | [7 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 2 | 1 | 5
| 223.4 | HS2-00002BJV1 | Maintenance Access Road to Pond (Off Bridleway 303/4) 01 | 1MC06-ASC-HW-FRM-CS06_CL22-000009-ACBOS | P01 | 2023-11-02 | 2023-11-07 | 2023-11-10 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600080 |  | Send Queries to Team on 07-Nov-23 | [7 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 3 | 1 | 5
| 223.4 | HS2-00002BJV2 | Maintenance Access Road to Pond (Off Bridleway 303/4) 02 | 1MC06-ASC-HW-FRM-CS06_CL22-000010-ACBOS | P01 | 2023-11-02 | 2023-11-07 | 2023-11-16 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600081 |  | Send Queries to Team on 07-Nov-23 | [7 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 7 | 1 | 5
| 223.4 | HS2-00002BJV3 | Bridleway 303/5 Link | 1MC06-ASC-HW-FRM-CS06_CL22-900011-ACBOS | P01 | 2023-11-02 | 2023-11-07 | 2023-11-09 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600087 |  | Send Queries to Team on 07-Nov-23 | [7 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 2 | 1 | 5
| 223.4 | HS2-00002J4YM | Bridleway 303/4 Accommodation Access Realignment | 1MC06-ASC-HW-FRM-CS06_CL22-900005-ACBOS | P01 | 2023-11-02 | 2023-11-07 | 2023-11-29 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600039 |  | Send Queries to Team on 07-Nov-23 | [7 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 16 | 1 | 5
| 235.01-1 | HS2-000001456 | Footpath SM101 Green Overbridge | 1MC07-ASC-BR-FRM-CS07_CL14-000002-ACBOS | P02 | 2023-11-07 |  | 2023-11-14 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600018 |  | FAIL - close to zero rebar - DT investigating - MONDAY |  | revised file rcvd 13-11-23 | [5 empty] | 10 - Complete | Lee | Kumar, M Praveen <mpraveen.kumar@arcadis.com> | 5 | 2
| 237.02 | HS2-00002EL0S | C3.L.81 Catchment | 1MC07-ASC-DR-FRM-CS07_CL23-000022-ACBOS | P02 | 2023-11-07 |  | 2023-11-08 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600019 | [9 empty] | 10 - Complete | Supriyan | B, Gopika <gopika.b@arcadis.com> | 1 | 0
| 237.02 | HS2-00002CTJT | C3.T.70 Catchment | 1MC07-ASC-DR-FRM-CS07_CL23-000004-ACBOS | P01 | 2023-11-07 | 2023-11-07 | 2023-11-08 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600059 | [9 empty] | 10 - Complete | Lee | B, Gopika <gopika.b@arcadis.com> | 1 | 0 | 0
| 218.02-1 | HS2-00002KRAM | IMD East Culvert Watercourse Diversion | 1MC06-ASC-DR-FRM-CS06_CL09-000097-ACBOS | P02 | 2023-11-08 | 2023-11-09 | 2023-11-10 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600166 | [9 empty] | 10 - Complete | Lee | Somashekar, Yashwanth KumarS <YashwanthKumar.S.Somashekar@arcadis.com> | 1 | 0 | 1
| 220.5 | HS2-00002BJUL | Maintenance Access Road MAP (Bridleway CHW/24 Upgrade) | 1MC06-ASC-HW-FRM-CS06_CL10-900029-ACBOS | P02 | 2023-11-08 | 2023-11-24 | 2023-11-27 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600089 |  | DT revising file based on LodG 22-11-23 |  | DT reworking model. Barriers / post issues | [5 empty] | 10 - Complete | Supriyan | KHABOUZE Zakaria <zakaria.khabouze@setec.com> | 1 | 2 | 16
| 220.5 | HS2-00002BJUM | Maintenance Access Road to Pond and MAP (Footpath 225-4 Upgrade) | 1MC06-ASC-HW-FRM-CS06_CL10-000024-ACBOS | P01 | 2023-11-08 | 2023-11-10 | 2023-11-13 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600084 |  | DT HAVE MADE CHANGES AND REISSUED | [7 empty] | 10 - Complete | Lee | KHABOUZE Zakaria <zakaria.khabouze@setec.com> | 1 | 1 | 2
| 220.5 | HS2-00002J4YG | Bridleway CHW/24 Link | 1MC06-ASC-HW-FRM-CS06_CL10-000022-ACBOS | P01 - still | 2023-11-08 | 2023-11-14 | 2023-11-15 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600054 |  | DT HAVE MADE CHANGES AND REISSUED | [7 empty] | 10 - Complete | Lee | KHABOUZE Zakaria <zakaria.khabouze@setec.com> | 1 | 1 | 6
| 209.2-3 | HS2-00002CT64 | River Thame Watercourse Diversion | 1MC06-ASC-DR-FRM-CS04_CL19-000044-ACBOS | P04 | 2023-11-09 | 2023-11-16 | 2023-11-17 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600001 |  | revised file rcvd 16-nov-23 | [7 empty] | 10 - Complete | Lee | SS, Saravanakumar <saravanakumar.ss@arcadis.com> | 1 | 1 | 7
| 202.4-4 | HS2-00002U7JY | Rocky Lane Ditch Slab | 1MC06-ASC-CV-FRM-CS03_CL05-000056-ACBOS | P01 | 2023-11-09 | 2023-11-14 | 2023-11-14 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600160 |  | Send back on 13-Nov-23, few mismatch w.r.t MPDT | [7 empty] | 10 - Complete | Supriyan | S, Supreeth <Supreeth.S@arcadis.com> & Tilici, Andreea <andreea.tilici@arcadis.com> | 0 | 1 | 5
| 223.4 | HS2-00002VNJ2 | Westbury Embankment - Ancillary Culvert 092 - AC2 | 1MC06-ASC-DR-FRM-CS06_CL22-000039-ACBOS | P01 | 2023-11-09 |  | 2023-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600119 | [9 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 3 | 0
| 223.4 | HS2-00002BVJ7 | C2.L.104 Catchment | 1MC06-ASC-DR-FRM-CS06_CL22-000004-ACBOS | P01.1 | 2023-11-10 |  | 2023-11-29 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600088 | [9 empty] | 10 - Complete | Supriyan | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 13 | 0
| 214.04 | HS2-000001307 | HS2-000001307 - Bridleway QUA/36 Accommodation Green Overbridge | 1MC06-CEK-BR-FRM-CS05-000002 | P06 | 2023-11-10 | 2023-12-13 |  |  | 1MC06-CEK-IM-DAT-CS05-600115 |  | Wrong HS2 Asset Class, send back on 14th Nov |  | Com_Type issue, send back on 18th Dec | [5 empty] | 99 - Cancelled | Supriyan | Fowler, Alex <alex.fowler@arcadis.com>
| 236.03 | HS2-000020P08 | Bridleway SM116 Realignment | 1MC07-ASC-HW-FRM-CS07_CL23-000031-ACBOS | P01 | 2023-11-13 | 2023-11-20 | 2023-11-22 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600046 |  | DsgnLf incomplete / Sdlsp spaces / Com_typs |  | revised file rcvd 20-11-23 | [5 empty] | 10 - Complete | Lee | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 2 | 2 | 7
| 236.03 | HS2-000025B3J | Accommodation Access Road (Under Oxford Canal Viaduct) | 1MC07-ASC-HW-FRM-CS07_CL23-000039-ACBOS | P01 | 2023-11-13 | 2023-11-15 | 2023-11-16 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600047 |  | ok Com_typ passable. | [7 empty] | 10 - Complete | Lee | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 1 | 1 | 2
| 235.01-2 | HS2-00002CX3F | Footpath SM101 Drainage System | 1MC07-ASC-DR-FRM-CS07_CL14-000027-ACBOS | P01 | 2023-11-14 | 2023-11-21 |  |  | 1MC07-CEK-IM-DAT-CS07_CL14-600002 |  | AssetName_2 / AssetDescription_2 / Com_typs all incorrect |  | revised file 21-11-23 | [5 empty] | 99 - Cancelled | Lee | Kumar, Pranav <pranav.kumar@arcadis.com>
| 218.02-1 | HS2-00002NSXP | OXD Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL09-000083-ACBOS | P01 | 2023-11-14 | 2023-11-15 | 2023-11-16 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600180 |  | Asset Name Mismatch, send back on 15-Nov-2023 | [7 empty] | 10 - Complete | Supriyan | Whyte, William <William.Whyte@arcadis.com> | 1 | 1 | 1
| 218.02-1 | HS2-00002NSXQ | OXD Boundary/ Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL09-000081-ACBOS | P01 | 2023-11-14 | 2023-11-15 | 2023-11-17 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600181 |  | Asset Name Mismatch, send back on 15-Nov-2023 | [7 empty] | 10 - Complete | Supriyan | Whyte, William <William.Whyte@arcadis.com> | 2 | 1 | 1
| 202.5-4 | HS2-00002Y8VP | Grove Farm Culvert Attenuation Tank | 1MC06-ASC-CV-FRM-CS03_CL06-000035-ACBOS | P02 | 2023-11-14 | 2023-11-17 | 2023-11-20 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600085 |  | many confirmations and lots of imcomplete items. |  | revised file rcvd 17-nov-23 | [5 empty] | 10 - Complete | Lee | Young, Sara <sara.young1@arcadis.com> | 1 | 2 | 3
| 220.5 | HS2-00002Y4JH | 084-AC2 Watercourse Diversion | 1MC06-ASC-DR-FRM-CS06_CL10-000114-ACBOS | P01 | 2023-11-14 | 2023-11-15 | 2023-11-16 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600124 |  | Wrong UAID_1, send back on 15th Nov | [7 empty] | 10 - Complete | Supriyan | Lorusso, Alberto <alberto.lorusso@arcadis.com> | 1 | 1 | 1
| 211.1 | HS2-00002BVG2 | Waddesdon South Cutting Landscape Earthworks | 1MC06-ASC-GT-FRM-CS04_CL20-000010-ACBOS | P04 | 2023-11-14 | 2023-11-17 | 2023-11-20 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600136 |  | Send back queires on 15th Nov | [7 empty] | 10 - Complete | Lee | Agata Woroch <AGWO@cowi.com> | 1 | 1 | 3
| 215.02-2 | HS2-00002CX36 | Civil 3D Solids Model - P-RAI-0799 | 1MC06-ASC-DR-FRM-CS06_CL09-000037-ACBOS | P01 | 2023-11-15 | 2023-11-17 |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600209 |  | PCRA workflow not completed, send back on 16th Nov |  | Many erroers, send back on 17th Nov | [5 empty] | 99 - Cancelled | Supriyan | samar.nouma@setec.com
| 215.02-2 | HS2-00002CT8V | Civil 3D Solids Model - P-RAI-0786 | 1MC06-ASC-DR-FRM-CS06_CL09-000035-ACBOS | P01 | 2023-11-15 |  | 2023-11-21 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600199 |  | PCRA workflow not completed, send back on 16th Nov | [7 empty] | 10 - Complete | Supriyan | samar.nouma@setec.com | 4 | 1
| 215.02-2 | HS2-00002CX35 | Civil 3D Solids Model - P-RAI-0795 | 1MC06-ASC-DR-FRM-CS06_CL09-000011-ACBOS | P01 | 2023-11-15 | 2023-11-16 |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600220 |  | PCRA workflow not completed, send back on 16th Nov | [7 empty] | 99 - Cancelled | Supriyan | samar.nouma@setec.com
| 211.1 | HS2-000001036 | Waddesdon South Cutting Phase 2 (Full Package) L3 - Waddesdon South Cutting | 1MC06-ASC-GT-FRM-CS04_CL20-000005-ACBOS | P04 | 2023-11-16 | 2023-11-16 | 2023-11-17 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600132 |  | Send back on 13-Nov-23, duplicate record found | [7 empty] | 10 - Complete | Supriyan | Agata Woroch <AGWO@cowi.com> | 1 | 1 | 0
| 209.2-2 | HS2-00002Y0AS | Bear Brook Overflow Watercourse Diversion | 1MC06-ASC-DR-FRM-CS04_CL19-000049-ACBOS | P01 | 2023-11-17 | 2023-11-28 | 2023-11-29 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600049 |  | AssetDescription_2 incorrect on all assets and Cats. |  | DT revising MPDT to WT-OW Ordinary watercourse for AssetDescription_2 22-Nov-23 |  | updated 28-Nov-23. |  |  |  | 10 - Complete | Lee | C, Venkatesh <venkatesh.chavan@arcadis.com> | 1 | 3 | 11
| 236.01 | HS2-00003B5AL | Oxford Canal South Embankment Access Stairs to Culvert Up Main | 1MC07-ASC-CV-FRM-CS07_CL23-000062-ACBOS | P01 | 2023-11-17 |  | 2023-11-21 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600111 | [9 empty] | 10 - Complete | Supriyan | chris.gilmour@fairhurst.co.uk | 2 | 0
| 236.01 | HS2-00002V04G | Oxford Canal South Embankment Access Stairs to Culvert Up Main | 1MC07-ASC-CV-FRM-CS07_CL23-000067-ACBOS | P02 | 2023-11-17 | 2023-11-17 | 2023-11-21 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600108 | [9 empty] | 10 - Complete | Lee | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 2 | 0 | 0
| 230.01 | HS2-000020NW9 | Maintenance Access Road to Pond (Off Banbury Lane SW) | 1MC07-ASC-HW-FRM-CS07_CL26-000028-ACBOS | P04 | 2023-11-17 | 2023-11-21 | 2023-11-23 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600010 |  | clarifications |  | revised file 21-11-23 |  | data checker seeminlgy stuck with old JSON, current one uploaded at 10.19 this morning |  |  |  | 10 - Complete | Lee | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 2 | 3 | 4
| 204.2 | HS2-000001399 | Mill House South Culvert | 1MC06-ASC-CV-FRM-CS03_CL17-000025-ACBOS | P02 | 2023-11-17 | 2023-11-20 | 2023-11-21 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600007 |  | clarifications |  | revised file 20-11-23 |  | need placeholder. |  |  |  | 10 - Complete | Lee | Sangalang, Orlando <orlando.sangalang@arcadis.com> | 1 | 3 | 3
| 218.02-1 | HS2-00002TMWU | Calvert IMD Crossover UTX No 1 | 1MC06-ASC-CV-FRM-CS06_CL10-000056-ACBOS | P01 | 2023-11-20 | 2023-11-22 | 2023-11-22 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600036 |  | revised file rcvd 21-11-23 |  | revised file 22-11-23 | [5 empty] | 10 - Complete | lee | Mehta, Jeet <jeet.mehta@arcadis.com> | 0 | 2 | 2
| 218.02-1 | HS2-00002TMWV | Calvert IMD Crossover UTX No 2 | 1MC06-ASC-CV-FRM-CS06_CL10-000057-ACBOS | P01 | 2023-11-20 | 2023-11-22 | 2023-11-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600041 |  | revised file rcvd 21-11-23 |  | revised file 22-11-23 | [5 empty] | 10 - Complete | lee | Mehta, Jeet <jeet.mehta@arcadis.com> | 1 | 2 | 2
| 218.02-1 | HS2-00002TMWW | Calvert IMD Crossover UTX No 3 | 1MC06-ASC-CV-FRM-CS06_CL10-000058-ACBOS | P01 | 2023-11-20 | 2023-11-22 | 2023-11-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600040 |  | revised file rcvd 21-11-23 |  | revised file 22-11-23 |  | 2 missing StrctrlIT in PCE |  |  |  | 10 - Complete | lee | Mehta, Jeet <jeet.mehta@arcadis.com> | 1 | 3 | 2
| 213.01-1 | HS2-00002CW1G | Station Road Drainage System | 1MC06-ASC-DR-FRM-CS04_CL20-000014-ACBOS | P01 | 2023-11-20 | 2023-11-22 | 2023-11-22 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600007 |  | CM_ISCI 1 value set as YES |  | fixed 22-11-23 | [5 empty] | 10 - Complete | Lee | Quadery, Riad <riad.quadery@arcadis.com> | 0 | 2 | 2
| 218.02-1 | HS2-00002KRAM | IMD East Culvert Watercourse Diversion | 1MC06-ASC-DR-FRM-CS06_CL09-000097-ACBOS | P03 | 2023-11-21 | 2023-11-21 | 2023-11-21 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600166 | [9 empty] | 10 - Complete | Supriyan | YashwanthKumar.S.Somashekar@arcadis.com | 0 | 0 | 0
| 218.02-1 | HS2-00002KRAL | IMD West Culvert Watercourse Diversion | 1MC06-ASC-DR-FRM-CS06_CL09-000098-ACBOS | P03 | 2023-11-21 | 2023-11-24 | 2023-11-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600169 |  | Feedbacks provided on 23rd |  | revised file 24-11-23 |  | Some discipline items updated in house - ACBOS - SQL - JSON complete - uploaded to PW for PCRA 27-Nov-23 |  |  |  | 10 - Complete | Lee | Tiwari, Devendrakumar <devendrakumar.tiwari@arcadis.com> | 1 | 3 | 3
| 236.01 | HS2-00003B5AM | Oxford Canal South Embankment Access Stairs to Underpass Down Main | 1MC07-ASC-CV-FRM-CS07_CL23-000063-ACBOS | P01 | 2023-11-21 | 2023-11-23 | 2023-11-23 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600112 |  | rebar / block work contradictions in STW |  | DT confirmed this is expected | [5 empty] | 10 - Complete | Lee | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 0 | 2 | 2
| 236.01 | HS2-00003B5AP | Oxford Canal South Embankment Access Stairs to Underpass Up Main | 1MC07-ASC-CV-FRM-CS07_CL23-000064-ACBOS | P01 | 2023-11-21 | 2023-11-21 | 2023-11-23 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600113 |  | rebar / block work contradictions in STW |  | DT confirmed this is expected | [5 empty] | 10 - Complete | Lee | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 2 | 2 | 0
| 236.01 | HS2-00003B5AR | Oxford Canal South Embankment Access Stairs to Viaduct Down Main | 1MC07-ASC-CV-FRM-CS07_CL23-000065-ACBOS | P01 | 2023-11-21 | 2023-11-21 | 2023-11-23 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600114 |  | rebar / block work contradictions in STW |  | DT confirmed this is expected | [5 empty] | 10 - Complete | Lee | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 2 | 2 | 0
| 236.01 | HS2-00003B5AU | Oxford Canal South Embankment Access Stairs to Viaduct Up Main | 1MC07-ASC-CV-FRM-CS07_CL23-000066-ACBOS | P01 | 2023-11-21 | 2023-11-23 | 2023-11-23 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600115 |  | rebar / block work contradictions in STW |  | DT confirmed this is expected | [5 empty] | 10 - Complete | Lee | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 0 | 2 | 2
| 209.2-3 | HS2-000020C0Z | Flood Compensation Area-065 | 1MC06-ASC-DR-FRM-CS04_CL19-000031-ACBOS | P01 | 2023-11-22 | 2023-11-24 | 2023-11-24 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600088 |  | Few Errors, send back on 22nd Nov | [7 empty] | 10 - Complete | Supriyan | srinatha.ka@arcadis.com | 0 | 1 | 2
| 209.1 | HS2-00002CT5T | C2.T.30 | 1MC06-ASC-DR-FRM-CS04_CL19-000007-ACBOS | P04 | 2023-11-22 | 2023-11-22 | 2023-11-22 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600046 |  | DT failed DAC sign off - revised file. |  | incorrect metrics |  | revised file rcvd |  | at insistance from DT PM In house update to ACBOS made for 14 CM_chg / CRT values for consistancy and PCRA. Parent ACBOS will be updated tomorrow by DT to match |  | 10 - Complete | Lee | Christopher Hackett <crht@cowi.com> | 0 | 4 | 0
| 218.02-1 | HS2-00002VK47 | EWR culvert watercourse diversion MAS crossing | 1MC06-ASC-CV-FRM-CS06_CL09-000042-ACBOS | P01 | 2023-11-23 | 2023-11-27 | 2023-11-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600261 | [9 empty] | 10 - Complete | Lee | Ul Mashood, Hammad <hammad.mashood@arcadis.com> | 0 | 0 | 4
| 218.02-1 | HS2-0000307ZQ | IMD East Watercourse Pedestrian Crossing 1 | 1MC06-ASC-CV-FRM-CS06_CL09-000073-ACBOS | P01 | 2023-11-23 | 2023-11-27 | 2023-11-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600259 |  | Com_Dscrptns all incorrect |  | 2 clarifications rqrd. | [5 empty] | 10 - Complete | Lee | Ul Mashood, Hammad <hammad.mashood@arcadis.com> | 2 | 2 | 4
| 218.02-1 | HS2-0000307ZR | IMD East Watercourse Pedestrian Crossing 2 | 1MC06-ASC-CV-FRM-CS06_CL09-000074-ACBOS | P01 | 2023-11-23 | 2023-11-27 | 2023-11-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600260 | [9 empty] | 10 - Complete | Lee | Ul Mashood, Hammad <hammad.mashood@arcadis.com> | 0 | 0 | 4
| 223.4 | HS2-00002BJV0 | Bridleway 303/4 and 303/22 Diversions | 1MC06-ASC-HW-FRM-CS06_CL22-000015-ACBOS | P01 | 2023-11-24 | 2023-11-27 | 2023-11-27 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600110 | [9 empty] | 10 - Complete | Supriyan | zakaria.khabouze@setec.com> | 0 | 0 | 3
| 223.4 | HS2-00002BJV1 | Maintenance Access Road to Pond (Off Bridleway 303/4) 01 | 1MC06-ASC-HW-FRM-CS06_CL22-000009-ACBOS | P01 | 2023-11-24 | 2023-11-27 | 2023-11-27 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600080 | [9 empty] | 10 - Complete | Supriyan | zakaria.khabouze@setec.com> | 0 | 0 | 3
| 223.4 | HS2-00002BJV2 | Maintenance Access Road to Pond (Off Bridleway 303/4) 02 | 1MC06-ASC-HW-FRM-CS06_CL22-000010-ACBOS | P01 | 2023-11-24 | 2023-11-27 | 2023-11-27 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600081 | [9 empty] | 10 - Complete | Supriyan | zakaria.khabouze@setec.com> | 0 | 0 | 3
| 226.1 | HS2-00002TMF0 | Whitfield ATS Telecoms | 1MC07-ASC-UT-FRM-CS07_CL12-000090-ACBOS | P01 | 2023-11-28 | 2023-12-01 | 2023-12-04 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600054 |  | all asset description 2 incorrect |  | some Com_RfrncNmbr incorrect |  | revised 30-nov-23 |  |  |  | 10 - Complete | Lee | B, Bharath Kumar <bharathkumar.b@arcadis.com> | 1 | 3 | 3
| 236.03 | HS2-000020P0F | Maintenance Access Road to Pond (Off Wills Pastures Road) | 1MC07-ASC-HW-FRM-CS07_CL23-000033-ACBOS | P01 | 2023-11-29 | 2023-12-01 | 2023-12-05 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600044 | [9 empty] | 10 - Complete | Supriyan | veenadhari.bavanam@arcadis.com> | 2 | 0 | 2
| 236.03 | HS2-00002U6LN | Bridleway SM95 Extension | 1MC07-ASC-HW-FRM-CS07_CL23-000044-ACBOS | P01 | 2023-11-29 | 2023-12-01 | 2023-12-05 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600107 | [9 empty] | 10 - Complete | Supriyan | veenadhari.bavanam@arcadis.com> | 2 | 0 | 2
| 224.4 | HS2-000020NPE | Turweston Farm Track (TUW/4) Realignment | 1MC06-ASC-HW-FRM-CS06_CL22-000004-ACBOS | P02 | 2023-11-30 | 2023-12-04 | 2023-12-06 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600108 |  | rvsd file 4-12-23 | [7 empty] | 10 - Complete | Lee | zakaria.khabouze@setec.com | 2 | 1 | 4
| 224.4 | HS2-000020RNJ | Footpath TUW/3 Diversion 3D Model | 1MC06-ASC-HW-FRM-CS06_CL22-000014-ACBOS | P02 | 2023-11-30 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL22-600109 |  | com_typ/Dscrptn some zero values to be confirmed | [7 empty] | 99 - Cancelled | Lee | zakaria.khabouze@setec.com
| 224.4 | HS2-00002BJV5 | Bridleway TUW/9 Diversion | 1MC06-ASC-HW-FRM-CS06_CL22-000013-ACBOS | P02 | 2023-11-30 | 2023-12-04 | 2023-12-06 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600094 |  | rvsd file 4-12-23 | [7 empty] | 10 - Complete | Lee | zakaria.khabouze@setec.com | 2 | 1 | 4
| 217.03 | HS2-00002CT8S | Addison Road Drainage System | 1MC06-ASC-DR-FRM-CS06_CL09-000027-ACBOS | P01 | 2023-11-30 | 2023-12-01 | 2023-12-04 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600110 | [9 empty] | 10 - Complete | Lee | Rai C, Keerthan <keerthan.raic@arcadis.com> | 1 | 0 | 1
| 222.2 | HS2-00002N7WG | Barton to Mixbury Cutting - Ancillary Culvert 088-AC1 | 1MC06-ASC-DR-FRM-CS06_CL21-000049-ACBOS | P02 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600016 | [9 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 1 | 0 | 0
| 222.2 | HS2-00002N7WH | Barton to Mixbury Cutting - Ancillary Culvert 088-AC2 | 1MC06-ASC-DR-FRM-CS06_CL21-000059-ACBOS | P02 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600009 | [9 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 1 | 0 | 0
| 222.2 | HS2-00002N7WJ | Barton to Mixbury Cutting - Ancillary Culvert 088-AC3 | 1MC06-ASC-DR-FRM-CS06_CL21-000060-ACBOS | P02 | 2023-12-04 | 2023-12-04 | 2023-12-06 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600003 | [9 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 2 | 0 | 0
| 220.5 | HS2-00002Y0RV | Bridleway CHW/24 Overbridge | 1MC06-ASC-BR-FRM-CS06_CL10-900001 | P01 | 2023-12-04 | 2023-12-04 | 2023-12-07 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600125 | [9 empty] | 10 - Complete | Lee | guillaume.hervoches@setec.com | 3 | 0 | 0
| 236.03 | HS2-00002CTJN | Oxford Canal North Embankment Boundary/Perimeter Fence Line | 1MC07-ASC-CV-FRM-CS07_CL23-000017-ACBOS | P01 | 2023-12-05 | 2023-12-05 | 2023-12-06 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600066 | [9 empty] | 10 - Complete | Supriyan | Duggina, Jayaram <jayaram.duggina@arcadis.com> | 1 | 0 | 0
| 236.03 | HS2-00002CTJP | Oxford Canal North Embankment Security Fence Line | 1MC07-ASC-CV-FRM-CS07_CL23-000033-ACBOS | P02 | 2023-12-05 | 2023-12-05 | 2023-12-06 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600069 | [9 empty] | 10 - Complete | Supriyan | Duggina, Jayaram <jayaram.duggina@arcadis.com> | 1 | 0 | 0
| 235.01 | HS2-00002N7UR | Boddington Cutting Group | 1MC07-ASC-CV-FRM-CS07_CL14-000018-ACBOS | P01 | 2023-12-05 | 2023-12-12 | 2023-12-13 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600125 |  | Com Type/ Description issue, send back on 05th Nov |  | Same OSGB for all L3 assets, send back to user | [5 empty] | 10 - Complete | Supriyan | PATIL, APOORVA <apoorva.patil@arcadis.com> | 1 | 2 | 7
| 226.3 | HS2-00002N7X1 | Brackley Embankment - Ancillary Culvert 097-AC1 | 1MC07-ASC-DR-FRM-CS07_CL12-000080-ACBOS | P02 | 2023-12-05 | 2023-12-05 | 2023-12-07 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600048 | [9 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 2 | 0 | 0
| 222.4 | HS2-00002N7WQ | Barton to Mixbury Cutting - Ancillary Culvert 089-AC4 | 1MC06-ASC-DR-FRM-CS06_CL21-000058-ACBOS | P02 | 2023-12-05 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL21-600006 |  | Com_typ and Com_RfrncNbmr & some clarifications. | [7 empty] | 99 - Cancelled | Lee | youssef.miri@setec.com
| 236.03 | HS2-00003D9CV | Oxford Canal North Embankment Access Stairs CH.118+727 | 1MC07-ASC-CV-FRM-CS07_CL23-000076-ACBOS | P01 | 2023-12-06 | 2023-12-07 | 2023-12-07 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600135 |  | missing FND category CM_CRT/Chg / asset Typ |  |  |  | revised file fcvd - No further comments |  |  |  | 10 - Complete | Supriyan | Alluvada, Neeraj <neeraj.alluvada@arcadis.com> | 0 | 2 | 1
| 236.03 | HS2-00003D9CW | Oxford Canal North Embankment Access Stairs CH.118+730 | 1MC07-ASC-CV-FRM-CS07_CL23-000077-ACBOS | P01 | 2023-12-06 | 2023-12-07 | 2023-12-07 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600136 |  | CM_CRT / Chg & Com_Typ and AssetName_2 edited in house with DT in Teams |  | revised ACBOS .xl sent to DT for PCRA |  | revised file fcvd - No further comments |  |  |  | 10 - Complete | Supriyan | Alluvada, Neeraj <neeraj.alluvada@arcadis.com> | 0 | 3 | 1
| 236.03 | HS2-00003D9CX | Oxford Canal North Embankment Access Stairs CH.119+900 | 1MC07-ASC-CV-FRM-CS07_CL23-000078-ACBOS | P01 | 2023-12-06 | 2023-12-07 | 2023-12-07 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600137 |  | CM_CRT / Chg & Com_Typ and AssetName_2 edited in house with DT in Teams |  | revised ACBOS .xl sent to DT for PCRA |  | revised file fcvd - No further comments |  |  |  | 10 - Complete | Supriyan | Alluvada, Neeraj <neeraj.alluvada@arcadis.com> | 0 | 3 | 1
| 236.03 | HS2-00003D9CY | Oxford Canal North Embankment Access Stairs CH.119+904 | 1MC07-ASC-CV-FRM-CS07_CL23-000079-ACBOS | P01 | 2023-12-06 | 2023-12-07 | 2023-12-07 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600138 |  | CM_CRT / Chg & Com_Typ and AssetName_2 edited in house with DT in Teams |  | revised ACBOS .xl sent to DT for PCRA |  | revised file fcvd - No further comments |  |  |  | 10 - Complete | Supriyan | Alluvada, Neeraj <neeraj.alluvada@arcadis.com> | 0 | 3 | 1
| 236.03 | HS2-00003GEF2 | Oxford Canal North Embankment 119 - DC1 | 1MC07-ASC-CV-FRM-CS07_CL23-000082-ACBOS | P01 | 2023-12-06 | 2023-12-07 | 2023-12-08 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600131 |  | LDW to amend in house to expedite. DT will not edit until tomorrow. |  | OSG Easting/ Northings confirmed as small L2 asset components all within same OS gridref. |  | waiting for India DT to PCRA revised ACBOS as per thos sent. Corrected JSON in Datachecker. |  | revised file checked on PW |  | 10 - Complete | Lee | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 1 | 4 | 1
| 236.03 | HS2-00003GEF3 | Oxford Canal North Embankment 119 - DC2 | 1MC07-ASC-CV-FRM-CS07_CL23-000083-ACBOS | P01 | 2023-12-06 | 2023-12-07 | 2023-12-08 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600132 |  | LDW to amend in house to expedite. DT will not edit until tomorrow. |  | OSG Easting/ Northings confirmed as small L2 asset components all within same OS gridref. |  | waiting for India DT to PCRA revised ACBOS as per thos sent. Corrected JSON in Datachecker. |  | revised file checked on PW |  | 10 - Complete | Lee | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 1 | 4 | 1
| 236.03 | HS2-00003GEF4 | Oxford Canal North Embankment 119 - DC3 | 1MC07-ASC-CV-FRM-CS07_CL23-000084-ACBOS | P01 | 2023-12-06 | 2023-12-07 | 2023-12-08 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600133 |  | LDW to amend in house to expedite. DT will not edit until tomorrow. |  | OSG Easting/ Northings confirmed as small L2 asset components all within same OS gridref. |  | waiting for India DT to PCRA revised ACBOS as per thos sent. Corrected JSON in Datachecker. |  | revised file checked on PW |  | 10 - Complete | Lee | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 1 | 4 | 1
| 236.03 | HS2-00003GEF5 | Oxford Canal North Embankment 119 - DC4 | 1MC07-ASC-CV-FRM-CS07_CL23-000085-ACBOS | P01 | 2023-12-06 | 2023-12-07 | 2023-12-08 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600134 |  | LDW to amend in house to expedite. DT will not edit until tomorrow. |  | OSG Easting/ Northings confirmed as small L2 asset components all within same OS gridref. |  | waiting for India DT to PCRA revised ACBOS as per thos sent. Corrected JSON in Datachecker. |  | revised file checked on PW |  | 10 - Complete | Lee | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 1 | 4 | 1
| 235.01 | HS2-000020134 | Stoneton Lane Green Overbridge | 1MC07-CEK-BR-FRM-CS07_CL14-000003 | P03 | 2023-12-06 | 2024-01-09 | 2024-01-11 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600019 |  | Send back on 7th Dec. Asset_Description, CM_ISCI and sdslp wrong | [7 empty] | 10 - Complete | Supriyan | Alex Webb <ALWB@COWI.COM> | 2 | 1 | 34
| 216.01-2 | HS2-00003D82Q | Sailing Club Access Drainage Culvert | 1MC06-ASC-DR-FRM-CS06_CL09-000109-ACBOS | P03 | 2023-12-07 | 2023-12-07 | 2023-12-09 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600251 |  | Com_Typ, DT fixing as per teams call. 5 min change. |  | File rcvd processing | [5 empty] | 10 - Complete | Lee | Sharkey, Ryan <Ryan.Sharkey@arcadis.com> | 1 | 2 | 0
| 237.03 | HS2-00003D9CP | Upper Radbourne Embankment Access Stairs CH.120+015 | 1MC07-ASC-CV-FRM-CS07_CL23-000070-ACBOS | P01 | 2023-12-11 | 2024-01-12 | 2024-01-16 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600140 |  | Asset Name Mismatch, send back on 12-Dec-23 |  | Com_dscrptn incorrect looks like confusion as asset description and Com_dscrptn should be exchanged - 8/1/24 |  | rvsd file rcvd 12/1/24 |  |  |  | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 2 | 3 | 32
| 237.03 | HS2-00003D9CQ | Upper Radbourne Embankment Access Stairs CH.120+027 | 1MC07-ASC-CV-FRM-CS07_CL23-000071-ACBOS | P01 | 2023-12-11 | 2024-01-12 | 2024-01-16 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600141 |  | Asset Name Mismatch, send back on 12-Dec-23 |  | Com_dscrptn incorrect looks like confusion as asset description and Com_dscrptn should be exchanged - 8/1/24 |  | rvsd file rcvd 12/1/24 |  |  |  | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 2 | 3 | 32
| 237.03 | HS2-00003D9CR | Upper Radbourne Embankment Access Stairs CH.120+031 | 1MC07-ASC-CV-FRM-CS07_CL23-000072-ACBOS | P01 | 2023-12-11 | 2024-01-15 | 2024-01-17 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600142 |  | Asset Name Mismatch, send back on 12-Dec-23 |  | Com_dscrptn incorrect looks like confusion as asset description and Com_dscrptn should be exchanged - 8/1/24 |  | rvsd file rcvd 12/1/24 |  |  |  | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 2 | 3 | 35
| 237.03 | HS2-00003D9CS | Upper Radbourne Embankment Access Stairs CH.120+390 | 1MC07-ASC-CV-FRM-CS07_CL23-000073-ACBOS | P01 | 2023-12-11 | 2024-01-16 | 2024-01-16 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600143 |  | Asset Name Mismatch, send back on 12-Dec-23 |  | Com_dscrptn incorrect looks like confusion as asset description and Com_dscrptn should be exchanged - 8/1/24 |  | rvsd file rcvd 12/1/24 |  |  |  | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 0 | 3 | 36
| 237.03 | HS2-00003D9CT | Upper Radbourne Embankment Access Stairs CH.120+395 | 1MC07-ASC-CV-FRM-CS07_CL23-000074-ACBOS | P01 | 2023-12-11 | 2024-01-15 | 2024-01-16 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600144 |  | Asset Name Mismatch, send back on 12-Dec-23 |  | Com_dscrptn incorrect looks like confusion as asset description and Com_dscrptn should be exchanged - 8/1/24 |  | rvsd file rcvd 12/1/24 |  |  |  | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 1 | 3 | 35
| 237.03 | HS2-00003D9CU | Upper Radbourne Embankment Access Stairs CH.120+410 | 1MC07-ASC-CV-FRM-CS07_CL23-000075-ACBOS | P01 | 2023-12-11 | 2024-01-17 | 2024-01-17 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600139 |  | Com_dscrptn incorrect looks like confusion as asset description and Com_dscrptn should be exchanged - 8/1/24 |  | Aslo UAID_1 incorrect - impact to AssetName_2 attribute 8/1/24 |  | rvsd file rcvd 12/1/24 |  | rvsd file 17/1/24 |  | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 0 | 4 | 37
| 234.02 | HS2-00002CTHS | Highfurlong Brook Diversion | 1MC07-ASC-DR-FRM-CS07_CL14-000076-ACBOS | P04 | 2023-12-11 | 2023-12-15 | 2024-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600056 |  | Asset Name missing, send back on 11th Dec |  | Few too small objects |  | Com_type Issue, send back to team |  |  |  | 10 - Complete | Supriyan | C, Venkatesh <venkatesh.chavan@arcadis.com> | 47 | 3 | 4
| 208.2 | HS2-00002CT5F | C2.T.25 HS2-00002C5SP | 1MC06-ASC-DR-FRM-CS04_CL18-000009-ACBOS | P04 | 2023-12-11 | 2023-12-13 | 2023-12-14 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600043 |  | Pond outlet and inlet values set as UAID_3 |  | file revised | [5 empty] | 10 - Complete | Lee | Ramos, Leo <Leomel.Ramos@arcadis.com> | 1 | 2 | 2
| 237.03 | HS2-00002CTJV | Upper Radbourne Embankment Boundary Fencing | 1MC07-ASC-CV-FRM-CS07_CL23-000015-ACBOS | P01 | 2023-12-12 | 2023-12-13 | 2023-12-14 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600146 |  | Com_type Issue send back to team on 13Dec2023 | [7 empty] | 10 - Complete | Supriyan | Martin, Joel <Joel.Martin@arcadis.com> | 1 | 1 | 1
| 237.03 | HS2-00002CTJW | Upper Radbourne Embankment Security Fence Line - Security Fence | 1MC07-ASC-CV-FRM-CS07_CL23-000035-ACBOS | P01 | 2023-12-12 | 2023-12-13 | 2023-12-14 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600145 |  | Com_type Issue send back to team on 13Dec2023 | [7 empty] | 10 - Complete | Supriyan | Martin, Joel <Joel.Martin@arcadis.com> | 1 | 1 | 1
| 208.2 | HS2-00002BVFD | C2.L.28 | 1MC06-ASC-DR-FRM-CS04_CL18-000002-ACBOS | P02 | 2023-12-12 | 2023-12-18 | 2023-12-20 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600027 |  | Com_Typ |  | revised file 18/12/23 | [5 empty] | 10 - Complete | Lee | Christopher Hackett <crht@cowi.com> | 2 | 2 | 6
| 208.2 | HS2-00002CT5N | C2.L.29 | 1MC06-ASC-DR-FRM-CS04_CL19-000004-ACBOS | P02 | 2023-12-12 | 2023-12-19 | 2023-12-20 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600025 |  | Com_Typ |  | revised file 19/12/23 | [5 empty] | 10 - Complete | Lee | Christopher Hackett <crht@cowi.com> | 1 | 2 | 7
| 215.02-2 | HS2-00002CX36 | Civil 3D Solids Model - P-RAI-0799 | 1MC06-ASC-DR-FRM-CS06_CL09-000037-ACBOS | P01 | 2023-12-14 | 2023-12-15 | 2023-12-20 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600209 |  | send back on 15th Dec |  | Com_Type issue, send back on 18th Dec |  | revised file rcvd 19/12/23 |  |  |  | 10 - Complete | Lee | samar.nouma@setec.com> | 3 | 3 | 1
| 201.3-3 | HS2-00002BJQU | HS2-00002C5PF Dutch Lands Farm to Rushmoor Wood (TLE/2) Footpath Realignment | 1MC06-ASC-HW-FRM-CS03_CL05-000004-ACBOS | P01 | 2023-12-14 | 2024-01-11 | 2024-01-12 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600107 |  | Asset Name_2, Com_Typ & Dscrptn, send back on 15-Dec-23 |  | revised file 05/14/23 |  | SdSlp value / 1 AssetName_2 issue |  | rvsd file 11/1/24 |  | 10 - Complete | Lee | Mohammad.Atieh@arcadis.com> | 1 | 4 | 28
| 215.02-2 | HS2-00002Y8VF | GSMR Compount Point 37 UTX No. 1 | 1MC06-ASC-CV-FRM-CS06_CL09-000044-ACBOS | P01 | 2023-12-15 |  | 2023-12-20 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600262 |  |  |  | revised file 09/15/23 | [5 empty] | 10 - Complete | Supriyan | jeet.mehta@arcadis.com | 3 | 1
| 215.02-2 | HS2-00002CT8V | Civil 3D Solids Model - P-RAI-0786 | 1MC06-ASC-DR-FRM-CS06_CL09-000035-ACBOS | P06 | 2023-12-15 | 2023-12-18 | 2023-12-20 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600199 |  | send back on 15th Dec, Com_Typ, Gtxtl, & confirmations of many 0 values and nulls |  | file revised 20/12/23 | [5 empty] | 10 - Complete | Lee | samar.nouma@setec.com | 2 | 2 | 3
| 215.02-2 | HS2-00002CX35 | ACBOS - C2.T.66.1 Catchment Model | 1MC06-ASC-DR-FRM-CS06_CL09-000011-ACBOS | P01 | 2023-12-15 | 2023-12-19 | 2023-12-20 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600220 |  | Many issue found send back on 18th Dec |  | revised fisu 19/12/23 | [5 empty] | 10 - Complete | Lee | NOUMA Samar <samar.nouma@setec.com> | 1 | 2 | 4
| 215.02-2 | HS2-00002EK76 | Calvert IMD connection UTX No1 | 1MC06-ASC-CV-FRM-CS06_CL09-000048-ACBOS | P01 | 2023-12-15 | 2023-12-15 | 2023-12-18 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600237 |  | SdSlp confirmation |  | Confirmed. | [5 empty] | 10 - Complete | Lee | jeet.mehta@arcadis.com | 1 | 2 | 0
| 215.02-2 | HS2-00002TMWR | Portway Farm ATS UTX No 1 | 1MC06-ASC-CV-FRM-CS06_CL09-000035-ACBOS | P01 | 2023-12-15 | 2023-12-18 | 2023-12-18 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600135 |  | SdSlp confirmation, All AssetName_2 mismatch |  | revised file 18-Dec-23 | [5 empty] | 10 - Complete | Lee | jeet.mehta@arcadis.com | 0 | 2 | 3
| 215.02-2 | HS2-00002TMWS | Portway Farm ATS UTX No 2 | 1MC06-ASC-CV-FRM-CS06_CL09-000036-ACBOS | P01 | 2023-12-15 | 2023-12-18 | 2023-12-18 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600138 |  | SdSlp confirmation, All AssetName_2 mismatch |  | revised file 18-Dec-23 | [5 empty] | 10 - Complete | Lee | jeet.mehta@arcadis.com | 0 | 2 | 3
| 215.02-2 | HS2-00002Y8VG | GSMR Compount Point 37 UTX No. 2 | 1MC06-ASC-CV-FRM-CS06_CL09-000045-ACBOS | P01 | 2023-12-15 | 2023-12-15 | 2023-12-18 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600240 |  | SdSlp confirmation |  | Confirmed. | [5 empty] | 10 - Complete | Lee | jeet.mehta@arcadis.com | 1 | 2 | 0
| 215.02-2 | HS2-00002Y8VH | GSMR Compount Point 37 UTX No. 3 | 1MC06-ASC-CV-FRM-CS06_CL09-000046-ACBOS | P01 | 2023-12-15 | 2023-12-15 | 2023-12-18 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600241 |  | SdSlp confirmation |  | Confirmed. | [5 empty] | 10 - Complete | Lee | jeet.mehta@arcadis.com | 1 | 2 | 0
| 215.02-2 | HS2-00002Y8VJ | GSMR Compount Point 37 UTX No. 4 | 1MC06-ASC-CV-FRM-CS06_CL09-000047-ACBOS | P01 | 2023-12-15 | 2023-12-15 | 2023-12-18 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600242 |  | SdSlp confirmation |  | Confirmed. | [5 empty] | 10 - Complete | Lee | jeet.mehta@arcadis.com | 1 | 2 | 0
| 215.02-2 | HS2-00002Y8VM | Calvert IMD.22 UTX No. 1 | 1MC06-ASC-CV-FRM-CS06_CL09-000051-ACBOS | P01 | 2023-12-15 | 2023-12-15 | 2023-12-18 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600245 |  | SdSlp confirmation |  | Confirmed. | [5 empty] | 10 - Complete | Lee | jeet.mehta@arcadis.com | 1 | 2 | 0
| 215.02-2 | HS2-00002Y8VN | Calvert IMD.22 UTX No. 2 | 1MC06-ASC-CV-FRM-CS06_CL09-000052-ACBOS | P03 | 2023-12-15 | 2023-12-15 | 2023-12-18 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600246 |  | SdSlp confirmation |  | Confirmed. | [5 empty] | 10 - Complete | Lee | jeet.mehta@arcadis.com | 1 | 2 | 0
1 | 238.02 | HS2-00002N7UU | Ladbroke Cutting | 1MC07-ASC-CV-FRM-CS07_CL24-000017-ACBOS | P01 | 2023-12-15 | 2023-12-15 | 2023-12-18 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600115 |  | Asset name mismatch Send back 15-Dec-2023 | [7 empty] | 10 - Complete | Supriyan | ArunKumar.S@arcadis.com> | 1 | 1 | 0
| 237.02 | HS2-00002CTJT | C3.T.70 Catchment | 1MC07-ASC-DR-FRM-CS07_CL23-000004-ACBOS | P02 | 2023-12-15 | 2023-12-18 | 2023-12-18 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600059 |  | Com_Typ, some confirmations required. |  | revised file 18-Dec-23 | [5 empty] | 10 - Complete | Lee | gopika.b@arcadis.com> | 0 | 2 | 3
| 237.02 | HS2-00002EL0S | C3.L.81 Catchment | 1MC07-ASC-DR-FRM-CS07_CL23-000022-ACBOS | P04 | 2023-12-15 | 2023-12-18 | 2023-12-18 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600019 |  | Com_Typ, some confirmations required. |  | revised file 18-Dec-23 | [5 empty] | 10 - Complete | Lee | gopika.b@arcadis.com> | 0 | 2 | 3
| 208.2 | HS2-00002CW19 | Maintenance Access Road to Pond (off Aylesbury Park Golf Course Grounds) Drainage System | 1MC06-ASC-DR-FRM-CS04_CL19-000011-ACBOS | P01 | 2023-12-15 |  | 2023-12-18 | [11 empty] | 10 - Complete | Supriyan | Gupta, Anil <anil.gupta@arcadis.com> | 1 | 0
| 237.02 | HS2-000020P0J | Bridleway SM96 Realignment | 1MC07-ASC-HW-FRM-CS07_CL23-000034-ACBOS | P01 | 2023-12-18 | 2024-01-04 | 2024-01-05 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600070 |  | Com_Type and Description issues, send back on 19th Dec |  | revised fisu 23/18/23 | [5 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 1 | 2 | 17
| 237.02 | HS2-00002CTJU | Footpath SM96a Realignment | 1MC07-ASC-HW-FRM-CS07_CL23-000043-ACBOS | P01 | 2023-12-18 | 2024-01-04 | 2024-01-05 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600056 |  | Com_Type and Description issues, send back on 19th Dec |  | revised fisu 23/18/23 | [5 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 1 | 2 | 17
| 215.02-2 | HS2-000020NK2 | Maintenance Access Road to Pond (Off School Hill Road East) | 1MC06-ASC-HW-FRM-CS06_CL09-000038-ACBOS | P01 | 2023-12-20 | 2024-01-05 | 2024-01-09 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600265 |  | DT do not have JSON place holders as yet |  | DT do not have ACBOS in PW yet. Files have been sent to carry out a preliminary check as they are having issues with mtric vs SMartFroms |  | many issues |  | revisd file rcvd 5/1/24 |  | 10 - Complete | Lee | Abedelkareem Alnajajreh <adan@cowi.com> | 2 | 4 | 16
| 215.02-2 | HS2-00002BJU3 | School Hill Road Realignment | 1MC06-ASC-HW-FRM-CS06_CL09-000045-ACBOS | P01 | 2023-12-20 | 2024-01-09 | 2024-01-10 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600263 |  | DT do not have ACBOS in PW yet. Files have been sent to carry out a preliminary check as they are having issues with mtric vs SMartFroms |  | many issues |  | rvsd file 9/1/24 |  |  |  | 10 - Complete | Lee | Abedelkareem Alnajajreh <adan@cowi.com> | 1 | 3 | 20
| 215.02-2 | HS2-00002CT8R | C2.H.35 | 1MC06-ASC-DR-FRM-CS06_CL09-000026-ACBOS | P01 | 2023-12-20 | 2024-01-11 | 2024-01-12 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600109 |  | Absolute FAIL on many many items |  | many issues |  | rvsd file 9/1/24 |  |  |  | 10 - Complete | Lee | Piotr Kozakiewicz <PIKZ@COWI.COM> | 1 | 3 | 22
| 215.02-2 | HS2-00002CT8Y | Maintenance Access Road to Pond (Off School Hill Road West) | 1MC06-ASC-HW-FRM-CS06_CL09-000041-ACBOS | P01 | 2023-12-20 | 2024-01-09 | 2024-01-11 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600266 |  | DT do not have ACBOS in PW yet. Files have been sent to carry out a preliminary check as they are having issues with mtric vs SMartFroms |  | many issues |  | rvsd file 9/1/24 |  |  |  | 10 - Complete | Lee | Abedelkareem Alnajajreh <adan@cowi.com> | 2 | 3 | 20
| 215.02-2 | HS2-00002NNHZ | School Hill Network Rail Compound Access | 1MC06-ASC-HW-FRM-CS06_CL09-000076-ACBOS | P01 | 2023-12-20 | 2024-01-05 | 2024-01-09 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600264 |  | DT do not have JSON place holders as yet |  | DT do not have ACBOS in PW yet. Files have been sent to carry out a preliminary check as they are having issues with mtric vs SMartFroms |  | many issues |  | revisd file rcvd 5/1/24 |  | 10 - Complete | Lee | Abedelkareem Alnajajreh <adan@cowi.com> | 2 | 4 | 16
| 230.01-2 | HS2-00002CTFP | Thorpe Mandeville Embankment Boundary/Perimeter Fence Line | 1MC07-ASC-CV-FRM-CS07_CL26-000038-ACBOS | P01 | 2023-12-21 |  | 2023-12-22 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600011 | [9 empty] | 10 - Complete | Supriyan | jayaram.duggina@arcadis.com> | 1 | 0
| 230.01-2 | HS2-00002CTFR | Thorpe Mandeville Embankment Security Fence Line | 1MC07-ASC-CV-FRM-CS07_CL26-000095-ACBOS | P01 | 2023-12-21 |  | 2024-01-05 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600002 | [9 empty] | 10 - Complete | Supriyan | jayaram.duggina@arcadis.com> | 5 | 0
| 228 | HS2-000033GP5 | Clean Water Pipe CFA_15_01 | 1MC07-ASC-UT-FRM-CS07_CL12-000103-ACBOS | P01 | 2023-12-22 |  | 2024-01-05 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600256 | [9 empty] | 10 - Complete | Supriyan | prashant.singh2@arcadis.com> | 4 | 0
| 238.01 | HS2-000001462 | Ladbroke Culvert | 1MC07-CEK-CV-FRM-CS07_CL24-600013 | P01 | 2024-01-02 | 2024-01-17 | 2024-01-18 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600051 |  | Com_Type / Description issue send back on 2/1/24 other empty atts need confirmation. | [7 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 15
| 238.01 | HS2-00003DL20 | Ladbroke Grove Embankment 122 - DC1 | 1MC07-ASC-CV-FRM-CS07_CL24-000063-ACBOS | P01 | 2024-01-03 | 2024-01-04 | 2024-01-09 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600109 |  | Some incomplete atts - some confirmation of zero values required. Sent 3/4/24 |  | responses rcvd 4/1/24 - all items resolved | [5 empty] | 10 - Complete | Lee | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 3 | 2 | 1
| 238.01 | HS2-00003DL21 | Ladbroke Grove Embankment 122 - DC2 | 1MC07-ASC-CV-FRM-CS07_CL24-000064-ACBOS | P01 | 2024-01-03 | 2024-01-04 | 2024-01-09 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600110 |  | Some incomplete atts - some confirmation of zero values required. Sent 3/4/24 |  | responses rcvd 4/1/24 - all items resolved |  | JSON Placeholder not set to WIP |  |  |  | 10 - Complete | Lee | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 3 | 3 | 1
| 238.01 | HS2-00003DL22 | Ladbroke Grove Embankment 122 - DC3 | 1MC07-ASC-CV-FRM-CS07_CL24-000065-ACBOS | P01 | 2024-01-03 | 2024-01-04 | 2024-01-09 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600111 |  | Some incomplete atts - some confirmation of zero values required. Sent 3/4/24 |  | responses rcvd 4/1/24 - all items resolved |  | JSON Placeholder not set to WIP |  |  |  | 10 - Complete | Lee | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 3 | 3 | 1
| 226.3 | HS2-00002N7X1 | Brackley Embankment - Ancillary Culvert 097-AC1 | 1MC07-ASC-DR-FRM-CS07_CL12-000080-ACBOS | P05 | 2024-01-08 | 2024-01-10 | 2024-01-11 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600048 | [9 empty] | 10 - Complete | Supriyan | youssef.miri@setec.com | 1 | 0 | 2
| 222.2 | HS2-00002N7WH | Barton to Mixbury Cutting - Ancillary Culvert 088-AC2 | 1MC06-ASC-DR-FRM-CS06_CL21-000059-ACBOS | P03 | 2024-01-08 | 2024-01-09 | 2024-01-10 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600009 | [9 empty] | 10 - Complete | Lee | youssef.miri@setec.com | 1 | 0 | 1
| 222.2 | HS2-00002N7WJ | Barton to Mixbury Cutting - Ancillary Culvert 088-AC3 | 1MC06-ASC-DR-FRM-CS06_CL21-000060-ACBOS | P03 | 2024-01-08 | 2024-01-09 | 2024-01-11 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600003 | [9 empty] | 10 - Complete | Lee | youssef.miri@setec.com | 2 | 0 | 1
| UFDR 203.F | HS2-00002TMEM | Wendover ATS Telecoms | 1MC06-ASC-UT-FRM-CS03_CL05-000045-ACBOS | P01 | 2024-01-09 | 2024-01-18 | 2024-01-18 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600074 |  | Send back on 10-Jan-24 |  | Issues found at Review, send back | [5 empty] | 10 - Complete | Supriyan | Cook, Ted <ted.cook@arcadis.com> | 0 | 2 | 9
| UFDR 203.F | HS2-00002TMET | Stoke Grove ATS Telecoms | 1MC06-ASC-UT-FRM-CS03_CL17-000040-ACBOS | P01 | 2024-01-09 | 2024-01-18 | 2024-01-18 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600073 |  | Send back on 10-Jan-24 |  | Send back because of Chainage | [5 empty] | 10 - Complete | Supriyan | Cook, Ted <ted.cook@arcadis.com> | 0 | 2 | 9
| 222.8 | HS2-00002BJUV | Bridleway 213/7 Overbridge | 1MC06-ASC-HW-FRM-CS06_CL21-000007-ACBOS | P01 | 2024-01-09 | 2024-01-10 | 2024-01-11 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600028 | [9 empty] | 10 - Complete | Supriyan | gladys.kouekam-nassi@setec.com> | 1 | 0 | 1
| 222.4 | HS2-00002N7WQ | Barton to Mixbury Cutting - Ancillary Culvert 089-AC4 | 1MC06-ASC-DR-FRM-CS06_CL21-000058-ACBOS | P03 | 2024-01-09 | 2024-01-10 | 2024-01-11 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600006 | [9 empty] | 10 - Complete | Supriyan | youssef.miri@setec.com | 1 | 0 | 1
| 222.2 | HS2-00002N7WG | Barton to Mixbury Cutting - Ancillary Culvert 088-AC1 | 1MC06-ASC-DR-FRM-CS06_CL21-000049-ACBOS | P03 | 2024-01-09 | 2024-01-10 | 2024-01-11 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600016 | [9 empty] | 10 - Complete | Supriyan | youssef.miri@setec.com | 1 | 0 | 1
| 238.01 | HS2-00002YNH7 | Ladbroke Grove Embankment Culvert - 122-AC3 | 1MC07-ASC-CV-FRM-CS07_CL24-000054-ACBOS | P01 | 2024-01-10 | 2024-01-18 | 2024-01-19 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600112 |  | Com_Typ, Com_Dscrptn, StrcrlIT, and some incomplete AssetDescription_3 |  | rvsd file 18-jan-24 | [5 empty] | 10 - Complete | Lee | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 1 | 2 | 8
| 237.02 | HS2-00002U6LP | Bridleway SM229 | 1MC07-ASC-HW-FRM-CS07_CL23-000045-ACBOS | P01 | 2024-01-10 | 2024-01-10 | 2024-01-12 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600147 | [9 empty] | 10 - Complete | Lee | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 2 | 0 | 0
| 226.2 | HS2-000001334 | Bridleway AX16 Accommodation Overbridge | 1MC07-CEK-BR-FRM-CS07_CL12-000006 | P01 | 2024-01-10 | 2024-01-24 | 2024-01-25 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600085 |  | MPDT load fail to SQL - file rebuiklt to V16 fail rebuilt to V15 and loads |  | NetVolumes for 4 items show as zero 0 in JSON - allowable |  | File reworked for OSGB fixes - 20-Feb-24 |  |  |  | 10 - Complete | Lee | DE OLIVEIRA DE ARAUJO Nuno Sergio <sergio.deoliveira@setec.com> | 1 | 3 | 14
| 222.8 | HS2-000001325 | Bridleway 213/7 Overbridge | 1MC06-CEK-BR-FRM-CS06_CL21-000004 | P01 | 2024-01-10 | 2024-01-18 | 2024-01-19 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600061 |  | failing to pass into SQL |  | material error |  | Full MPDT rebuild required |  |  |  | 10 - Complete | Lee | Harry Forbes <HRFO@COWI.COM> | 1 | 3 | 8
| 208.2 | HS2-00002CT5P | C2.T.27 | 1MC06-ASC-DR-FRM-CS04_CL19-000005-ACBOS | P02 | 2024-01-10 |  | 2024-01-12 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600016 | [9 empty] | 10 - Complete | Supriyan | Anna Kowalewicz <ANKZ@cowi.com> | 2 | 0
| 207.2 | HS2-00002CW1B | Oat Close Bridleway (SBH/19) Drainage System | 1MC06-ASC-DR-FRM-CS04_CL18-000015-ACBOS | P01 | 2024-01-10 | 2024-02-01 | 2024-02-02 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600025 |  | DT have requested cancel - Issue with Modelling |  | DT retagging. |  | rvsd file 31/1/24 |  |  |  | 10 - Complete | Lee | Cordero, Jan <Jan.Cordero@arcadis.com> | 1 | 3 | 22
| 205.3 | HS2-00002CW1F | Standalls Farm Access (SMA 16) Drainage System | 1MC06-ASC-DR-FRM-CS04_CL18-000013-ACBOS | P02 | 2024-01-10 | 2024-01-10 | 2024-01-12 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600026 | [9 empty] | 10 - Complete | Lee | Cordero, Jan <Jan.Cordero@arcadis.com> | 2 | 0 | 0
| 209.2-3 | HS2-00003GL99 | River Thame Watercourses Ground reprofiling | 1MC06-ASC-GT-FRM-CS04_CL19-000029-ACBOS | P01 | 2024-01-11 | 2024-01-11 | 2024-01-11 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600091 |  | Com_Typ, Com_Dscrptn, SdSlp | [7 empty] | 10 - Complete | Lee | Chatterjee, Sourav <SouravKumar.Chatterjee@arcadis.com> | 0 | 1 | 0
| 204.3-1 | HS2-00002CW1A | Nash Lee Orchard Footpath (ELL/20) Drainage System | 1MC06-ASC-DR-FRM-CS03_CL17-000012-ACBOS | P01 | 2024-01-11 |  | 2024-01-12 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600108 | [9 empty] | 10 - Complete | Supriyan | Ka, Srinatha <srinatha.ka@arcadis.com> | 1 | 0
| 226.2 | HS2-00002GUVX | Bridleway AX16 Accommodation Drainage | 1MC07-ASC-DR-FRM-CS07_CL12-000030-ACBOS | P01 | 2024-01-11 |  | 2024-01-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600075 | [9 empty] | 10 - Complete | Supriyan | youssef.miri@setec.com | 5 | 0
| 235.01-2 | HS2-000001091 | Boddington Cutting | 1MC07-ASC-GT-FRM-CS07_CL14-000001-ACBOS | P01 | 2024-01-15 | 2024-02-06 |  |  | 1MC07-CEK-IM-DAT-CS07_CL14-600086 |  | send back on 16-Jan-24 |  | Link not working, send back on 24-Jan |  | Send back on 30-Jan-2024 |  | Asset count mismatch send back on 07-Feb-2024 |  | 99 - Cancelled | Supriyan | K P, Deepak <deepak.kp@arcadis.com>
| 235.01-2 | HS2-00002BVMB | Boddington Cutting Landscape Earthworks | 1MC07-ASC-GT-FRM-CS07_CL14-000010-ACBOS | P01 | 2024-01-15 | 2024-02-06 | 2024-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600022 |  | send back on 16-Jan-24; Link not working, send back on 24-Jan; 31-Jan-2024 returned as old schema used |  | Link not working, send back on 24-Jan |  | Old LoDM, send back to get the data on new LoDM on 31st Jan 2024 |  |  |  | 10 - Complete | Supriyan | K P, Deepak <deepak.kp@arcadis.com> | 1 | 3 | 22
| 213.01-1 | HS2-000020NF2 | Station Road Realignment (Including Buckingham Road and Fidlers Field Road) | 1MC06-ASC-HW-FRM-CS04_CL20-000013-ACBOS | P03 | 2024-01-15 | 2024-01-16 | 2024-01-18 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600108 |  | Com_Typ, Com_Dscrptn |  | rvsd file 16-Jan-24 | [5 empty] | 10 - Complete | Lee | van Dijk, Jeroen <jeroen.vandijk@arcadis.com> | 2 | 2 | 1
| 213.01-1 | HS2-00002BJTK | Doddershall House and South Farms Accommodation Access Road | 1MC06-ASC-HW-FRM-CS05-000022-ACBOS | P03 | 2024-01-15 | 2024-01-16 | 2024-01-18 |  | 1MC06-CEK-IM-DAT-CS05-600093 |  | Com_Typ, Com_Dscrptn |  | rvsd file 16-Jan-24 | [5 empty] | 10 - Complete | Lee | van Dijk, Jeroen <jeroen.vandijk@arcadis.com> | 2 | 2 | 1
| 230.01-2 | HS2-00002CTF4 | C3.L.24 Catchment | 1MC07-ASC-DR-FRM-CS07_CL25-000006-ACBOS | P03 | 2024-01-17 | 2024-01-18 | 2024-01-19 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600003 |  | send back on 18-Jan-24 | [7 empty] | 10 - Complete | Supriyan |  | 1 | 1 | 1
| 201.3-3 | HS2-00002CW0U | Dutch Lands Farm to Rushmoor Wood (TLE/2) Drainage System | 1MC06-ASC-DR-FRM-CS03_CL05-000028-ACBOS | P02 | 2024-01-17 | 2024-01-18 | 2024-01-19 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600039 |  | SdSlp confirmations. <10 leading space issue on Com_Dscription text - resolved in house. |  | confirmed 18-jan-24 | [5 empty] | 10 - Complete | Lee | Ka, Srinatha <srinatha.ka@arcadis.com> | 1 | 2 | 1
| 205.3 | HS2-00002CW1L | Whitethorn Farm Access (SMA/9) Drainage System | 1MC06-ASC-DR-FRM-CS04_CL18-000017-ACBOS | P02 | 2024-01-17 | 2024-01-18 | 2024-01-19 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600028 |  | send back on 18-Jan-24 | [7 empty] | 10 - Complete | Supriyan | Cordero, Jan <Jan.Cordero@arcadis.com> | 1 | 1 | 1
| 218.01-2 | HS2-00002Y0EY | C2.T.66.3 Catchment Model | 1MC06-ASC-DR-FRM-CS06_CL10-000088-ACBOS | P03 | 2024-01-18 |  | 2024-01-19 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600267 | [9 empty] | 10 - Complete | Supriyan | NOUMA Samar <samar.nouma@setec.com> | 1 | 0
| 228 | HS2-000020NUC | Maintenance Access Road to Pond (Off Radstone Road) | 1MC07-ASC-HW-FRM-CS07_CL12-000012-ACBOS | P01 | 2024-01-18 | 2024-01-23 | 2024-01-24 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600121 |  | send back on 18-Jan-24 | [7 empty] | 10 - Complete | Supriyan | <Conor.Egan@wsp.com> | 1 | 1 | 5
| 228 | HS2-00002VXUJ | Maintenance Access Road to GSMR (off Maintenance Access Road to Pond Radstone) and Compound | 1MC07-ASC-HW-FRM-CS07_CL12-000064-ACBOS | P01 | 2024-01-18 | 2024-01-23 | 2024-01-25 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600179 |  | send back on 18-Jan-24 | [7 empty] | 10 - Complete | Supriyan | <Conor.Egan@wsp.com> | 2 | 1 | 5
| 230.01-2 | HS2-00003D82U | Thorpe Mandeville Embankment 105 - DC1 | 1MC07-ASC-CV-FRM-CS07_CL26-000105-ACBOS | P02 | 2024-01-19 | 2024-02-05 | 2024-02-06 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600129 |  | missing values / confirmations / identical chainage / Osgb values sent 19-1-24 |  |  |  | Rvsd file 5-2-24 |  |  |  | 10 - Complete | Lee | vruddhika.naik@arcadis.com | 1 | 2 | 17
| 230.01-2 | HS2-00003D82V | Thorpe Mandeville Embankment 105 - DC2 | 1MC07-ASC-CV-FRM-CS07_CL26-000106-ACBOS | P02 | 2024-01-19 | 2024-02-05 | 2024-02-06 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600130 |  | missing values / confirmations / identical chainage / Osgb values sent 19-1-24 |  | also missing IfcPresentationLayers & UAID_1 mismatch with Smartforms data & ACBOS file PW metadata |  | Rvsd file 5-2-24 |  |  |  | 10 - Complete | Lee | vruddhika.naik@arcadis.com | 1 | 3 | 17
1 | 238.02 | HS2-00003AQDJ | Ladbroke Cutting Group | 1MC07-ASC-CV-FRM-CS07_CL24-000062-ACBOS | P01 | 2024-01-19 |  | 2024-01-22 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600116 | [9 empty] | 10 - Complete | Supriyan | PATIL, APOORVA <apoorva.patil@arcadis.com> | 1 | 0
| 228 | HS2-00002BVK3 | C3.T.13 Catchment | 1MC07-CEK-DR-FRM-CS07_CL12-000019 | P04 | 2024-01-19 | 2024-02-01 | 2024-02-01 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600122 |  | Com_type and othe issues, send back on 22-Jan-2024; rvsd file 25-1-24; chaninage errors?? HLD for advice | [7 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 0 | 1 | 13
| 228 | HS2-00002CTEF | C3.L.14 Catchment | 1MC07-CEK-DR-FRM-CS07_CL12-000020 | P04 | 2024-01-19 | 2024-01-29 | 2024-02-01 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600132 |  | Com_type and othe issues, send back on 22-Jan-2024; rvsd file 25-1-24; PPE DsgnFlw values invalid; Fixed 29-1-24 | [7 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 3 | 1 | 10
| 228 | HS2-00002CTEG | C3.L.15 Catchment | 1MC07-CEK-DR-FRM-CS07_CL12-000021 | P04 | 2024-01-19 | 2024-01-26 | 2024-01-30 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600131 |  | Com_type and othe issues, send back on 22-Jan-2024 |  | rvsd file 25-1-24 | [5 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 2 | 2 | 7
| 228 | HS2-00002CTEK | C3.L.18 Catchment | 1MC07-CEK-DR-FRM-CS07_CL12-000024 | P04 | 2024-01-19 | 2024-02-07 | 2024-02-08 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600079 |  | Com_type and othe issues, send back on 22-Jan-2024; rvsd file 25-1-24; Sdslp values incorrect; 31-Jan-24 returned as missing GdMt |  | PCRA FAIL 2-2-24 Hghtm attribute missing. | MPDT rework | done in house 7-2-24 |  |  |  | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 3 | 19
| 228 | HS2-00002CX3H | Footpath AN22 Accommodation Overbridge Drainage System | 1MC07-CEK-DR-FRM-CS07_CL12-000009 | P03 | 2024-01-19 | 2024-01-26 | 2024-01-30 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600010 |  | Com_type and othe issues, send back on 22-Jan-2024 |  | rvsd file 25-1-24 | [5 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 2 | 2 | 7
| 228 | HS2-000032TBV | Maintenance Access Road to Pond (off Radstone Road) Drainage System | 1MC07-ASC-DR-FRM-CS07_CL12-000085 | P03 | 2024-01-19 | 2024-01-26 | 2024-01-30 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600187 |  | Com_type and othe issues, send back on 22-Jan-2024 |  | rvsd file 25-1-24 | [5 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 2 | 2 | 7
| 214.1 | HS2-00002CW17 | Greatmoor Road (Part of CAG/2) Drainage System | 1MC06-ASC-DR-FRM-CS05-000024-ACBOS | P01 | 2024-01-19 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600058 |  | rvsd file 25/1/24 |  | POC away till Monday - |  | missing atts abiguity regardinmg IDR state - PM has comfirmed IDR is 21/3/24 |  | Poosble Pre IDR works, For Pre-PDR, No ACBOS Required |  | 99 - Cancelled | Supriyan | Aleksandra Batog <ALBT@COWI.COM>
| 215.02-2 | HS2-00002CT8R | C2.H.35 | 1MC06-ASC-DR-FRM-CS06_CL09-000026-ACBOS | P07 | 2024-01-23 | 2024-01-23 | 2024-01-24 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600109 |  | rvsds file 23/1/24 | [7 empty] | 10 - Complete | Lee | Piotr Kozakiewicz <PIKZ@COWI.COM> | 1 | 1 | 0
1 | 238.02 | HS2-00002N7UV | Ladbroke Cutting Group | 1MC07-ASC-CV-FRM-CS07_CL24-000018-ACBOS | P01 | 2024-01-23 | 2024-01-24 | 2024-01-24 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600024 | [9 empty] | 10 - Complete | Supriyan | PATIL, APOORVA <apoorva.patil@arcadis.com> | 0 | 0 | 1
| 208.2 | HS2-000020RKT | Lower Hartwell Viaduct Footpath SBH/32 | 1MC06-ASC-HW-FRM-CS04_CL19-000003-ACBOS | P01 | 2024-01-23 | 2024-02-06 | 2024-02-07 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600034 |  | confirmations rqrd sent to DT 24-1-24 | 2024-02-01 | Com Typs - 2-2-24 | 2024-02-06 | Still using old schema and P04 doc set |  |  |  | 10 - Complete | Lee | N, Chaithra <chaithra.n@arcadis.com> | 1 | 3 | 14
| 208.2 | HS2-000020RKU | Pond Access in Aylesbury Park Golf Course | 1MC06-ASC-HW-FRM-CS04_CL19-000004-ACBOS | P01 | 2024-01-23 | 2024-02-06 | 2024-02-07 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600027 |  | confirmations rqrd sent to DT 24-1-24 | 2024-02-01 | Com Typs 2-2-24 | 2024-02-06 | Still using old schema and P04 doc set |  |  |  | 10 - Complete | Lee | N, Chaithra <chaithra.n@arcadis.com> | 1 | 3 | 14
| 208.2 | HS2-00003B5FT | Maintenance Access Road to Pond (off Old A418 Oxford Road) | 1MC06-ASC-HW-FRM-CS04_CL18-000020-ACBOS | P01 | 2024-01-23 | 2024-02-06 | 2024-02-07 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600144 |  | confirmations rqrd sent to DT 24-1-24 | 2024-02-01 | Com Typs 2-2-24 | 2024-02-06 | Still using old schema and P04 doc set | ok | DT Changed JSON file name |  | 10 - Complete | Lee | N, Chaithra <chaithra.n@arcadis.com> | 1 | 4 | 14
| 217.04-2 | HS2-000020NK6 | SCL/7, 8 and 9 Footpath Diversion | 1MC06-ASC-HW-FRM-CS06_CL09-000031-ACBOS | P02 | 2024-01-24 | 2024-02-14 | 2024-02-19 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600097 |  | Com_Typ / Dscrptn, Confirmations 25-1-24 | 2024-02-08 | ACBOS still at Check state - cannot access. | [5 empty] | 10 - Complete | Lee | Quirante, Dan <dan.quirante@arcadis.com> | 3 | 2 | 21
| 226.2 | HS2-000020NTD | Bridleway AX16 Diversion | 1MC07-ASC-HW-FRM-CS07_CL12-000007-ACBOS | P01 | 2024-01-24 | 2024-01-29 | 2024-01-29 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600089 |  | Com Typs |  | Rvsd file 26-1-24 | [5 empty] | 10 - Complete | Lee | KHABOUZE Zakaria <zakaria.khabouze@setec.com> | 0 | 2 | 5
| 226.2 | HS2-00002VXUH | Maintenance Access Road to GSMR (off Bridleway AX16 Diversion) and Compound | 1MC07-ASC-HW-FRM-CS07_CL12-000028-ACBOS | P01 | 2024-01-24 |  | 2024-01-29 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600173 |  | confirmations rqrd sent to DT 24-1-24 |  | Com Typs |  | Rvsd file 26-1-24 |  |  |  | 10 - Complete | Lee | KHABOUZE Zakaria <zakaria.khabouze@setec.com> | 3 | 3
| 221.2 | HS2-000001322 | School End Overbridge | 1MC06-ASC-BR-FRM-C002-CL10-900002 | P01 | 2024-01-24 | 2024-04-30 | 2024-05-01 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600019 |  | Com_Typ / Dscrptn issues, confirmations, many 0.000* RebarVolumes questionable as will round to 0, same with NetVolumes - DT to Confirm 25-1-24 | MPDT rework | Shear Studs, some erroneuous zer values. 25-Apr-24 | [5 empty] | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 1 | 2 | 97
| 237.01-2 | HS2-00002YNH5 | Crossing of Bridleway SM229 to River Itchen Tributary | 1MC07-ASC-CV-FRM-CS07_CL23-000049-ACBOS | P04 | 2024-01-25 | 2024-01-25 | 2024-01-26 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600076 | [9 empty] | 10 - Complete | Lee | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 1 | 0 | 0
| 235.01 | HS2-00003GJJH | Althorpe Estate Clean Water | 1MC07-ASC-UT-FRM-CS07_CL14-000039-ACBOS | P01 | 2024-01-25 | 2024-03-28 | 2024-04-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600175 |  | Confirmations and CM_CRT set as 04 26-1-24 | ACBOS not at Review state PC only | DsgnFlwBss incorrect / 1 NetVolume set as 4E-05 7-feb-24 | File still not PCRA, still some issues 18-Mar-24 | chainages to be updated. 2/4/24 |  |  |  | 10 - Complete | Lee | Kamboj, Mohit <mohit.kamboj@arcadis.com> | 1 | 3 | 63
| 226.2 | HS2-00002GUVX | Bridleway AX16 Accommodation Drainage | 1MC07-ASC-DR-FRM-CS07_CL12-000030-ACBOS | P05 | 2024-01-25 |  | 2024-01-30 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600075 |  | 1 Mntg incomplete sent 25-1-24 | [7 empty] | 10 - Complete | Lee | youssef.miri@setec.com | 3 | 1
| 228 | HS2-000001338 | Footpath AN22 Accommodation Overbridge | 1MC07-CEK-BR-FRM-CS07_CL12-000007 | P04 | 2024-01-26 | 2024-02-07 | 2024-02-08 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600137 |  | Error on Ffwk and Ftop, send back for clarity on 30-Jan-24 | [7 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 12
| 228 | HS2-00002BVK9 | Footpath AN22 Diversion | 1MC07-ASC-HW-FRM-CS07_CL12-000004-ACBOS | P01 | 2024-01-26 |  | 2024-01-29 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600027 | [9 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 1 | 0
| 205.3 | HS2-00002CW1F | Standalls Farm Access (SMA 16) Drainage System | 1MC06-ASC-DR-FRM-CS04_CL18-000013-ACBOS | P03 | 2024-01-26 |  | 2024-01-30 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600026 | [9 empty] | 10 - Complete | Supriyan | Jan.Cordero@arcadis.com | 2 | 0
| 237.05 | HS2-000001099 | Ladbroke Grove Cutting | 1MC07-ASC-GT-FRM-CS07_CL23-000003-ACBOS | P01 | 2024-01-29 |  | 2024-01-31 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600014 |  | ACBOS received via email. Checked and JSON produced and put in checker | [7 empty] | 10 - Complete | Supriyan | Matthew Coote <mtce@cowi.com> | 2 | 1
| 221 | HS2-00002NNHV | Barton Hartshorn Culvert Watercourse Diversion | 1MC06-ASC-DR-FRM-CS06_CL21-000062-ACBOS | P02 | 2024-01-29 | 2024-03-06 | 2024-03-07 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600008 |  | Send back on 31-Jan-2024 |  | CM_Chg and CM_CRT wrong version send back on 04-Mar -2024 |  | Wrong co-ordinate | rvsd 6/3/24 |  |  | 10 - Complete | Supriyan | Lorusso, Alberto <alberto.lorusso@arcadis.com> | 1 | 3 | 37
| 205.3 | HS2-00002CW1L | Whitethorn Farm Access (SMA/9) Drainage System | 1MC06-ASC-DR-FRM-CS04_CL18-000017-ACBOS | P04 | 2024-01-29 |  | 2024-01-31 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600028 | [9 empty] | 10 - Complete | Supriyan | Gupta, Anil <anil.gupta@arcadis.com> | 2 | 0
| UFDR 203.E | HS2-00002CT3W | CSO-02-6202T | 1MC06-ASC-UT-FRM-CS03_CL06-000048-ACBOS | P01 | 2024-01-30 |  | 2024-02-01 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600072 | [9 empty] | 10 - Complete | Supriyan | Cook, Ted <ted.cook@arcadis.com> | 2 | 0
| UFDR 203.E | HS2-00002CT46 | CSO-02-7200T | 1MC06-ASC-UT-FRM-CS03_CL06-000021-ACBOS | P01 | 2024-01-30 |  | 2024-02-02 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600005 | [9 empty] | 10 - Complete | Supriyan | Cook, Ted <ted.cook@arcadis.com> | 3 | 0
| UFDR 203.E | HS2-00002FG43 | CSO-02-6203T | 1MC06-ASC-UT-FRM-CS03_CL06-000020-ACBOS | P01 | 2024-01-30 |  | 2024-02-01 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600030 | [9 empty] | 10 - Complete | Supriyan | Cook, Ted <ted.cook@arcadis.com> | 2 | 0
| 218.01-2 | HS2-00002CT9X | C2.T.67 Catchment Model | 1MC06-ASC-DR-FRM-CS06_CL10-000004-ACBOS | P03 | 2024-01-30 |  | 2024-02-02 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600070 | [9 empty] | 10 - Complete | Supriyan | MATTOUSSI Farah <farah.mattoussi@setec.com> | 3 | 0
| 218.01-2 | HS2-00002NNHP | Twyford East Culvert Watercourse Diversion | 1MC06-ASC-DR-FRM-CS06_CL10-000074-ACBOS | P01 | 2024-01-30 | 2024-02-07 | 2024-02-07 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600034 |  | Send back on 01-Feb-2024 | [7 empty] | 10 - Complete | Supriyan | Rogers, Andrew <andrew.rogers2@arcadis.com> | 0 | 1 | 8
| 229.03 | HS2-000001438 | Greatworth Hall Culvert | 1MC07-ASC-CV-FRM-CS07_CL12-000058-ACBOS | P01 | 2024-01-30 | 2024-01-31 | 2024-02-01 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600277 |  | Send back on 31-Jan-2024, wrong asset count |  | Send back on 31-Jan-2024, wrong UAID_2 | [5 empty] | 10 - Complete | Supriyan | john.lamb@fairhurst.co.uk> | 1 | 2 | 1
| 220.3 | HS2-00002BVH8 | C2.L.73 Catchment | 1MC06-ASC-DR-FRM-CS06_CL10-000021-ACBOS | P01 | 2024-01-31 |  | 2024-02-02 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600068 | [9 empty] | 10 - Complete | Supriyan | gladys.kouekam-nassi@setec.com> | 2 | 0
| 220.3 | HS2-00002CW0Q | Byway PBI/5A Drainage System | 1MC06-ASC-DR-FRM-CS06_CL10-000015-ACBOS | P01 | 2024-01-31 |  | 2024-02-02 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600008 | [9 empty] | 10 - Complete | Supriyan | gladys.kouekam-nassi@setec.com> | 2 | 0
| 208.2 | HS2-000001029 | Oxford Road Embankment | 1MC06-ASC-GT-FRM-CS04_CL19-000003-ACBOS | P01 | 2024-01-31 | 2024-02-06 | 2024-02-07 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600033 |  | Com_Typs. Some zeros need confirmation. Many identicsl chaninages 1-2-24 | 2024-02-06 | [6 empty] | 10 - Complete | Lee | dominika.bieniasz@arcadis.com> | 1 | 1 | 6
| 208.2 | HS2-000001297 | Footpath SBH/32 Overbridge | 1MC06-CEK-BR-FRM-CS04_CL19-000006 | P01 | 2024-01-31 | 2024-02-05 | 2024-02-07 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600032 |  | Com_Typ, Dscrptn, StrcrlT, CM_Chg/ CRT, various incomplete / confirmations. To DT 1-2-24 | Rvsd File 6-2-24 | MPDT rework | done in house |  |  |  |  | 10 - Complete | Lee | HRFO@COWI.COM> | 2 | 2 | 5
| 208.2 | HS2-00002BVFF | Oxford Road Embankment Landscape Earthworks | 1MC06-ASC-GT-FRM-CS04_CL19-000007-ACBOS | P01 | 2024-01-31 | 2024-02-06 | 2024-02-07 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600026 |  | Com_Typs. Some zeros need confirmation. Many identicsl chaninages 1-2-24 | Rvsd File 2-2-24 | Com_Typs still not complient 5-2-24 | 2024-02-06 |  |  |  |  | 10 - Complete | Lee | dominika.bieniasz@arcadis.com> | 1 | 2 | 6
| 208.2 | HS2-00002SZLX | Footpath SBH/32 Overbridge Impact Protection Walls | 1MC06-CEK-CV-FRM-CS04_CL19-000047 | P01 | 2024-01-31 | 2024-02-06 | 2024-02-08 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600017 |  | Com_Typ, Dscrptn, StrcrlT, CM_Chg/ CRT, various incomplete / confirmations. To DT 1-2-24 | Rvsd File 6-2-24 | MPDT rework | done in house |  |  |  |  | 10 - Complete | Lee | HRFO@COWI.COM> | 2 | 2 | 6
| UFDR 229.A | HS2-00002CTFG | CSO-04-3109T | 1MC07-ASC-UT-FRM-CS07_CL25-000021-ACBOS | P02 | 2024-02-01 | 2024-02-01 | 2024-02-02 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600030 | [9 empty] | 10 - Complete | Supriyan | T, Sithrubi <sithrubi.t@arcadis.com> | 1 | 0 | 0
| 237.02 | HS2-00003GSK0 | Lower Radbourne Embankment Ecology Pond - 1 | 1MC07-ASC-EV-FRM-CS07_CL23-000002-ACBOS | P01 | 2024-02-01 | 2024-02-05 | 2024-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600149 |  | Data in old LoDM. Send back on 2nd Feb | [7 empty] | 10 - Complete | Supriyan | B, Gopika <gopika.b@arcadis.com> | 2 | 1 | 4
| 237.02 | HS2-00003GSK1 | Oxford Canal North Embankment Ecology Pond - 1 | 1MC07-ASC-EV-FRM-CS07_CL23-000003-ACBOS | P01 | 2024-02-01 | 2024-02-05 | 2024-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600150 |  | Data in old LoDM. Send back on 2nd Feb | [7 empty] | 10 - Complete | Supriyan | B, Gopika <gopika.b@arcadis.com> | 2 | 1 | 4
| 237.02 | HS2-00003GSK2 | Oxford Canal North Embankment Ecology Pond - 2 | 1MC07-ASC-EV-FRM-CS07_CL23-000004-ACBOS | P01 | 2024-02-01 | 2024-02-05 | 2024-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600151 |  | Data in old LoDM. Send back on 2nd Feb | [7 empty] | 10 - Complete | Supriyan | B, Gopika <gopika.b@arcadis.com> | 2 | 1 | 4
| 237.02 | HS2-00003GSK3 | Oxford Canal South Embankment Ecology Pond - 1 | 1MC07-ASC-EV-FRM-CS07_CL23-000005-ACBOS | P01 | 2024-02-01 | 2024-02-05 | 2024-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600152 |  | Data in old LoDM. Send back on 2nd Feb | [7 empty] | 10 - Complete | Supriyan | B, Gopika <gopika.b@arcadis.com> | 2 | 1 | 4
| 237.02 | HS2-00003GSK4 | Oxford Canal South Embankment Ecology Pond - 2 | 1MC07-ASC-EV-FRM-CS07_CL23-000006-ACBOS | P01 | 2024-02-01 | 2024-02-05 | 2024-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600154 |  | Data in old LoDM. Send back on 2nd Feb | [7 empty] | 10 - Complete | Supriyan | B, Gopika <gopika.b@arcadis.com> | 2 | 1 | 4
| 237.02 | HS2-00003GSK5 | Oxford Canal South Embankment Ecology Pond - 3 | 1MC07-ASC-EV-FRM-CS07_CL23-000007-ACBOS | P01 | 2024-02-01 | 2024-02-05 | 2024-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600153 |  | Data in old LoDM. Send back on 2nd Feb | [7 empty] | 10 - Complete | Supriyan | B, Gopika <gopika.b@arcadis.com> | 2 | 1 | 4
| 228 | HS2-00002NNHX | Helmdon Culvert Watercourse Diversion | 1MC07-ASC-DR-FRM-CS07_CL12-000083-ACBOS | P01 | 2024-02-01 | 2024-02-15 | 2024-02-16 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600049 |  | Query send on 2nd of Feb and Reminded on 5th Feb. Awaiting for response |  | Send back on 14th Feb, multiple functioning group |  | GTxtl issue, send back on 15th Feb |  |  |  | 10 - Complete | Supriyan | Puri, Anna <anamika.puri@wsp.com> | 1 | 3 | 14
| 228 | HS2-00003B2GL | Greatworth South Embankment Planting Plot 1 | 1MC07-ASC-EV-FRM-CS07_CL12-900015 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-12 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600207 |  | netVolume, Com_Typ.2-2-24 | 2024-05-05 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 2 | 1 | 7
| 228 | HS2-00003B2GM | Greatworth South Embankment Planting Plot 2 | 1MC07-ASC-EV-FRM-CS07_CL12-900016 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600206 |  | netVolume, Com_Typ.2-2-24 | 2024-02-05 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 7
| 228 | HS2-00003B2GN | Greatworth South Cutting Planting Plot 12 | 1MC07-ASC-EV-FRM-CS07_CL12-900012 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600205 |  | netVolume, Com_Typ.2-2-24 | 2024-02-05 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 7
| 228 | HS2-00003B2GP | Greatworth South Cutting Planting Plot 11 | 1MC07-ASC-EV-FRM-CS07_CL12-900011 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600204 |  | netVolume, Com_Typ.2-2-24 | 2024-02-07 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 7
| 228 | HS2-00003B2GQ | Greatworth South Cutting Planting Plot 13 | 1MC07-ASC-EV-FRM-CS07_CL12-900013 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600203 |  | netVolume, Com_Typ.2-2-24 | 2024-02-07 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 7
| 228 | HS2-00003B2GR | Greatworth South Cutting Planting Plot 14 | 1MC07-ASC-EV-FRM-CS07_CL12-900014 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600202 |  | netVolume, Com_Typ.2-2-24 | 2024-02-07 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 3 | 1 | 7
| 228 | HS2-00003B2GS | Greatworth South Cutting Planting Plot 8 | 1MC07-ASC-EV-FRM-CS07_CL12-900008 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600201 |  | netVolume, Com_Typ.2-2-24 | 2024-02-07 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 7
| 228 | HS2-00003B2GT | Greatworth South Cutting Planting Plot 7 | 1MC07-ASC-EV-FRM-CS07_CL12-900007 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600200 |  | netVolume, Com_Typ.2-2-24 | 2024-02-07 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 7
| 228 | HS2-00003B2GU | Greatworth South Cutting Planting Plot 9 | 1MC07-ASC-EV-FRM-CS07_CL12-900009 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600199 |  | netVolume, Com_Typ.2-2-24 | 2024-02-07 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 7
| 228 | HS2-00003B2GV | Greatworth South Cutting Planting Plot 10 | 1MC07-ASC-EV-FRM-CS07_CL12-900010 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600198 |  | netVolume, Com_Typ.2-2-24 | 2024-02-07 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 7
| 228 | HS2-00003B2GW | Greatworth South Cutting Planting Plot 3 | 1MC07-ASC-EV-FRM-CS07_CL12-900003 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600197 |  | netVolume, Com_Typ.2-2-24 | 2024-02-07 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 7
| 228 | HS2-00003B2GX | Greatworth South Cutting Planting Plot 4 | 1MC07-ASC-EV-FRM-CS07_CL12-900004 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600196 |  | netVolume, Com_Typ.2-2-24 | 2024-02-07 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 7
| 228 | HS2-00003B2GY | Greatworth South Cutting Planting Plot 5 | 1MC07-ASC-EV-FRM-CS07_CL12-900005 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600195 |  | netVolume, Com_Typ.2-2-24 | 2024-02-07 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 7
| 228 | HS2-00003B2GZ | Greatworth South Cutting Planting Plot 6 | 1MC07-ASC-EV-FRM-CS07_CL12-900006 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600194 |  | netVolume, Com_Typ.2-2-24 | 2024-02-07 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 7
| 228 | HS2-00003B2H0 | Greatworth South Cutting Planting Plot 1 | 1MC07-ASC-EV-FRM-CS07_CL12-900001 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600193 |  | netVolume, Com_Typ.2-2-24 | 2024-02-05 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 7
| 228 | HS2-00003B2H1 | Greatworth South Cutting Planting Plot 2 | 1MC07-ASC-EV-FRM-CS07_CL12-900002 | P01 | 2024-02-01 | 2024-02-08 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600192 |  | netVolume, Com_Typ.2-2-24 | 2024-02-05 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 3 | 1 | 7
| 208.2 | HS2-00003GNA7 | Lower Hartwell No.1 Culvert Transition and E&R | 1MC06-ASC-GT-FRM-CS04_CL19-000026-ACBOS | P01 | 2024-02-01 | 2024-02-05 | 2024-02-06 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600092 |  | Sdslp syntax sent 2-2-24 | 2024-05-05 | [6 empty] | 10 - Complete | Lee | Bieniasz, Dominika <dominika.bieniasz@arcadis.com> | 1 | 1 | 4
| 208.2 | HS2-00003GNA8 | Lower Hartwell No.2 Culvert Transition and E&R | 1MC06-ASC-GT-FRM-CS04_CL19-000028-ACBOS | P01 | 2024-02-01 | 2024-02-05 | 2024-02-06 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600093 |  | Sdslp syntax sent 2-2-24 | 2024-05-05 | [6 empty] | 10 - Complete | Lee | Bieniasz, Dominika <dominika.bieniasz@arcadis.com> | 1 | 1 | 4
| UFDR 224.H | HS2-000020CHA | CSO-04-1302P | 1MC06-ASC-UT-FRM-CS06_CL22-000021-ACBOS | P01 | 2024-02-02 | 2024-02-06 | 2024-02-07 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600107 |  | Data is incomplete , send back on 05th Feb | 2024-02-06 | Reduced attribution Non HS2 Utils | [5 empty] | 10 - Complete | Supriyan | B, Bharath Kumar <bharathkumar.b@arcadis.com> | 1 | 2 | 4
| 238.01 | HS2-00003DL20 | Ladbroke Grove Embankment 122 - DC1 | 1MC07-ASC-CV-FRM-CS07_CL24-000063-ACBOS | P03 | 2024-02-02 | 2024-02-05 | 2024-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600109 |  | Send back as requested by DT after JSON production on 01-Feb-2024 | [7 empty] | 10 - Complete | Supriyan | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 2 | 1 | 3
| 238.01 | HS2-00003DL21 | Ladbroke Grove Embankment 122 - DC2 | 1MC07-ASC-CV-FRM-CS07_CL24-000064-ACBOS | P03 | 2024-02-02 | 2024-02-05 | 2024-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600110 |  | Send back as requested by DT after JSON production on 01-Feb-2024 | [7 empty] | 10 - Complete | Supriyan | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 2 | 1 | 3
| 238.01 | HS2-00003DL22 | Ladbroke Grove Embankment 122 - DC3 | 1MC07-ASC-CV-FRM-CS07_CL24-000065-ACBOS | P03 | 2024-02-02 | 2024-02-05 | 2024-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600111 |  | Send back as requested by DT after JSON production on 01-Feb-2024 | [7 empty] | 10 - Complete | Supriyan | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 2 | 1 | 3
| 218.01-2 | HS2-000033GN1 | OXD 27 Access Track Crossing 1 | 1MC06-ASC-CV-FRM-CS06_CL09-000078- ACBOS | P01 | 2024-02-05 | 2024-02-06 | 2024-02-08 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600268 |  | few comments | 2024-02-06 | JSON PlaceHolder incorrect. NOT JSON PLACEHOLDER AT ALL. | [5 empty] | 10 - Complete | Lee | Mani, Velumani <Velumani.Mani@arcadis.com> | 2 | 2 | 1
| 204.4-1 | HS2-00002CT2R | Wendover Dean South Embankment Noise Barrier Line | 1MC06-CEK-CV-FRM-CS03_CL05-000067 | P01 | 2024-02-05 | 2024-02-09 | 2024-02-13 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600027 |  | incomplete MPDT, send back on 7th Feb | [7 empty] | 10 - Complete | Supriyan | Trine Norsk <trno@cowi.com> | 2 | 1 | 4
| 204.4-1 | HS2-00002CT2W | Wendover Dean North Embankment Noise Barrier Line | 1MC06-CEK-CV-FRM-CS03_CL05-000068 | P01 | 2024-02-05 | 2024-02-13 | 2024-02-14 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600001 |  | incomplete MPDT, send back on 7th Feb |  | Wrong OSGB | [5 empty] | 10 - Complete | Supriyan | Trine Norsk <trno@cowi.com> | 1 | 2 | 8
| 204.4-1 | HS2-00002CT30 | Rocky Lane Cutting Noise Barrier Line | 1MC06-CEK-CV-FRM-CS03_CL05-000069 | P01 | 2024-02-05 | 2024-02-09 | 2023-02-13 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600010 |  | incomplete MPDT, send back on 7th Feb | [7 empty] | 10 - Complete | Supriyan | Trine Norsk <trno@cowi.com>
| 235.01 | HS2-00002CX3F | Footpath SM101 Drainage System | 1MC07-ASC-DR-FRM-CS07_CL14-000027-ACBOS | P04 | 2024-02-05 | 2024-02-07 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600002 |  | No comments | [7 empty] | 10 - Complete | Lee | B, Gopika <gopika.b@arcadis.com> | 4 | 1 | 2
| 229.03 | HS2-00002N7UB | Greatworth North Cutting Group - Ancillary Culvert 101-AC3 | 1MC07-ASC-CV-FRM-CS07_CL12-000043-ACBOS | P01 | 2024-02-05 | 2024-02-06 | 2024-02-08 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600279 | [9 empty] | 10 - Complete | Supriyan | Graeme Millen <graeme.millen@fairhurst.co.uk> | 2 | 0 | 1
| UFDR 232.B | HS2-000020CJG | CSO-04-1323 | 1MC07-ASC-UT-FRM-CS07_CL26-000008-ACBOS | P01 | 2024-02-06 | 2024-02-07 | 2024-02-08 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600026 | [9 empty] | 10 - Complete | Supriyan | T, Sithrubi <sithrubi.t@arcadis.com> | 1 | 0 | 1
| 224.4 | HS2-000033GP4 | Clean Water Pipe CFA_14_14 | 1MC06-ASC-UT-FRM-CS06_CL22-000053-ACBOS | P01 | 2024-02-06 | 2024-02-07 | 2024-02-08 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600216 |  | Data in old LoDM. Send back on 7nd Feb | [7 empty] | 10 - Complete | Supriyan | B, Bharath Kumar <bharathkumar.b@arcadis.com> | 1 | 1 | 1
| 237.05 | HS2-00003D82S | Ladbroke Grove Cutting | 1MC07-ASC-CV-FRM-CS07_CL23-000061-ACBOS | P01 | 2024-02-07 | 2024-02-12 | 2024-02-12 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600155 | [9 empty] | 10 - Complete | Supriyan | S, Arun Kumar <ArunKumar.S@arcadis.com> | 0 | 0 | 5
| 235.01 | HS2-000020NZW | Footpath SM101 Realignment | 1MC07-ASC-HW-FRM-CS07_CL14-000033-ACBOS | P02 | 2024-02-07 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600023 |  | 1 com_typ issue. 8-2-24 | 9-feb-24. | [6 empty] | 10 - Complete | Lee | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 2 | 1 | 2
| 237.05-2 | HS2-000001460 | Lower Radbourne Farm Accommodation Overbridge | 1MC07-CEK-BR-FRM-CS07_CL23-600002 | P04 | 2024-02-08 | 2024-02-21 | 2024-02-23 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600017 |  | Couple of Confirmations required. | 13/02/2024 - all confirmed as MDQCR items | Rvsd file sent 20-feb-24 with Rebar for Parapets added. | [5 empty] | 10 - Complete | Lee | Aitor Reyes Gurruchaga <AIGU@cowi.com> | 2 | 2 | 13
| 238.01 | HS2-00002CTK7 | Ladbroke Grove Embankment Boundary/Perimeter Fence Line | 1MC07-ASC-CV-FRM-CS07_CL24-000023-ACBOS | P02 | 2024-02-08 | 2024-02-19 | 2024-02-22 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600053 |  | incorrect chainages in FND class | 2024-02-19 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 3 | 1 | 11
| 238.01 | HS2-00002CTK8 | Ladbroke Grove Embankment Security Fence Line | 1MC07-ASC-CV-FRM-CS07_CL24-000043-ACBOS | P02 | 2024-02-08 | 2024-02-08 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600046 |  | None. | [7 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 3 | 1 | 0
| 238.01 | HS2-00002TG2Q | Ladbroke Grove Access Track | 1MC07-ASC-HW-FRM-CS07_CL24-000034-ACBOS | P02 | 2024-02-08 | 2024-02-08 | 2024-02-20 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600038 |  | some confirmation required | [7 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 8 | 1 | 0
| 213.06 | HS2-00002CW0Z | HS2-00002C5T1 - Footpath QUA/26 Drainage System | 1MC06-CEK-DR-FRM-CS05-000004 |  | 2024-02-08 | 2024-02-12 | 2024-02-14 |  | 1MC06-CEK-IM-DAT-CS05-600059 |  | Com_Typ / Cm_CRT & Chg / StrcrlT - sent 12-feb-24 | 2024-02-12 | [6 empty] | 10 - Complete | Lee | Rai C, Keerthan <keerthan.raic@arcadis.com> | 2 | 1 | 4
| 204.3 | HS2-000001288 | Footpath ELL/20 Overbridge | 1MC06-CEK-BR-FRM-CS03_CL17-000005 | P01 | 2024-02-08 | 2024-02-20 | 2024-02-22 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600003 |  | various incomplete attributes / confirmations required. 12-feb-24 | [7 empty] | 10 - Complete | Lee | Harry Forbes <HRFO@COWI.COM> | 2 | 1 | 12
| 204.3 | HS2-00002SZLW | Footpath ELL/20 Overbridge Impact Protection Walls | 1MC06-CEK-CV-FRM-CS03_CL17-000048 | P01 | 2024-02-08 | 2024-02-16 | 2024-02-25 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600064 |  | various incomplete attributes / confirmations required. 12-feb-24 | 2024-02-16 | [6 empty] | 10 - Complete | Lee | Harry Forbes <HRFO@COWI.COM> | 5 | 1 | 8
| UFDR 228.F | HS2-00003CFCL | Greatworth Reservoir - Drain pipe CSO-100-0002 | 1MC07-ASC-UT-FRM-CS07_CL12-000110-ACBOS | P01 | 2024-02-09 | 2024-03-01 | 2024-03-01 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600283 |  | Asset decription , conflict with Smartform. Send back on 13-feb-2024 | [7 empty] | 10 - Complete | Supriyan | Singh, Prashant <prashant.singh2@arcadis.com> | 0 | 1 | 21
| 237.02 | HS2-00002WUS2 | Oxford Canal North Embankment Planting - East Plot 3 | 1MC07-ASC-EV-REP-CS07_CL23-000015 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600092 |  | Request rcvd COB 9th |  |  |  | schema rebuild |  |  |  | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 2 | 0
| 237.02 | HS2-00002WUS3 | Oxford Canal North Embankment Planting - East Plot 4 | 1MC07-ASC-EV-REP-CS07_CL23-000016 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600093 |  | Request rcvd COB 9th |  |  |  | schema rebuild |  |  |  | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 2 | 0
| 237.02 | HS2-00002WUS4 | Oxford Canal North Embankment Planting - West Plot 1 | 1MC07-ASC-EV-REP-CS07_CL23-000017 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600094 |  | Request rcvd COB 9th |  |  |  | schema rebuild |  |  |  | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 2 | 0
| 237.02 | HS2-00002WUS5 | Oxford Canal North Embankment Planting - West Plot 2 | 1MC07-ASC-EV-REP-CS07_CL23-000018 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600095 |  | Request rcvd COB 9th |  |  |  | schema rebuild |  |  |  | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 2 | 0
| 237.02 | HS2-00002WUS6 | Oxford Canal North Embankment Planting - West Plot 3 | 1MC07-ASC-EV-REP-CS07_CL23-000019 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600096 |  | Request rcvd COB 9th |  |  |  | schema rebuild |  |  |  | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 2 | 0
| 237.02 | HS2-00002WUS7 | Oxford Canal North Embankment Planting - West Plot 4 | 1MC07-ASC-EV-REP-CS07_CL23-000021 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600097 |  | Request rcvd COB 9th |  |  |  | schema rebuild |  |  |  | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 2 | 0
| 237.02 | HS2-00002WURR | Oxford Canal South Embankment Planting - East Plot 1 | 1MC07-CEK-EV-PLN-CS07_CL23-000005 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600098 |  | Request rcvd COB 9th |  | Com_Typ, Com_Arsqm |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WURS | Oxford Canal South Embankment Planting - East Plot 2 | 1MC07-CEK-EV-PLN-CS07_CL23-000006 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600099 |  | Request rcvd COB 9th |  | Com_Typ, Com_Arsqm |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WURT | Oxford Canal South Embankment Planting - West Plot 1 | 1MC07-CEK-EV-PLN-CS07_CL23-000007 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600100 |  | Request rcvd COB 8th |  | Cat metrics / Com_Typ, Com_Arsqm |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WURU | Oxford Canal South Embankment Planting - West Plot 2 | 1MC07-CEK-EV-PLN-CS07_CL23-000008 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600101 |  | Request rcvd COB 8th |  | QuantityDetails - some values with comma separation. Com_Arsqm - Some incomplete Category Metrics FAIL |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WURV | Oxford Canal South Embankment Planting - West Plot 3 | 1MC07-CEK-EV-PLN-CS07_CL23-000009 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600102 |  | Request rcvd COB 9th |  | Com_Typ |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WURW | Oxford Canal Viaduct Planting - Plot 1 | 1MC07-ASC-EV-REP-CS07_CL23-000022 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600103 |  | Request rcvd COB 9th |  | Com_Typ - non compliant Gtxtl - Incorrect ElvtnAlg - incomplete Some Mtrl with trailing spaces |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WURX | Oxford Canal Viaduct Planting - Plot 2 | 1MC07-ASC-EV-REP-CS07_CL23-000023 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600104 |  | Request rcvd COB 9th |  | ElvtnAlg - some incomplete Com_Arsqm - Some with GIS as Value GTxtl set to yes is not acceptable | mterics FAIL | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WURY | Oxford Canal Viaduct Planting - Plot 3 | 1MC07-ASC-EV-REP-CS07_CL23-000024 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600105 |  | Request rcvd COB 9th |  | Com_Typ |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WURZ | Oxford Canal Viaduct Planting - Plot 4 | 1MC07-ASC-EV-REP-CS07_CL23-000025 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600106 |  | Request rcvd COB 9th |  |  |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 2 | 0
| 237.02 | HS2-00002WUS0 | Oxford Canal North Embankment Planting - East Plot 1 | 1MC07-ASC-EV-REP-CS07_CL23-000014 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600090 |  | Request rcvd COB 9th |  | Com_Typ - incorrect Height incorrect syntax numeric only expected. |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WUS1 | Oxford Canal North Embankment Planting - East Plot 2 | 1MC07-ASC-EV-REP-CS07_CL23-000020 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600091 |  | Request rcvd COB 9th |  | Com_Typ - incorrect Com_Arsqm - incomplete |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WUS8 | Lower Radbourne South Viaduct Planting - East Plot 1 | 1MC07-ASC-EV-REP-CS07_CL23-000003 | P05 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600085 |  | Request rcvd COB 9th |  |  |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 2 | 0
| 237.02 | HS2-00002WUS9 | Lower Radbourne South Viaduct Planting - West Plot 1 | 1MC07-ASC-EV-REP-CS07_CL23-000004 | P05 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600084 |  | Request rcvd COB 9th |  |  |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 2 | 0
| 237.02 | HS2-00002WUSA | Upper Radbourne Embankment Planting - East Plot 1 | 1MC07-ASC-EV-REP-CS07_CL23-000026 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600086 |  | Request rcvd COB 9th |  | Com_Typ |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WUSB | Upper Radbourne Embankment Planting - East Plot 2 | 1MC07-ASC-EV-REP-CS07_CL23-000027 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600087 |  | Request rcvd COB 9th |  | Com_Typ |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WUSC | Upper Radbourne Embankment Planting - West Plot 1 | 1MC07-ASC-EV-REP-CS07_CL23-000028 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600088 |  | Request rcvd COB 9th |  | Com_Typ |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WUSD | Upper Radbourne Embankment Planting - West Plot 2 | 1MC07-ASC-EV-REP-CS07_CL23-000029 | P01 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600089 |  | Request rcvd COB 9th |  | Com_Typ |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WUSE | Lower Radbourne North Viaduct Planting - Plot 1 | 1MC07-ASC-EV-REP-CS07_CL23-000001 | P04 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600083 |  | Request rcvd COB 8th |  | Com_Typs GTxtl non-compliant., ElvtnAlg - incomplete Trailing spaces |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WUSF | Lower Radbourne North Viaduct Planting - Plot 2 | 1MC07-ASC-EV-REP-CS07_CL23-000002 | P06 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600082 |  | Request rcvd COB 9th |  | LSH (2) - NetVolume - incomplete NV-SL-PL-HD (1) - Com_Arsqm incomplete Com_Typ GTxtl non-compliant., |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WUSG | Lower Radbourne Embankment Planting - East Plot 1 | 1MC07-ASC-EV-REP-CS07_CL23-000010 | P05 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600078 |  | Request rcvd COB 9th |  | metrics FAIL, Com_Typ |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WUSH | Lower Radbourne Embankment Planting - East Plot 2 | 1MC07-ASC-EV-REP-CS07_CL23-000011 | P05 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600081 |  | Request rcvd COB 9th |  | Com_Typ, Com_Arsqm |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WUSJ | Lower Radbourne Embankment Planting - West Plot 1 | 1MC07-ASC-EV-REP-CS07_CL23-000012 | P04 | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600080 |  | Request rcvd COB 9th |  | Com_Typ |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 237.02 | HS2-00002WUSK | Lower Radbourne Embankment Planting - West Plot 2 | 1MC07-ASC-EV-REP-CS07_CL23-000013 |  | 2024-02-09 | 2024-02-09 | 2024-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600079 |  | Request rcvd COB 9th |  | Com_Typ, Com_Arsqm |  | schema rebuild |  |  |  | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 3 | 0
| 205.3 | HS2-00002BJS2 | Footpath SMA-8-2 Link | 1MC06-ASC-HW-FRM-CS03_CL17-000024-ACBOS | P01 | 2024-02-09 | 2024-02-13 | 2024-02-19 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600015 |  | Multiple feedbacks, send back on 13-Feb-2024 | [7 empty] | 10 - Complete | Supriyan | Abdelmalik Hassen <ABHS@cowi.com> | 4 | 1 | 4
22 | UFDR 202.B | HS2-000020CDN | CSO-02-1203HV | 1MC06-ASC-UT-FRM-CS03_CL05-000015-ACBOS | P01 | 2024-02-12 | 2024-02-12 | 2024-02-20 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600052 |  | Reduced attribution - UKPN Utility | [7 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 6 | 1 | 0
22 | UFDR 202.B | HS2-000020CDP | CSO-02-3101 | 1MC06-ASC-UT-FRM-CS03_CL05-000024-ACBOS | P01 | 2024-02-12 | 2024-02-12 | 2024-02-16 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600053 |  | Reduced attribution - UKPN Utility | [7 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 4 | 1 | 0
22 | UFDR 202.B | HS2-000020CDQ | CSO-02-6200 | 1MC06-ASC-UT-FRM-CS03_CL05-000022-ACBOS | P01 | 2024-02-12 | 2024-02-12 | 2024-02-16 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600050 |  | Reduced attribution - UKPN Utility | [7 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 4 | 1 | 0
22 | UFDR 202.B | HS2-00002CT3A | CSO-02-1203LV | 1MC06-ASC-UT-FRM-CS03_CL05-000018-ACBOS | P01 | 2024-02-12 | 2024-02-12 | 2024-02-20 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600036 |  | Reduced attribution - UKPN Utility | [7 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 6 | 1 | 0
22 | UFDR 202.B | HS2-00002TG2R | Rocky Lane UKPN Substation | 1MC06-ASC-UT-FRM-CS03_CL05-000017-ACBOS | P01 | 2024-02-12 | 2024-02-12 | 2024-02-16 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600098 |  | Reduced attribution - UKPN Utility | [7 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 4 | 1 | 0
| 235.01 | HS2-00002TMFD | Boddington ATS Telecoms | 1MC07-ASC-UT-FRM-CS07_CL14-000024-ACBOS | P01 | 2024-02-12 | 2024-02-12 | 2024-02-16 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600066 | [9 empty] | 10 - Complete | Supriyan | T, Sithrubi <sithrubi.t@arcadis.com> | 4 | 0 | 0
| 220.3 | HS2-000001320 | Restricted Byway PBI-5A Accommodation Overbridge | 1MC06-CEK-BR-FRM-CS06_CL10-000004 | P06 | 2024-02-12 | 2024-03-15 | 2024-03-18 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600058 |  | DT have changes in MPDT - HOLD 13-2-24 | expected 16-feb-24 | Many incomplete new schema attribiutes 27-Feb-24 | 2024-03-08 | DT reworking 11/3/24 | 2024-03-14 |  |  | 10 - Complete | Lee | DE OLIVEIRA DE ARAUJO Nuno Sergio <sergio.deoliveira@setec.com> | 1 | 3 | 32
| 207.2 | HS2-000032LLR | Stoke Brook Enhancements | 1MC06-ASC-DR-FRM-CS04_CL18-000081-ACBOS | P01 | 2024-02-12 | 2024-02-16 | 2024-02-20 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600145 |  | Com_Type is not as per guidline , send abck on 14th Feb | [7 empty] | 10 - Complete | Supriyan | Humphries, Ted <ted.humphries@arcadis.com> | 2 | 1 | 4
| UFDR 232.B | HS2-000020CJG | CSO-04-1323 | 1MC07-ASC-UT-FRM-CS07_CL26-000008-ACBOS | P02 | 2024-02-13 | 2024-02-15 | 2024-02-16 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600026 | [9 empty] | 10 - Complete | Supriyan | T, Sithrubi <sithrubi.t@arcadis.com> | 1 | 0 | 2
| 237.02 | HS2-000001096 | Upper Radbourne Embankment | 1MC07-ASC-GT-FRM-CS07_CL23-000004-ACBOS | P02 | 2024-02-13 | 2024-02-15 | 2024-02-16 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600072 |  | old LoDM, send back on 14th Feb | [7 empty] | 10 - Complete | Supriyan | K P, Deepak <deepak.kp@arcadis.com> | 1 | 1 | 2
| 237.02 | HS2-00002BVMV | Upper Radbourne Embankment Landscape Earthworks | 1MC07-ASC-GT-FRM-CS07_CL23-000009-ACBOS | P02 | 2024-02-13 | 2024-02-15 | 2024-02-16 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600058 |  | Multiple comments send back on 15th Feb | [7 empty] | 10 - Complete | Supriyan | K P, Deepak <deepak.kp@arcadis.com> | 1 | 1 | 2
| 218.02 | HS2-00002D2S2 | Calvert IMD Mitigation Earthworks | 1MC06-ASC-GT-FRM-CS06_CL09-000012-ACBOS | P03 | 2024-02-13 | 2024-02-20 | 2024-02-20 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600085 |  | Com_Typs, SdSlp , AnglSlp, ElvtnAlg , Gtxtl (LSH & LSS) | 2024-02-16 | Com_typ fixed in house/ no JSOn release until DT update PW | PW file update 20-feb-24 |  |  |  |  | 10 - Complete | Lee | MATTOUSSI Farah <farah.mattoussi@setec.com> | 0 | 2 | 7
| 235.01-2 | HS2-000001091 | Boddington Cutting | 1MC07-ASC-GT-FRM-CS07_CL14-000001-ACBOS | P05 | 2024-02-14 | 2024-02-16 | 2024-02-19 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600086 |  | None. (clarifications by Teams only needed for some 0 values) | [7 empty] | 10 - Complete | Lee | K P, Deepak <deepak.kp@arcadis.com> | 1 | 1 | 2
| 228 | HS2-000001437 | Greatworth Dry Valley Drop Inlet Culvert | 1MC07-CEK-BR-FRM-CS07_CL12-000013 | P05 | 2024-02-14 | 2024-02-20 | 2024-02-25 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600134 |  | Many incomplete attribution - Complete or confirm 16-feb-24 | 2024-02-20 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 3 | 1 | 6
| 228 | HS2-00002CTEC | Greatworth South Embankment Boundary/Perimeter Fence Line | 1MC07-ASC-CV-FRM-CS07_CL12-000032-ACBOS | P01 | 2024-02-14 | 2024-02-14 | 2024-02-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600128 |  | Trialing space in UAID_1 - fixed in house -DT updating ACBOS PW file concurrently | [7 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 3 | 1 | 0
| 228 | HS2-00002CTEE | Greatworth South Embankment Security Fence Line | 1MC07-ASC-CV-FRM-CS07_CL12-000038-ACBOS | P01 | 2024-02-14 | 2024-02-15 | 2024-02-16 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600135 | [9 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 1 | 0 | 1
| 228 | HS2-00002CTEM | Greatworth South Cutting Boundary/Perimeter Fence Line | 1MC07-ASC-CV-FRM-CS07_CL12-000031-ACBOS | P01 | 2024-02-14 | 2024-02-14 | 2024-02-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600025 | [9 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 3 | 0 | 0
| 228 | HS2-00002CTEP | Greatworth South Cutting Security Fence Line | 1MC07-ASC-CV-FRM-CS07_CL12-000052-ACBOS | P01 | 2024-02-14 | 2024-02-14 | 2024-02-15 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600021 | [9 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 1 | 0 | 0
| 205.3 | HS2-000020NBF | Whitethorn Farm (SMA-9) Footpath and Accommodation Access Realignment | 1MC06-ASC-HW-FRM-CS03_CL17-000025-ACBOS | P01 | 2024-02-14 | 2024-02-16 | 2024-02-23 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600004 |  | Some attribution <0.000 will round to Zero. Confirmation of N/A items. 16-feb-24 | 2024-02-16 | [6 empty] | 10 - Complete | Lee | Abdelmalik Hassen <ABHS@cowi.com> | 5 | 1 | 2
| UFDR 210.B | HS2-00002TMEJ | Putlowes ATS Telecoms | 1MC06-ASC-UT-FRM-CS04_CL20-000074-ACBOS | P01 | 2024-02-15 | 2024-02-16 | 2024-02-19 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600151 |  | Zero values - confirmation rqrd. DT contact out of office - emailed 16-feb-24 | 2024-02-16 | [6 empty] | 10 - Complete | Lee | T, Sithrubi <sithrubi.t@arcadis.com> | 1 | 1 | 1
| 220.3 | HS2-000020NL8 | Maintenance Access Road to Pond and MAP (Off Byway PBI/5A) | 1MC06-ASC-HW-FRM-CS06_CL10-000011-ACBOS | P01 | 2024-02-15 | 2024-02-19 | 2024-02-21 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600059 |  | Com_Typ incorrect / Zero & Null value items to be confirmed. 16-feb-24 | 2024-02-19 | [6 empty] | 10 - Complete | Lee | youssef.miri@setec.com | 2 | 1 | 4
| 208.2 | HS2-00002CT5P | C2.T.27 | 1MC06-ASC-DR-FRM-CS04_CL19-000005-ACBOS | P04 | 2024-02-15 | 2024-02-15 | 2024-02-16 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600016 | [9 empty] | 10 - Complete | Lee | Anna Kowalewicz <ANKZ@cowi.com> | 1 | 0 | 0
| UFDR 210.B | HS2-000020CF8 | CSO-02-3301 | 1MC06-ASC-UT-FRM-CS04_CL20-000037-ACBOS | P01 | 2024-02-16 | 2024-02-16 | 2024-02-20 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600124 | [9 empty] | 10 - Complete | Supriyan | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 2 | 0 | 0
| UFDR 210.B | HS2-000020CF9 | CSO-02-3113 | 1MC06-ASC-UT-FRM-CS04_CL20-000033-ACBOS | P01 | 2024-02-16 | 2024-02-16 | 2024-02-19 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600127 | [9 empty] | 10 - Complete | Supriyan | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 1 | 0 | 0
| UFDR 203.E | HS2-00002CT46 | CSO-02-7200T | 1MC06-ASC-UT-FRM-CS03_CL06-000021-ACBOS | P02 | 2024-02-16 | 2024-02-16 | 2024-02-19 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600005 | [9 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 1 | 0 | 0
| 237.05 | HS2-00002CX39 | Ladbroke Grove Farm Access Drainage System | 1MC07-ASC-DR-FRM-CS07_CL23-000017-ACBOS | P01 | 2024-02-16 | 2024-02-21 | 2024-02-22 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600035 |  | Send back on 19th Feb, Com_type issues | [7 empty] | 10 - Complete | Supriyan | Charuvil Vivekanandan, Amrutha <Amrutha.CharuvilVivekananda@arcadis.com> | 1 | 1 | 5
| 228 | HS2-00002DVEJ | Greatworth South Embankment Landscape Earthworks | 1MC07-ASC-GT-FRM-CS07_CL12-000014-ACBOS | P01 | 2024-02-16 | 2024-02-16 | 2024-02-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600012 |  | coupls of Sdslp / Gtxtl blanks - confirmed by DT as intended. | [7 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> - reza.kabir@wsp.com | 5 | 1 | 0
| 201.4 | HS2-00002CT27 | Grims Ditch North Retaining Wall | 1MC06-ASC-CV-FRM-CS03_CL05-000011-ACBOS | P01 | 2024-02-16 | 2024-02-20 | 2024-02-22 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600095 |  | Send back on 19-Feb-2024, multiple observations | 2024-02-20 | [6 empty] | 10 - Complete | Lee | L, Surendar <surendar.loganathan@arcadis.com> | 2 | 1 | 4
| 201.4 | HS2-00002CT28 | Grims Ditch South Retaining Wall | 1MC06-ASC-CV-FRM-CS03_CL05-000010-ACBOS | P01 | 2024-02-16 | 2024-02-20 | 2024-02-22 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600096 |  | Send back on 19-Feb-2024, multiple observations | 2024-02-20 | [6 empty] | 10 - Complete | Lee | L, Surendar <surendar.loganathan@arcadis.com> | 2 | 1 | 4
| 204.3-1 | HS2-00002N7VA | Stoke Mandeville South Embankment 056-AC9 | 1MC06-ASC-CV-FRM-CS03_CL17-000015-ACBOS | P03 | 2024-02-19 | 2024-03-01 | 2024-03-01 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600063 |  | ACBOS not PCR on PW | 2024-02-20 | OSGB values all integer. Com_Type issue, send back on 20th Dec | 2024-02-26 | Still using old schema and P04 doc set - Confirmations required 26-feb-24 | push to JSON while I wait. |  |  | 10 - Complete | Lee | Saranga, Bhargavi <bhargavi.saranga@arcadis.com> | 0 | 3 | 11
| 220.3 | HS2-000020RMA | Footpath PBI/5 Link | 1MC06-ASC-HW-FRM-CS06_CL10-000013-ACBOS | P01 | 2024-02-19 | 2024-02-20 | 2024-02-22 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600063 |  | zero value confirmations. 19-2-24 | 2024-02-20 | [6 empty] | 10 - Complete | Lee | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 2 | 1 | 1
| 220.3 | HS2-00002BJUJ | Byway Pbi5A Diversion Overbridge Realignment | 1MC06-ASC-HW-FRM-CS06_CL10-000002-ACBOS | P01 | 2024-02-19 | 2024-02-22 | 2024-02-22 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600067 | [9 empty] | 10 - Complete | Lee | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 0 | 0 | 3
| 220.3 | HS2-00002J4YN | Footpath PBI-6 Diversion | 1MC06-ASC-HW-FRM-CS06_CL10-000023-ACBOS | P01 | 2024-02-19 | 2024-02-19 | 2024-02-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600055 |  | ClrncVrt / SdSlp Zer (0) value confirmations - sent 22/2/24 | [7 empty] | 10 - Complete | Lee | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 4 | 1 | 0
| 220.3 | HS2-00002VXUA | Maintenance Access Road to Storage Area (off Byway PBI/5A Realignment) | 1MC06-ASC-HW-FRM-CS06_CL10-000031-ACBOS | P01 | 2024-02-19 | 2024-02-19 | 2024-02-23 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600236 |  | ClrncVrt / SdSlp Zer (0) value confirmations - sent 22/2/24 | [7 empty] | 10 - Complete | Lee | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 4 | 1 | 0
| 220.3 | HS2-00002VXUB | Maintenance Access Road to GSMR (off Byway PBI/5A Realignment) and Compound | 1MC06-ASC-HW-FRM-CS06_CL10-900025-ACBOS | P01 | 2024-02-19 | 2024-02-19 | 2024-02-25 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600122 |  | ClrncVrt / SdSlp Zer (0) value confirmations - sent 22/2/24 | [7 empty] | 10 - Complete | Lee | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 4 | 1 | 0
| 205.3 | HS2-00002N7VN | Aylesbury South Cutting 060-AC2 | 1MC06-ASC-CV-FRM-CS04_CL18-000030-ACBOS | P01 | 2024-02-19 | 2024-02-19 | 2024-02-20 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600108 | [9 empty] | 10 - Complete | Lee | Sangalang, Orlando <orlando.sangalang@arcadis.com> | 1 | 0 | 0
| 230.01-2 | HS2-00002CTFU | Culworth Brook Diversion | 1MC07-ASC-DR-FRM-CS07_CL26-000107-ACBOS | P01 | 2024-02-20 | 2024-02-21 | 2024-02-22 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600005 |  | Incomplete ACBOS, Com_type issue, send back on 21-Feb-2024 | [7 empty] | 10 - Complete | Lee | Bulusu, Sai Sravan Kumar <saisravankumar.bulusu@arcadis.com> | 1 | 1 | 1
5 | 201.0-1 | HS2-000001016 | SHC Phase 4 | 1MC06-ASC-GT-FRM-CS03_CL05-000004-ACBOS | P01 | 2024-02-20 | 2024-02-23 | 2024-02-26 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600084 |  | PARTIAL IDR - NEW TO ME!!! |  | Com_Type ussue and other observations. Send back on 22-Feb-2024 | [5 empty] | 10 - Complete | Supriyan | Chatterjee, Sourav <SouravKumar.Chatterjee@arcadis.com> | 1 | 2 | 3
| 205.3 | HS2-000001292 | Footpath SMA/16 Accommodation Overbridge | 1MC06-CEK-BR-FRM-CS04_CL18-000007 | P01 | 2024-02-20 |  | 2024-02-21 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600058 | [9 empty] | 10 - Complete | Supriyan | HRFO@COWI.COM> | 1 | 0
| 205.3 | HS2-00002BJSA | SMA16-Standalls Farm Footbridge Public Rights of Way | 1MC06-ASC-HW-FRM-CS04_CL18-000007-ACBOS | P02 | 2024-02-20 | 2024-02-22 | 2024-02-22 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600076 |  | send back on 20-Feb-2024 | [7 empty] | 10 - Complete | Supriyan | jamie.gill@arcadis.com> | 0 | 1 | 2
| 237.05-3 | HS2-000001461 | Ladbroke Grove Farm Accommodation Overbridge | 1MC07-CEK-BR-FRM-CS07_CL23-600001 | P03 | 2024-02-21 | 2024-02-21 | 2024-02-23 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600018 |  | Com_type issue, and wrong Mtrl. Send back on 21-Feb-2024 | [7 empty] | 10 - Complete | Lee | Aitor Reyes Gurruchaga <AIGU@cowi.com> | 2 | 1 | 0
| 238.01 | HS2-000001100 | Ladbroke Grove Embankment | 1MC07-ASC-GT-FRM-CS07_CL23-000002-ACBOS | P01 | 2024-02-21 | 2024-02-26 | 2024-02-27 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600032 |  | com_typs / confirmations 23/2/24 | 2024-02-26 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 5
| 238.01 | HS2-00002BVNA | Ladbroke Grove Embankment Landscape Earthworks | 1MC07-ASC-GT-FRM-CS07_CL24-000006-ACBOS | P01 | 2024-02-21 | 2024-02-21 | 2024-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600054 |  | com_typs / confirmations 23/2/24 | [7 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 5 | 1 | 0
| 228 | HS2-000001069 | Greatworth South Embankment | 1MC07-ASC-GT-FRM-CS07_CL12-000005-ACBOS | P01 | 2024-02-21 | 2024-02-23 | 2024-02-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600119 |  | Incomplete file, observations. Send back on 22-Feb-2024 | [7 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 0 | 1 | 2
| 205.3 | HS2-00002N7VF | Aylesbury South Cutting 058-AC9 | 1MC06-ASC-CV-FRM-CS04_CL18-000023-ACBOS | P01 | 2024-02-21 | 2024-02-22 | 2024-02-22 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600004 |  | Queries, send back on 22-Feb-2024 | [7 empty] | 10 - Complete | Supriyan | Saranga, Bhargavi <bhargavi.saranga@arcadis.com> | 0 | 1 | 1
| UFDR 226.A | HS2-000020CHF | CSO-04-1307 | 1MC07-ASC-UT-FRM-CS07_CL12-000013-ACBOS | P01 | 2024-02-23 | 2024-02-26 | 2024-02-27 | Yes | 1MC07-CEK-IM-DAT-CS07_CL12-600087 |  | No PCRA of ACBOS, send back on 26th Feb | [7 empty] | 10 - Complete | Supriyan | bharathkumar.b@arcadis.com> | 1 | 1 | 3
| 215.02-02 | HS2-00002BJU3 | School Hill Road Realignment | 1MC06-ASC-HW-FRM-CS06_CL09-000045-ACBOS | P03 | 2024-02-23 | 2024-04-11 | 2024-04-16 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600263 |  | Old LoDM and other issues, send back on 26th Feb | rvsd file 7/3/24 | issues unresolved. 7/3/24 | 2024-04-11 |  |  |  |  | 10 - Complete | Lee | Abedelkareem Alnajajreh <adan@cowi.com> | 3 | 2 | 48
| 215.02-02 | HS2-00002CT8Y | Maintenance Access Road to Pond (Off School Hill Road West) | 1MC06-ASC-HW-FRM-CS06_CL09-000041-ACBOS | P02 | 2024-02-23 | 2024-03-12 | 2024-03-13 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600266 |  | Old LoDM and other issues, send back on 26th Feb | rvsd file 7/3/24 | issues unresolved. 7/3/24 | rvsd file 12-Mar-24 |  |  |  |  | 10 - Complete | Lee | Abedelkareem Alnajajreh <adan@cowi.com> | 1 | 2 | 18
| 216.01 | HS2-00002CT8T | HS2-00002C5T4 - Perry Hill Road Drainage System | 1MC06-ASC-DR-FRM-CS06_CL09-000028-ACBOS | P01 | 2024-02-23 | 2024-02-23 | 2024-02-23 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600201 | [9 empty] | 10 - Complete | Supriyan | keerthan.raic@arcadis.com> | 0 | 0 | 0
| 205.03 | HS2-000001289 | Footpath SMA9 Accommodation Overbridge | 1MC06-CEK-BR-FRM-CS04_CL18-000009 | P01 | 2024-02-23 |  | 2024-02-23 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600057 | [9 empty] | 10 - Complete | Supriyan | AIGU@cowi.com> | 0 | 0
| 229.03 | HS2-00003B2GH | Greatworth North Embankment Cutting | 1MC07-ASC-CV-FRM-CS07_CL12-000106-ACBOS | P01 | 2024-02-26 | 2024-02-26 | 2024-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600285 |  | couple of confirmations 26-feb-24 | 2024-02-26 | [6 empty] | 10 - Complete | Lee | PATIL, APOORVA <apoorva.patil@arcadis.com> | 2 | 1 | 0
| 207.2 | HS2-00003BPJG | Aylesbury Embankment Landscape Earthworks - Oat Close Bridleway (SBH/19) Re-alignment | 1MC06-ASC-GT-FRM-CS04_CL18-000017-ACBOS | P01 | 2024-02-26 | 2024-02-26 | 2024-02-28 |  | 1MC06-CEK-IM-DAT-CS04_CL18-000005 |  | Gtxtl confirmed as none. | [7 empty] | 10 - Complete | Lee | SouravKumar.Chatterjee@arcadis.com | 2 | 1 | 0
| UFDR 204.A | HS2-000020CED | CSO-02-6204 | 1MC06-ASC-UT-FRM-CS03_CL17-000034-ACBOS | P01 | 2024-02-28 |  | 2024-02-29 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600040 | [9 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com> | 1 | 0
| 210.2-2 | HS2-000001299 | Putlowes Accommodation Overbridge | 1MC06-CEK-BR-FRM-CS04_CL20-000001 | P03 | 2024-02-28 | 2024-02-28 | 2024-02-28 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600034 | [9 empty] | 10 - Complete | Supriyan | Aitor Reyes Gurruchaga <AIGU@cowi.com> | 0 | 0 | 0
| 204.3-1 | HS2-00002BJS0 | Nash Lee Orchard (ELL-20) Footpath Realignment | 1MC06-ASC-HW-FRM-CS03_CL17-000006-ACBOS | P03.2 | 2024-02-28 | 2024-03-01 | 2024-03-05 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600011 |  | Com_Type and other issues, send back on 29th Feb | [7 empty] | 10 - Complete | Supriyan | Gregory, Gillian <gillian.gregory@arcadis.com> | 2 | 1 | 2
| 237.05 | HS2-00002BVN5 | Ladbroke Grove Cutting Landscape Earthworks | 1MC07-ASC-GT-FRM-CS07_CL23-000011-ACBOS | P01.1 | 2024-02-28 |  | 2024-03-01 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600007 |  | zero value confirmations. 29-2-24 | [7 empty] | 10 - Complete | Lee | Matthew Coote <mtce@cowi.com> | 2 | 1
| 235.01 | HS2-00002TMFD | Boddington ATS Telecoms | 1MC07-ASC-UT-FRM-CS07_CL14-000024-ACBOS | P02 | 2024-02-28 |  | 2024-02-29 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600066 |  | confirmations of omissions. Expect intended, creating JSON while waiting 28-feb-24 | [7 empty] | 10 - Complete | Lee | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 1 | 1
| 234.02 | HS2-00002CTHS | Highfurlong Brook Diversion | 1MC07-ASC-DR-FRM-CS07_CL14-000076-ACBOS | P09 | 2024-02-28 |  | 2024-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600056 | [9 empty] | 10 - Complete | Supriyan | C, Venkatesh <venkatesh.chavan@arcadis.com> | 0 | 0
| 228.1 | HS2-00003BPM6 | Clean Water Pipe CFA_14_13 | 1MC07-ASC-UT-FRM-CS07_CL12-000108-ACBOS | P02 | 2024-02-28 | 2024-03-12 | 2024-03-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600208 |  | Incomplete MPDT, send back on 28th Feb |  | Send back on 29th, Co-ordinates are same | rvsd 7/3/24 | all chainges identical / reduced attribution 3rd party | rvsd 12-Mar-23 | Colin Reith TQ-801 statement 11/3/24 |  | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 4 | 4 | 13
| 207.2 | HS2-00002CT4W | C2.L.22 Catchment | 1MC06-ASC-DR-FRM-CS04_CL18-000003-ACBOS | P01 | 2024-02-28 | 2024-02-28 | 2024-02-29 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600081 |  | trailing spaces / confirmations / odd values of .nnn or .n 28-feb-24 | 2024-02-28 | [6 empty] | 10 - Complete | Lee | Gupta, Anil <anil.gupta@arcadis.com> | 1 | 1 | 0
| 204.3-1 | HS2-00002N7V9 | Stoke Mandeville South Embankment 056-AC8 | 1MC06-ASC-CV-FRM-CS03_CL17-000016-ACBOS | P02 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600066 |  | zero value confirmations. 29-2-24 |  | accidentally revised ACBOS file | [5 empty] | 10 - Complete | Lee | Saranga, Bhargavi <bhargavi.saranga@arcadis.com> | 0 | 2 | 0
| 204.3-1 | HS2-00002ZM6N | Stoke Mandeville South Embankment 056-AC7 | 1MC06-ASC-CV-FRM-CS03_CL17-000034-ACBOS | P03 | 2024-02-29 | 2024-03-01 | 2024-03-01 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600104 |  | zero value confirmations. 29-2-24 |  | DT fixing MTRL / IFC / GdMt mismatch by morning 1/3/24 | rcvd 1/3/24 |  |  |  |  | 10 - Complete | Lee | Saranga, Bhargavi <bhargavi.saranga@arcadis.com> | 0 | 2 | 1
| 235.01 | HS2-00002CUCM | Banbury Road Warwick Road | 1MC07-ASC-DR-FRM-CS07_CL14-000019-ACBOS | P02 | 2024-02-29 | 2024-02-29 | 2024-03-01 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600005 | [9 empty] | 10 - Complete | Supriyan | M, Nischitha <nischitha.m@arcadis.com> | 1 | 0 | 0
| 237.05 | HS2-000020P0U | Radbourne Lane Realignment | 1MC07-ASC-HW-FRM-CS07_CL23-000036-ACBOS | P01 | 2024-03-01 | 2024-03-04 | 2024-03-05 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600064 |  | Multiple Observations, send back 04-MAr-2024 | 2024-03-04 | [6 empty] | 10 - Complete | Lee | Matthew Coote <mtce@cowi.com> | 1 | 1 | 3
| 237.05 | HS2-000020P0W | Maintenace Acess Road to Pond (Off Radbourne Lane South) | 1MC07-ASC-HW-FRM-CS07_CL23-000037-ACBOS | P01 | 2024-03-01 | 2024-03-04 | 2024-03-05 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600037 |  | Com_type and other issues, send back on 04-Mar-2024 | 2024-03-04 | [6 empty] | 10 - Complete | Lee | Matthew Coote <mtce@cowi.com> | 1 | 1 | 3
| 237.05 | HS2-00002TMWF | Ladbroke Grove Cutting Access Stairs | 1MC07-ASC-CV-FRM-CS07_CL23-000100-ACBOS | P01 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600160 | [9 empty] | 10 - Complete | Supriyan | Martin, Joel <Joel.Martin@arcadis.com> | 0 | 0 | 3
| 237.05 | HS2-00003G3SJ | Ladbroke Grove Cutting Access Stairs CH.121+020 | 1MC07-ASC-CV-FRM-CS07_CL23-000102-ACBOS | P01 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600159 | [9 empty] | 10 - Complete | Supriyan | Martin, Joel <Joel.Martin@arcadis.com> | 0 | 0 | 3
| 207.2 | HS2-000020RKL | Oat Close Bridleway (SBH-19) Realignment | 1MC06-ASC-HW-FRM-CS04_CL18-000003-ACBOS | P01 | 2024-03-01 | 2024-03-05 | 2024-03-06 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600069 |  | Com_Type , Com_Description issues, send back on 04-Mar-2024 | [7 empty] | 10 - Complete | Supriyan | jamie.gill@arcadis.com> | 1 | 1 | 4
| 205.03 | HS2-000001289 | Footpath SMA9 Accommodation Overbridge | 1MC06-CEK-BR-FRM-CS04_CL18-000009 | P02 | 2024-03-01 | 2024-03-04 | 2024-03-04 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600057 | [9 empty] | 10 - Complete | Lee | AIGU@cowi.com> | 0 | 0 | 3
| 238.02_2 | HS2-00002YNH8 | Ladbroke Cutting Culvert 124-AC3 | 1MC07-ASC-CV-FRM-CS07_CL24-000053-ACBOS | P01 | 2024-03-04 | 2024-03-05 | 2024-03-06 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600113 |  | clarifications odd rebar values. 4-3-24 | 2024-03-05 | [6 empty] | 10 - Complete | Lee | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 1 | 1 | 1
| 229.01-1 | HS2-00003B5FS | Greatworth Access Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL25-000025-ACBOS | P01 | 2024-03-04 | 2024-03-04 | 2024-03-06 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600068 | [9 empty] | 10 - Complete | Supriyan | B, Gopika <gopika.b@arcadis.com> | 2 | 0 | 0
| 235.01 | HS2-00003GEF1 | Boddington Cutting | 1MC07-ASC-CV-FRM-CS07_CL14-000097-ACBOS | P01 | 2024-03-04 | 2024-03-05 | 2024-03-06 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600183 | [9 empty] | 10 - Complete | Supriyan | S, Arun Kumar <ArunKumar.S@arcadis.com> | 1 | 0 | 1
| 235.01 | HS2-00003GEEY | Boddington Cutting | 1MC07-ASC-CV-FRM-CS07_CL14-000094-ACBOS | P01 | 2024-03-04 | 2024-03-05 | 2024-03-06 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600179 |  | ABT rebar confirmation rqrd. 5-Mar-24 | 2024-03-05 | [6 empty] | 10 - Complete | Lee | S, Arun Kumar <ArunKumar.S@arcadis.com> | 1 | 1 | 1
| 235.01 | HS2-00003GEEZ | Boddington Cutting | 1MC07-ASC-CV-FRM-CS07_CL14-000095-ACBOS | P01 | 2024-03-04 | 2024-03-05 | 2024-03-06 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600180 |  | ABT rebar confirmation rqrd. 5-Mar-24 | 2024-03-05 | [6 empty] | 10 - Complete | Lee | S, Arun Kumar <ArunKumar.S@arcadis.com> | 1 | 1 | 1
| 235.01 | HS2-00003GEF0 | Boddington Cutting | 1MC07-ASC-CV-FRM-CS07_CL14-000096-ACBOS | P01 | 2024-03-04 | 2024-03-05 | 2024-03-06 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600181 |  | ABT rebar confirmation rqrd. 5-Mar-24 | 2024-03-05 | [6 empty] | 10 - Complete | Lee | S, Arun Kumar <ArunKumar.S@arcadis.com> | 1 | 1 | 1
| 235.01 | HS2-00003H077 | Boddington Cutting | 1MC07-ASC-CV-FRM-CS07_CL14-000106-ACBOS | P01 | 2024-03-04 | 2024-03-05 | 2024-03-06 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600182 |  | ABT rebar confirmation rqrd. 5-Mar-24 | 2024-03-05 | [6 empty] | 10 - Complete | Lee | S, Arun Kumar <ArunKumar.S@arcadis.com> | 1 | 1 | 1
| UFDR 204.A | HS2-000020CEB | CSO-02-3108P | 1MC06-ASC-UT-FRM-CS03_CL17-000030-ACBOS | P01 | 2024-03-05 | 2024-03-05 | 2024-03-07 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600042 | [9 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com> | 2 | 0 | 0
| 235.01 | HS2-00003GJJR | Boddington Cutting Access Stairs CH.115.880 | 1MC07-ASC-CV-FRM-CS07_CL14-000056-ACBOS | P01 | 2024-03-05 | 2024-03-12 | 2024-03-13 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600173 |  | MxmmPrmttdWght & Clarifications. 7/3/24 | 2024-03-11 | chainage rework 11-Mar-24 | rvsd file 12-Mar-24 |  |  |  |  | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 1 | 2 | 7
| 235.01 | HS2-00003GJJS | Boddington Cutting Access Stairs CH.115.930 | 1MC07-ASC-CV-FRM-CS07_CL14-000047-ACBOS | P01 | 2024-03-05 | 2024-03-12 | 2024-03-13 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600171 |  | MxmmPrmttdWght & Clarifications. 7/3/24 | 2024-03-11 | chainage rework 11-Mar-24 | rvsd file 12-Mar-24 |  |  |  |  | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 1 | 2 | 7
| 235.01 | HS2-00003GJJT | Boddington Cutting Access Stairs CH.115.940 | 1MC07-ASC-CV-FRM-CS07_CL14-000050-ACBOS | P01 | 2024-03-05 | 2024-03-12 | 2024-03-13 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600172 |  | MxmmPrmttdWght & Clarifications. 7/3/24 | 2024-03-11 | chainage rework 11-Mar-24 | rvsd file 12-Mar-24 |  |  |  |  | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 1 | 2 | 7
| 228.2 | HS2-000001436 | Helmdon Culvert | 1MC07-CEK-BR-FRM-CS07_CL12-000012 | P06 | 2024-03-05 | 2024-03-06 | 2024-03-07 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600120 |  | Wrong sdslp, sent back on 06-Mar-2024 | [7 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 1
| 212.3 | HS2-00002YD78 | SMA/9 GSM-R Compound and Access Road | 1MC06-ASC-HW-FRM-CS04_CL18-000058-ACBOS | P02 | 2024-03-05 | 2024-03-07 | 2024-03-08 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600146 |  | AnglSlp values incorrect - inconsistent with Sdslp as per DAC_02 KB 6/3/24 | rvsd 7-Mar-24 | [6 empty] | 10 - Complete | Lee | Mallya, Bharath <bharath.mallya@arcadis.com> | 1 | 1 | 2
| 212.3 | HS2-00002YYN2 | Access to GSM-R Compound Point 33 | 1MC06-ASC-HW-FRM-CS04_CL20-000092-ACBOS | P02 | 2024-03-05 | 2024-03-07 | 2024-03-08 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600221 |  | AnglSlp values incorrect - inconsistent with Sdslp as per DAC_02 KB 6/3/24 | rvsd 7-Mar-24 | [6 empty] | 10 - Complete | Lee | Mallya, Bharath <bharath.mallya@arcadis.com> | 1 | 1 | 2
| 212.3 | HS2-00002YZKU | GSM-R Compound Point 33 | 1MC06-ASC-HW-FRM-CS04_CL20-000094-ACBOS | P02 | 2024-03-05 | 2024-03-05 | 2024-03-07 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600220 |  | None | [7 empty] | 10 - Complete | Lee | Mallya, Bharath <bharath.mallya@arcadis.com> | 2 | 1 | 0
| 212.3 | HS2-00002ZM2B | Putlowes GSM-R Compound and Access Road | 1MC06-ASC-HW-FRM-CS04_CL20-000089-ACBOS | P02 | 2024-03-05 | 2024-03-07 | 2024-03-08 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600219 |  | AnglSlp values incorrect - inconsistent with Sdslp as per DAC_02 KB 6/3/24 | rvsd 7-Mar-24 | [6 empty] | 10 - Complete | Lee | Mallya, Bharath <bharath.mallya@arcadis.com> | 1 | 1 | 2
| 207.2 | HS2-000001293 | Bridleway SBH/19 Overbridge | 1MC06-CEK-BR-FRM-CS04_CL18-000010 | P09 | 2024-03-05 | 2024-03-07 | 2024-03-07 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600065 |  | Confirmations and incomplete GlyMtrl, MxmmPrmttdWght 6/3/24 | rvsd 7/3/24 | [6 empty] | 10 - Complete | Lee | HRFO@COWI.COM | 0 | 1 | 2
| 207.2 | HS2-00002CT4Z | C2.T.21 Catchment | 1MC06-ASC-DR-FRM-CS04_CL18-000006-ACBOS | P01 | 2024-03-05 | 2024-03-05 | 2024-03-07 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600080 |  | AnglSlp values incorrect - inconsistent with Sdslp as per DAC_02 KB 6/3/24 |  | JSON olace holder changed 8/3/24 | [5 empty] | 10 - Complete | Supriyan | Ramos, Leo <Leomel.Ramos@arcadis.com> | 2 | 2 | 0
| 207.2 | HS2-00002N7VP | Aylesbury Embankment - Ancillary Culvert 060-AC4 | 1MC06-ASC-CV-FRM-CS04_CL18-000033-ACBOS | P01 | 2024-03-05 | 2024-03-07 | 2024-03-07 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600087 |  | Com_type is not as per guidline , send abck on 06th March | [7 empty] | 10 - Complete | Supriyan | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com> | 0 | 1 | 2
| 207.2 | HS2-00002N7VQ | Aylesbury Embankment - Ancillary Culvert 061-AC1 | 1MC06-ASC-CV-FRM-CS04_CL18-000031-ACBOS | P01 | 2024-03-05 | 2024-03-06 | 2024-03-07 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600147 |  | Com_type issues, send back on 6th March |  | JSON olace holder changed 8/3/24 | [5 empty] | 10 - Complete | Supriyan | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com> | 1 | 2 | 1
| 205.3 | HS2-000020NBF | Whitethorn Farm (SMA-9) Footpath and Accommodation Access Realignment | 1MC06-ASC-HW-FRM-CS03_CL17-000025-ACBOS | P02 | 2024-03-05 | 2024-03-05 | 2024-03-06 | Yes | 1MC06-CEK-IM-DAT-CS03_CL17-600004 |  | offline acbos sent with updated coords. 5-Mar-24 | [7 empty] | 10 - Complete |  | Bhattacharya, Ayan <Ayan.Bhattacharya@arcadis.com> | 1 | 1 | 0
| 229.03 | HS2-00003B2GJ | Greatworth North Embankment Cutting | 1MC07-ASC-CV-FRM-CS07_CL12-000107-ACBOS | P01 | 2024-03-06 | 2024-03-11 | 2024-03-12 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600286 |  | reba confirmations / identical chainages 7/3/24 | [7 empty] | 10 - Complete | Lee | PATIL, APOORVA <apoorva.patil@arcadis.com> | 1 | 1 | 5
| 219.3 | HS2-00002CTA0 | Cowley Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000032-ACBOS | P01 | 2024-03-06 | 2024-03-06 | 2024-03-08 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600062 |  | None | [7 empty] | 10 - Complete | Lee | youssef.miri@setec.com | 2 | 1 | 0
| 219.3 | HS2-00002CTA4 | Twyford Cutting Boundary/Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000028-ACBOS | P01 | 2024-03-06 | 2024-03-07 | 2024-03-08 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600066 |  | None | [7 empty] | 10 - Complete | Lee | youssef.miri@setec.com | 1 | 1 | 1
| 219.3 | HS2-00002CTA6 | Twyford Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000035-ACBOS | P01 | 2024-03-06 | 2024-03-07 | 2024-03-08 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600099 |  | None | [7 empty] | 10 - Complete | Lee | youssef.miri@setec.com | 1 | 1 | 1
| 219.3 | HS2-00002CT9Y | Cowley Embankment Boundary/Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000026-ACBOS | P01 | 2024-03-06 | 2024-03-06 | 2024-03-07 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600060 | [9 empty] | 10 - Complete | Supriyan | youssef.miri@setec.com | 1 | 0 | 0
| 219.3 | HS2-000033GP3 | Clean Water Pipe CFA_13_08 | 1MC06-CEK-UT-FRM-CS06_CL10-600014 | P01 | 2024-03-06 | 2024-03-11 | 2024-03-12 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600208 |  | few confirmations / some non integer where integer required. 8/3/24 | 2024-03-11 | [6 empty] | 10 - Complete | Lee | Singh, Prashant <prashant.singh2@arcadis.com> | 1 | 1 | 5
| UFDR 222.B | HS2-0000245Z8 | CSO-03-6201 | 1MC06-ASC-UT-FRM-CS06_CL21-000033-ACBOS | P01 | 2024-03-07 | 2024-03-11 | 2024-03-11 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600024 |  | all chainges identical / reduced attribution 3rd party | [7 empty] | 10 - Complete | Lee | B, Bharath Kumar <bharathkumar.b@arcadis.com> | 0 | 1 | 4
| 224.F | HS2-000020CH8 | CSO-04-1301P | 1MC06-ASC-UT-FRM-CS06_CL22-000028-ACBOS | P01 | 2024-03-07 | 2024-03-07 | 2024-03-08 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600106 | [9 empty] | 10 - Complete | Lee | White, Nick <Nicholas.White@arcadis.com> | 1 | 0 | 0
| 205.3 | HS2-000020NBF | Whitethorn Farm (SMA-9) Footpath and Accommodation Access Realignment | 1MC06-ASC-HW-FRM-CS03_CL17-000025-ACBOS | P03 | 2024-03-07 10:55 | 2024-03-07 10:55 | 2024-03-07 12:46 | Yes | 1MC06-CEK-IM-DAT-CS03_CL17-600004 | [9 empty] | 10 - Complete | Lee | Abdelmalik Hassen <ABHS@cowi.com> | 0 | 0 | 0
| UFDR 232.C | HS2-000020CJE | CSO-04-3124 | 1MC07-ASC-UT-FRM-CS07_CL26-000027-ACBOS | P01 | 2024-03-08 | 2024-03-08 | 2024-03-11 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600034 | [9 empty] | 10 - Complete | Supriyan | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 1 | 0 | 0
| UFDR 232.C | HS2-000020CJF | CSO-04-3113 | 1MC07-ASC-UT-FRM-CS07_CL26-000025-ACBOS | P01 | 2024-03-08 | 2024-03-08 | 2024-03-11 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600025 | [9 empty] | 10 - Complete | Supriyan | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 1 | 0 | 0
| UFDR 232.C | HS2-00002FEA3 | C23-109-0003 | 1MC07-ASC-UT-FRM-CS07_CL26-000029-ACBOS | P01 | 2024-03-08 | 2024-03-08 | 2024-03-11 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600070 | [9 empty] | 10 - Complete | Supriyan | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 1 | 0 | 0
| UFDR 204.E | HS2-000020CEE | CSO-02-2201 (SGN) | 1MC06-ASC-UT-FRM-CS03_CL17-000022-ACBOS | P01 | 2024-03-08 | 2024-03-11 | 2024-03-13 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600043 |  | Old Schema used all chainges identical / reduced attribution 3rd party | Colin Reith TQ-801 statement 11/3/24 | [6 empty] | 10 - Complete | Lee | Anthony Payne <aype@cowi.com> | 2 | 1 | 3
| UFDR 204.E | HS2-000020CEF | CSO-02-3300 (Vodafone) | 1MC06-ASC-UT-FRM-CS03_CL17-000023-ACBOS | P01 | 2024-03-08 | 2024-03-11 | 2024-03-13 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600045 |  | Old Schema used all chainges identical / reduced attribution 3rd party | Colin Reith TQ-801 statement 11/3/24 | [6 empty] | 10 - Complete | Lee | Anthony Payne <aype@cowi.com> | 2 | 1 | 3
| UFDR 204.E | HS2-000020CEG | CSO-02-3109 (BT Openreach) | 1MC06-ASC-UT-FRM-CS03_CL17-000024-ACBOS | P01 | 2024-03-08 | 2024-03-11 | 2024-03-13 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600046 |  | Old Schema used all chainges identical / reduced attribution 3rd party | Colin Reith TQ-801 statement 11/3/24 | [6 empty] | 10 - Complete | Lee | Anthony Payne <aype@cowi.com> | 2 | 1 | 3
| UFDR 204.E | HS2-000020CEH | CSO-02-3110 (BT Openreach) | 1MC06-ASC-UT-FRM-CS03_CL17-000025-ACBOS | P01 | 2024-03-08 | 2024-03-11 | 2024-03-13 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600044 |  | Old Schema used all chainges identical / reduced attribution 3rd party | Colin Reith TQ-801 statement 11/3/24 | [6 empty] | 10 - Complete | Lee | Anthony Payne <aype@cowi.com> | 2 | 1 | 3
| 235.01-2 | HS2-00003GEES | Boddington Cutting (Banbury Road OB) 116 - DC1 | 1MC07-ASC-CV-FRM-CS07_CL14-000093-ACBOS | P01 | 2024-03-11 | 2024-03-12 | 2024-03-13 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600184 | [9 empty] | 10 - Complete | Lee | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 1 | 0 | 1
| 235.01-2 | HS2-00003GEET | Boddington Cutting (Banbury Road OB) 115 - DC2 | 1MC07-ASC-CV-FRM-CS07_CL14-000091-ACBOS | P01 | 2024-03-11 | 2024-03-12 | 2024-03-13 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600185 | [9 empty] | 10 - Complete | Lee | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 1 | 0 | 1
| 235.01-2 | HS2-00003GEEU | Boddington Cutting (Banbury Road OB) 115 - DC3 | 1MC07-ASC-CV-FRM-CS07_CL14-000092-ACBOS | P01 | 2024-03-11 | 2024-03-12 | 2024-03-13 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600186 | [9 empty] | 10 - Complete | Lee | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 1 | 0 | 1
| 204.2-1 | HS2-000001025 | Stoke Mandeville South Embankment | 1MC06-ASC-GT-FRM-CS03_CL17-000001-ACBOS | P08 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600001 | [9 empty] | 10 - Complete | Supriyan | Chatterjee, Sourav <SouravKumar.Chatterjee@arcadis.com> | 2 | 0 | 0
| 204.2-1 | HS2-00002F0X2 | Stoke Mandeville South Embankment Landscape Earthworks | 1MC06-ASC-GT-FRM-CS03_CL17-000004-ACBOS | P02 | 2024-03-11 |  |  |  | 1MC06-CEK-IM-DAT-CS03_CL17-600022 | [9 empty] | 99 - Cancelled | Supriyan | Chatterjee, Sourav <SouravKumar.Chatterjee@arcadis.com>
| 235.01 | HS2-00002CTJD | Boddington Cutting Boundary/Perimeter Fence Line | 1MC07-ASC-CV-FRM-CS07_CL14-000005-ACBOS | P01 | 2024-03-11 | 2024-03-19 | 2024-03-22 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600003 |  | Old Schema used CM_CRT & Chg using P04. | 2024-03-19 | [6 empty] | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 3 | 1 | 8
| 235.01 | HS2-00002CTJE | Boddington Cutting Security Fence Line | 1MC07-ASC-CV-FRM-CS07_CL14-000008-ACBOS | P01 | 2024-03-11 | 2024-03-19 | 2024-03-22 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600006 |  | Old Schema used CM_CRT & Chg using P04. | 2024-03-19 | [6 empty] | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 3 | 1 | 8
| 221.2 | HS2-000020357 | The Green Highway Realignment | 1MC06-ASC-HW-FRM-CS06_CL10-000012-ACBOS | P01 | 2024-03-11 | 2024-03-11 | 2024-03-12 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600020 |  | send feedback on missing attributes, 0's and null on 11-Mar-2024 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600029 | [5 empty] | 10 - Complete | Supriyan | zakaria.khabouze@setec.com> | 1 | 2 | 0
| 221.2 | HS2-000020NLY | Chetwode ATS Access Road and Maintenance Access Road to Pond (P-RAI-0846) | 1MC06-ASC-HW-FRM-CS06_CL10-000008-ACBOS | P01 | 2024-03-11 | 2024-03-12 | 2024-03-13 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600026 |  | send queries regaring 0's, blank and missing attribute on 11-Mar-2024 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600027 | [5 empty] | 10 - Complete | Supriyan | zakaria.khabouze@setec.com> | 1 | 2 | 1
| 221.2 | HS2-000020NLZ | Footpath CHW/18 Accommodation Access Realignment | 1MC06-ASC-HW-FRM-CS06_CL10-900022-ACBOS | P01 | 2024-03-11 | 2024-03-12 | 2024-03-13 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600027 |  | Send queries on 0's, null, missing attribute on 11-March-2024 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600026 | [5 empty] | 10 - Complete | Supriyan | zakaria.khabouze@setec.com> | 1 | 2 | 1
| 221.2 | HS2-00002QH92 | Footpath CHW/18 Diversion | 1MC06-ASC-HW-FRM-CS06_CL10-000019-ACBOS | P01 | 2024-03-11 | 2024-03-11 | 2024-03-12 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600029 |  | Send Queires on Blank, 0's and null on 11-Mar-2024 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600020 | [5 empty] | 10 - Complete | Supriyan | zakaria.khabouze@setec.com> | 1 | 2 | 0
| 220.3 | HS2-00002N7W7 | Twyford Cutting - Ancillary Culvert 083-AC1 | 1MC06-ASC-DR-FRM-CS06_CL10-000075-ACBOS | P01 | 2024-03-11 | 2024-03-14 | 2024-03-18 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600050 |  | some values set to Please choose , 2 com _typ incorrect. Some 0 value confirmations rqrd. 12/3/24 | 2024-03-14 | [6 empty] | 10 - Complete | Lee | GOIMARD Thomas <thomas.goimard@setec.com> | 2 | 1 | 3
| 220.3 | HS2-000032217 | Twyford Cutting - Ancillary Culvert 083 - AC2 | 1MC06-ASC-DR-FRM-CS06_CL10-000073-ACBOS | P01 | 2024-03-11 | 2024-03-11 | 2024-03-18 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600135 |  | some values set to Please choose , Some 0 value confirmations rqrd. 12/3/24 | 2024-03-13 | [6 empty] | 10 - Complete | Lee | GOIMARD Thomas <thomas.goimard@setec.com> | 5 | 1 | 0
| UFDR 230.B | HS2-000020CJA | CSO-04-1321 | 1MC07-ASC-UT-FRM-CS07_CL26-000004-ACBOS | P01 | 2024-03-12 | 2024-03-13 | 2024-03-14 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600076 | [9 empty] | 10 - Complete | Supriyan | Varma, Srinivasa <srinivasa.varma@arcadis.com> | 1 | 0 | 1
| 229.01-1 | HS2-000025B2C | MPDT - Greatworth Green Tunnel South Portal Building - Architectural Model | 1MC07-CEK-AR-FRM-CS07_CL25-600002 | P01 | 2024-03-12 | 2024-04-03 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 | [5 empty] | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 46 | 2 | 22
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - External Works MPDT | 1MC07-CEK-CV-FRM-CS07_CL25-000008 | P01 | 2024-03-12 | 2024-05-30 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 |  | Com_typs - incorrect 29/4/24 | rev 3.0 file exported. There is a 4.1 minor rev live but POC on AL |  |  | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 7 | 3 | 79
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - Structures MPDT | 1MC07-ASC-CV-FRM-CS07-000001-ACBOS | P01 | 2024-03-12 | 2024-04-10 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 | [5 empty] | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 41 | 2 | 29
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - Electrical CMS MPDT | 1MC07-CEK-EL-FRM-CS07_CL25-000006 | P01 | 2024-03-12 | 2024-04-04 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 | [5 empty] | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 45 | 2 | 23
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - Electrical External MPDT | 1MC07-CEK-EL-FRM-CS07_CL25-000007 | P01 | 2024-03-12 | 2024-04-04 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 | [5 empty] | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 45 | 2 | 23
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - Electrical Lighting MPDT | 1MC07-CEK-EL-FRM-CS07_CL25-000008 | P01 | 2024-03-12 | 2024-04-04 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 | [5 empty] | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 45 | 2 | 23
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - Electrical Lightning and Earthing MPDT | 1MC07-CEK-EL-FRM-CS07_CL25-000009 | P01 | 2024-03-12 | 2024-04-04 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 | [5 empty] | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 45 | 2 | 23
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - Electrical Small Power MPDT | 1MC07-CEK-EL-FRM-CS07_CL25-000010 | P01 | 2024-03-12 | 2024-04-04 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 | [5 empty] | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 45 | 2 | 23
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - Fire Detection and Alarm MPDT | 1MC07-CEK-FI-FRM-CS07_CL25-000004 | P01 | 2024-03-12 | 2024-04-03 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 | [5 empty] | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 46 | 2 | 22
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - Fire Gas Suppression MPDT | 1MC07-CEK-FI-FRM-CS07_CL25-000005 | P01 | 2024-03-12 | 2024-04-03 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 | [5 empty] | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 46 | 2 | 22
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - Fire Hydrant System MPDT | 1MC07-CEK-FI-FRM-CS07_CL25-000006 | P01 | 2024-03-12 | 2024-04-03 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 | [5 empty] | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 46 | 2 | 22
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - Mechanical Ventilation MPDT | 1MC07-CEK-ME-FRM-CS07_CL25-000004 | P01 | 2024-03-12 | 2024-04-04 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 | [5 empty] | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 45 | 2 | 23
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - Public Health Above Ground Drainage MPDT | 1MC07-CEK-ME-FRM-CS07_CL25-000005 | P01 | 2024-03-12 | 2024-04-03 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 | [5 empty] | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 46 | 2 | 22
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - Mechanical Heating and Cooling MPDT | 1MC07-CEK-ME-FRM-CS07_CL25-000006 | P01 | 2024-03-12 | 2024-04-04 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 | [5 empty] | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 45 | 2 | 23
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South Portal Building - Telecom Security MPDT | 1MC07-CEK-RC-FRM-CS07_CL25-000006 | P01 | 2024-03-12 | 2024-04-04 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | Done. No Issues | Metrics fail to match Smartforms. 1-May-24 |  |  |  | missing SnakeGrids | 2024-04-04 | File c hecked. Loaded to SQL |  | 10 - Complete | Lee | shashank.bs@arcadis.com | 45 | 3 | 23
| 238.01 | HS2-00002CTK9 | Ladbroke Watercourse Diversion | 1MC07-ASC-DR-FRM-CS07_CL24-000053-ACBOS | P02 | 2024-03-12 | 2024-03-13 | 2024-03-14 | Yes | 1MC07-CEK-IM-DAT-CS07_CL24-600044 |  | NSW category has no data. 101 expected component 91 in Acbos 10 NSW missing. Other than that everything else is perfect. | 2024-03-13 | [6 empty] | 10 - Complete | Lee | Puri, Anna <anamika.puri@wsp.com> | 1 | 1 | 1
| 213.02 | HS2-000001040 | Quainton Cutting Earthworks | 1MC06-ASC-GT-FRM-CS05-000010-ACBOS | P02 | 2024-03-12 | 2024-03-13 | 2024-03-14 |  | 1MC06-CEK-IM-DAT-CS05-600098 |  | ACBOS is not completed with PCRA, send back on 13-Mar-2024 | [7 empty] | 10 - Complete | Supriyan | farah.mattoussi@setec.com | 1 | 1 | 1
| 213.02 | HS2-00002BVGE | Quainton Cutting Mitigation Earthworks | 1MC06-ASC-GT-FRM-CS05-000013-ACBOS | P02 | 2024-03-12 | 2024-03-13 | 2024-03-15 |  | 1MC06-CEK-IM-DAT-CS05-600095 |  | Multiple observations, send back on 13-Mar-2024 | [7 empty] | 10 - Complete | Supriyan | MATTOUSSI Farah <farah.mattoussi@setec.com> | 2 | 1 | 1
| 235.01-2 | HS2-00003H075 | ACBOS - Boddington Cutting (Banbury Road OB) 115 - DC4 | 1MC07-ASC-CV-FRM-CS07_CL14-000104-ACBOS | P01 | 2024-03-13 | 2024-03-13 | 2024-03-19 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600187 | [9 empty] | 10 - Complete | Supriyan | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 4 | 0 | 0
| 235.01-2 | HS2-00003H076 | ACBOS - Boddington Cutting (Banbury Road OB) 115 - DC5 | 1MC07-ASC-CV-FRM-CS07_CL14-000105-ACBOS | P01 | 2024-03-13 | 2024-03-13 | 2024-03-19 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600188 | [9 empty] | 10 - Complete | Supriyan | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 4 | 0 | 0
| 238.01 | HS2-00002BVN8 | C3.L.73 Catchment | 1MC07-CEK-DR-FRM-CS07_CL23-000009 | P03 | 2024-03-13 | 2024-03-13 | 2024-03-14 | YES | 1MC07-CEK-IM-DAT-CS07_CL24-600055 | [9 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 1 | 0 | 0
| 237.05 | HS2-00002CTK3 | C3.T.71 Catchment | 1MC07-ASC-DR-FRM-CS07_CL23-000005-ACBOS | P03 | 2024-03-13 | 2024-03-21 | 2024-03-22 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600030 |  | incorrect JSON placeholder corrected 22-Mar-24 | [7 empty] | 10 - Complete | Lee | Charuvil Vivekanandan, Amrutha <Amrutha.CharuvilVivekananda@arcadis.com> | 1 | 1 | 8
| 221.2 | HS2-00002CW0X | Footpath CHW/18 and green Road Closure Drainage System | 1MC06-ASC-DR-FRM-CS06_CL10-000018-ACBOS | P05 | 2024-03-14 | 2024-03-15 | 2024-03-18 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600009 | [9 empty] | 10 - Complete | Supriyan | youssef.miri@setec.com | 1 | 0 | 1
| 219.3 | HS2-0000386U9 | 82-SL1 Cowley Embankment Vehicular Bridge - Earthworks Transition - 3D model | 1MC06-ASC-BR-FRM-CS06_CL10-000026-ACBOS | P01 | 2024-03-14 | 2024-03-22 | 2024-03-27 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600205 |  | wrong sdslp format, comas instead of dots. Send back on 18th Mar 2024 | [7 empty] | 10 - Complete | Supriyan | MARQUES GOMES Barbara <barbara.marquesgomes@setec.com> | 3 | 1 | 8
| 219.3 | HS2-0000386UA | 82-SL2 Cowley Embankment Pedestrian Bridge - Earthworks Transition - 3D model | 1MC06-ASC-BR-FRM-CS06_CL10-000029-ACBOS | P01 | 2024-03-14 | 2024-03-22 | 2024-03-27 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600207 |  | wrong sdslp format, Send back on 18th Mar 2024 | [7 empty] | 10 - Complete | Supriyan | MARQUES GOMES Barbara <barbara.marquesgomes@setec.com> | 3 | 1 | 8
| 213.02 | HS2-00002BVGC | Quainton Cutting Earthworks | 1MC06-ASC-DR-FRM-CS05-000004-ACBOS | P01 | 2024-03-14 | 2024-03-15 | 2024-03-18 |  | 1MC06-CEK-IM-DAT-CS05-600094 |  | Few queries, send file on 15-Mar-2024 | [7 empty] | 10 - Complete | Supriyan | farah.mattoussi@setec.com | 1 | 1 | 1
| 204.2-1 | HS2-000001025 | Stoke Mandeville South Embankment | 1MC06-ASC-GT-FRM-CS03_CL17-000001-ACBOS | P09 | 2024-03-15 | 2024-03-18 | 2024-03-19 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600001 | [9 empty] | 10 - Complete | Supriyan | SouravKumar.Chatterjee@arcadis.com | 1 | 0 | 3
| 204.2-1 | HS2-00002F0X2 | Stoke Mandeville South Embankment Landscape Earthworks | 1MC06-ASC-GT-FRM-CS03_CL17-000004-ACBOS | P03 | 2024-03-15 | 2024-03-18 | 2024-03-18 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600022 | [9 empty] | 10 - Complete | Supriyan | SouravKumar.Chatterjee@arcadis.com | 0 | 0 | 3
| 237.05 | HS2-00002CTK4 | Radbourne ATS Access Road | 1MC07-ASC-HW-FRM-CS07_CL23-000040-ACBOS | P01 | 2024-03-15 | 2024-03-19 | 2024-03-19 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600031 | [9 empty] | 10 - Complete | Supriyan | Matthew Coote <mtce@cowi.com> | 0 | 0 | 4
| 213.02 | HS2-00002CT76 | C2.T.49 Catchment | 1MC06-ASC-DR-FRM-CS05-000026-ACBOS | P08 | 2024-03-15 | 2024-03-19 | 2024-03-20 |  | 1MC06-CEK-IM-DAT-CS05-600122 |  | send back with queries on 18th Mar 2024 | [7 empty] | 10 - Complete | Supriyan | farah.mattoussi@setec.com | 1 | 1 | 4
| UFDR 232.C | HS2-000020CJH | CSO-04-6107 | 1MC07-ASC-UT-FRM-CS07_CL26-000021-ACBOS | P01 | 2024-03-18 | 2024-03-19 | 2024-03-19 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600027 | [9 empty] | 10 - Complete | Supriyan | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 0 | 0 | 1
| 229.01-1 | HS2-000020359 | Greatworth Park Access Reinstatement | 1MC07-ASC-HW-FRM-CS07_CL25-000020-ACBOS | P01 | 2024-03-18 | 2024-03-19 | 2024-03-20 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600040 |  | wronf Angle slope, send back on 19th March | [7 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 1 | 1 | 1
| 229.01-1 | HS2-00002CTF7 | Footpath AN39 Reinstatement | 1MC07-ASC-HW-FRM-CS07_CL25-000028-ACBOS | P01 | 2024-03-18 | 2024-03-18 | 2024-03-19 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600001 | [9 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 1 | 0 | 0
| 229.01-1 | HS2-00002CTF8 | Footpath AN4 Reinstatement | 1MC07-ASC-HW-FRM-CS07_CL25-000029-ACBOS | P01 | 2024-03-18 | 2024-03-18 | 2024-04-04 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600002 | [9 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 11 | 0 | 0
| UFDR 204.A | HS2-000020CEC | CSO-02-1207 (UKPN) | 1MC06-ASC-UT-FRM-CS03_CL17-000017-ACBOS | P01 | 2024-03-19 | 2024-03-20 | 2024-03-21 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600041 |  | Few queries, and JSON place holder is missing. Send back on 20th Mar | [7 empty] | 10 - Complete | Supriyan | Anthony Payne <aype@cowi.com> | 1 | 1 | 1
| 238.02_2 | HS2-000037830 | Ladbroke Cutting Ancillary Pipe Culvert | 1MC07-ASC-CV-FRM-CS07_CL24-000057-ACBOS | P01 | 2024-03-19 | 2024-03-20 | 2024-03-21 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600114 | [9 empty] | 10 - Complete | Supriyan | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 1 | 0 | 1
| 204.2-1 | HS2-00002CT4N | C2.T.18 Catchment | 1MC06-ASC-DR-FRM-CS03_CL17-000006-ACBOS | P04 | 2024-03-19 | 2024-03-20 | 2024-03-22 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600009 |  | Sdslp and other issues. Send back on 20th March | [7 empty] | 10 - Complete | Supriyan | leomel.ramos@arcadis.com | 2 | 1 | 1
| 204.2-1 | HS2-00002CT4P | C2.T.20 Catchment | 1MC06-ASC-DR-FRM-CS03_CL17-000007-ACBOS | P04 | 2024-03-19 | 2024-03-20 | 2024-03-22 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600008 |  | Wrong Com Type and other issues, send back on 20th March | [7 empty] | 10 - Complete | Supriyan | leomel.ramos@arcadis.com | 2 | 1 | 1
| 204.2-1 | HS2-000030TD4 | Stoke Mandeville South Embankment Load Transfer Platform (North) | 1MC06-ASC-GT-FRM-CS03_CL17-000010-ACBOS | P01 | 2024-03-19 | 2024-03-27 | 2024-03-28 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600130 |  | Wrong Com Type, send back on 20th March | [7 empty] | 10 - Complete | Supriyan | Lasisi, Adewole <adewole.lasisi@arcadis.com> | 1 | 1 | 8
| 204.2-1 | HS2-000030TD5 | Stoke Mandeville South Embankment Load Transfer Platform (South) | 1MC06-ASC-GT-FRM-CS03_CL17-000012-ACBOS | P01 | 2024-03-19 | 2024-03-27 | 2024-03-28 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600131 |  | Wrong Com Type, send back on 20th March | [7 empty] | 10 - Complete | Supriyan | Lasisi, Adewole <adewole.lasisi@arcadis.com> | 1 | 1 | 8
| 237.05 | HS2-000032216 | Maintenance Access Road to Switch and Crossing MS2.11 | 1MC07-ASC-HW-FRM-CS07_CL23-000046-ACBOS | P01 | 2024-03-19 | 2024-03-20 | 2024-03-21 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600077 |  | Wrong UAID_1, send back 20th March | [7 empty] | 10 - Complete | Supriyan | Matthew Coote <mtce@cowi.com> | 1 | 1 | 1
| 229.03 | HS2-00002N7UD | Greatworth Green Tunnel Group - Ancillary Culvert 102-AC1 | 1MC07-ASC-CV-FRM-CS07_CL25-000006-ACBOS | P01 | 2024-03-19 | 2024-03-21 | 2024-03-22 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600059 |  | Mtrl / GdMT error on one L3, send back on 21-Mar-2024 | [7 empty] | 10 - Complete | Supriyan | Graeme Millen <graeme.millen@fairhurst.co.uk> | 1 | 1 | 2
| 212.3 | HS2-00002EK6X | Marsh Lane Radio Compound UTX | 1MC06-ASC-CV-FRM-CS04_CL18-000045-ACBOS | P01 | 2024-03-19 | 2024-03-22 | 2024-03-27 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600032 |  | Wrong Com Type and other issues, send back on 20th March | [7 empty] | 10 - Complete | Supriyan | surendar.loganathan@arcadis.com | 3 | 1 | 3
| 212.3 | HS2-00002Y0AR | Marsh Lane Perturbation Crossover UTX | 1MC06-ASC-CV-FRM-CS04_CL18-000068-ACBOS | P01 | 2024-03-19 | 2024-03-21 | 2024-03-22 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600148 |  | Wrong Com Type and other issues, send back on 20th March | [7 empty] | 10 - Complete | Supriyan | surendar.loganathan@arcadis.com | 1 | 1 | 2
| 229.03 | HS2-00002N7UC | Greatworth North Cutting Group - Ancillary Culvert 101-AC4 | 1MC07-ASC-CV-FRM-CS07_CL12-000044-ACBOS | P01 | 2024-03-20 | 2024-03-22 | 2024-03-27 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600280 |  | precast rebar - DT have identified missing values. Mtrl / GdMt mismatch found in ACBOS Dac check 21-mar-24 | 2024-03-22 | [6 empty] | 10 - Complete | Lee | Graeme Millen <graeme.millen@fairhurst.co.uk> | 3 | 1 | 2
| 229.01 | HS2-00002EK7K | Greatworth Green Tunnel South Portal UTX | 1MC07-ASC-CV-FRM-CS07_CL12-000049-ACBOS | P01 | 2024-03-20 | 2024-03-26 | 2024-03-28 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600013 |  | Com_type issues and other isses, send back on 21-Mar-2024 |  | Send back again as Com_type is not updated on 22-Mar-2024 | 2024-03-22 | DT have realised about identical component chainages - reworking ACBOS | 2024-03-26 | Srtfrms metrics out by one UTD asset | 2024-03-26 | 10 - Complete | Lee | Salazar, Dana <dana.salazar@arcadis.com> | 2 | 4 | 6
| 216.01 | HS2-000020NL1 | Field Access track (Off West Street) | 1MC06-ASC-HW-FRM-CS06_CL09-000023-ACBOS | P03 | 2024-03-20 | 2024-03-20 | 2024-03-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600102 |  | Dt confirm omission in teams call | [7 empty] | 10 - Complete | Lee | PraveenReddy.Yaruva@arcadis.com> | 5 | 1 | 0
| 216.01 | HS2-000020RM2 | West Street Realignment | 1MC06-ASC-HW-FRM-CS06_CL09-000022-ACBOS | P03 | 2024-03-20 | 2024-03-25 | 2024-03-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600100 |  | Dt confirm omission in teams call |  | 2 NetVolumes need to be set to non zero. 0.0001 would suffice. | [5 empty] | 10 - Complete | Lee | PraveenReddy.Yaruva@arcadis.com> | 2 | 2 | 5
| 216.01 | HS2-000020356 | Sewage Works Accomodation and Pond Access Road | 1MC06-ASC-HW-FRM-CS06_CL09-000024-ACBOS | P03 | 2024-03-20 | 2024-03-22 | 2024-03-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600156 |  | Wrong CM_CRT, send back on 22nd March 2024 | [7 empty] | 10 - Complete | Supriyan | PraveenReddy.Yaruva@arcadis.com> | 3 | 1 | 2
| 212.3 | HS2-00002EK71 | Thame Valley North Viaduct Radio Compound UTX | 1MC06-ASC-CV-FRM-CS04_CL19-000014-ACBOS | P01 | 2024-03-20 | 2024-03-22 | 2024-03-22 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600015 | [9 empty] | 10 - Complete | Supriyan | veerabhadraswamy.sp@arcadis.com> | 0 | 0 | 2
| 212.3 | HS2-00002EK72 | Putlowes Rail System Compound (ATS) UTX | 1MC06-ASC-CV-FRM-CS04_CL20-000047-ACBOS | P01 | 2024-03-20 | 2024-03-22 | 2024-03-22 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600005 | [9 empty] | 10 - Complete | Supriyan | veerabhadraswamy.sp@arcadis.com> | 0 | 0 | 2
| 212.3 | HS2-00002EK73 | Briar Hill Farm Radio Compound UTX | 1MC06-ASC-CV-FRM-CS04_CL20-000020-ACBOS | P01 | 2024-03-20 | 2024-03-22 | 2024-03-25 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600002 | [9 empty] | 10 - Complete | Supriyan | veerabhadraswamy.sp@arcadis.com> | 1 | 0 | 2
| 238.02_2 | HS2-00003H6PG | Ladbroke Cutting Ancillary Pipe Culvert 2 | 1MC07-ASC-CV-FRM-CS07_CL24-000066-ACBOS | P01 | 2024-03-21 | 2024-03-21 | 2023-03-27 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600119 | [9 empty] | 10 - Complete | Lee | Chris Gilmour <chris.gilmour@fairhurst.co.uk>
| 210.2-2 | HS2-000001299 | Putlowes Accommodation Overbridge | 1MC06-CEK-BR-FRM-CS04_CL20-000001 | P05 | 2024-03-21 | 2024-04-08 | 2024-04-09 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600034 |  | few odd value numbers. 1E+20 . | 2024-04-08 | [6 empty] | 10 - Complete | Lee | Aitor Reyes Gurruchaga <AIGU@cowi.com> | 1 | 1 | 18
| 237.05 | HS2-00002CTK5 | Ladbroke Grove Cutting Boundary Fence | 1MC07-ASC-CV-FRM-CS07_CL23-000059-ACBOS | P01 | 2024-03-21 | 2024-04-16 | 2024-04-22 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600028 |  | all GAT class UAID_2 incorrect 22-Mar-24 | 2024-03-26 | UAID_2 still incorfect sent back 26/3/24 | 2024-03-27 | DT have asked for HOLD as design change for fencing underway 5/5/24 | 2024-04-10 | SmartFroms mismatch 15-4-24 |  | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 4 | 4 | 26
| 237.05 | HS2-00002CTK6 | Ladbroke Grove Cutting Security Fence Line - Security Fence | 1MC07-ASC-CV-FRM-CS07_CL23-000099-ACBOS | P01 | 2024-03-21 | 2024-04-10 | 2024-04-12 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600029 |  | com_typs | 2024-03-27 |  |  | DT have asked for HOLD as design change for fencing underway 5/5/24 | 2024-04-10 |  |  | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 2 | 2 | 20
| 227.1 | HS2-00002N7X2 | Radstone Road Ancillary Culvert 097-AC2 | 1MC07-CEK-BR-FRM-CS07_CL12-600007 | P01 | 2024-03-21 | 2024-03-26 |  |  | 1MC07-CEK-IM-DAT-CS07_CL12-600047 |  | old schema, some confirmations needed 25/3/24 | 2024-03-26 | Old schema is not valid for post L3 - 28/03/2024 | [5 empty] | 99 - Cancelled | Lee | Puri, Anna <anamika.puri@wsp.com>
| 219.3 | HS2-00002CT9Y | Cowley Embankment Boundary/Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000026-ACBOS |  | 2024-03-21 | 2024-03-21 | 2024-03-27 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600060 |  | couple of odd zero values for Lgnth 22-Mar-24 | 25/3/24 - DT confirm omissions are intentional | [6 empty] | 10 - Complete | Lee | MIRI Youssef <youssef.miri@setec.com> | 4 | 1 | 0
| 219.3 | HS2-00002CTA0 | Cowley Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000032-ACBOS |  | 2024-03-21 | 2024-03-21 | 2024-03-27 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600062 | [9 empty] | 10 - Complete | Lee | MIRI Youssef <youssef.miri@setec.com> | 4 | 0 | 0
| 212.4 | HS2-00002Y0AT | Bicester Road Embankment No.1 Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL20-000071-ACBOS | P01 | 2024-03-21 | 2024-03-26 | 2024-03-28 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600236 |  | placeholders - incorrectly named. CM_ICI set as yes rebar confirmations 25/3/24 |  | DT asked for priority 27-Mar-24 | [5 empty] | 10 - Complete | Lee | Mortazavi, Shahed <shahed.mortazavi@arcadis.com> | 2 | 2 | 5
| 212.4 | HS2-00002Y479 | Bicester Road Embankment No.2 Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL20-000072-ACBOS | P01 | 2024-03-21 | 2024-03-26 | 2024-03-28 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600237 |  | placeholders - incorrectly named. rebar confirmations 25/3/24 |  | DT asked for priority 27-Mar-24 | [5 empty] | 10 - Complete | Lee | Mortazavi, Shahed <shahed.mortazavi@arcadis.com> | 2 | 2 | 5
| UFDR 230.C | HS2-000020CJ6 | CSO-04-1319 | 1MC07-ASC-UT-FRM-CS07_CL26-000011-ACBOS | P01 | 2024-03-22 | 2024-03-22 | 2024-03-27 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600017 | [9 empty] | 10 - Complete | Lee | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 3 | 0 | 0
| UFDR 221.D | HS2-000020CGK | Manthorne Farm Overbridge | 1MC06-ASC-UT-FRM-CS06_CL10-000019-ACBOS | P01 | 2024-03-22 | 2024-03-22 | 2024-03-26 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600017 |  | file contains incorrect UAID_2 for all items. No snake grid values |  | DT had sent incorrect UAID in JSON req. updating snakegrids now 26-mar-24 1136hrs | [5 empty] | 10 - Complete | Lee | Kamboj, Mohit <mohit.kamboj@arcadis.com> | 2 | 2 | 0
| UFDR 221.D | HS2-000020CGL | Manthorne Farm Overbridge | 1MC06-ASC-UT-FRM-CS06_CL10-000007-ACBOS | P02 | 2024-03-22 | 2024-03-22 | 2024-03-26 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600021 | [9 empty] | 10 - Complete | Lee | Kamboj, Mohit <mohit.kamboj@arcadis.com> | 2 | 0 | 0
| 221.2_1 | HS2-000001321 | Footpath CHW/18 Accommodation Overbridge | 1MC06-CEK-BR-FRM-CS06_CL10-000005 | P03 | 2024-03-22 | 2024-03-22 | 2024-04-03 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600018 |  | Issues with MPDT solved In house 2-Apr-24 | [7 empty] | 10 - Complete | Lee | DE OLIVEIRA DE ARAUJO Nuno Sergio <sergio.deoliveira@setec.com> | 6 | 1 | 0
| 204.2-1 | HS2-00002EK6W | Stoke Mandeville Maintenance Loop UTX No2 | 1MC06-ASC-CV-FRM-CS03_CL17-000011-ACBOS | P01 | 2024-03-22 | 2024-03-22 | 2024-03-28 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600019 | [9 empty] | 10 - Complete | Lee | S P, Veerabhadraswamy <veerabhadraswamy.sp@arcadis.com> | 4 | 0 | 0
| UFDR 228.A | HS2-000020CHV | CSO-04-1316 | 1MC07-ASC-UT-FRM-CS07_CL12-000028-ACBOS | P01 | 2024-03-25 | 2024-03-25 | 2024-03-27 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600006 | [9 empty] | 10 - Complete | Lee | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 2 | 0 | 0
| UFDR 228.A | HS2-00002FE9V | CSO-04-1317 | 1MC07-ASC-UT-FRM-CS07_CL25-000025-ACBOS | P01 | 2024-03-25 | 2024-03-25 | 2024-03-27 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600012 | [9 empty] | 10 - Complete | Lee | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 2 | 0 | 0
| UFDR 228.A | HS2-00002TTH9 | 1314 Greatworth Hall Ground Mounted Substation | 1MC07-ASC-UT-FRM-CS07_CL12-000109 | P01 | 2024-03-25 | 2024-03-25 | 2024-03-28 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600159 | [9 empty] | 10 - Complete | Lee | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 3 | 0 | 0
| UFDR 228.A | HS2-000020CHT | CSO-04-1314 | 1MC07-ASC-UT-FRM-CS07_CL12-000026-ACBOS | P01 | 2024-03-25 |  | 2024-03-27 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600038 | [9 empty] | 10 - Complete | Supriyan | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 2 | 0
| UFDR 228.A | HS2-000020CHU | CSO-04-1315 | 1MC07-ASC-UT-FRM-CS07_CL12-000027-ACBOS | P01 | 2024-03-25 | 2024-03-25 | 2024-03-27 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600007 | [9 empty] | 10 - Complete | Supriyan | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 2 | 0 | 0
| 237.05 | HS2-00002TKV0 | Ladbroke Grove Cutting | 1MC07-ASC-CV-FRM-CS07_CL23-000029-ACBOS | P01 | 2024-03-26 | 2024-03-29 | 2024-04-02 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600156 |  | Com_type and other issues, send back on 27Mar2024 |  | UAID_3 worng mapping send back on 28-Mar-2024 | [5 empty] | 10 - Complete | Supriyan | PHILIPOSE, IMMANUEL <immanuel.philipose@arcadis.com> | 0 | 2 | 3
| 237.05 | HS2-000032216 | Maintenance Access Road to Switch and Crossing MS2.11 | 1MC07-ASC-HW-FRM-CS07_CL23-000046-ACBOS | P02 | 2024-03-26 | 2024-03-26 | 2024-03-28 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600077 | [9 empty] | 10 - Complete | Supriyan | Matthew Coote <mtce@cowi.com> | 2 | 0 | 0
| 235.01 | HS2-00002TKUY | Boddington Cutting | 1MC07-ASC-CV-FRM-CS07_CL14-000061-ACBOS | P01 | 2024-03-26 | 2024-03-28 | 2024-04-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600176 |  | all chainages identical for all components, and start / end. | 2024-03-28 | [6 empty] | 10 - Complete | Lee | PHILIPOSE, IMMANUEL <immanuel.philipose@arcadis.com> | 1 | 1 | 2
| 235.01 | HS2-00002TKUZ | Boddington Cutting Oxford Cananl | 1MC07-ASC-CV-FRM-CS07_CL14-000078-ACBOS | P01 | 2024-03-26 | 2024-03-28 | 2024-04-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600177 |  | all chainages identical for all components, and start / end. | 2024-03-28 | [6 empty] | 10 - Complete | Lee | PHILIPOSE, IMMANUEL <immanuel.philipose@arcadis.com> | 1 | 1 | 2
| 227.1 | HS2-000001336 | Radstone Road Overbridge | 1MC07-CEK-BR-FRM-CS07_CL12-000001 | P10 | 2024-03-26 | 2024-03-27 |  |  | 1MC07-CEK-IM-DAT-CS07_CL12-600142 |  | Com_type and Com_Description issue, send back on 26th Mar -2024 | Sent back to the team 28/03/2024 to bring up to latest standards as a post L3 deliverable | [6 empty] | 99 - Cancelled | Supriyan | Egan, Conor <Conor.Egan@wsp.com>
| 227.1 | HS2-00002CQQF | Radstone Road Drainage System | 1MC07-CEK-DR-FRM-CS07_CL12-000005 | P13 | 2024-03-26 | 2024-03-27 | 2024-04-02 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600152 |  | Com_type and Com_Description issue, send back on 26th Mar -2024 | [7 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 2 | 1 | 1
| 220.3 | HS2-000001320 | Restricted Byway PBI-5A Accommodation Overbridge | 1MC06-CEK-BR-FRM-CS06_CL10-000004 | P08 | 2024-03-26 | 2024-04-10 | 2024-04-12 | Yes | 1MC06-CEK-IM-DAT-CS06_CL10-600058 |  | Height Min with 0's , send back on 27-Mar-2024 |  | Incorrect coordinates. 27-Mar-24 | 2024-04-10 |  |  |  |  | 10 - Complete | Lee | DE OLIVEIRA DE ARAUJO Nuno Sergio <sergio.deoliveira@setec.com>; KOSSARA Hafsa <hafsa.kossara@setec.com>; HERVOCHES Guillaume <guillaume.hervoches@setec.com>; BUSSON Etienne <etienne.busson@setec.com> | 2 | 2 | 15
| 212.4 | HS2-00002ZM2A | Thame Valley North Embankment No.1 Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL19-000052-ACBOS | P01 | 2024-03-26 | 2024-03-26 | 2024-04-02 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600095 | [9 empty] | 10 - Complete | Lee | Saranga, Bhargavi <bhargavi.saranga@arcadis.com> | 3 | 0 | 0
| 237.05 | HS2-00002TMFE | Radbourne ATS Telecoms | 1MC07-ASC-UT-FRM-CS07_CL23-000024-ACBOS | P01 | 2024-03-27 | 2024-03-27 | 2024-04-03 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600026 |  | Sdslp 0 confirmations. 28/3/24 | 2024-04-02 | [6 empty] | 10 - Complete | Lee | Agnieszka Cytowska <agcy@cowi.com> | 3 | 1 | 0
| 216.01 | HS2-000020NKK | Portway Farm ATS Access Road off Perry Hill Road | 1MC06-ASC-HW-FRM-CS06_CL09-000029-ACBOS | P02 | 2024-03-27 | 2024-04-15 | 2024-04-15 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600095 | Done, No Issues | ACBOS not apprpoved , initmated on 28-Mar-2024 |  | sdslp and angleslope conflict. Send back on 03-Apr-2024 |  | ACBOS PCRA not done, informed team on 08-April-2024 |  |  |  | 10 - Complete | Supriyan | M, Shambhulinga <Shambhulinga.M@arcadis.com> | 0 | 3 | 19
| 216.01 | HS2-00002BJUF | IMD Access off Perry Hill | 1MC06-ASC-HW-FRM-CS06_CL09-000026-ACBOS | P02 | 2024-03-27 | 2024-04-09 | 2024-04-11 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600116 |  | ACBOS not apprpoved , initmated on 28-Mar-2024 |  | MnmmThcknssM is 0 in FND, query send on 03-Apr-2024 |  | ACBOS PCRA not done, informed team on 08-April-2024 | done |  |  | 10 - Complete | Supriyan | M, Shambhulinga <Shambhulinga.M@arcadis.com> | 2 | 3 | 13
| 216.01 | HS2-00002CT90 | Charndon Lodge Pumping Station and Pond Access Road | 1MC06-ASC-HW-FRM-CS06_CL09-000028-ACBOS | P02 | 2024-03-27 | 2024-04-15 | 2024-04-15 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600203 | Done, No Issues | ACBOS not apprpoved , initmated on 28-Mar-2024 |  | sdslp and angleslope conflict. Send back on 03-Apr-2024 |  | ACBOS PCRA not done, informed team on 08-April-2024 |  |  |  | 10 - Complete | Supriyan | M, Shambhulinga <Shambhulinga.M@arcadis.com> | 0 | 3 | 19
| 212.4 | HS2-00002Y47A | Bicester Road Embankment No.3 Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL20-000073-ACBOS | P01 | 2024-03-27 | 2024-03-28 | 2024-04-02 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600238 |  | Com_typ & dscrptn incorrect - need to be swapped and some changed 28/3/24 | 2024-03-28 | [6 empty] | 10 - Complete | Lee | Sangalang, Orlando <orlando.sangalang@arcadis.com> | 1 | 1 | 1
| UFDR 237.C | HS2-000020CK7 | CNO-121-003 | 1MC07-ASC-UT-FRM-CS07_CL23-000007-ACBOS | P02 | 2024-03-28 | 2024-03-28 | 2024-04-02 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600002 | [9 empty] | 10 - Complete | Supriyan | Varma, Srinivasa <srinivasa.varma@arcadis.com> | 1 | 0 | 0
| 235.01-2 | HS2-00003GEEX | ACBOS - Boddington Cutting (Stoneton Lane Green Bridge) 116 - DC 3 - 3D Model (Revit) | 1MC07-ASC-CV-FRM-CS07_CL14-000100-ACBOS | P01 | 2024-03-28 | 2024-03-28 | 2024-04-03 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600191 | [9 empty] | 10 - Complete | Supriyan | NagaJanardhana.Pola@arcadis.com> | 2 | 0 | 0
| 233.01-2 | HS2-00002EK85 | Chipping Warden Green Tunnel North Portal and Chipping Warden MPATS UTX | 1MC07-ASC-CV-FRM-CS07_CL14-000026-ACBOS | P03 | 2024-03-28 | 2024-03-28 | 2024-04-03 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600012 | [9 empty] | 10 - Complete | Lee | dana.salazar@arcadis.com> | 2 | 0 | 0
| 237.05 | HS2-00002CX3B | Lower Radbourne and Ladbroke Farm Access Drainage System | 1MC07-ASC-DR-FRM-CS07_CL23-000018-ACBOS | P02 | 2024-03-28 | 2024-03-28 | 2024-04-02 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600036 | [9 empty] | 10 - Complete | Supriyan | Charuvil Vivekanandan, Amrutha <Amrutha.CharuvilVivekananda@arcadis.com> | 1 | 0 | 0
| 220.5 | HS2-00002CTAL | Padbury Brook Diversion 01 | 1MC06-ASC-DR-FRM-CS06_CL10-000083-ACBOS | P05 | 2024-03-28 | 2024-04-04 | 2024-04-04 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600085 |  | Com_type issue, send back on 29th March |  | Com_type issue, on GRT, informed DT on 04-Apr-2024 | [5 empty] | 10 - Complete | Supriyan | Lorusso, Alberto <alberto.lorusso@arcadis.com> | 0 | 2 | 7
| 218.02 | HS2-00002D2S2 | Calvert IMD Mitigation Earthworks | 1MC06-ASC-GT-FRM-CS06_CL09-000012-ACBOS | P04 | 2024-03-28 | 2024-03-29 | 2024-04-02 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600085 |  | Queries on 0's send back on 29Mar2024 | [7 empty] | 10 - Complete | Supriyan | MATTOUSSI Farah <farah.mattoussi@setec.com> | 0 | 1 | 1
| 212.4 | HS2-0000386T9 | Bicester Road Embankment No.4 Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL20-000077-ACBOS | P01 | 2024-03-28 | 2024-03-28 | 2024-04-02 | YES | 1MC06-CEK-IM-DAT-CS04_CL20-600239 | [9 empty] | 10 - Complete | Lee | Sangalang, Orlando <orlando.sangalang@arcadis.com> | 1 | 0 | 0
| 212.4 | HS2-0000386TC | Wayside Farm Inverted Siphon Maintenance Access Ditch Slab No.2 | 1MC06-ASC-CV-FRM-CS04_CL20-000079-ACBOS | P01 | 2024-03-28 | 2024-03-28 | 2024-04-02 | Yes | 1MC06-CEK-IM-DAT-CS04_CL20-600241 | [9 empty] | 10 - Complete | Lee | bhargavi.saranga@arcadis.com | 1 | 0 | 0
| 212.3 | HS2-00002EK6Z | Sedrup Rail Systems Compound (ATS) UTX | 1MC06-ASC-CV-FRM-CS04_CL18-000015-ACBOS | P01 | 2024-03-28 | 2024-03-28 | 2024-04-02 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600030 | [9 empty] | 10 - Complete | Supriyan | veerabhadraswamy.sp@arcadis.com> | 1 | 0 | 0
| 219.3 | HS2-00002YCW4 | 82-SL1 Cowley Embankment Vehicular Bridge | 1MC06-ASC-BR-FRM-CS06_CL10-900009 | P01 | 2024-03-29 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL10-600132 |  | Com_Description and other issues, send back on 01-Apr-2024 | [7 empty] | 99 - Cancelled | Supriyan | guillaume.hervoches@setec.com>
| 219.3 | HS2-000031EEZ | 82-SL2 Cowley Embankment Pedestrian Bridge | 1MC06-ASC-BR-FRM-CS06_CL10-900010 | P01 | 2024-03-29 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL10-600132 |  | Com_Description and other issues, send back on 01-Apr-2024 | [7 empty] | 99 - Cancelled | Supriyan | guillaume.hervoches@setec.com>
| 219.3 | HS2-000031EF0 | 83-SL1 Twyford Cutting Pedestrian Slab | 1MC06-ASC-BR-FRM-CS06_CL10-900007 | P01 | 2024-03-29 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL10-600133 |  | Com_Description and other issues, send back on 01-Apr-2024 | [7 empty] | 99 - Cancelled | Supriyan | guillaume.hervoches@setec.com>
| 219.3 | HS2-000037YLE | 83-SL4 Twyford Cutting Vehicular Slab | 1MC06-ASC-BR-FRM-C002-CL10-900001 | P01 | 2024-03-29 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL10-600133 |  | Com_Description and other issues, send back on 01-Apr-2024 | [7 empty] | 99 - Cancelled | Supriyan | guillaume.hervoches@setec.com>
| 219.3 | HS2-000037YLG | 83-SL5 Twyford Cutting Vehicular Slab | 1MC06-ASC-BR-FRM-CS06_CL10-900003 | P01 | 2024-03-29 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL10-600133 |  | Com_Description and other issues, send back on 01-Apr-2024 | [7 empty] | 99 - Cancelled | Supriyan | guillaume.hervoches@setec.com>
| 219.3 | HS2-00002CTA4 | Twyford Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000028-ACBOS | P02 | 2024-04-02 | 2024-04-02 | 2024-04-03 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600066 | [9 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 1 | 0 | 0
| 216.01 | HS2-00002BJUE | Maintenance Access Road to Pond 01 (Off IMD access) | 1MC06-ASC-HW-FRM-CS06_CL09-000027-ACBOS | P02 | 2024-04-02 | 2024-04-02 | 2024-04-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600115 | [9 empty] | 10 - Complete | Supriyan | M, Shambhulinga <Shambhulinga.M@arcadis.com> | 1 | 0 | 0
| 216.01 | HS2-00002BJUG | Perry Hill Road Realignment | 1MC06-ASC-HW-FRM-CS06_CL09-000025-ACBOS | P01 | 2024-04-02 | 2024-04-09 | 2024-04-09 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600113 |  | sdslp, com_type and other issues, send back on 03-April-2024 |  | ACBOS PCRA not done, informed team on 08-April-2024 | [5 empty] | 10 - Complete | Supriyan | M, Shambhulinga <Shambhulinga.M@arcadis.com> | 0 | 2 | 7
| 212.4 | HS2-00003B93V | Putlowes Farm Access Road Ditch Slab No.2 | 1MC06-ASC-CV-FRM-CS04_CL20-000080-ACBOS | P01 | 2024-04-02 | 2024-04-04 | 2024-04-05 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600242 |  | Com_Typs 3/4/24 | 2024-04-04 | [6 empty] | 10 - Complete | Lee | Surajpal Singh <SLSH@cowi.com> | 1 | 1 | 2
| 212.3 | HS2-00003GNAB | Point 32 GSM-R Compound | 1MC06-ASC-GT-FRM-CS04_CL20-000027-ACBOS | P01 | 2024-04-02 | 2024-04-08 | 2024-04-09 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600222 |  | Com_Typ Com_Dscrptn Sdslp syntax 3-4-24 | [7 empty] | 10 - Complete | Lee | fahri.abdullahu@arcadis.com | 1 | 1 | 6
| 235.01-2 | HS2-000001091 | Boddington Cutting | 1MC07-ASC-GT-FRM-CS07_CL14-000001-ACBOS | P06 | 2024-04-03 | 2024-04-04 | 2024-04-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600086 |  | Old Schema. Com_Typ - incorrect. Com_Dscrptn - incorrect. Sdslp - Incorrect syntax. Com_RfrncNmbr - incomplete. 3/4/24 | 2024-04-04 | [6 empty] | 10 - Complete | Lee | K P, Deepak <deepak.kp@arcadis.com> | 1 | 1 | 1
| 237.05 | HS2-000020P1F | Ladbroke Grove Farm Accommodation Access Realignment | 1MC07-ASC-HW-FRM-CS07_CL23-000038-ACBOS | P01 | 2024-04-03 | 2024-04-04 | 2024-04-04 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600006 |  | Send back on 03-April-2024, com_type issue |  | Eronious Chainage, send back on 03-Apr-2024 | [5 empty] | 10 - Complete | Supriyan | Matthew Coote <mtce@cowi.com> | 0 | 2 | 1
| 233.01 | HS2-00002CX3A | Appletree Lane Drainage System | 1MC07-ASC-DR-FRM-CS07_CL13-000002-ACBOS | P02 | 2024-04-03 | 2024-04-04 | 2024-04-05 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600003 |  | InltPnt - incorrect , no Osgb coords 3/4/24 | 2024-04-04 | [6 empty] | 10 - Complete | Lee | M, Nischitha <nischitha.m@arcadis.com> | 1 | 1 | 1
| 221.2 | HS2-000020NLZ | Footpath CHW/18 Accommodation Access Realignment | 1MC06-ASC-HW-FRM-CS06_CL10-900022-ACBOS | P01 | 2024-04-03 | 2024-04-03 | 2024-04-05 | Yes | 1MC06-CEK-IM-DAT-CS06_CL10-600027 | [9 empty] | 10 - Complete | Lee | zakaria.khabouze@setec.com> | 2 | 0 | 0
| 221.2 | HS2-00002CTB0 | School End Road Drainage System | 1MC06-ASC-DR-FRM-CS06_CL10-000014-ACBOS | P02 | 2024-04-03 | 2024-04-03 | 2024-04-05 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600003 | [9 empty] | 10 - Complete | Lee | MIRI Youssef <youssef.miri@setec.com> | 2 | 0 | 0
| 214.09 | HS2-00002TTH6 | Solids | 1MC06-ASC-HW-FRM-CS05-000081-ACBOS | P01 | 2024-04-03 | 2024-04-04 | 2024-04-08 |  | 1MC06-CEK-IM-DAT-CS05-600196 |  | DT reworking file 3-4-24 | 2024-04-04 | [6 empty] | 10 - Complete | Lee | shaun.ambrose@arcadis.com | 2 | 1 | 1
| 214.09 | HS2-00003G3SK | Headwall | 1MC06-CEK-DR-FRM-CS05-000078 | P01 | 2024-04-03 | 2024-04-05 | 2024-04-05 |  | 1MC06-CEK-IM-DAT-CS05-600195 |  | no Smartforms data 3-4-24 | 2024-04-04 | incorrect UAID_2 in ACBOS 4-4-24 | 2024-04-05 |  |  |  |  | 10 - Complete | Lee | shaun.ambrose@arcadis.com | 0 | 2 | 2
| 212.4 | HS2-0000386TB | Wayside Farm Inverted Siphon Maintenance Access Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS04_CL20-000078-ACBOS | P01 | 2024-04-03 | 2024-04-05 | 2024-04-07 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600240 |  | Same Chainage for all assets, informed DT on 04-April-2024 |  | Com_type issues | [5 empty] | 10 - Complete | Supriyan | orlando.sangalang@arcadis.com | 0 | 2 | 2
| 233.01-2 | HS2-00002TMFA | Chipping Warden Green Tunnel North Portal Building Fire Fighting Water | 1MC07-ASC-UT-FRM-CS07_CL13-000038-ACBOS | P03 | 2024-04-04 | 2024-04-04 | 2024-04-04 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600024 | [9 empty] | 10 - Complete | Supriyan | T, Sithrubi <sithrubi.t@arcadis.com> | 0 | 0 | 0
| 233.01-2 | HS2-00002TMFC | Chipping Warden MPATS Telecoms | 1MC07-ASC-UT-FRM-CS07_CL13-000036-ACBOS | P02 | 2024-04-04 | 2024-04-04 | 2024-04-04 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600022 | [9 empty] | 10 - Complete | Supriyan | T, Sithrubi <sithrubi.t@arcadis.com> | 0 | 0 | 0
| 237.05 | HS2-00003B93P | Ladbroke Grove Cutting | 1MC07-ASC-CV-FRM-CS07_CL23-000053-ACBOS | P01 | 2024-04-04 | 2024-04-04 | 2024-04-07 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600161 | [9 empty] | 10 - Complete | Supriyan | Afsal, Muhammed <muhammed.afsal@arcadis.com> | 1 | 0 | 0
| 237.05 | HS2-00003B93Q | Ladbroke Grove Cutting | 1MC07-ASC-CV-FRM-CS07_CL23-000054-ACBOS | P01 | 2024-04-04 | 2024-04-04 | 2024-04-07 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600162 | [9 empty] | 10 - Complete | Supriyan | Afsal, Muhammed <muhammed.afsal@arcadis.com> | 1 | 0 | 0
| 237.05 | HS2-00003B93R | Ladbroke Grove Cutting | 1MC07-ASC-CV-FRM-CS07_CL23-000055-ACBOS | P01 | 2024-04-04 | 2024-04-04 | 2024-04-07 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600163 | [9 empty] | 10 - Complete | Supriyan | PATIL, APOORVA <apoorva.patil@arcadis.com> | 1 | 0 | 0
| 228.2 | HS2-000001339 | Bridleway AN37 Accommodation Overbridge | 1MC07-CEK-BR-FRM-CS07_CL12-000008 | P04 | 2024-04-04 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL12-600136 |  | Old Schema. 5/4/24 |  | DT reworking file as of 12-Jul-24 due to design change | [5 empty] | 99 - Cancelled | Lee | Egan, Conor <Conor.Egan@wsp.com>
| 227.1 | HS2-00003B5FR | HSRS Day 2 Power Supply Additional Ducts Radstone Rd Overbridge | 1MC07-ASC-UT-FRM-CS07_CL12-000105-ACBOS | P01 | 2024-04-04 | 2024-04-05 | 2024-04-07 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600191 |  | Same Chainage for all assets. Asset name is wrong. Send back on 04-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 0 | 1 | 1
| 219.3 | HS2-00002CTA6 | Twyford Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000035-ACBOS | P02 | 2024-04-04 | 2024-04-04 | 2024-04-08 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600099 | [9 empty] | 10 - Complete | Lee | youssef.miri@setec.com | 2 | 0 | 0
| UFDR 235.C | HS2-000020CJU | CSO-04-1326 | 1MC07-ASC-UT-FRM-CS07_CL14-000005-ACBOS | P01 | 2024-04-05 | 2024-04-05 | 2024-04-08 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600078 | [9 empty] | 10 - Complete | Lee | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 1 | 0 | 0
| UFDR 235.C | HS2-000020CJV | CSO-04-1327 | 1MC07-ASC-UT-FRM-CS07_CL14-000007-ACBOS | P01 | 2024-04-05 | 2024-04-05 | 2024-04-08 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600079 | [9 empty] | 10 - Complete | Lee | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 1 | 0 | 0
| UFDR 229.B | HS2-000020CHZ | CSO-04-3107P | 1MC07-ASC-UT-FRM-CS07_CL25-000054-ACBOS | P02 | 2024-04-05 | 2024-04-05 | 2024-04-08 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600044 |  | all start / End chainages identical and across all classifications. | DT confirmed in email that this is agreed. | [6 empty] | 10 - Complete | Lee | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 1 | 1 | 0
| UFDR 229.B | HS2-000020CJ0 | CSO-04-3108P | 1MC07-ASC-UT-FRM-CS07_CL25-000056-ACBOS | P02 | 2024-04-05 | 2024-04-05 | 2024-04-09 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600051 | [9 empty] | 10 - Complete | Lee | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 2 | 0 | 0
| UFDR 229.B | HS2-000020CJ1 | CSO-04-6104P | 1MC07-ASC-UT-FRM-CS07_CL25-000046-ACBOS | P02 | 2024-04-05 | 2024-04-05 | 2024-04-09 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600033 | [9 empty] | 10 - Complete | Lee | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 2 | 0 | 0
| UFDR 229.B | HS2-000020CJ2 | CSO-04-3109P | 1MC07-ASC-UT-FRM-CS07_CL25-000058-ACBOS | P02 | 2024-04-05 | 2024-04-05 | 2024-04-09 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600034 | [9 empty] | 10 - Complete | Lee | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 2 | 0 | 0
| UFDR 229.B | HS2-00002FE9X | C23-102-0002P | 1MC07-ASC-UT-FRM-CS07_CL25-000050-ACBOS | P02 | 2024-04-05 | 2024-04-05 | 2024-04-09 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600008 | [9 empty] | 10 - Complete | Lee | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 2 | 0 | 0
| UFDR 229.B | HS2-00002FE9Z | C23-102-0003P | 1MC07-ASC-UT-FRM-CS07_CL25-000052-ACBOS | P02 | 2024-04-05 | 2024-04-05 | 2024-04-09 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600016 | [9 empty] | 10 - Complete | Lee | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 2 | 0 | 0
| 233.01-2 | HS2-00002TMFB | Chipping Warden Green Tunnel North Portal Building Telecoms | 1MC07-ASC-UT-FRM-CS07_CL13-000034-ACBOS | P03 | 2024-04-05 | 2024-04-05 | 2024-04-08 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600043 | [9 empty] | 10 - Complete | Supriyan | T, Sithrubi <sithrubi.t@arcadis.com> | 1 | 0 | 0
| 235.01 | HS2-00003JG3Z | Wormleighton Sidings UTX 2 | 1MC07-ASC-CV-FRM-CS07_CL14-000108-ACBOS | P01 | 2024-04-05 | 2024-04-05 | 2024-04-08 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600190 | [9 empty] | 10 - Complete | Supriyan | Behera, Latika <latika.behera@arcadis.com> | 1 | 0 | 0
| 235.01 | HS2-00003JG3Y | Wormleighton Sidings UTX 1 | 1MC07-ASC-CV-FRM-CS07_CL14-000107-ACBOS | P01 | 2024-04-05 | 2024-04-05 | 2024-04-09 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600189 | [9 empty] | 10 - Complete | Lee | S, Arun Kumar <ArunKumar.S@arcadis.com> | 2 | 0 | 0
| 219.3 | HS2-000033GP3 | Clean Water Pipe CFA_13_08 | 1MC06-CEK-UT-FRM-CS06_CL10-600014 | P02 | 2024-04-05 | 2024-04-11 | 2024-04-15 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600208 |  | parent PW file need update for DgnFlwBss to be set blank or Zero(0) 11/4/24 | [7 empty] | 10 - Complete | Lee | Singh, Prashant <prashant.singh2@arcadis.com> | 2 | 1 | 6
| 218.02 | HS2-00002VK41 | Portway Culvert Access Road Bridge MAS | 1MC06-ASC-CV-FRM-CS06_CL09-000040-ACBOS | P01 | 2024-04-05 | 2024-04-05 | 2024-04-08 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600276 |  | Com_typ & Dscrptn all incorrect. 4/4/24 | 2024-04-05 | [6 empty] | 10 - Complete | Lee | Prajwal.Bontala@arcadis.com | 1 | 1 | 0
| 212.4 | HS2-00003GNAD | Needles Overbridge Clean Water | 1MC06-ASC-UT-FRM-CS04_CL20-000096-ACBOS | P01 | 2024-04-05 | 2024-04-08 | 2024-04-09 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600235 |  | PCRA of ACBOS is pending, send back on 08-April-2024 | [7 empty] | 10 - Complete | Supriyan | Kamboj, Mohit <mohit.kamboj@arcadis.com> | 1 | 1 | 3
| 212.4 | HS2-00003B5FW | Cranwell Farm and Bridleway FMA-1 Realignment – Ditch Slab | 1MC06-ASC-HW-FRM-CS04_CL20-000052-ACBOS | P03 | 2024-04-05 | 2024-04-10 | 2024-04-12 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600212 |  | Cm_CRT& Cm_Chg all set to P04. sent to DT 8/4/24 | 2024-04-10 | [6 empty] | 10 - Complete | Lee | Abdelmalik Hassen <ABHS@cowi.com> | 2 | 1 | 5
| UFDR 228.F | HS2-00003CFCL | Greatworth Reservoir - Drain pipe CSO-100-0002 | 1MC07-ASC-UT-FRM-CS07_CL12-000110-ACBOS | P02 | 2024-04-08 | 2024-04-09 | 2024-04-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600283 |  | old LoDM, minimum Tagging, identical start / end chainage. Send back on 9th April 2024 | [7 empty] | 10 - Complete | Supriyan | Singh, Prashant <prashant.singh2@arcadis.com> | 0 | 1 | 1
| 229.01-1 | HS2-00002C3YS | B4525 Welsh Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL25-000008-ACBOS | P01 | 2024-04-08 | 2024-04-12 | 2024-04-15 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600053 | Done, No Issues | 0's , query send on 9th April2024 | [7 empty] | 10 - Complete | Supriyan | B, Gopika <gopika.b@arcadis.com> | 1 | 1 | 4
| 237.05 | HS2-000020P0N | Maintenance Access Road to Pond (Off Lower Radbourne Farm Access Road East) | 1MC07-ASC-HW-FRM-CS07_CL23-000035-ACBOS | P01 | 2024-04-08 | 2024-04-08 | 2024-04-09 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600008 | [9 empty] | 10 - Complete | Supriyan | Matthew Coote <mtce@cowi.com> | 1 | 0 | 0
| 218.02 | HS2-000035UXF | HS2-00002CTDB - IMD Access Road Drainage system | 1MC06-CEK-DR-FRM-CS06_CL09-000054 | P01 | 2024-04-08 | 2024-04-08 | 2024-04-10 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600313 | [9 empty] | 10 - Complete | Lee | J V, Lokesh <lokesh.jv@arcadis.com> | 2 | 0 | 0
| 212.4 | HS2-00002CT67 | Thame Valley North Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS04_CL19-000033-ACBOS | P01 | 2024-04-08 | 2024-04-19 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600003 |  | com_typ 9/4/24 | [7 empty] | 10 - Complete | Lee | Sangalang, Orlando <orlando.sangalang@arcadis.com> | 5 | 1 | 11
| 212.4 | HS2-00002CT6A | Thame Valley North Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS04_CL19-000021-ACBOS | P01 | 2024-04-08 | 2024-04-19 | 2024-04-29 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600021 |  | com_typ 9/4/24 | [7 empty] | 10 - Complete | Lee | Sangalang, Orlando <orlando.sangalang@arcadis.com> | 6 | 1 | 11
| 218.02 | HS2-00002YXB3 | Twyford Viaduct Access Point Staircase Upmain Ch82275 | 1MC06-ASC-CV-FRM-CS06_CL10-900069-ACBOS | P01 | 2024-04-09 | 2024-04-23 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600212 | Done , no issues | incorrect ACBOS link. | 2024-04-23 | rebar tiny volumes rounding to zero - DT confim expected | [5 empty] | 10 - Complete | Lee | Isaac.wong@arcadis.com | 5 | 2 | 14
| 218.02 | HS2-00002YXB4 | Twyford Viaduct Access Point Staircase Downmain Ch82280 | 1MC06-ASC-CV-FRM-CS06_CL10-000068-ACBOS | P01 | 2024-04-09 | 2024-04-29 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600213 | Done , no issues | Com_type incorrect 10/4/24 | 2024-04-23 | less than 0.000n RebarVolume. To DT 26-Apr-24 to confirm or amend | 2024-04-29 |  |  |  |  | 10 - Complete | Lee | Isaac.wong@arcadis.com | 1 | 2 | 20
| 218.02 | HS2-00003124G | Portway Culvert Chamber Access Downmain 80955 | 1MC06-ASC-CV-FRM-CS06_CL09-000070-ACBOS | P01 | 2024-04-09 | 2024-04-24 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600278 | Done , no issues | Com_type incorrect 10/4/24 | 2024-04-23 | placeholder not at WIP | done |  |  |  |  | 10 - Complete | Lee | Isaac.wong@arcadis.com | 4 | 2 | 15
| 218.02 | HS2-00003124H | Twyford East Culvert Chamber Access Downmain 81712 | 1MC06-ASC-CV-FRM-CS06_CL10-900071-ACBOS | P01 | 2024-04-09 | 2024-04-30 | 2024-05-01 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600214 |  | incorrect ACBOS link. - fixed 30/4/24 | 2024-04-30 | [6 empty] | 10 - Complete | Lee | Isaac.wong@arcadis.com | 1 | 1 | 21
| 218.02 | HS2-00003124J | West Street Overbridge Downmain 81140 | 1MC06-ASC-CV-FRM-CS06_CL09-000071-ACBOS | P01 | 2024-04-09 | 2024-04-24 | 2024-05-01 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600280 | Done , no issues | Com_type incorrect 10/4/24 | 2024-04-23 | placeholder not at WIP | done |  |  |  |  | 10 - Complete | Lee | Isaac.wong@arcadis.com | 5 | 2 | 15
| 218.02 | HS2-00003124K | West Street Overbridge Upmain 81230 | 1MC06-ASC-CV-FRM-CS06_CL09-900073-ACBOS | P01 | 2024-04-09 | 2024-04-24 | 2024-05-01 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600279 | Done , no issues | Com_type incorrect 10/4/24 | 2024-04-23 | placeholder not at WIP | done |  |  |  |  | 10 - Complete | Lee | Isaac.wong@arcadis.com | 5 | 2 | 15
| 212.4 | HS2-00002Y47A | Bicester Road Embankment No.3 Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL20-000073-ACBOS | P01 | 2024-04-09 | 2024-04-10 | 2024-04-11 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600238 |  | Snakegrid co-ordinates are zero, and other zero's too. Send back on 10-Apr-2024 | 2024-04-10 | [6 empty] | 10 - Complete | Lee | mohamad.alzoubi@arcadis.com | 1 | 1 | 1
| 233.01-2 | HS2-00002NJ06 | Chipping Warden Green Tunnel North Portal | 1MC07-CEK-TN-FRM-CS07_CL14-000001 | P03 | 2024-04-10 | 2024-04-29 | 2024-05-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600042 |  | com_typ & confirmation 11-4-24 some Coordinate issues. | 2024-04-17 | smartforms mismatch | [5 empty] | 10 - Complete | Lee | David Pink <dapi@cowi.com> | 3 | 2 | 19
| 233.01-2 | HS2-00002NJ06 | Chipping Warden Green Tunnel North Portal | 1MC07-ASC-TN-FRM-CS07_CL14-000003-ACBOS | P02 | 2024-04-10 | 2024-04-25 | 2024-05-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600042 |  | com_typ & confirmation 11-4-24 some Coordinate issues. | 2024-04-17 | mtrl mismatches | 2024-04-29 |  |  |  |  | 10 - Complete | Lee | David Pink <dapi@cowi.com> | 5 | 2 | 15
| 233.01-2 | HS2-00002NJ06 | Chipping Warden Green Tunnel North Portal | 1MC07-ASC-TN-FRM-CS07_CL13-000008-ACBOS | P01 | 2024-04-10 | 2024-04-25 | 2024-05-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600042 |  | com_typ & confirmation 11-4-24 some Coordinate issues. | 2024-04-17 | smartforms mismatch | [5 empty] | 10 - Complete | Lee | David Pink <dapi@cowi.com> | 5 | 2 | 15
| 229.01-1 | HS2-00002TMF1 | Greatworth Green Tunnel South Portal | 1MC07-ASC-UT-FRM-CS07_CL12-000094-ACBOS | P01 | 2024-04-10 | 2024-06-06 | 2024-06-07 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600051 | Done , no issues | ACBOS Corrupt, not getting converted , send back on 12-Apr-2024 |  | sdslp is not in format, send back on 25-Apr-2025 and send back again on 29-Apr-2024. Mtrl vs GdMt conflict- send back on 09-May-2024. UniclassID Issue send back on 30-May-2024 | [5 empty] | 10 - Complete | Supriyan | Agnieszka Cytowska <agcy@cowi.com> | 1 | 2 | 57
| 229.01-1 | HS2-00002TMF2 | Greatworth Green Tunnel South Portal | 1MC07-ASC-UT-FRM-CS07_CL12-000092-ACBOS | P01 | 2024-04-10 | 2024-05-07 | 2024-05-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600050 | Done, No Issues | ACBOS workflow not complted, sdslp format, send back on 12-Apr-2024 |  | Design flow basis, send back on 29-Apr-20204 | [5 empty] | 10 - Complete | Supriyan | Agnieszka Cytowska <agcy@cowi.com> | 2 | 2 | 27
| 229.01-1 | HS2-00002TMF4 | Greatworth Green Tunnel South Portal | 1MC07-ASC-UT-FRM-CS07_CL12-000096-ACBOS | P01 | 2024-04-10 | 2024-05-22 | 2024-06-05 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600052 | Done , issues found | UAID_1 and sdslp feedback, send back on 12-Apr-2024 |  | OSGB issues, sdslp issues, send abck on 25-Apr-2025. Wrong uniclass ID. Send back on 16th May2024. Again found uniclassID issues, send back on 17th May 2024 | [5 empty] | 10 - Complete | Supriyan | Agnieszka Cytowska <agcy@cowi.com> | 9 | 2 | 42
| 237.05 | HS2-000020P16 | Lower Radbourne Farm Accommodation Access Realignment | 1MC07-ASC-HW-FRM-CS07_CL23-000041-ACBOS | P01 | 2024-04-10 | 2024-04-16 | 2024-04-17 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600009 |  | DT reworking OsgbE/N to match CE checks. JSON not required for 5 day review. | 2024-04-15 | look like OS still the same | 2024-04-16 |  |  |  |  | 10 - Complete | Lee | Matthew Coote <mtce@cowi.com> | 1 | 2 | 6
| 235.01 | HS2-00002CTJD | Boddington Cutting Boundary/Perimeter Fence Line | 1MC07-ASC-CV-FRM-CS07_CL14-000005-ACBOS | P02 | 2024-04-10 | 2024-04-10 | 2024-04-16 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600003 | [9 empty] | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> |  | 0 | 0
| 235.01 | HS2-00002CTJE | Boddington Cutting Security Fence Line | 1MC07-ASC-CV-FRM-CS07_CL14-000008-ACBOS | P02 | 2024-04-10 | 2024-04-12 | 2024-04-17 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600006 |  | smartfroms mismatch 11/4/24 | 2024-04-12 | [6 empty] | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> |  | 1 | 2
| 229.03 | HS2-00003124E | Greatworth North Embankment and Cutting Access Stairs | 1MC07-ASC-CV-FRM-CS07_CL12-000111-ACBOS | P01 | 2024-04-10 | 2024-06-03 | 2024-06-05 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600288 |  | Many zero's, send for confirmation on 12April2024 | [7 empty] | 10 - Complete | Supriyan | Martin, Joel <Joel.Martin@arcadis.com> | 2 | 1 | 54
| 227.1 | HS2-00002CQQF | Radstone Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL12-000004-ACBOS | P02 | 2024-04-10 | 2024-04-12 | 2024-04-15 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600152 | Done, Issues reported | Co-ordinate issue and other observations, send back on 12-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 2
| 215.02-02 | HS2-00002CT8Y | Maintenance Access Road to Pond (Off School Hill Road West) | 1MC06-ASC-HW-FRM-CS06_CL09-000041-ACBOS | P02 | 2024-04-11 | 2024-04-19 | 2024-04-23 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600266 |  | OS coords issues 12-apr-24 | 2024-04-19 | OS coords issues 19-apr-24 | 2024-04-19 | ClrncVrt .05 value not auto updating through SQL to 0.05 like ThknsAvrg or Dpth values do. Pick up Monday woth Partha |  |  |  | 10 - Complete | Lee | Abedelkareem Alnajajreh <adan@cowi.com> | 2 | 3 | 8
| 227.B | HS2-000020CHM | CSO-04-3104 Diverted Telecoms Cables | 1MC07-ASC-UT-FRM-CS07_CL12-000056-ACBOS | P01 | 2024-04-12 | 2024-04-16 | 2024-04-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600148 | Done, No Issues | OSGB co-ordinates are identical, send back on 15-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | Nicholas.White@arcadis.com | 3 | 1 | 4
| 227.B | HS2-0000245Z9 | CSO-04-2201 Diverted Gas Main | 1MC07-ASC-UT-FRM-CS07_CL12-000058-ACBOS | P01 | 2024-04-12 | 2024-04-17 | 2024-04-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600156 | Done, No Issues | AssetDescription_2 mismatch, send back on 15-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | Nicholas.White@arcadis.com | 2 | 1 | 5
| 227.B | HS2-00002FE9M | CSO-04-6102P | 1MC07-ASC-UT-FRM-CS07_CL12-000038-ACBOS | P01 | 2024-04-12 | 2024-04-15 | 2024-04-15 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600067 | Done, No Issues | [8 empty] | 10 - Complete | Supriyan | Nicholas.White@arcadis.com | 0 | 0 | 3
| 227.B | HS2-00002FE9P | CSO-04-2202 | 1MC07-ASC-UT-FRM-CS07_CL12-000078-ACBOS | P01 | 2024-04-12 | 2024-04-17 | 2024-04-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600061 | Done, No Issues | OSGB co-ordinates are identical, snakegrid is missing . Send back on 15-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | Nicholas.White@arcadis.com | 2 | 1 | 5
| 225 | HS2-00002CTE3 | River Great Ouse Diversion 02 | 1MC07-ASC-DR-FRM-CS07_CL12-000084-ACBOS | P01 | 2024-04-12 | 2024-04-12 | 2024-04-22 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600102 |  | Com_Rfrnce showing as missing in DAC check..ACBOS does not contain column for this GRT class SP to investigate 16-APR-24 | [7 empty] | 10 - Complete | Lee | Lorusso, Alberto <alberto.lorusso@arcadis.com> | 6 | 1 | 0
| 219.3 | HS2-00002YCW4 | 82-SL1 Cowley Embankment Vehicular Bridge | 1MC06-ASC-BR-FRM-CS06_CL10-900009 | P02 | 2024-04-12 | 2024-04-29 | 2024-05-03 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600226 |  | JSON placeholder is incorrect, wrong Maximum Permitted Weight. Send back on 16-Apr-2024 |  | Maximum permitted wight issues end back on 25-Apr-2024 | [5 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 4 | 2 | 17
| 219.3 | HS2-000031EEZ | 82-SL2 Cowley Embankment Pedestrian Bridge | 1MC06-ASC-BR-FRM-CS06_CL10-900010 | P02 | 2024-04-12 | 2024-04-29 | 2024-05-03 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600222 | Done, No Issues | JSON placeholder is incorrect, wrong Maximum Permitted Weight. Send back on 16-Apr-2024 |  | Maximum permitted wight issues end back on 25-Apr-2024 | [5 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 4 | 2 | 17
| 219.3 | HS2-000031EF0 | 83-SL1 Twyford Cutting Pedestrian Slab | 1MC06-ASC-BR-FRM-CS06_CL10-900007 | P02 | 2024-04-12 | 2024-05-07 | 2024-05-08 | YES | 1MC06-CEK-IM-DAT-CS06_CL10-600225 | Done, No Issues | JSON placeholder is incorrect, wrong Maximum Permitted Weight. Send back on 16-Apr-2024 |  | Maximum permitted wight issues end back on 25-Apr-2024, Insite vs pre cast issue send bak 30-Apr-2024 | [5 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 1 | 2 | 25
| 219.3 | HS2-000037YLE | 83-SL4 Twyford Cutting Vehicular Slab | 1MC06-ASC-BR-FRM-C002-CL10-900001 | P02 | 2024-04-12 | 2024-04-29 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600224 | Done, No Issues | JSON placeholder is incorrect, wrong Maximum Permitted Weight. Send back on 16-Apr-2024 |  | Maximum permitted wight issues end back on 25-Apr-2024 | [5 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 1 | 2 | 17
| 219.3 | HS2-000037YLG | 83-SL5 Twyford Cutting Vehicular Slab | 1MC06-ASC-BR-FRM-CS06_CL10-900003 | P02 | 2024-04-12 | 2024-04-29 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600223 | Done, No Issues | JSON placeholder is incorrect, wrong Maximum Permitted Weight. Send back on 16-Apr-2024 |  | Maximum permitted wight issues end back on 25-Apr-2024 | [5 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 1 | 2 | 17
12 | UFDR 211.A | HS2-000020CFE | CSO-02-1216 | 1MC06-ASC-UT-FRM-CS04_CL20-000016-ACBOS | P01 | 2024-04-15 | 2024-04-16 | 2024-04-17 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600113 | Done, No issues | [8 empty] | 10 - Complete | Supriyan | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 1 | 0 | 1
12 | UFDR 211.A | HS2-000020CFF | CSO-02-3115 | 1MC06-ASC-UT-FRM-CS04_CL20-000020-ACBOS | P01 | 2024-04-15 | 2024-04-16 | 2024-04-17 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600087 | Done, No issues | [8 empty] | 10 - Complete | Supriyan | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 1 | 0 | 1
12 | UFDR 211.A | HS2-000020CFG | CSO-02-7202 | 1MC06-ASC-UT-FRM-CS04_CL20-000021-ACBOS | P01 | 2024-04-15 | 2024-04-15 | 2024-04-19 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600088 | Done, No Issues | [8 empty] | 10 - Complete | Supriyan | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 4 | 0 | 0
12 | UFDR 211.A | HS2-000031J4L | Waddesdon Compact Substation | 1MC06-ASC-UT-FRM-CS04_CL20-000091-ACBOS | P01 | 2024-04-15 | 2024-04-17 |  |  | 1MC06-CEK-IM-DAT-CS04_CL20-600245 | Done, No Issues | Send queries on 0's on 17-Apr-2024. 22nd April we informed DT about incorrect HS2_class used for many ZZ--ZZ items. It's sent back to DT. |  | DT retagging | [5 empty] | 99 - Cancelled | Partha | Mainstone, Eloise <eloise.mainstone@arcadis.com>
| 238.02-2 | HS2-000020P2P | Footpath SM89 Extension | 1MC07-ASC-HW-FRM-CS07_CL24-000024-ACBOS | P01 | 2024-04-15 | 2024-04-18 | 2024-04-23 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600059 | Done, found issues | Incomplete ACBOS, send back on 17-Apr-2024 |  | OSGB co-ordinate delta issue, send back on 18-Apri-2024 | [5 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 3 | 2 | 3
| 238.02-2 | HS2-00002CTKE | Footpath SM33 Diversion (west of HS2) | 1MC07-ASC-HW-FRM-CS07_CL24-000029-ACBOS | P01 | 2024-04-15 | 2024-04-17 | 2024-04-19 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600079 | Done, No Issues | Send queries on 0's, on 17-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 2 | 1 | 2
| 214.09 | HS2-00002TTH6 | FCC PRoW Bridleway Diversion | 1MC06-ASC-HW-FRM-CS05-000081-ACBOS | P03 | 2024-04-15 | 2024-04-15 | 2024-04-17 |  | 1MC06-CEK-IM-DAT-CS05-600195 |  | DT changed JSON placeholder. | 2024-04-15 | [6 empty] | 10 - Complete | Lee | jeroen.vandijk@arcadis.com | 2 | 1 | 0
| 238.01 | HS2-00002CTK9 | Ladbroke Watercourse Diversion | 1MC07-ASC-DR-FRM-CS07_CL24-000053-ACBOS | P04 | 2024-04-15 | 2024-04-23 | 2024-04-24 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600044 | Done, one record with issue | OSGB issue and Com_descriptions with suffics, send back on 16-Apr-2024 |  | Com_Referance Missing and OSGB conversion error, send abck on 23-Apr-2024 | [5 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 1 | 2 | 8
| 227.1 | HS2-000001336 | Radstone Road Overbridge | 1MC07-CEK-BR-FRM-CS07_CL12-000001 | P11 | 2024-04-15 | 2024-04-23 | 2024-04-24 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600142 | Done, major OSGB coordinate issue | OSGB issue, send back on 16-Apr-2024 | OSGB issue, send back on 18-Apr-2024 | Drop down value error in GDMt, send back on 23-Apr-2023 | [5 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 1 | 2 | 8
| 219.3 | HS2-000033XXU | Twyford Cutting Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL10-900001 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600150 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 16-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 1 | 1 | 7
| 219.3 | HS2-000033XXV | Twyford Cutting Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL10-900002 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600149 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 16-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 1 | 1 | 7
| 219.3 | HS2-000033XXW | Twyford Cutting Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL10-900003 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600148 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 16-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XXX | Twyford Cutting Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL10-900004 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600147 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 16-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XXY | Twyford Cutting Planting Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL10-900005 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600146 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 16-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XXZ | Twyford Cutting Planting Plot 6 | 1MC06-ASC-EV-FRM-CS06_CL10-900006 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600145 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 17-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XY0 | Twyford Cutting Planting Plot 7 | 1MC06-ASC-EV-FRM-CS06_CL10-900007 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600144 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 17-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XY1 | Twyford Cutting Planting Plot 8 | 1MC06-ASC-EV-FRM-CS06_CL10-900008 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600143 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 17-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XY2 | Twyford Viaduct Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL10-900009 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600142 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 17-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XY3 | Twyford Viaduct Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL10-900010 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600141 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 17-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XY4 | Twyford Viaduct Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL10-900011 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600140 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 17-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XY5 | Twyford Viaduct Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL10-900012 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600139 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 17-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XXN | Cowley Embankment Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL10-900013 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600156 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 17-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XXP | Cowley Embankment Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL10-900014 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600155 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 17-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XXQ | Cowley Embankment Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL10-900015 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600154 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 17-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XXR | Cowley Embankment Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL10-900016 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600153 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 17-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XXS | Cowley Embankment Planting Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL10-900017 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600152 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 17-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 219.3 | HS2-000033XXT | Cowley Embankment Planting Plot 6 | 1MC06-ASC-EV-FRM-CS06_CL10-900018 | P01 | 2024-04-15 | 2024-04-22 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600151 | Done : Issues | Com_typ, Dscrptn , chainage values, Osgb values. 17-Apr-24 | 2024-04-22 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 1 | 7
| 214.09 | HS2-00003G3SK | FCC PRoW Bridleway Diversion Drainage | 1MC06-CEK-DR-FRM-CS05-000078 | P01 | 2024-04-15 | 2024-04-15 | 2024-04-17 |  | 1MC06-CEK-IM-DAT-CS05-600196 | Done, No Issues | [8 empty] | 10 - Complete | Lee | jeroen.vandijk@arcadis.com | 2 | 0 | 0
| 212.4 | HS2-00002WUMM | Thame Valley South Embankment Planting - East Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL19-000017 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600068 | Done, Issues reported | OSGB issues, Com_type and other issues, send back on 17-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 1 | 3
| 212.4 | HS2-00002WUMN | Thame Valley South Embankment Planting - East Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL19-000018 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600069 | Done, Issues reported | OSGB issues, Com_type and other issues, send back on 17-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 1 | 3
| 212.4 | HS2-00002WUMP | Thame Valley South Embankment Planting - West Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL19-000019 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600070 | Done, Issues reported | OSGB issues, Com_type and other issues, send back on 17-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 1 | 3
| 212.4 | HS2-00002WUMQ | Thame Valley South Embankment Planting - West Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL19-000020 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600071 | Done, Issues reported | OSGB issues, Com_type and other issues, send back on 17-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 1 | 3
| 212.4 | HS2-00002WUMR | Thame Valley Viaduct Planting - Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL19-000021 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600072 | Done, Issues reported | OSGB issues, Com_type and other issues, send back on 17-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 1 | 3
| 212.4 | HS2-00002WUMS | Thame Valley Viaduct Planting - Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL19-000022 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600073 | [9 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 0 | 3
| 212.4 | HS2-00002WUMT | Thame Valley North Embankment Planting - East Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL19-000013 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600074 | [9 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 0 | 3
| 212.4 | HS2-00002WUMU | Thame Valley North Embankment Planting - East Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL19-000014 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600075 | [9 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 0 | 3
| 212.4 | HS2-00002WUMV | Thame Valley North Embankment Planting - West Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL19-000015 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600076 | [9 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 0 | 3
| 212.4 | HS2-00002WUMW | Thame Valley North Embankment Planting - West Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL19-000016 | P01 | 2024-04-15 | 2024-04-26 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600077 | Done , issue found | OSGB Out of tolerance , send back on 24April2024 | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 2 | 1 | 11
| 212.4 | HS2-00002WUMX | Putlowes Cutting Planting - East Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL20-000014 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600159 | [9 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 0 | 3
| 212.4 | HS2-00002WUMY | Putlowes Cutting Planting - East Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL20-000015 | P01 | 2024-04-15 | 2024-04-26 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600160 | Done , issue found | OSGB Out of tolerance , send back on 24April2024 | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 2 | 1 | 11
| 212.4 | HS2-00002WUMZ | Putlowes Cutting Planting - East Plot 3 | 1MC06-CEK-EV-FRM-CS04_CL20-000016 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600161 | [9 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 0 | 3
| 212.4 | HS2-00002WUN0 | Putlowes Cutting Planting - West Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL20-000017 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600162 | [9 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 0 | 3
| 212.4 | HS2-00002WUN1 | Bicester Road Embankment Planting - North Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL20-000007 | P01 | 2024-04-15 | 2024-04-26 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600163 | Done , issue found | OSGB Out of tolerance , send back on 24April2024 | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 2 | 1 | 11
| 212.4 | HS2-00002WUN2 | Bicester Road Embankment Planting - North Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL20-000008 | P01 | 2024-04-15 | 2024-04-26 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600164 | Done , issue found | OSGB Out of tolerance , send back on 24April2024 | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 2 | 1 | 11
| 212.4 | HS2-00002WUN3 | Bicester Road Embankment Planting - North Plot 3 | 1MC06-CEK-EV-FRM-CS04_CL20-000009 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600165 | [9 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 0 | 3
| 212.4 | HS2-00002WUN4 | Bicester Road Embankment Planting - South Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL20-000010 | P01 | 2024-04-15 | 2024-04-26 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600166 | Done , issue found | OSGB issue send back on 25-Apr-2024, one asset missing | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 2 | 1 | 11
| 212.4 | HS2-00002WUN5 | Waddesdon South Cutting Planting - East Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL20-000042 | P01 | 2024-04-15 | 2024-04-26 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600168 | Done, No Issues | two asset missing. Send back on 25-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 2 | 1 | 11
| 212.4 | HS2-00002WUN6 | Waddesdon South Cutting Planting - East Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL20-000043 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600169 | No issues | [8 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 0 | 3
| 212.4 | HS2-00002WUN7 | Waddesdon South Cutting Planting - East Plot 3 | 1MC06-CEK-EV-FRM-CS04_CL20-000044 | P01 | 2024-04-15 | 2024-04-26 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600170 | Done, Issues reported | OSGB issues, send back on 25-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 2 | 1 | 11
| 212.4 | HS2-00002WUN8 | Waddesdon South Cutting Planting - East Plot 4 | 1MC06-CEK-EV-FRM-CS04_CL20-000045 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-26 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600171 | No issues | [8 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 6 | 0 | 3
| 212.4 | HS2-00002WUN9 | Waddesdon South Cutting Planting - East Plot 5 | 1MC06-CEK-EV-FRM-CS04_CL20-000046 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600172 | No issues | [8 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 8 | 0 | 3
| 212.4 | HS2-00002WUNA | Waddesdon South Cutting Planting - East Plot 6 | 1MC06-CEK-EV-FRM-CS04_CL20-000047 | P01 | 2024-04-15 | 2024-04-26 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600173 | Issues found | OSGB issues , send back on 25-Apr | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 2 | 1 | 11
| 212.4 | HS2-00002WUNB | Waddesdon South Cutting Planting - East Plot 7 | 1MC06-CEK-EV-FRM-CS04_CL20-000048 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600174 | No issues | [8 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 8 | 0 | 3
| 212.4 | HS2-00002WUNC | Waddesdon South Cutting Planting - West Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL20-000049 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600175 | No issues | [8 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 8 | 0 | 3
| 212.4 | HS2-00002WUND | Waddesdon South Cutting Planting - West Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL20-000050 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600176 | Issues found | CM_Chg and CM_CRT not consistant both P04 and P05 exisitng in the data change to P05. send back on 25-Apr | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 8 | 1 | 3
| 212.4 | HS2-00002WUNE | Waddesdon South Cutting Planting - West Plot 3 | 1MC06-CEK-EV-FRM-CS04_CL20-000051 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600177 | No issues | [8 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 8 | 0 | 3
| 212.4 | HS2-00002WUNF | Waddesdon South Cutting Planting - West Plot 4 | 1MC06-CEK-EV-FRM-CS04_CL20-000052 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600178 | No issues | [8 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 8 | 0 | 3
| 212.4 | HS2-00002WUNG | Waddesdon South Cutting Planting - West Plot 5 | 1MC06-CEK-EV-FRM-CS04_CL20-000053 | P01 | 2024-04-15 | 2024-04-26 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600179 | Issues found | OSGB issues , send back on 25-Apr | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 2 | 1 | 11
| 212.4 | HS2-00002WUNH | Waddesdon South Cutting Planting - West Plot 6 | 1MC06-CEK-EV-FRM-CS04_CL20-000054 | P01 | 2024-04-15 | 2024-04-18 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600180 | No issues | [8 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 8 | 0 | 3
| 212.4 | HS2-00002WUNJ | Waddesdon South Cutting Planting - West Plot 7 | 1MC06-CEK-EV-FRM-CS04_CL20-000055 | P01 | 2024-04-15 | 2024-04-26 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600181 | Issues found | OSGB issues , send back on 25-Apr | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 2 | 1 | 11
| 212.4 | HS2-000038V0R | Putlowes Cutting Planting - West Plot 2 | 1MC06-ASC-EV-REP-CS04_CL20-000001 | P01 | 2024-04-15 | 2024-04-26 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600223 | No issues | HS2-00003JY3J&HS2-00003JY3K missing, send back on 25-Apr | [7 empty] | 10 - Complete | Supriyan | Stebbings, Darrell <darrell.stebbings@arcadis.com> | 2 | 1 | 11
| UFDR 216.D | HS2-00002TUPL | Portway Farm ATS Telecoms | 1MC06-ASC-UT-FRM-CS06_CL09-000083-ACBOS | P01 | 2024-04-16 | 2024-04-16 | 2024-04-19 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600227 | Done, No Issues | [8 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 3 | 0 | 0
| UFDR 216.D | HS2-00002NHZA | West Street C23-081-0001P | 1MC06-ASC-UT-FRM-CS06_CL09-000094-ACBOS | P01 | 2024-04-16 | 2024-04-16 | 2024-04-19 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600182 | Done, No Issues | ACBOS /SMRTFRMS mismatch 1 missing from CUT in ACBOS - SMRTFRMS updated 18/4/24 | 2024-04-18 | [6 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 3 | 1 | 0
| UFDR 216.D | HS2-00002TUPP | IMD Electric | 1MC06-ASC-UT-FRM-CS06_CL09-000087-ACBOS | P01 | 2024-04-16 | 2024-04-19 | 2024-04-22 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600230 | Issue found | OS Coords issues 18-4-24 | 2024-04-19 | [6 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 1 | 1 | 3
| UFDR 216.D | HS2-00002TUPQ | IMD Telecoms | 1MC06-ASC-UT-FRM-CS06_CL09-000085-ACBOS | P02 | 2024-04-16 | 2024-04-16 | 2024-04-19 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600231 | Done, No Issues | [8 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 3 | 0 | 0
| UFDR 216.D | HS2-00002TUPM | IMD Potable Water | 1MC06-ASC-UT-FRM-CS06_CL09-000078-ACBOS | P01 | 2024-04-16 | 2024-04-19 | 2024-04-22 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600228 | Issue found | OS Coords issues 18-4-24 | 2024-04-19 | [6 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 1 | 1 | 3
| UFDR 216.D | HS2-00002TTR1 | West Street CSO-03-6110P | 1MC06-ASC-UT-FRM-CS06_CL09-000072-ACBOS | P01 | 2024-04-16 | 2024-04-19 | 2024-04-22 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600225 | Issue found | OS Coords issues 18-4-24 | 2024-04-19 | [6 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 1 | 1 | 3
| UFDR 216.D | HS2-00002TTR0 | West Street CSO-03-3110P | 1MC06-ASC-UT-FRM-CS06_CL09-000071-ACBOS | P01 | 2024-04-16 | 2024-04-19 | 2024-04-22 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600224 | Issue found | OS Coords issues 18-4-24 | 2024-04-19 | [6 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 1 | 1 | 3
| UFDR 216.D | HS2-000020CGE | West Street CSO-03-6101P | 1MC06-ASC-UT-FRM-CS06_CL09-000031-ACBOS | P01 | 2024-04-16 | 2024-04-16 | 2024-04-22 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600148 | Done, No Issues | [8 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 4 | 0 | 0
| UFDR 216.D | HS2-000020CGD | West Street CSO-03-3101P | 1MC06-ASC-UT-FRM-CS06_CL09-000033-ACBOS | P01 | 2024-04-16 | 2024-04-16 | 2024-04-19 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600147 | Done, No Issues | [8 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 3 | 0 | 0
| UFDR 216.D | HS2-00002YGQH | IMD Foul Water Pumping Station | 1MC06-ASC-UT-FRM-CS06_CL09-000096-ACBOS | P01 | 2024-04-16 | 2024-04-19 | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600235 | Issue found | OS Coords issues 18-4-24 | 2024-04-19 | Cannot view in DAC checker 22/4/24 | [5 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 3 | 2 | 3
| UFDR 216.D | HS2-00002TUPN | IMD Foul Water | 1MC06-ASC-UT-FRM-CS06_CL09-000081-ACBOS | P01 | 2024-04-16 | 2024-04-16 | 2024-04-19 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600229 | Done, No Issues | [8 empty] | 10 - Complete | Lee | Cook, Ted <ted.cook@arcadis.com> | 3 | 0 | 0
| UFDR 208.B | HS2-000020CEY | CSO-02-2203 | 1MC06-ASC-UT-FRM-CS04_CL18-000028-ACBOS | P01 | 2024-04-16 | 2024-04-22 | 2024-04-23 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600008 | [9 empty] | 10 - Complete | Lee | T, Sithrubi <sithrubi.t@arcadis.com> | 1 | 0 | 6
| 223.8 | HS2-000037YLY | 91-SL1 Mixbury Embankment Pedestrian Slab | 1MC06-ASC-BR-FRM-CS06_CL22-900001 | P01 | 2024-04-16 | 2024-05-28 |  |  | 1MC06-CEK-IM-DAT-CS06_CL22-600116 | Found issues | OSGB issues and MxmmPrmttdWght - 9999. Send back on 29-Apr-2024 |  | OSGB issues, send back on 29-May-2024 and JSON placeholder issue | [5 empty] | 99 - Cancelled | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
| 223.8 | HS2-000037YLZ | 91-SL3 Mixbury Embankment Pedestrian Slab | 1MC06-ASC-BR-FRM-CS06_CL22-900002 | P01 | 2024-04-16 | 2024-05-28 |  |  | 1MC06-CEK-IM-DAT-CS06_CL22-600116 | No issues | MxmmPrmttdWght - 9999. Send back on 29-Apr-2024 |  | JSON placeHolder incorrect. Inform team on 29-May-2024 | [5 empty] | 99 - Cancelled | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
| 223.8 | HS2-00002YCW9 | 91-SL2 Mixbury Embankment Pedestrian Slab | 1MC06-ASC-BR-FRM-CS06_CL22-900004 | P01 | 2024-04-16 | 2024-05-28 |  |  | 1MC06-CEK-IM-DAT-CS06_CL22-600116 | No issues | MxmmPrmttdWght - 9999. Send back on 29-Apr-2024 |  | JSON Placeholderis not correct, send back on 29-May-2029 | [5 empty] | 99 - Cancelled | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
| 221.2 | HS2-00002BJUR | School End Road Realignment | 1MC06-ASC-HW-FRM-CS06_CL10-000005-ACBOS | P01 | 2024-04-16 | 2024-04-18 | 2024-04-19 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600024 | Done, No Issues | 0's found in PVM, need correction, send back on 18-Apr-2024 | [7 empty] | 10 - Complete | Supriyan | KHABOUZE Zakaria <zakaria.khabouze@setec.com> | 1 | 1 | 2
| 221.2 | HS2-000020NM3 | Maintenance Access Road to Pond (Off School End Road - North) | 1MC06-ASC-HW-FRM-CS06_CL10-000009-ACBOS | P01 | 2024-04-16 | 2024-04-19 | 2024-04-19 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600023 | Done, No Issues | [8 empty] | 10 - Complete | Supriyan | KHABOUZE Zakaria <zakaria.khabouze@setec.com> | 0 | 0 | 3
| 221.2 | HS2-000020NM2 | Maintenance Access Road to Pond (Off School End Road - South) | 1MC06-ASC-HW-FRM-CS06_CL10-000010-ACBOS | P02 | 2024-04-16 | 2024-04-19 | 2024-04-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600022 | Done, one record with issue | OSGB dDelta issue, send back on 18-Apr-2024 | 2024-04-19 | Mtrl value is wroing, send back on 23-Apr-2024 | [5 empty] | 10 - Complete | Supriyan | KHABOUZE Zakaria <zakaria.khabouze@setec.com> | 2 | 2 | 3
| 221.2 | HS2-00002VXUC | Maintenance Access Road to GSMR (off School End Road Realignment) and Compound | 1MC06-ASC-HW-FRM-CS06_CL10-000026-ACBOS | P01 | 2024-04-16 | 2024-04-19 | 2024-04-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600126 | Done, one record with issue | OSGB dDelta issue, send back on 18-Apr-2024 | 2024-04-19 | [6 empty] | 10 - Complete | Supriyan | KHABOUZE Zakaria <zakaria.khabouze@setec.com> | 2 | 1 | 3
| 208.4 | HS2-00002CW0R | Calley Farm Access (SBH/34) Drainage System | 1MC06-ASC-DR-FRM-CS04_CL18-000014-ACBOS | P01 | 2024-04-16 | 2024-04-29 | 2024-04-30 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600028 | Done, Issues reported | OSGB issues, send back on 25-Apr-2024 |  | Wrong OSGB for one asset, send back on 29th Apr | [5 empty] | 10 - Complete | Supriyan | Cordero, Jan <Jan.Cordero@arcadis.com> | 1 | 2 | 13
| 218.02-1 | HS2-00002NSXQ | OXD Boundary/ Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL09-000081-ACBOS | P01 | 2024-04-17 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600181 | No issues | Old LoM, Com Type issues, send back on 01-May-2024 | [7 empty] | 99 - Cancelled | Supriyan | william.whyte@arcadis.com
| 218.02-1 | HS2-00002NSXP | OXD Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL09-000083-ACBOS | P01 | 2024-04-17 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600180 | No issues | Old LoM, Com Type issues, send back on 01-May-2024 | [7 empty] | 99 - Cancelled | Supriyan | william.whyte@arcadis.com
23 | 204.1-1 | HS2-000001024 | Wendover North Cutting | 1MC06-ASC-GT-FRM-CS03_CL17-000002-ACBOS | P05 | 2024-04-17 | 2024-05-01 | 2024-05-02 | YES | 1MC06-CEK-IM-DAT-CS03_CL17-600035 |  | Com_Dscrptns all copies of Com_Typ. Confirming zero(0) values. 30/4/24 | [7 empty] | 10 - Complete | Supriyan | Chatterjee, Sourav <SouravKumar.Chatterjee@arcadis.com> | 1 | 1 | 14
23 | 204.1-1 | HS2-00002Y8VY | Wendover North Cutting-Low Permeability Wall | 1MC06-ASC-GT-FRM-CS03_CL17-000011-ACBOS | P03 | 2024-04-17 | 2024-05-01 | 2024-05-02 | YES | 1MC06-CEK-IM-DAT-CS03_CL17-600076 |  | Com_Typ / Dscrptn. 30/4/24 | [7 empty] | 10 - Complete | Supriyan | Chatterjee, Sourav <SouravKumar.Chatterjee@arcadis.com> | 1 | 1 | 14
| 219.3 | HS2-0000386UA | 82-SL2 Cowley Embankment Pedestrian Bridge-Earthworks Transition | 1MC06-ASC-BR-FRM-CS06_CL10-000029-ACBOS | P03 | 2024-04-17 | 2024-04-17 | 2024-04-22 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600207 | Done, No Issues | [8 empty] | 10 - Complete | Lee | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 3 | 0 | 0
| 218.02 | HS2-000020NKT | Maintenance Access Road to Pond 02 (Off IMD Access) | 1MC06-ASC-HW-FRM-CS06_CL09-000039-ACBOS | P02 | 2024-04-17 | 2024-05-07 | 2024-05-09 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600096 | Issues found | OSGB Issues, Com_type and other issues, send back on 30-Apr-2024 |  | Com_Type issue, Wrong OSGB and Angle Slope issues, send back on 05-May-2024 | [5 empty] | 10 - Complete | Supriyan | dan.quirante@arcadis.com | 2 | 2 | 20
| 218.02 | HS2-00003124B | Maintenance Access to Calvert IMD Sewage Pumping Station | 1MC06-ASC-HW-FRM-CS06_CL09-000088-ACBOS | P01 | 2024-04-17 | 2024-05-07 | 2024-05-09 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600315 | Issues found | OSGB Issues, Com_type and other issues, send back on 30-Apr-2024 |  | Angle Slope issues, send back on 05-May-2024 | [5 empty] | 10 - Complete | Supriyan | dan.quirante@arcadis.com | 2 | 2 | 20
| 218.02 | HS2-00003124C | Calvert IMD Access Road | 1MC06-ASC-HW-FRM-CS06_CL09-000092-ACBOS | P02 | 2024-04-17 | 2024-05-07 | 2024-05-09 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600314 | Issues found | OSGB Issues, Com_type and other issues, send back on 30-Apr-2024 |  | Angle Slope issues, send back on 05-May-2024 | [5 empty] | 10 - Complete | Lee | dan.quirante@arcadis.com | 2 | 2 | 20
| 218.02 | HS2-00003CCJX | Maintenance Access Road to Pond 1003 | 1MC06-ASC-HW-FRM-CS06_CL09-900096-ACBOS | P01 | 2024-04-17 | 2024-05-07 | 2024-05-09 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600282 | Issues found | OSGB Issues, Com_type and other issues, send back on 30-Apr-2024 |  | Angle Slope issues, send back on 05-May-2024 | [5 empty] | 10 - Complete | Supriyan | dan.quirante@arcadis.com | 2 | 2 | 20
| 204.2-1 | HS2-00002CT4P | C2.T.20 Catchment | 1MC06-ASC-DR-FRM-CS03_CL17-000007-ACBOS | P06 | 2024-04-18 | 2024-04-19 | 2024-04-19 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600008 |  | Incorrect com_type/description, sent back on 18/04/2024 | 2024-04-19 | [6 empty] | 10 - Complete | Alex | leomel.ramos@arcadis.com | 0 | 1 | 1
| 201.0-6 | HS2-00002CT2H | Bowood Lane Drainage System | 1MC06-ASC-DR-FRM-CS03_CL05-000024-ACBOS | P01 | 2024-04-19 | 2024-04-23 | 2024-04-25 | YES | 1MC06-CEK-IM-DAT-CS03_CL05-600019 |  | OSGB coords 22/4/24 | 2024-04-23 | [6 empty] | 10 - Complete | Lee | Hallado, Ruel <Ruel.Hallado@arcadis.com> | 2 | 1 | 4
| 227.1 | HS2-00002N7X2 | Radstone Road Ancillary Culvert 097-AC2 | 1MC07-CEK-BR-FRM-CS07_CL12-600007 | P04 | 2024-04-19 | 2024-04-24 | 2024-04-25 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600047 | Done, Issues reported | request received mid afternoon 19/4/24 |  | wont load to SQL rebuild required. 19-apr-24 | 2024-04-22 | ok |  |  |  | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 3 | 5
| 212.4 | HS2-00002CT6E | Bicester Road Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS04_CL20-000030-ACBOS |  | 2024-04-19 | 2024-04-19 | 2024-04-29 | YES | 1MC06-CEK-IM-DAT-CS04_CL20-600120 | Done No Issues | [8 empty] | 10 - Complete | Lee | orlando.sangalang@arcadis.com | 6 | 0 | 0
| 212.4 | HS2-00002CT6D | Bicester Road Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS04_CL20-000050-ACBOS |  | 2024-04-19 | 2024-04-19 | 2024-04-29 | YES | 1MC06-CEK-IM-DAT-CS04_CL20-600119 | Done No Issues | [8 empty] | 10 - Complete | Lee | orlando.sangalang@arcadis.com | 6 | 0 | 0
| 212.4 | HS2-00002CT6B | Putlowes Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS04_CL19-000022-ACBOS |  | 2024-04-19 | 2024-04-19 | 2024-04-29 | YES | 1MC06-CEK-IM-DAT-CS04_CL20-600027 | Done No Issues | [8 empty] | 10 - Complete | Lee | orlando.sangalang@arcadis.com | 6 | 0 | 0
| 212.4 | HS2-00002CT68 | Putlowes Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS04_CL19-000034-ACBOS |  | 2024-04-19 | 2024-04-19 | 2024-04-29 | YES | 1MC06-CEK-IM-DAT-CS04_CL20-600024 | Done No Issues | [8 empty] | 10 - Complete | Lee | orlando.sangalang@arcadis.com | 6 | 0 | 0
| 212.4 | HS2-00002CT5Z | Thame Valley South Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS04_CL19-000019-ACBOS |  | 2024-04-19 | 2024-04-19 | 2024-04-29 | YES | 1MC06-CEK-IM-DAT-CS04_CL19-600009 | Done No Issues | [8 empty] | 10 - Complete | Lee | orlando.sangalang@arcadis.com | 6 | 0 | 0
| 212.4 | HS2-00002CT5X | Thame Valley South Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS04_CL19-000032-ACBOS |  | 2024-04-19 | 2024-04-19 | 2024-04-29 | YES | 1MC06-CEK-IM-DAT-CS04_CL19-600041 | Done No Issues | [8 empty] | 10 - Complete | Lee | orlando.sangalang@arcadis.com | 6 | 0 | 0
| 212.4 | HS2-00002CT6K | Waddesdon South Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS04_CL20-000031-ACBOS |  | 2024-04-19 | 2024-04-19 | 2024-04-29 | YES | 1MC06-CEK-IM-DAT-CS04_CL20-600138 | Done No Issues | [8 empty] | 10 - Complete | Lee | orlando.sangalang@arcadis.com | 6 | 0 | 0
| 212.4 | HS2-00002CT6H | Waddesdon South Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS04_CL20-000051-ACBOS |  | 2024-04-19 | 2024-04-19 | 2024-04-29 | YES | 1MC06-CEK-IM-DAT-CS04_CL20-600140 | Done No Issues | [8 empty] | 10 - Complete | Lee | orlando.sangalang@arcadis.com | 6 | 0 | 0
| 233.01-2 | HS2-000020364 | Appletree Lane Reinstatement | 1MC07-ASC-HW-FRM-CS07_CL13-000011-ACBOS | P02 | 2024-04-22 | 2024-04-22 | 2024-05-01 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600020 | No issues | [8 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 7 | 0 | 0
| 229.01-1 | HS2-00002CTF8 | Footpath AN4 Reinstatement | 1MC07-ASC-HW-FRM-CS07_CL25-000029-ACBOS | P02 | 2024-04-22 |  | 2024-05-03 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600002 | [9 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 9 | 0
| 229.01-1 | HS2-00002CTF7 | Footpath AN39 Reinstatement | 1MC07-ASC-HW-FRM-CS07_CL25-000028-ACBOS | P02 | 2024-04-22 |  | 2024-05-03 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600001 | [9 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 9 | 0
| 237.05 | HS2-00002BVMZ | C3.L.69 Catchment | 1MC07-ASC-DR-FRM-CS07_CL23-000011-ACBOS | P02 | 2024-04-22 | 2024-04-24 | 2024-05-01 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600012 | Issues - Fixed | OSGB coords 22/4/24 few other items. | 2024-04-24 | [6 empty] | 10 - Complete | Lee | Charuvil Vivekanandan, Amrutha <Amrutha.CharuvilVivekananda@arcadis.com> | 5 | 1 | 2
| 218.02 | HS2-000031248 | TWY 16 Footpath Crossing | 1MC06-ASC-CV-FRM-CS06_CL10-000090-ACBOS | P02 | 2024-04-22 |  | 2024-04-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600210 | Done. No Issues | [8 empty] | 10 - Complete | Lee | Ul Mashood, Hammad <hammad.mashood@arcadis.com> | 2 | 0
| 238.02-2 | HS2-000025B3T | Accommodation Access Road (Off A423 Banbury Road) | 1MC07-ASC-HW-FRM-CS07_CL24-000027-ACBOS | P01 | 2024-04-23 | 2024-05-10 | 2024-05-14 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600066 | Done, found issues | Com_Typ, OS coords 23/4/24 | 2024-05-07 | CUT com_Typ as CUT, fixed in house to Cut, while DT update PW file, to expediate. 9/5/24 Failing to load to SQL 9-May-24 | [5 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 2 | 2 | 17
| 204.2-1 | HS2-00002TKV4 | Maintenance Siding Access Level 3 | 1MC06-ASC-HW-FRM-CS03_CL17-000041-ACBOS | P04 | 2024-04-23 | 2024-04-24 | 2024-04-24 | YES | 1MC06-CEK-IM-DAT-CS03_CL17-600074 | Fail | Osgb - Com_typs. | 2024-04-24 | [6 empty] | 10 - Complete | Lee | Thompson, Stephen <stephen.thompson@arcadis.com> | 0 | 1 | 1
| 201.0-6 | HS2-00002BJQX | Bowood Lane Realignment | 1MC06-ASC-HW-FRM-CS03_CL05-000014-ACBOS | P01 | 2024-04-23 | 2024-04-24 | 2024-04-25 | YES | 1MC06-CEK-IM-DAT-CS03_CL05-600108 | Done No Issues | Com_typs, AnglSlp | 2024-04-24 | 1MC06-CEK-IM-DAT-CS03_CL05-600086 DT supplied incirrect JSON link. | 2024-04-24 |  |  |  |  | 10 - Complete | Lee | H, Chandrakantesh <Chandrakantesh.H@arcadis.com> | 1 | 2 | 1
| 237.05 | HS2-00002EK8B | Radbourne ATS UTX | 1MC07-ASC-CV-FRM-CS07_CL23-000013-ACBOS | P01 | 2024-04-23 | 2024-04-23 | 2024-04-25 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600157 | Done, No Issues | [8 empty] | 10 - Complete | Lee | K S, Abhisheka <abhisheka.ks@arcadis.com> | 2 | 0 | 0
| 213.05 | HS2-00002CW0N | HS2-00002C5T1-Bridleway QUA/28A Drainage System | 1MC06-ASC-DR-FRM-CS05-000021-ACBOS |  | 2024-04-23 | 2024-04-23 | 2024-04-25 | yes | 1MC06-CEK-IM-DAT-CS05-600009 | [9 empty] | 10 - Complete | Lee | lokesh.jv@arcadis.com | 2 | 0 | 0
| 221.2_1 | HS2-000001321 | Footpath CHW/18 Accommodation Overbridge | 1MC06-CEK-BR-FRM-CS06_CL10-000005 | P04 | 2024-04-24 | 2024-04-24 | 2024-04-25 | YES | 1MC06-CEK-IM-DAT-CS06_CL10-600018 |  | MPDT wont load | [7 empty] | 10 - Complete | Lee | DE OLIVEIRA DE ARAUJO Nuno Sergio <sergio.deoliveira@setec.com> | 1 | 1 | 0
| 227.1 | HS2-000025B28 | Radstone Road Realignment | 1MC07-ASC-HW-FRM-CS07_CL12-000001-ACBOS | P03 | 2024-04-24 | 2024-04-26 | 2024-04-29 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600155 | Done, Issues reported | OS coords , AnglSlp 25-Apr-24 | 26-Apr-24 @1458hrs | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 2
| 227.1 | HS2-000025B29 | Maintenance Access Road to Pond (Off Radstone Road East) | 1MC07-ASC-HW-FRM-CS07_CL12-000016-ACBOS | P03 | 2024-04-24 | 2024-04-26 | 2024-04-29 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600150 | Done, No Issues | AnglSlp 25-Apr-24 | 26-Apr-24 @1458hrs | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 2
| 218.02 | HS2-00003CCJY | Maintenance Access Road to Pond 0992 | 1MC06-ASC-HW-FRM-CS06_CL09-000094-ACBOS | P01 | 2024-04-24 | 2024-05-02 | 2024-05-07 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600281 | Issues found | OSGB issues , send back on 01-May-2024 | [7 empty] | 10 - Complete | Supriyan | Quirante, Dan <dan.quirante@arcadis.com> | 2 | 1 | 8
| 218.02 | HS2-00003124A | Footpath SCL6 | 1MC06-ASC-HW-FRM-CS06_CL09-000086-ACBOS | P02 | 2024-04-24 | 2024-05-07 | 2024-05-09 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600316 | Issues found | OSGB Issues, Com_type, send back on 01-May-2024 |  | Angle Slope issues, send back on 05-May-2024 | [5 empty] | 10 - Complete | Supriyan | dan.quirante@arcadis.com | 2 | 2 | 13
| 218.02 | HS2-00002TPZ5 | Portway Culvert and Pond Access | 1MC06-ASC-HW-FRM-CS06_CL09-000071-ACBOS | P02 | 2024-04-24 | 2024-05-07 | 2024-05-09 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600124 | Issues found | OSGB Issues, Com_type, send back on 01-May-2024 |  | Angle Slope issues, send back on 05-May-2024 | [5 empty] | 10 - Complete | Supriyan | dan.quirante@arcadis.com | 2 | 2 | 13
| 218.02 | HS2-00002CT9Q | Twyford Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000095-ACBOS | P02 | 2024-04-24 | 2024-05-02 | 2024-05-03 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600082 | No issues | Com_type and other issues , send back on 01-May-2024 | [7 empty] | 10 - Complete | Supriyan | Whyte, William <William.Whyte@arcadis.com> | 1 | 1 | 8
| 218.02 | HS2-00002CT9N | Twyford Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000093-ACBOS | P02 | 2024-04-24 | 2024-05-02 | 2024-05-03 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600077 | No issues | Com_type and other issues , old LoDM, send back on 01-May-2024 | [7 empty] | 10 - Complete | Supriyan | Whyte, William <William.Whyte@arcadis.com> | 1 | 1 | 8
| 218.02 | HS2-00002CTDA | Calvert Infrastructure Maintenance Depot Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL09-000087-ACBOS | P02 | 2024-04-24 | 2024-05-02 | 2024-05-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600218 | No issues | Com_type and other issues , send back on 01-May-2024 | [7 empty] | 10 - Complete | Supriyan | Whyte, William <William.Whyte@arcadis.com> | 1 | 1 | 8
| 218.02 | HS2-00002CTD9 | Calvert Infrastructure Maintenance Depot Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL09-000085-ACBOS | P02 | 2024-04-24 | 2024-05-02 | 2024-05-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600215 | Issues found | Com_type and other issues , send back on 01-May-2024 | [7 empty] | 10 - Complete | Supriyan | Whyte, William <William.Whyte@arcadis.com> | 1 | 1 | 8
| 208.4 | HS2-00002N7VS | Aylesbury North Cutting - Ancillary Culvert 061-AC5 | 1MC06-ASC-CV-FRM-CS04_CL18-000012-ACBOS | P01 | 2024-04-24 | 2024-05-01 | 2024-05-03 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600086 | No issues | Query send on 0's , send on 01-May-2024 | [7 empty] | 10 - Complete | Supriyan | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com> | 2 | 1 | 7
| 208.4 | HS2-00002N7VT | Aylesbury North Cutting 061-AC6 | 1MC06-ASC-CV-FRM-CS04_CL18-000017-ACBOS | P01 | 2024-04-24 | 2024-05-01 | 2024-05-03 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600083 | No issues | Query send on 0's , send on 01-May-2024 | [7 empty] | 10 - Complete | Supriyan | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com> | 2 | 1 | 7
| 235.01-1 | HS2-000025B3A | Hill Farm Accommodation Access Road | 1MC07-ASC-HW-FRM-CS07_CL14-000035-ACBOS | P01 | 2024-04-25 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL14-600024 | Issues Found | Send back on 03-May-2024 | [7 empty] | 99 - Cancelled | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com>
| 235.01-1 | HS2-00002J4YX | Maintenance Access Road to Pond (off Realigned Banbury Road (East side of HS2)) | 1MC07-ASC-HW-FRM-CS07_CL14-000042-ACBOS | P01 | 2024-04-25 | 2024-05-08 | 2024-05-09 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600026 | No issues | Cm_Chg version issue, Com_type and other issues, send back on 03-May-2024 | [7 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 1 | 1 | 13
| 233.01 | HS2-00002EF97 | A361 Byfield Road Realignment | 1MC07-ASC-HW-FRM-CS07_CL13-000015-ACBOS | P01 | 2024-04-25 | 2024-05-08 | 2024-05-09 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600016 | No issues | CM_CHg and CM_CRT not consistant, Com_Type issues, send back on 03-May-2024 | [7 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 1 | 1 | 13
| 229.01-1 | HS2-00002TMF3 | Greatworth Green Tunnel South Portal | 1MC07-ASC-UT-FRM-CS07_CL12-000098-ACBOS | P01 | 2024-04-26 | 2024-05-14 | 2024-05-20 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600053 | Issues found | ACBOS PCRA is pending, send back on 07-May-2024 |  | OSGB Spacing Issue , Send back on 17 May -2024 via team chat. | 2024-05-17 |  |  |  |  | 10 - Complete | Rakesh | Agnieszka Cytowska <agcy@cowi.com> | 4 | 2 | 18
23 | 204.1-1 | HS2-000030KBA | Spring Chamber Ground Water Catchment | 1MC06-ASC-DR-FRM-CS03_CL17-000072-ACBOS | P01 | 2024-04-26 |  | 2024-05-08 | YES | 1MC06-CEK-IM-DAT-CS03_CL17-600077 | Issues Found | Com_type , OSGB and other issues. Send back on 03-May-2024 | [7 empty] | 10 - Complete | Supriyan | Hallado, Ruel <Ruel.Hallado@arcadis.com> | 7 | 1
| 229.03 | HS2-00002N7U9 | Greatworth North Embankment Group - Ancillary Culvert 101-AC1 | 1MC07-ASC-CV-FRM-CS07_CL12-000041-ACBOS | P01 | 2024-04-26 | 2024-05-07 | 2024-05-08 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600278 | [9 empty] | 10 - Complete | Rakesh | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 1 | 0 | 11
| 213.07 | HS2-00003HWH2 | NR flood relief and watercourse culverts Earthworks Transition 3D Model | 1MC06-ASC-GT-FRM-CS04_CL20-000060-ACBOS | P01 | 2024-04-26 |  | 2024-05-03 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600224 | No issues | [8 empty] | 10 - Complete | Supriyan | MATTOUSSI Farah <farah.mattoussi@setec.com> | 5 | 0
| 208.4 | HS2-00003GL98 | Flood Compensation Area | 1MC06-ASC-DR-FRM-CS04_CL19-000057-ACBOS | P01 | 2024-04-26 | 2024-05-09 | 2024-05-10 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600096 | Found issues | OSGB and GTxtl isses, send back on 07-May-2024 | [7 empty] | 10 - Complete | Supriyan | Ka, Srinatha <srinatha.ka@arcadis.com> | 1 | 1 | 13
23 | 204.1-1 | HS2-00002BVF0 | C2.T.16 Catchment | 1MC06-ASC-DR-FRM-CS03_CL17-000005-ACBOS | P01 | 2024-04-29 |  | 2024-05-07 | YES | 1MC06-CEK-IM-DAT-CS03_CL17-600060 | [9 empty] | 10 - Complete | Alex | Ramos, Leo <Leomel.Ramos@arcadis.com> | 5 | 0
23 | 204.1-1 | HS2-00002YYN4 | Low Permeability Wall Ground Water Catchment | 1MC06-ASC-DR-FRM-CS03_CL17-000069-ACBOS | P01 | 2024-04-29 |  | 2024-05-07 | YES | 1MC06-CEK-IM-DAT-CS03_CL17-600078 | [9 empty] | 10 - Complete | Alex | Ramos, Leo <Leomel.Ramos@arcadis.com> | 5 | 0
| 229.03 | HS2-00003B2GK | Greatworth North Embankment and Cutting Group | 1MC07-ASC-CV-FRM-CS07_CL25-000027-ACBOS | P01 | 2024-04-29 | 2024-05-04 | 2024-05-07 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600067 | [9 empty] | 10 - Complete | Rakesh | PATIL, APOORVA <apoorva.patil@arcadis.com> | 0 | 0 | 5
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-AR-FRM-CS07_CL14-600001 | P03 | 2024-04-30 | 2024-05-13 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | ok to load 13-May-24 | Loaded 668 - OK |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 8 | 2 | 13
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-ASC-CV-FRM-CS07_CL13-000010-ACBOS | P07 | 2024-04-30 | 2024-05-21 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | Issues found - fixed 21/5/24 | SHARED Multi Discipline JSON |  | ok to load 16-May-24 | Loaded |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 2 | 2 | 21
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-CV-FRM-CS07_CL14-000034 | P01 | 2024-04-30 | 2024-05-16 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | ok to load 16-May-24 | Loaded |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 5 | 2 | 16
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-EL-FRM-CS07_CL14-000001 | P02 | 2024-04-30 | 2024-05-13 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | ok to load 13-May-24 | loaded 1411 ok |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 8 | 2 | 13
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-EL-FRM-CS07_CL14-000002 | P02 | 2024-04-30 | 2024-05-14 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | ok to load 15-May-24 | Loaded 194 ok |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 7 | 2 | 14
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-EL-FRM-CS07_CL14-000003 | P02 | 2024-04-30 | 2024-05-14 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | ok to load 15-May-24 | loaded 149 ok |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 7 | 2 | 14
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-EL-FRM-CS07_CL14-000004 | P02 | 2024-04-30 | 2024-05-14 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | ok to load 15-May-24 | Loaded 250 ok |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 7 | 2 | 14
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-EL-FRM-CS07_CL14-000005 | P02 | 2024-04-30 | 2024-05-14 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | ok to load 15-May-24 | Loaded 189 ok |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 7 | 2 | 14
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-FI-FRM-CS07_CL14-000001 | P01 | 2024-04-30 | 2024-05-14 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | PPE have no SrrndMtrl, PPE have no DsgnFlw or DsgnFlwBss, PPE have no FlwDrctn - fixed and justified where appropriate. - Load 13-May-24 | Loaded 257 ok |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 7 | 2 | 14
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-FI-FRM-CS07_CL14-000002 | P01 | 2024-04-30 | 2024-05-14 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | PPE have no SrrndMtrl, PPE have no DsgnFlw or DsgnFlwBss, PPE have no FlwDrctn - fixed and justified where appropriate. - Load 13-May-24 | Loaded 493 ok |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 7 | 2 | 14
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-FI-FRM-CS07_CL14-000003 | P01 | 2024-04-30 | 2024-05-20 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | ok to load 20-May-24 | loaded 181 ok |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 3 | 2 | 20
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-ME-FRM-CS07_CL14-000001 | P02 | 2024-04-30 | 2024-05-14 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | ok to load 15-May-24 | Loaded 478 rebuilt |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 7 | 2 | 14
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-ME-FRM-CS07_CL14-000002 | P02 | 2024-04-30 | 2024-05-14 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | ok to load 15-May-24 | Loaded 325 ok |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 7 | 2 | 14
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-ME-FRM-CS07_CL14-000003 | P03 | 2024-04-30 | 2024-05-14 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | ok to load 15-May-24 | loaded 143 ok |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 7 | 2 | 14
| 233.01-2 | HS2-00002CTHF | Chipping Warden Tunnel North Portal Building | 1MC07-CEK-RC-FRM-CS07_CL14-000001 | P02 | 2024-04-30 | 2024-05-14 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | SHARED Multi Discipline JSON |  | ok to load 15-May-24 | Loaded 38 OK |  |  |  |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com> | 7 | 2 | 14
23 | 204.1-1 | HS2-00002EK6V | Stoke Mandeville Maintenance Loop UTX No1 | 1MC06-ASC-CV-FRM-CS03_CL17-000010-ACBOS | P01 | 2024-04-30 |  | 2024-05-07 | YES | 1MC06-CEK-IM-DAT-CS03_CL17-600016 | [9 empty] | 10 - Complete | Alex | S P, Veerabhadraswamy <veerabhadraswamy.sp@arcadis.com> | 4 | 0
| 208.4 | HS2-000001295 | Footpath SBH-34 Overbridge | 1MC06-CEK-BR-FRM-CS04_CL18-000008 | P01 | 2024-04-30 | 2024-05-07 | 2024-05-10 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600149 | No issues | send back on 07-May-2024, Design flow is not correct | [7 empty] | 10 - Complete | Supriyan | Harry Forbes <HRFO@COWI.COM> | 3 | 1 | 7
| UFDR 226.A | HS2-00002TTH7 | A43 Oxford Road Switching Station | 1MC07-ASC-UT-FRM-CS07_CL12-000099-ACBOS | P01 | 2024-05-01 |  | 2024-05-07 | YES | 1MC07-CEK-IM-DAT-CS07_CL12-600158 | [9 empty] | 10 - Complete | Supriyan | Kamboj, Mohit <mohit.kamboj@arcadis.com> | 3 | 0
| 201.0-6 | HS2-00002BJQX | Bowood Lane Realignment | 1MC06-ASC-HW-FRM-CS03_CL05-000014-ACBOS | P02 | 2024-05-01 |  | 2024-05-07 | YES | 1MC06-CEK-IM-DAT-CS03_CL05-600108 | [9 empty] | 10 - Complete | Alex | Gregory, Gillian <gillian.gregory@arcadis.com> | 3 | 0
| 201.0-6 | HS2-00002CT2H | Bowood Lane Drainage System | 1MC06-ASC-DR-FRM-CS03_CL05-000024-ACBOS | P02 | 2024-05-01 |  | 2024-05-07 | YES | 1MC06-CEK-IM-DAT-CS03_CL05-600019 | [9 empty] | 10 - Complete | Alex | Hallado, Ruel <Ruel.Hallado@arcadis.com> | 3 | 0
| 228.1 | HS2-00002CX3Q | Bridleway AN14 Diversion Drainage | 1MC07-ASC-DR-FRM-CS07_CL12-000023-ACBOS | P02 | 2024-05-01 | 2024-05-14 | 2024-05-16 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600016 | Issues Found | OSGB issues, send back on 09-May-2024 | [7 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 2 | 1 | 13
| 220.5 | HS2-00002Y4JH | 084-AC2 Watercourse Diversion | 1MC06-ASC-DR-FRM-CS06_CL10-000114-ACBOS | P03 | 2024-05-01 | 2024-05-09 | 2024-05-10 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600124 | No issues | 2 assets missing and other issues, send back on 07-May-2024 | [7 empty] | 10 - Complete | Supriyan | alberto.lorusso@arcadis.com> | 1 | 1 | 8
| 208.4 | HS2-000020NC4 | Maintenance Access Road to Pond (North Arm off Calley Farm) | 1MC06-ASC-HW-FRM-CS04_CL18-000019-ACBOS | P01 | 2024-05-01 | 2024-05-03 | 2024-05-07 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600012 | Issues found | Com_type, and other issues found. Send back on 03-May-2024 | [7 empty] | 10 - Complete | Rakesh | Ayan.Bhattacharya@arcadis.com> | 1 | 1 | 2
| 208.4 | HS2-00002BJSK | Maintenance Access Road to Pond (South Arm off Calley Farm - South) | 1MC06-ASC-HW-FRM-CS04_CL18-000023-ACBOS | P01 | 2024-05-01 | 2024-05-06 | 2024-05-09 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600070 | Issues found | Com_type, and other issues found. Send back on 06-May-2024 | [7 empty] | 10 - Complete | Rakesh | Ayan.Bhattacharya@arcadis.com> | 2 | 1 | 5
| 238.02-2 | HS2-000020P2G | Maintenance Access Road to Pond (Off A423 Banbury Road South) | 1MC07-ASC-HW-FRM-CS07_CL24-000022-ACBOS | P01 | 2024-05-02 | 2024-05-07 | 2024-05-13 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600052 | [9 empty] | 10 - Complete | Supriyan | Conor.Egan@wsp.com> | 4 | 0 | 5
| UFDR 210.B | HS2-000020CF7 | CSO-02-2204 | 1MC06-ASC-UT-FRM-CS04_CL20-000030-ACBOS | P01 | 2024-05-03 | 2024-05-14 | 2024-05-14 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600123 |  | updated AssetDescription_2 (Gas Pipeline Route) as per EKFB Smart form(Gas Pressure Route) . | [7 empty] | 10 - Complete | Rakesh | eloise.mainstone@arcadis.com> | 0 | 1 | 11
10 | 233.01-3 | HS2-00002EK7X | Chipping Warden Green Tunnel South Portal UTX | 1MC07-ASC-CV-FRM-CS07_CL13-000009-ACBOS | P01 | 2024-05-03 | 2024-05-03 | 2024-05-10 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600015 | [9 empty] | 10 - Complete | Supriyan | muthukumar.p@arcadis.com> | 4 | 0 | 0
| 223.8 | HS2-00002CTC2 | Mixbury Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000018-ACBOS | P01 | 2024-05-03 | 2024-05-08 | 2024-05-08 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600049 | [9 empty] | 10 - Complete | Rakesh | MIRI Youssef <youssef.miri@setec.com> | 0 | 0 | 5
| 223.8 | HS2-00002CTC4 | Mixbury Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000023-ACBOS | P01 | 2024-05-03 | 2024-05-14 | 2024-05-15 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600050 | No issues | OSGB co-ordinate issues, send back on 10-May-2024 | [7 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 1 | 1 | 11
| 223.8 | HS2-00002CTC9 | Mixbury Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000022-ACBOS | P01 | 2024-05-03 | 2024-05-14 | 2024-05-15 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600079 | No issues | [8 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 1 | 0 | 11
| 223.8 | HS2-00002CTCC | Westbury Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000025-ACBOS | P01 | 2024-05-03 | 2024-05-14 | 2024-05-17 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600084 | No issues | Com_type issues, send back on 14-May-2024 |  | couple of Com_dscrptn need edits. 15/5/24 | [5 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 3 | 2 | 11
10 | 233.01-3 | HS2-00002TMF9 | Chipping Warden Green Tunnel South Portal | 1MC07-ASC-UT-FRM-CS07_CL26-000044-ACBOS | P01 | 2024-05-07 | 2024-06-06 | 2024-06-12 | issues found | 1MC07-CEK-IM-DAT-CS07_CL26-600012 | Issues found | Incorrect SdSlp value & row count in Cut class. |  | Incorrect SdSlp value & ifclayer & uniclass ID mismatch send back to team on 20 May 24. Ghost records in Cut Class , incorrect SdSlp & Uniclass ID values send back to team on 30 May 24. | [5 empty] | 10 - Complete | Rakesh | Agnieszka Cytowska <agcy@cowi.com> | 4 | 2 | 30
| 229.01-1 | HS2-00003B5FS | Greatworth Access Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL25-000025-ACBOS | P02 | 2024-05-07 | 2024-05-07 | 2024-05-09 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600068 | [9 empty] | 10 - Complete | Rakesh | gopika.b@arcadis.com> | 2 | 0 | 0
| 218.02 | HS2-00002CT9P | Twyford Embankment Noise Barrier Line | 1MC06-ASC-CV-FRM-CS06_CL10-000067-ACBOS | P01 | 2024-05-07 | 2024-05-09 | 2024-05-13 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600211 | Done No issues | Com_typs. Sent back 9/5/24. |  | Failing SQL load 10-May-24 had to split to tab per class and then class of 1688 components into 3 | loaded 13/5/24 |  |  |  |  | 10 - Complete | Lee | karthiban.sr@arcadis.com> | 2 | 2 | 2
| 218.02 | HS2-00002VK41 | Portway Culvert Access Road Bridge MAS | 1MC06-ASC-CV-FRM-CS06_CL09-000040-ACBOS | P01.1 | 2024-05-07 | 2024-05-09 | 2024-05-10 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600276 | Done No issues | Com_Type & Dscrptn. IfcPresentationLayer. Sent back 9/5/24 | 2024-05-09 | [6 empty] | 10 - Complete | Lee | Bontala, Prajwal <prajwal.bontala@arcadis.com> | 1 | 1 | 2
| 238.02-2 | HS2-00002CTKE | Footpath SM33 Diversion (west of HS2) | 1MC07-ASC-HW-FRM-CS07_CL24-000029-ACBOS | P02 | 2024-05-08 | 2024-05-09 | 2024-05-14 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600079 | No issues | [8 empty] | 10 - Complete | Lee | Conor.Egan@wsp.com> | 3 | 0 | 1
| 238.02-2 | HS2-000020P2P | Footpath SM89 Extension | 1MC07-ASC-HW-FRM-CS07_CL24-000024-ACBOS | P04 | 2024-05-08 | 2024-05-10 | 2024-05-10 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600059 | Done | [8 empty] | 10 - Complete | Rakesh | Conor.Egan@wsp.com> | 0 | 0 | 2
| 238.02-2 | HS2-000020P2N | Maintenance Access Road to Pond (Off A423 Banbury Road North) | 1MC07-ASC-HW-FRM-CS07_CL24-000023-ACBOS | P01 | 2024-05-08 | 2024-05-20 | 2024-05-22 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600058 | No issues | File has reverted to old ACBOS with many issues - Looks like MDM export failiure? 17-May-24 | rvsd 20-May-24 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 2 | 1 | 12
| 234.05 | HS2-00002TGP5 | Lower Boddington Embankment 114-DC1 | 1MC07-ASC-CV-FRM-CS07_CL14-000116-ACBOS | P01 | 2024-05-08 | 2024-05-08 | 2024-05-09 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600196 | Done | [8 empty] | 10 - Complete | Rakesh | vruddhika.naik@arcadis.com> | 1 | 0 | 0
| 234.05 | HS2-00003A346 | Lower Boddington Embankment 114-DC2 | 1MC07-ASC-CV-FRM-CS07_CL14-000117-ACBOS | P01 | 2024-05-08 | 2024-05-08 | 2024-05-09 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600197 | Done | [8 empty] | 10 - Complete | Rakesh | vruddhika.naik@arcadis.com> | 1 | 0 | 0
| 234.05 | HS2-00003A347 | Lower Boddington Embankment 114-DC3 | 1MC07-ASC-CV-FRM-CS07_CL14-000118-ACBOS | P01 | 2024-05-08 | 2024-05-09 | 2024-05-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600198 | Done No Issues | [8 empty] | 10 - Complete | Rakesh | vruddhika.naik@arcadis.com> | 1 | 0 | 1
| 234.05 | HS2-00003A34A | Lower Boddington Embankment 115-DC4 | 1MC07-ASC-CV-FRM-CS07_CL14-000119-ACBOS | P01 | 2024-05-08 | 2024-05-09 | 2024-05-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600201 | Done No Issues | [8 empty] | 10 - Complete | Rakesh | vruddhika.naik@arcadis.com> | 1 | 0 | 1
| 234.05 | HS2-00003A34B | Lower Boddington Embankment 115-DC5 | 1MC07-ASC-CV-FRM-CS07_CL14-000120-ACBOS | P01 | 2024-05-08 | 2024-05-09 | 2024-05-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600202 | Done No Issues | [8 empty] | 10 - Complete | Rakesh | vruddhika.naik@arcadis.com> | 1 | 0 | 1
| 234.05 | HS2-00003A349 | Lower Boddington Embankment 114-DC7 | 1MC07-ASC-CV-FRM-CS07_CL14-000122-ACBOC | P01 | 2024-05-08 | 2024-05-09 | 2024-05-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600200 | Done No Issues | [8 empty] | 10 - Complete | Lee | vruddhika.naik@arcadis.com> | 1 | 0 | 1
| 234.05 | HS2-00003A348 | Lower Boddington Embankment 114-DC6 | 1MC07-ASC-CV-FRM-CS07_CL14-000121-ACBOC | P01 | 2024-05-08 | 2024-05-09 | 2024-05-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600199 | Done No Issues | [8 empty] | 10 - Complete | Lee | vruddhika.naik@arcadis.com> | 1 | 0 | 1
13 | 213.07-1 | HS2-00003HWH2 | NR flood relief and watercourse culverts Earthworks Transition 3D Model | 1MC06-ASC-GT-FRM-CS04_CL20-000060-ACBOS |  | 2024-05-08 | 2024-05-14 | 2024-05-20 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600224 |  | Sdslp value is incorrect. send back on 17-May-2024 | [7 empty] | 10 - Complete | Rakesh | MATTOUSSI Farah <farah.mattoussi@setec.com> | 4 | 1 | 6
| 208.4 | HS2-000020NC7 | Calley Farm (SBH-34) Footpath and Accommodation Access Realignment | 1MC06-ASC-HW-FRM-CS04_CL18-000014-ACBOS | P01 | 2024-05-08 | 2024-05-22 | 2024-05-24 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600013 | No issues | com_Typs and metrics not matching Smrtfrms. Sent back 14/5/24 | 2024-05-22 | [6 empty] | 10 - Complete | Lee | Abdelmalik Hassen <ABHS@cowi.com> Cezary Przybyla <CEPY@cowi.com> | 2 | 1 | 14
| 238.01 | HS2-00002CTK9 | Ladbroke Watercourse Diversion | 1MC07-ASC-DR-FRM-CS07_CL24-000053-ACBOS | P04 | 2024-05-09 | 2024-05-13 | 2024-05-14 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600044 | [9 empty] | 10 - Complete | Rakesh | Egan, Conor <Conor.Egan@wsp.com> | 1 | 0 | 4
| 208.4 | HS2-00003HWH7 | Bridleway AX18 Overbridge | 1MC06-ASC-DR-FRM-CS04_CL19-000058-ACBOS | P01 | 2024-05-10 | 2024-05-13 | 2024-05-14 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600097 | [9 empty] | 10 - Complete | Rakesh | Ka, Srinatha <srinatha.ka@arcadis.com> | 1 | 0 | 3
| UFDR 226.A | HS2-000020CHD | CSO-04-1306 | 1MC07-ASC-UT-FRM-CS07_CL12-000012-ACBOS | PO1 | 2024-05-14 | 2024-05-15 | 2024-05-15 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600116 | [9 empty] | 10 - Complete | Rakesh | Kamboj, Mohit <mohit.kamboj@arcadis.com> | 0 | 0 | 1
| 238.02-2 | HS2-00002C3Z1 | A423 Banbury Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL24-000012-ACBOS | PO1 | 2024-05-14 | 2024-05-15 | 2024-05-23 | issues found | 1MC07-CEK-IM-DAT-CS07_CL24-600076 | Issues found | Trailing space in UAID 1 RebarDensity & RebarVolume is 0 SdSlp value is ''o" |  | OSGB co-ordinate delta issue, send back on 17-May-2024 “0” for LwstLvl & FnshInvrtLvl for CHB asset class Send back to team on 22-May-24 . | [5 empty] | 10 - Complete | Rakesh | Egan, Conor <Conor.Egan@wsp.com> | 6 | 2 | 1
13 | 213.07-1 | HS2-00003CCK1 | TB - Flood Compensation Area 071 C | 1MC06-ASC-DR-FRM-CS04_CL20-000135-ACBOS | P01 | 2024-05-14 | 2024-05-14 | 2024-05-16 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600227 | [9 empty] | 10 - Complete | Rakesh | Rogers, Andrew <andrew.rogers2@arcadis.com> | 2 | 0 | 0
13 | 213.07-1 | HS2-00003CCJZ | TB - Flood Compensation Area 071 A | 1MC06-ASC-DR-FRM-CS04_CL20-000131-ACBOS | P01 | 2024-05-14 | 2024-05-15 | 2024-05-16 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600225 | No issues | [8 empty] | 10 - Complete | Rakesh | Rogers, Andrew <andrew.rogers2@arcadis.com> | 1 | 0 | 1
13 | 213.07-1 | HS2-00003CCK0 | TB - Flood Compensation Area 071 B | 1MC06-ASC-DR-FRM-CS04_CL20-000133-ACBOS | P01 | 2024-05-14 | 2024-06-03 | 2024-06-07 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600226 | issues found | Ifclayer & uniclass ID mismatch found and send back to team on 16 May 24 |  | Missing ComRfrncNmbr column added to GRT cat. MDM scema in house fix. | 2024-06-06 |  |  |  |  | 10 - Complete | Lee | Rogers, Andrew <andrew.rogers2@arcadis.com> | 4 | 2 | 20
13 | 213.07-1 | HS2-00002D88S | Tetchwick Brook Watercourse Diversion | 1MC06-ASC-DR-FRM-CS04_CL20-000107-ACBOS | P01 | 2024-05-14 | 2024-06-06 | 2024-06-07 | issues found | 1MC06-CEK-IM-DAT-CS04_CL20-600233 |  | OSGB issues, send back on 16-May-2024 |  | Again found OSGB issues, send back on 04-June-2024 | [5 empty] | 10 - Complete | Lee | Rogers, Andrew <andrew.rogers2@arcadis.com> | 1 | 2 | 23
| 237.05 | HS2-000001099 | Ladbroke Grove Cutting | 1MC07-ASC-GT-FRM-CS07_CL23-000003-ACBOS | P06 | 2024-05-14 | 2024-05-14 | 2024-05-15 | YES | 1MC07-CEK-IM-DAT-CS07_CL23-600014 | No issues |  |  |  |  | 10 - Complete | Supriyan | Matthew Coote <mtce@cowi.com> |  | 10 - Complete | Lee | Matthew Coote <mtce@cowi.com> | 1 | 2 | 0
| 237.05 | HS2-00002CTK5 | Ladbroke Grove Cutting Boundary Fence | 1MC07-ASC-CV-FRM-CS07_CL23-000059-ACBOS | P01 | 2024-05-14 | 2024-05-15 | 2024-05-16 | YES | 1MC07-CEK-IM-DAT-CS07_CL23-600028 |  | Metrics don’t macth Smrtfrms. 14/5/24 | rvsd 15-may-24 |  |  | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> |  | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 1 | 3 | 1
| 229.03 | HS2-00002N7UB | Greatworth North Cutting Group - Ancillary Culvert 101-AC3 | 1MC07-ASC-CV-FRM-CS07_CL12-000043-ACBOS | P02 | 2024-05-14 | 2024-05-16 | 2024-05-17 | issues found | 1MC07-CEK-IM-DAT-CS07_CL12-600279 |  | OSGB issues and one extra record, send back on 16-May-2024 | [7 empty] | 10 - Complete | Supriyan | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 1 | 1 | 2
| 223.8 | HS2-00002CTC2 | Mixbury Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000018-ACBOS | P01 | 2024-05-14 | 2024-05-14 | 2024-05-15 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600049 | No issues | [8 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 1 | 0 | 0
| 223.8 | HS2-00002CTC7 | Mixbury Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000017-ACBOS | P01 | 2024-05-14 | 2024-05-14 | 2024-05-15 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600078 | No issues | [8 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 1 | 0 | 0
| 223.8 | HS2-00002CTCA | Westbury Embankment Boundary Perimeter Line | 1MC06-ASC-CV-FRM-CS06_CL22-000020-ACBOS | P01 | 2024-05-14 | 2024-05-14 | 2024-05-16 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600083 | No issues | [8 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 2 | 0 | 0
| 218.02 | HS2-00003124C | Calvert IMD Access Road | 1MC06-ASC-HW-FRM-CS06_CL09-000092-ACBOS | P02 | 2024-05-14 | 2024-05-14 | 2024-05-15 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600314 | Issues found | uniclass / IFC layer mismatch edited in house. DT have updated IFC / ACBOS PW file. |  |  |  | 10 - Complete | Lee | dan.quirante@arcadis.com |  | 10 - Complete | Lee | Khan, Sal <sal.khan@arcadis.com> | 1 | 3 | 0
| 227.2 | HS2-000001337 | Bridleway AX18 Overbridge | 1MC07-CEK-BR-FRM-CS07_CL12-000002 | P09 | 2024-05-17 | 2024-05-17 | 2024-05-21 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600141 | Issues Found | OSGB issus, send back on 17-05-2024 | [7 empty] | 10 - Complete | Supriyan | Conor.Egan@wsp.com> | 2 | 1 | 0
10 | 233.01-3 | HS2-00002TMF8 | Chipping Warden Green Tunnel South Portal | 1MC07-ASC-UT-FRM-CS07_CL26-000042-ACBOS | P01 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600014 | No issues | [8 empty] | 10 - Complete | Supriyan | Agnieszka Cytowska <agcy@cowi.com> | 1 | 0 | 0
17 | 229.01-2 | HS2-00002TMF6 | Greatworth Green Tunnel North Portal Building | 1MC07-ASC-UT-FRM-CS07_CL25-000073-ACBOS | P01 | 2024-05-20 | 2024-05-21 | 2024-05-21 | No Issue | 1MC07-CEK-IM-DAT-CS07_CL25-600054 | [9 empty] | 10 - Complete | Rakesh | Agnieszka Cytowska <agcy@cowi.com> | 0 | 0 | 1
| 233.01 | HS2-00002CX3A | Appletree Lane Drainage System | 1MC07-ASC-DR-FRM-CS07_CL13-000002-ACBOS | P04 | 2024-05-21 | 2024-05-22 | 2024-05-29 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600003 | No issues | Uniclass / IFC layer mismatch send back on 22May2024 | [7 empty] | 10 - Complete | Supriyan | M, Nischitha <nischitha.m@arcadis.com> | 4 | 1 | 1
| UFDR 222.B | HS2-0000245Z8 | CSO-03-6201P | 1MC06-ASC-UT-FRM-CS06_CL21-000033-ACBOS | P02 | 2024-05-22 | 2024-05-28 | 2024-05-30 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600024 | No issues | One asset on wrong location, send back on 27-May-2024 | [7 empty] | 10 - Complete | Supriyan | Kamboj, Mohit <mohit.kamboj@arcadis.com> | 2 | 1 | 6
| 234.04-2 | HS2-00002WUQQ | Lower Boddington Cutting Planting-East Plot 1 | 1MC07-ASC-EV-REP-CS07_CL14-000023 | P01 | 2024-05-22 | 2024-05-22 | 2024-05-29 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600139 | [9 empty] | 10 - Complete | Supriyan | philip.clarke@arcadis.com | 4 | 0 | 0
| 234.04-2 | HS2-00002WUQR | Lower Boddington Cutting Planting-East Plot 2 | 1MC07-ASC-EV-REP-CS07_CL14-000024 | P01 | 2024-05-22 | 2024-05-22 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600140 | [9 empty] | 10 - Complete | Rakesh | philip.clarke@arcadis.com | 1 | 0 | 0
| 234.04-2 | HS2-00002WUQS | Lower Boddington Cutting Planting-East Plot 3 | 1MC07-ASC-EV-REP-CS07_CL14-000025 | P01 | 2024-05-22 | 2024-05-22 | 2024-05-30 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600141 | [9 empty] | 10 - Complete | Supriyan | philip.clarke@arcadis.com | 5 | 0 | 0
| 234.04-2 | HS2-00002WUQT | Lower Boddington Cutting Planting-West Plot 1 | 1MC07-ASC-EV-REP-CS07_CL14-000026 | P01 | 2024-05-22 | 2024-05-22 | 2024-05-30 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600142 |  | Wrong Snake grid - send back on 23-May-2024 | [7 empty] | 10 - Complete | Supriyan | philip.clarke@arcadis.com | 5 | 1 | 0
| 234.04-2 | HS2-00002WUQU | Lower Boddington Cutting Planting-West Plot 2 | 1MC07-ASC-EV-REP-CS07_CL14-000027 | P01 | 2024-05-22 | 2024-05-22 | 2024-05-29 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600143 | [9 empty] | 10 - Complete | Rakesh | philip.clarke@arcadis.com | 4 | 0 | 0
| 234.04-2 | HS2-00002WUQV | Lower Boddington Cutting Planting-West Plot 3 | 1MC07-ASC-EV-REP-CS07_CL14-000028 | P01 | 2024-05-22 | 2024-05-23 | 2024-05-29 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600144 | No issues | [8 empty] | 10 - Complete | Rakesh | philip.clarke@arcadis.com | 3 | 0 | 1
| 234.04-2 | HS2-00002WUQW | Lower Boddington Cutting Planting-West Plot 4 | 1MC07-ASC-EV-REP-CS07_CL14-000029 | P01 | 2024-05-22 | 2024-05-23 | 2024-05-29 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600145 | No issues | [8 empty] | 10 - Complete | Rakesh | philip.clarke@arcadis.com | 3 | 0 | 1
| 234.04-2 | HS2-00002WUQX | Lower Boddington Cutting Planting-West Plot 5 | 1MC07-ASC-EV-REP-CS07_CL14-000030 | P01 | 2024-05-22 | 2024-05-23 | 2024-05-29 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600146 | No issues | [8 empty] | 10 - Complete | Rakesh | philip.clarke@arcadis.com | 3 | 0 | 1
| 234.04-2 | HS2-00002WUQY | Lower Boddington Embankment Planting-East Plot 1 | 1MC07-ASC-EV-REP-CS07_CL14-000001 | P01 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600131 | No issues | [8 empty] | 10 - Complete | Rakesh | philip.clarke@arcadis.com | 0 | 0 | 1
| 234.04-2 | HS2-00002WUQZ | Lower Boddington Embankment Planting-East Plot 2 | 1MC07-ASC-EV-REP-CS07_CL14-000002 | P01 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600132 | No issues | [8 empty] | 10 - Complete | Rakesh | philip.clarke@arcadis.com | 0 | 0 | 1
| 234.04-2 | HS2-00002WUR1 | Lower Boddington Embankment Planting-East Plot 4 | 1MC07-ASC-EV-REP-CS07_CL14-000004 | P01 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600134 | No issues | [8 empty] | 10 - Complete | Rakesh | philip.clarke@arcadis.com | 0 | 0 | 1
| 234.04-2 | HS2-00002WUR2 | Lower Boddington Embankment Planting-East Plot 5 | 1MC07-ASC-EV-REP-CS07_CL14-000005 | P01 | 2024-05-22 | 2024-05-23 | 2024-05-29 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600135 | No issues | [8 empty] | 10 - Complete | Rakesh | philip.clarke@arcadis.com | 3 | 0 | 1
| 234.04-2 | HS2-00002WUR3 | Lower Boddington Embankment Planting-West Plot 1 | 1MC07-ASC-EV-REP-CS07_CL14-000006 | P01 | 2024-05-22 | 2024-05-23 | 2024-05-30 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600136 | No issues | [8 empty] | 10 - Complete | Rakesh | philip.clarke@arcadis.com | 4 | 0 | 1
| 234.04-2 | HS2-00002WUR4 | Lower Boddington Embankment Planting-West Plot 2 | 1MC07-ASC-EV-REP-CS07_CL14-000007 | P01 | 2024-05-22 | 2024-05-22 | 2024-05-28 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600137 | [9 empty] | 10 - Complete | Rakesh | philip.clarke@arcadis.com | 3 | 0 | 0
| 234.04-2 | HS2-00002WUR5 | Lower Boddington Embankment Planting-West Plot 3 | 1MC07-ASC-EV-REP-CS07_CL14-000008 | P01 | 2024-05-22 | 2024-05-22 | 2024-05-30 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600138 | [9 empty] | 10 - Complete | Supriyan | philip.clarke@arcadis.com | 5 | 0 | 0
| 230.01-3 | HS2-00002CTFQ | Thorpe Mandeville Embankment Noise Barrier Line | 1MC07-ASC-CV-FRM-CS07_CL26-000115-ACBOS | P01 | 2024-05-22 | 2024-05-22 | 2024-05-29 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600158 |  | Metrics don’t macth Smrtfrms. Com _typs incorrect. 1/5/24 | rvsd 2/5/24 | DT revising file 13-May-24 | 2024-05-14 |  |  |  |  | 10 - Complete | Lee | Vasilev, Hristo <hristo.vasilev@arcadis.com> | 4 | 2 | 0
| 230.03-2 | HS2-00002TGPD | Lower Thorpe South Embankment Ditch Crossings | 1MC07-ASC-CV-FRM-CS07_CL26-000081-ACBOS | P01 | 2024-05-22 | 2024-05-22 | 2024-05-30 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600161 | [9 empty] | 10 - Complete | Supriyan | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 5 | 0 | 0
| 223.8 | HS2-000039DSD | Mossycorner Spinney (Bat Licence) Ecological Mitigation Site | 1MC06-ASC-EV-FRM-CS06_CL21-000008-ACBOS | P01 | 2024-05-22 | 2024-05-22 | 2024-05-30 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600228 | [9 empty] | 10 - Complete | Supriyan | MIRI Youssef <youssef.miri@setec.com> | 5 | 0 | 0
3 | 212.5 | HS2-00002YD7F | Aylesbury Embankment Vehicular Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS04_CL18-000075-ACBOS | P01 | 2024-05-22 | 2024-05-22 | 2024-05-30 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600155 | Issue found | Issue found with Decmial values which are coming with commas .Send back to team on 22-May-23 via teams. OSGB coordinates issue found send back to team on 27/05/24 via teams | [7 empty] | 10 - Complete | Rakesh | bhargavi.saranga@arcadis.com> | 5 | 1 | 0
| UFDR 210.B | HS2-00002V04E | C23-068-001 | 1MC06-ASC-UT-FRM-CS04_CL20-000082-ACBOS | P01 | 2024-05-23 | 2024-05-24 | 2024-05-28 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600155 | Issue found | Start Chainge is greater than end chainage | [7 empty] | 10 - Complete | Rakesh | eloise.mainstone@arcadis.com> | 1 | 1 | 1
| UFDR 210.B | HS2-000020CFB | CSO-02-6212 | 1MC06-ASC-UT-FRM-CS04_CL20-000032-ACBOS | P01 | 2024-05-23 | 2024-05-24 | 2024-05-28 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600146 | Issue found | Start & end chainage are same , com_type/Desc & snake grid coordinates are missing | [7 empty] | 10 - Complete | Rakesh | eloise.mainstone@arcadis.com> | 1 | 1 | 1
| UFDR 210.B | HS2-000020CFA | CSO-02-3114 | 1MC06-ASC-UT-FRM-CS04_CL20-000035-ACBOS | P01 | 2024-05-23 | 2024-05-24 | 2024-05-28 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600143 | Issue found | Start & end chainage are same , com_type/Desc & snake grid coordinates are missing | [7 empty] | 10 - Complete | Rakesh | eloise.mainstone@arcadis.com> | 1 | 1 | 1
| UFDR 210.B | HS2-00002TU6N | C23-069-0002 | 1MC06-ASC-UT-FRM-CS04_CL20-000072-ACBOS | P01 | 2024-05-23 | 2024-05-24 | 2024-05-28 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600154 | [9 empty] | 10 - Complete | Rakesh | eloise.mainstone@arcadis.com> | 1 | 0 | 1
| UFDR 210.B | HS2-00002ZH4F | C23-069-003 | 1MC06-ASC-UT-FRM-CS04_CL20-000090-ACBOS | P01 | 2024-05-23 | 2024-05-24 | 2024-05-28 |  | 1MC06-CEK-UT-DAT-CS04_CL20-000001 | [9 empty] | 10 - Complete | Rakesh | eloise.mainstone@arcadis.com> | 1 | 0 | 1
| 210.2-2 | HS2-00003GNAE | Putlowes Farm Clean Water | 1MC06-ASC-UT-FRM-CS04_CL20-000095-ACBOS | P01 | 2024-05-23 | 2024-05-31 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600234 | Issue found | OSGB coordinates , Sdslp issue send back to team on 27/05/24 | [7 empty] | 10 - Complete | Rakesh | richard.heinen@arcadis.com> | 4 | 1 | 8
| 230.03-2 | HS2-00002CTFX | Lower Thorpe South Embankment Noise Barrier Line | 1MC07-ASC-CV-FRM-CS07_CL26-000114-ACBOS | P01 | 2024-05-24 | 2024-06-04 | 2024-06-17 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600156 | No issues | Uniclass ID isuee , and other issues, send back on 28-May-2024 |  | Query send on 0's on 05-June-2024 |  | Picked up by Lee 14-Jun-24. |  |  |  | 10 - Complete | Lee | hristo.vasilev@arcadis.com> | 9 | 3 | 11
| 226.1_2 | HS2-000001333 | 83-SL1 Twyford Cutting Pedestrian Slab | 1MC07-CEK-BR-FRM-CS07_CL12-000003 | P03 | 2024-05-24 | 2024-05-28 | 2024-05-30 | Yes | 1MC07-CEK-IM-DAT-CS07_CL12-600086 |  | Missing WdthMx, MtrlPp incorrect | [7 empty] | 10 - Complete | Supriyan | guillaume.hervoches@setec.com | 2 | 1 | 4
| 218.02 | HS2-00003B931 | Calvert Infrastructure Maintenance Depot Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL09-900031 | P01 | 2024-05-24 |  | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600302 | Issue found | uniclass attribute value are incorrect ,send back to team on 28 May 24 | [7 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 5 | 1
| 218.02 | HS2-00003B932 | Calvert Infrastructure Maintenance Depot Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL09-900032 | P01 | 2024-05-24 | 2024-05-27 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600301 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 1 | 0 | 3
| 218.02 | HS2-00003B933 | Calvert Infrastructure Maintenance Depot Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL09-900033 | P01 | 2024-05-24 | 2024-05-28 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600300 | No issues | [8 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 1 | 0 | 4
| 218.02 | HS2-00003B92J | Twyford Embankment planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL09-900003 | P01 | 2024-05-24 | 2024-05-24 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600312 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 2 | 0 | 0
| 218.02 | HS2-00003B92L | Twyford Embankment planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL09-900007 | P01 | 2024-05-24 | 2024-05-24 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600310 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 2 | 0 | 0
| 218.02 | HS2-00003B92N | Twyford Embankment planting Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL09-900011 | P01 | 2024-05-24 | 2024-05-24 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600308 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 2 | 0 | 0
| 218.02 | HS2-00003B92Q | Twyford Embankment planting Plot 7 | 1MC06-ASC-EV-FRM-CS06_CL09-900015 | P01 | 2024-05-24 | 2024-05-24 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600220 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 2 | 0 | 0
| 218.02 | HS2-00003B92U | Twyford Embankment planting Plot 11 | 1MC06-ASC-EV-FRM-CS06_CL09-900023 | P01 | 2024-05-24 | 2024-05-24 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600306 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 2 | 0 | 0
| 218.02 | HS2-00003B92W | Twyford Embankment planting Plot 13 | 1MC06-ASC-EV-FRM-CS06_CL10-900023 | P01 | 2024-05-24 | 2024-05-29 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600216 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 3 | 0 | 5
| 218.02 | HS2-00003B92X | Twyford Embankment planting Plot 14 | 1MC06-ASC-EV-FRM-CS06_CL09-900027 | P01 | 2024-05-24 | 2024-05-29 |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600305 |  |  |  | FILE REPLACED BY DT WITH NEW REVISION P02 - 04 -6-24 | [5 empty] | 99 - Cancelled | Rakesh | daniel.slika@arcadis.com>
| 218.02 | HS2-00003B935 | Calvert Cutting Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL09-900001 | P01 | 2024-05-24 | 2024-05-29 |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600298 |  |  |  | FILE REPLACED BY DT WITH NEW REVISION P02 - 04 -6-24 | [5 empty] | 99 - Cancelled | Rakesh | daniel.slika@arcadis.com>
| 218.02 | HS2-00003B938 | Calvert Cutting Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL09-900006 | P01 | 2024-05-24 | 2024-05-29 |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600295 |  |  |  | FILE REPLACED BY DT WITH NEW REVISION P02 - 04 -6-24 | [5 empty] | 99 - Cancelled | Rakesh | daniel.slika@arcadis.com>
| 218.02 | HS2-00003B93A | Calvert Cutting Planting Plot 6 | 1MC06-ASC-EV-FRM-CS06_CL09-900010 | P01 | 2024-05-24 | 2024-05-29 |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600293 |  |  |  | FILE REPLACED BY DT WITH NEW REVISION P02 - 04 -6-24 | [5 empty] | 99 - Cancelled | Rakesh | daniel.slika@arcadis.com>
| 218.02 | HS2-00003B93C | Calvert Cutting Planting Plot 8 | 1MC06-ASC-EV-FRM-CS06_CL09-900014 | P01 | 2024-05-24 | 2024-05-29 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600291 | Issue found | N/A found in QuantityDetails send back to team on 29 May 24 | [7 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 3 | 1 | 5
| 218.02 | HS2-00003B93G | Calvert Cutting Planting Plot 12 | 1MC06-ASC-EV-FRM-CS06_CL09-900020 | P01 | 2024-05-24 | 2024-05-29 |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600288 |  | FILE REPLACED BY DT WITH NEW REVISION P02 - 04 -6-24 | [7 empty] | 99 - Cancelled | Rakesh | daniel.slika@arcadis.com>
| 218.02 | HS2-00003B93J | Calvert Cutting Planting Plot 14 | 1MC06-ASC-EV-FRM-CS06_CL09-900024 | P01 | 2024-05-24 | 2024-05-29 |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600286 |  | FILE REPLACED BY DT WITH NEW REVISION P02 - 04 -6-24 | [7 empty] | 99 - Cancelled | Rakesh | daniel.slika@arcadis.com>
| 218.02 | HS2-00003B93M | Calvert Cutting Planting Plot 17 | 1MC06-ASC-EV-FRM-CS06_CL09-900028 | P01 | 2024-05-24 | 2024-05-29 |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600283 |  | FILE REPLACED BY DT WITH NEW REVISION P02 - 04 -6-24 | [7 empty] | 99 - Cancelled | Rakesh | daniel.slika@arcadis.com>
| 218.02 | HS2-00003B92Z | Calvert Infrastructure Maintenance Depot Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL09-900029 | P01 | 2024-05-24 | 2024-05-27 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600304 | No issues | [8 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 1 | 0 | 3
| 218.02 | HS2-00003B930 | Calvert Infrastructure Maintenance Depot Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL09-900030 | P01 | 2024-05-24 | 2024-05-27 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600303 | No issues | [8 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 1 | 0 | 3
| 218.02 | HS2-00003B934 | Calvert Infrastructure Maintenance Depot Plot 6 | 1MC06-ASC-EV-FRM-CS06_CL09-900034 | P01 | 2024-05-24 | 2024-05-28 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600299 | No issues | [8 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 1 | 0 | 4
| 218.02 | HS2-00003B92K | Twyford Embankment planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL09-900005 | P01 | 2024-05-24 |  | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600311 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 5 | 0
| 218.02 | HS2-00003B92M | Twyford Embankment planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL09-900009 | P01 | 2024-05-24 | 2024-05-24 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600309 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 2 | 0 | 0
| 218.02 | HS2-00003B92R | Twyford Embankment planting Plot 8 | 1MC06-ASC-EV-FRM-CS06_CL09-900017 | P01 | 2024-05-24 | 2024-05-24 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600219 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 2 | 0 | 0
| 218.02 | HS2-00003B92S | Twyford Embankment planting Plot 9 | 1MC06-ASC-EV-FRM-CS06_CL09-900018 | P01 | 2024-05-24 | 2024-05-24 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600218 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 2 | 0 | 0
| 218.02 | HS2-00003B92T | Twyford Embankment planting Plot 10 | 1MC06-ASC-EV-FRM-CS06_CL09-900021 | P01 | 2024-05-24 | 2024-05-24 | 2024-05-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600307 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com> | 2 | 0 | 0
| 218.02 | HS2-00003B92V | Twyford Embankment planting Plot 12 | 1MC06-ASC-EV-FRM-CS06_CL10-900022 | P01 | 2024-05-24 | 2024-05-29 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600217 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 3 | 0 | 5
| 218.02 | HS2-00003B936 | Calvert Cutting Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL09-900002 | P01 | 2024-05-24 | 2024-05-29 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600297 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 3 | 0 | 5
| 218.02 | HS2-00003B937 | Calvert Cutting Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL09-900004 | P01 | 2024-05-24 | 2024-05-29 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600296 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 3 | 0 | 5
| 218.02 | HS2-00003B939 | Calvert Cutting Planting Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL09-900008 | P01 | 2024-05-24 | 2024-05-29 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600294 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 3 | 0 | 5
| 218.02 | HS2-00003B93B | Calvert Cutting Planting Plot 7 | 1MC06-ASC-EV-FRM-CS06_CL09-900012 | P01 | 2024-05-24 | 2024-05-29 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600292 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 3 | 0 | 5
| 218.02 | HS2-00003B93D | Calvert Cutting Planting Plot 9 | 1MC06-ASC-EV-FRM-CS06_CL09-900016 | P01 | 2024-05-24 | 2024-05-29 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600290 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 3 | 0 | 5
| 218.02 | HS2-00003B93F | Calvert Cutting Planting Plot 11 | 1MC06-ASC-EV-FRM-CS06_CL09-900019 | P01 | 2024-05-24 | 2024-05-29 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600289 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 3 | 0 | 5
| 218.02 | HS2-00003B93H | Calvert Cutting Planting Plot 13 | 1MC06-ASC-EV-FRM-CS06_CL09-900022 | P01 | 2024-05-24 | 2024-05-29 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600287 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 3 | 0 | 5
| 218.02 | HS2-00003B93K | Calvert Cutting Planting Plot 15 | 1MC06-ASC-EV-FRM-CS06_CL09-900025 | P01 | 2024-05-24 | 2024-05-29 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600285 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 3 | 0 | 5
| 218.02 | HS2-00003B93L | Calvert Cutting Planting Plot 16 | 1MC06-ASC-EV-FRM-CS06_CL09-900026 | P01 | 2024-05-24 | 2024-05-29 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600284 | [9 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 3 | 0 | 5
21 | 214.07 | HS2-00002Y8V9 | Quainton ATFS UTX 1 | 1MC06-ASC-CV-FRM-CS05-000070-ACBOS | P01 | 2024-05-24 | 2024-05-24 | 2024-05-30 |  | 1MC06-CEK-IM-DAT-CS05-600240 | [9 empty] | 10 - Complete | Supriyan | vinay.meharwade@arcadis.com> | 3 | 0 | 0
21 | 214.07 | HS2-00002Y8VA | Quainton ATFS UTX 2 | 1MC06-ASC-CV-FRM-CS05-000071-ACBOS | P01 | 2024-05-24 | 2024-05-24 | 2024-05-30 |  | 1MC06-CEK-IM-DAT-CS05-600241 | [9 empty] | 10 - Complete | Supriyan | vinay.meharwade@arcadis.com> | 3 | 0 | 0
21 | 214.07 | HS2-00002Y8VB | Quainton ATFS UTX 3 | 1MC06-ASC-CV-FRM-CS05-000072-ACBOS | P01 | 2024-05-24 | 2024-05-24 | 2024-06-12 |  | 1MC06-CEK-IM-DAT-CS05-600242 | [9 empty] | 10 - Complete | Supriyan | vinay.meharwade@arcadis.com> | 12 | 0 | 0
21 | 214.07 | HS2-00002Y8VC | Quainton ATFS UTX 4 | 1MC06-ASC-CV-FRM-CS05-000073-ACBOS | P01 | 2024-05-24 | 2024-05-24 | 2024-05-30 |  | 1MC06-CEK-IM-DAT-CS05-600243 | [9 empty] | 10 - Complete | Supriyan | vinay.meharwade@arcadis.com> | 3 | 0 | 0
21 | 214.07 | HS2-00002Y8VD | Quainton ATFS UTX 5 | 1MC06-ASC-CV-FRM-CS05-000074-ACBOS | P01 | 2024-05-24 | 2024-05-24 | 2024-05-30 |  | 1MC06-CEK-IM-DAT-CS05-600244 | [9 empty] | 10 - Complete | Supriyan | vinay.meharwade@arcadis.com> | 3 | 0 | 0
21 | 214.07 | HS2-00002Y8VE | Quainton ATFS UTX 6 | 1MC06-ASC-CV-FRM-CS05-000075-ACBOS | P01 | 2024-05-24 | 2024-05-24 | 2024-05-30 |  | 1MC06-CEK-IM-DAT-CS05-600245 | [9 empty] | 10 - Complete | Supriyan | vinay.meharwade@arcadis.com> | 3 | 0 | 0
21 | 214.07 | HS2-00003B2G9 | Quainton ATFS UTX 7 | 1MC06-ASC-CV-FRM-CS05-000107-ACBOS | P01 | 2024-05-24 | 2024-05-24 | 2024-05-30 |  | 1MC06-CEK-IM-DAT-CS05-600292 | [9 empty] | 10 - Complete | Supriyan | vinay.meharwade@arcadis.com> | 3 | 0 | 0
21 | 214.07 | HS2-00003B2GA | Quainton ATFS UTX 8 | 1MC06-ASC-CV-FRM-CS05-000108-ACBOS | P01 | 2024-05-24 | 2024-05-24 | 2024-05-30 |  | 1MC06-CEK-IM-DAT-CS05-600293 | [9 empty] | 10 - Complete | Supriyan | vinay.meharwade@arcadis.com> | 3 | 0 | 0
21 | 214.07 | HS2-00003B2GB | Quainton ATFS UTX 9 | 1MC06-ASC-CV-FRM-CS05-000109-ACBOS | P01 | 2024-05-24 | 2024-05-24 | 2024-05-30 |  | 1MC06-CEK-IM-DAT-CS05-600294 | [9 empty] | 10 - Complete | Supriyan | vinay.meharwade@arcadis.com> | 3 | 0 | 0
21 | 214.07 | HS2-00003B2GC | Quainton ATFS UTX 10 | 1MC06-ASC-CV-FRM-CS05-000106-ACBOS | P01 | 2024-05-24 | 2024-05-24 | 2024-05-30 |  | 1MC06-CEK-IM-DAT-CS05-600295 | [9 empty] | 10 - Complete | Supriyan | vinay.meharwade@arcadis.com> | 3 | 0 | 0
| 219.3 | HS2-000031EEZ | 82-SL2 Cowley Embankment Pedestrian Bridge | 1MC06-ASC-BR-FRM-CS06_CL10-900010 | C01 | 2024-05-28 | 2024-05-29 | 2024-05-29 | Yes | 1MC06-CEK-IM-DAT-CS06_CL10-600222 |  | Coordinate issue - all but 3 are incorrect - via Teams | [7 empty] | 10 - Complete | Alex | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 0 | 1 | 1
7 | 215.03 | HS2-00003GL96 | Calvert IMD.22 UTX No. 3 | 1MC06-ASC-CV-FRM-CS06_CL09-000099-ACBOS | P01 | 2024-05-28 | 2024-05-28 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600274 | [9 empty] | 10 - Complete | Supriyan | jeet.mehta@arcadis.com> | 4 | 0 | 0
7 | 215.03 | HS2-00003GL97 | Calvert IMD.22 UTX No. 4 | 1MC06-ASC-CV-FRM-CS06_CL09-000100-ACBOS | P01 | 2024-05-28 | 2024-05-28 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600275 | [9 empty] | 10 - Complete | Supriyan | jeet.mehta@arcadis.com> | 4 | 0 | 0
| 211.1-3, 211.1-4. Ambiguous in JSON request | HS2-00002F0X7 | Existing A41 Bicester Road Narrowing | 1MC06-ASC-HW-FRM-CS04_CL20-000025-ACBOS | P07 | 2024-05-29 | 2024-06-05 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600015 | Issues found | OSGB issues and many other issues, send back on 31-May-2024 |  | Trailing space on critical fileds, send back on 04-June-2024 |  | Mtrl conflict insitu vs Pre-cast. Send back 0n 05-June-2024 |  |  |  | 10 - Complete | Supriyan | Upadhye, Sumith <sumith.upadhye@arcadis.com> | 1 | 3 | 7
| 223.8 | HS2-0000386TG | Mixbury Cutting Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL22-900001 | P01 | 2024-05-29 | 2024-06-03 | 2024-06-07 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600156 | Issue found | Spacing issue in UAID 1 send back to team on 30-05-2024 | [7 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 4 | 1 | 5
| 223.8 | HS2-0000386TH | Mixbury Cutting Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL22-900002 | P01 | 2024-05-29 | 2024-06-03 | 2024-06-07 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600155 |  | Spacing issue in UAID 1 send back to team on 31-05-2024 | [7 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 4 | 1 | 5
| 223.8 | HS2-0000386TK | Mixbury Cutting Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL22-900003 | P01 | 2024-05-29 | 2024-06-03 | 2024-06-07 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600154 |  | Spacing issue in UAID 1 send back to team on 31-05-2024 | [7 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 4 | 1 | 5
| 223.8 | HS2-0000386TL | Mixbury Cutting Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL22-900004 | P01 | 2024-05-29 | 2024-06-03 | 2024-06-07 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600153 |  | Spacing issue in UAID 1 send back to team on 31-05-2024 | [7 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 4 | 1 | 5
| 223.8 | HS2-0000386TN | Mixbury Cutting Planting Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL22-900005 | P01 | 2024-05-29 | 2024-06-03 | 2024-06-07 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600152 | [9 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 4 | 0 | 5
| 223.8 | HS2-0000386TP | Mixbury Cutting Planting Plot 6 | 1MC06-ASC-EV-FRM-CS06_CL22-900006 | P01 | 2024-05-29 | 2024-06-03 | 2024-06-07 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600151 | [9 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 4 | 0 | 5
| 223.8 | HS2-0000386TR | Mixbury Cutting Planting Plot 7 | 1MC06-ASC-EV-FRM-CS06_CL22-900007 | P01 | 2024-05-29 | 2024-06-03 | 2024-06-07 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600150 | [9 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 4 | 0 | 5
| 223.8 | HS2-0000386TS | Mixbury Embankment Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL22-900008 | P01 | 2024-05-29 | 2024-05-29 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600149 | [9 empty] | 10 - Complete | Supriyan | SAAB Hassan <hassan.saab@setec.com> | 6 | 0 | 0
| 223.8 | HS2-0000386TU | Mixbury Embankment Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL22-900009 | P01 | 2024-05-29 | 2024-05-29 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600148 | [9 empty] | 10 - Complete | Supriyan | SAAB Hassan <hassan.saab@setec.com> | 6 | 0 | 0
| 223.8 | HS2-0000386TV | Mixbury Embankment Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL22-900010 | P01 | 2024-05-29 | 2024-05-29 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600147 | [9 empty] | 10 - Complete | Supriyan | SAAB Hassan <hassan.saab@setec.com> | 6 | 0 | 0
| 223.8 | HS2-0000386TX | Mixbury Embankment Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL22-900011 | P01 | 2024-05-29 | 2024-05-29 | 2024-06-07 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600146 | [9 empty] | 10 - Complete | Supriyan | SAAB Hassan <hassan.saab@setec.com> | 7 | 0 | 0
| 223.8 | HS2-0000386TY | Westbury Embankment Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL22-900012 | P01 | 2024-05-29 |  | 2024-06-07 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600145 | [9 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 7 | 0
| 223.8 | HS2-0000386U0 | Westbury Embankment Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL22-900013 | P01 | 2024-05-29 | 2024-05-29 | 2024-06-10 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600144 | [9 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 8 | 0 | 0
| 223.8 | HS2-0000386U1 | Westbury Embankment Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL22-900014 | P01 | 2024-05-29 | 2024-05-29 | 2024-06-10 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600143 | [9 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 8 | 0 | 0
| 223.8 | HS2-0000386U3 | Westbury Embankment Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL22-900015 | P01 | 2024-05-29 | 2024-05-29 | 2024-06-10 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600142 | [9 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 8 | 0 | 0
| 223.8 | HS2-0000386U4 | Westbury Embankment Planting Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL22-900016 | P01 | 2024-05-29 | 2024-05-29 | 2024-06-10 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600141 | [9 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 8 | 0 | 0
| 223.8 | HS2-0000386U6 | Westbury Embankment Planting Plot 6 | 1MC06-ASC-EV-FRM-CS06_CL22-900017 | P01 | 2024-05-29 | 2024-05-29 | 2024-06-10 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600140 | [9 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 8 | 0 | 0
| 223.8 | HS2-0000386U7 | Westbury Embankment Planting Plot 7 | 1MC06-ASC-EV-FRM-CS06_CL22-900018 | P01 | 2024-05-29 | 2024-05-29 | 2024-06-10 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600139 | [9 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 8 | 0 | 0
| 208.4 | HS2-00003JQJP | Landscape Bund between Overbridges SBH-19 and SMA-16 UP trackside | 1MC06-ASC-GT-FRM-CS04_CL18-000018-ACBOS | P01 | 2024-05-29 | 2024-05-31 | 2024-05-31 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600150 | Issues found | OSGB issues, send back on 31-May-2024 | [7 empty] | 10 - Complete | Supriyan | Chatterjee, Sourav <SouravKumar.Chatterjee@arcadis.com> | 0 | 1 | 2
| UFDR 210.B | HS2-00002V04E | C23-068-001 | 1MC06-ASC-UT-FRM-CS04_CL20-000082-ACBOS | P01 | 2024-05-30 |  | 2024-05-30 | Yes | 1MC06-CEK-IM-DAT-CS04_CL20-600155 |  | Quick reprocess to swap chainages over | [7 empty] | 10 - Complete | Alex | colin.reith@arcadis.com | 0 | 1
| 230.01-3 | HS2-00002TGPA | Thorpe Mandeville Embankment Access Stairs | 1MC07-ASC-CV-FRM-CS07_CL26-000083-ACBOS | P01 | 2024-05-30 | 2024-05-30 | 2024-06-05 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600055 | [9 empty] | 10 - Complete | Supriyan | Alluvada, Neeraj <neeraj.alluvada@arcadis.com> | 4 | 0 | 0
| 230.01-3 | HS2-00003AL3P | Thorpe Mandeville Embankment Access Stairs-West | 1MC07-ASC-CV-FRM-CS07_CL26-000107-ACBOS | P01 | 2024-05-30 | 2024-05-30 | 2024-06-05 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600155 | [9 empty] | 10 - Complete | Supriyan | Alluvada, Neeraj <neeraj.alluvada@arcadis.com> | 4 | 0 | 0
| 215.02-02 | HS2-00002CT8Y | Maintenance Access Road to Pond (Off School Hill Road West) | 1MC06-ASC-HW-FRM-CS06_CL09-000041-ACBOS | P02 | 2024-05-30 | 2024-05-31 | 2024-05-31 | Yes | 1MC06-CEK-IM-DAT-CS06_CL09-600266 | No issues | Uniclass / IfcPresentationLayer mismatch | 2024-05-31 | [6 empty] | 10 - Complete | Lee | Abedelkareem Alnajajreh <adan@cowi.com> | 0 | 1 | 1
| 213.08 | HS2-00002YPE9 | Footpath QUA _26 Accommodation Underbridge Staircase Downmain Ch73620 | 1MC06-ASC-CV-FRM-CS05-000063-ACBOS | P01 | 2024-05-30 | 2024-05-30 | 2024-06-04 |  | 1MC06-CEK-IM-DAT-CS05-600201 | [9 empty] | 10 - Complete | Supriyan | Isaac.wong@arcadis.com | 3 | 0 | 0
| 213.08 | HS2-000031B41 | Woods Drop Inlet Culvert Access Staircase Downmain Ch73650 | 1MC06-ASC-CV-FRM-CS05-000096-ACBOS | P01 | 2024-05-30 | 2024-05-30 | 2024-06-04 |  | 1MC06-CEK-IM-DAT-CS05-600210 | [9 empty] | 10 - Complete | Supriyan | Isaac.wong@arcadis.com | 3 | 0 | 0
| 213.08 | HS2-00002YPE7 | Network Rail Doddershall Access Point Staircase Upmain Ch27020 | 1MC06-ASC-CV-FRM-CS05-000061-ACBOS | P01 | 2024-05-30 | 2024-05-30 | 2024-05-31 |  | 1MC06-CEK-IM-DAT-CS05-600199 | [9 empty] | 10 - Complete | Supriyan | Isaac.wong@arcadis.com | 1 | 0 | 0
| 213.08 | HS2-00002YPE8 | Network Rail Doddershall Access Point Staircase Upmain Ch26440 | 1MC06-ASC-CV-FRM-CS05-000062-ACBOS | P01 | 2024-05-30 | 2024-05-30 | 2024-06-03 |  | 1MC06-CEK-IM-DAT-CS05-600200 | [9 empty] | 10 - Complete | Supriyan | Isaac.wong@arcadis.com | 2 | 0 | 0
| 213.08 | HS2-00002YPEA | Bridleway QUA 28A Accommodation Overbridge Maintenance Access Point Staircase Downmain Ch72938 | 1MC06-ASC-CV-FRM-CS05-000064-ACBOS | P01 | 2024-05-30 | 2024-05-30 | 2024-06-04 |  | 1MC06-CEK-IM-DAT-CS05-600202 | [9 empty] | 10 - Complete | Supriyan | Isaac.wong@arcadis.com | 3 | 0 | 0
| 213.08 | HS2-000031B3W | Box Culvert No.1 Access Staircase Downmain Ch72560 | 1MC06-ASC-CV-FRM-CS05-000090-ACBOS | P01 | 2024-05-30 | 2024-05-30 | 2024-06-04 |  | 1MC06-CEK-IM-DAT-CS05-600205 | [9 empty] | 10 - Complete | Supriyan | Isaac.wong@arcadis.com | 3 | 0 | 0
| 213.08 | HS2-000031B3V | Box Culvert No.1 Access Staircase Downmain Ch72633 | 1MC06-ASC-CV-FRM-CS05-000091-ACBOS | P01 | 2024-05-30 | 2024-05-30 | 2024-06-04 |  | 1MC06-CEK-IM-DAT-CS05-600204 | [9 empty] | 10 - Complete | Supriyan | Isaac.wong@arcadis.com | 3 | 0 | 0
| 213.08 | HS2-000031B3X | Box Culvert No.4 Access Staircase Downmain Ch73190 | 1MC06-ASC-CV-FRM-CS05-000092-ACBOS | P01 | 2024-05-30 | 2024-05-30 | 2024-06-04 |  | 1MC06-CEK-IM-DAT-CS05-600206 | [9 empty] | 10 - Complete | Supriyan | Isaac.wong@arcadis.com | 3 | 0 | 0
| 213.08 | HS2-000031B3Y | Box Culvert No.4,6 and 7 Access Staircase Downmain Ch73300 | 1MC06-ASC-CV-FRM-CS05-000093-ACBOS | P01 | 2024-05-30 | 2024-05-30 | 2024-06-04 |  | 1MC06-CEK-IM-DAT-CS05-600207 | [9 empty] | 10 - Complete | Supriyan | Isaac.wong@arcadis.com | 3 | 0 | 0
| 213.08 | HS2-000031B3Z | Box Culvert No.6 Access Staircase Downmain Ch73410 | 1MC06-ASC-CV-FRM-CS05-000094-ACBOS | P01 | 2024-05-30 | 2024-05-30 | 2024-06-04 |  | 1MC06-CEK-IM-DAT-CS05-600208 | [9 empty] | 10 - Complete | Supriyan | Isaac.wong@arcadis.com | 3 | 0 | 0
| 213.08 | HS2-000031B40 | Box Culvert No.7 Access Staircase Downmain Ch73465 | 1MC06-ASC-CV-FRM-CS05-000095-ACBOS | P01 | 2024-05-30 | 2024-05-30 | 2024-06-04 |  | 1MC06-CEK-IM-DAT-CS05-600209 | [9 empty] | 10 - Complete | Supriyan | Isaac.wong@arcadis.com | 3 | 0 | 0
3 | 212.5 | HS2-000035Q93 | Oxford Road Embankment Ditch Slab No.5 | 1MC06-ASC-CV-FRM-CS04_CL19-000060-ACBOS | P01 | 2024-05-30 | 2024-06-18 | 2024-06-20 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600082 | No issues | Com_Type issue, send back on 06-June-2024 | 18-jun-24 Taken by Lee | [6 empty] | 10 - Complete | Lee | Bolton, Christopher <christopher.bolton@arcadis.com> | 2 | 1 | 19
1 | 238.02 | HS2-000020P2G | Maintenance Access Road to Pond (Off A423 Banbury Road South) | 1MC07-ASC-HW-FRM-CS07_CL24-000022-ACBOS | P05 | 2024-11-21 |  | 2024-11-22 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600052 | No issues | OS Grid conversion on HS2-00003DAZ6 - 21-nov-24 Fixed in house - DT to catch up PW ACBOS | 2024-11-21 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1
| 211.1-3,211.1-4. (Technical Debt Works) | HS2-00002F0X6 | Blackgrove Road Realignment | 1MC06-ASC-HW-FRM-CS04_CL20-000023-ACBOS | P01 | 2024-05-31 | 2024-06-06 | 2024-06-10 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600016 |  | Com_Type issue and uniclass conflict, send back on 04-June-2024 |  | UAID_3 missing. Send back on 5-June-2024 | [5 empty] | 10 - Complete | Supriyan | Upadhye, Sumith | 2 | 2 | 6
| 235.01 | HS2-00002WUR6 | Boddington Cutting Planting-East Plot 1 | 1MC07-ASC-EV-REP-CS07_CL14-000031 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600147 | [9 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WUR7 | Boddington Cutting Planting-East Plot 2 | 1MC07-ASC-EV-REP-CS07_CL14-000032 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600148 | [9 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WUR8 | Boddington Cutting Planting-East Plot 3 | 1MC07-ASC-EV-REP-CS07_CL14-000033 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600149 | [9 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WUR9 | Boddington Cutting Planting-East Plot 4 | 1MC07-ASC-EV-REP-CS07_CL14-000034 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600150 | [9 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WURA | Boddington Cutting Planting-East Plot 5 | 1MC07-ASC-EV-REP-CS07_CL14-000035 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600151 | [9 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WURB | Boddington Cutting Planting-East Plot 6 | 1MC07-ASC-EV-REP-CS07_CL14-000036 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600152 | [9 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WURC | Boddington Cutting Planting-East Plot 7 | 1MC07-ASC-EV-REP-CS07_CL14-000037 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600153 | [9 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WURD | Boddington Cutting Planting-East Plot 8 | 1MC07-ASC-EV-REP-CS07_CL14-000038 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600154 | [9 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WURE | Boddington Cutting Planting-West Plot 1 | 1MC07-ASC-EV-REP-CS07_CL14-000039 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600155 | [9 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WURF | Boddington Cutting Planting-West Plot 2 | 1MC07-ASC-EV-REP-CS07_CL14-000040 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600156 | [9 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WURG | Boddington Cutting Planting-West Plot 3 | 1MC07-ASC-EV-REP-CS07_CL14-000041 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600157 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WURH | Boddington Cutting Planting-West Plot 4 | 1MC07-ASC-EV-REP-CS07_CL14-000042 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600158 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WURJ | Boddington Cutting Planting-West Plot 5 | 1MC07-ASC-EV-REP-CS07_CL14-000043 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600159 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WURK | Boddington Cutting Planting-West Plot 6 | 1MC07-ASC-EV-REP-CS07_CL14-000044 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600160 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WURL | Boddington Cutting Planting-West Plot 7 | 1MC07-ASC-EV-REP-CS07_CL14-000045 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600161 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WURM | Boddington Cutting Planting-West Plot 8 | 1MC07-ASC-EV-REP-CS07_CL14-000046 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-10 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600162 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 235.01 | HS2-00002WURN | Boddington Cutting Planting-West Plot 9 | 1MC07-ASC-EV-REP-CS07_CL14-000047 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-11 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600163 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 7 | 0 | 0
| 235.01 | HS2-00002WURP | Boddington Cutting Planting-West Plot 10 | 1MC07-ASC-EV-REP-CS07_CL14-000048 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-11 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600164 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 7 | 0 | 0
| 235.01 | HS2-00002WURQ | Boddington Cutting Planting-West Plot 11 | 1MC07-ASC-EV-REP-CS07_CL14-000049 | P01 | 2024-05-31 | 2024-05-31 | 2024-06-11 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600165 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 7 | 0 | 0
21 | 214.07 | HS2-00002CT81 | Maintenance Access Road to Pond (Connecting CAG 2 and GUN 28) | 1MC06-ASC-HW-FRM-CS05-000027-ACBOS | P02 | 2024-05-31 | 2024-07-08 | 2024-07-09 |  | 1MC06-CEK-IM-DAT-CS05-600285 |  | old schema, some confirmations needed, AngSlp incorrect, Com_Typ Dscrptn incordect 17-jun-24 | 2024-06-20 | ACBOS now revised to latest schema - enabling Uniclass / IFC check - Failing on PVM 1 item. P04 doc refs for CM_CRT & CM_Chg for all BLD category assets. Com_ArSqM still set as Zero (0). Sent back 21-Jun-24. | 2024-06-21 | Com_ArsqM updated | 2024-07-02 | Review check fail - perimeter and other atts identified ad inconsistent. 4-jul-24 | 2024-07-05 | 10 - Complete | Lee | Quirante, Dan <dan.quirante@arcadis.com> | 1 | 4 | 38
| 238.02_2 | HS2-000025B3V | A423 Banbury Road Realignment | 1MC07-ASC-HW-FRM-CS07_CL24-000031-ACBOS | P02 | 2024-06-03 | 2024-06-06 | 2024-06-06 | YES | 1MC07-CEK-IM-DAT-CS07_CL24-600067 |  | IFC / Uniclass mismatches. GFL zero value in Lgnth ZZ-ZZ com_typ as "101 other things?" 4/6/24 | 2024-06-06 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 0 | 1 | 3
| 210.2-2 | HS2-00002BJT6 | Putlowes Farm Access Road Realignment | 1MC06-ASC-HW-FRM-CS04_CL20-000036-ACBOS | P04 | 2024-06-03 | 2024-06-14 | 2024-06-18 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600023 | Issues found | CM_Isci, uniclass - IFC mismatches Com_Dscrptn, sent 11/6/24 | 2024-06-13 | NOT RESOLVED sent back 13-jun-24 | 2024-06-14 | N/A in Gtxtl - fixed 17-jun-24 |  |  |  | 10 - Complete | Lee | Abdelmalik Hassen <ABHS@cowi.com> | 2 | 3 | 11
| 210.2-2 | HS2-00002ZM2C | Putlowes Farm Watercourse Diversion | 1MC06-ASC-DR-FRM-CS04_CL20-000116-ACBOS | P02 | 2024-06-03 | 2024-06-13 | 2024-06-17 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600214 |  | Com_typ / Dscrptn sent back 11/6/24 | 2024-06-13 | [6 empty] | 10 - Complete | Lee | Bulusu, Sai Sravan Kumar <saisravankumar.bulusu@arcadis.com> | 2 | 1 | 10
| 204.2-2 | HS2-00003JN86 | Stoke Mandeville South Embankment Chalkshire Stream Enhancement | 1MC06-ASC-DR-FRM-CS03_CL17-000082-ACBOS | P01 | 2024-06-03 | 2024-06-12 | 2024-06-17 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600132 |  | Com_Dscrptn - GFL. 11/6/24 | 2024-06-12 | [6 empty] | 10 - Complete | Lee | C, Venkatesh <venkatesh.chavan@arcadis.com> | 3 | 1 | 9
| 229.03 | HS2-000001072 | Greatworth North Cutting | 1MC07-ASC-GT-FRM-CS07_CL12-000003-ACBOS | P01 | 2024-06-03 | 2024-06-20 | 2024-06-27 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600020 | Issue found | Ifc layer & uniclass ID mismatch , send back to team on 19 Jun 2024. | 2024-06-20 | Still found Ifc layer & uniclass ID mismatch , send back to team on 24 Jun 2024. | [5 empty] | 10 - Complete | Rakesh | Matthew Coote <mtce@cowi.com> | 5 | 2 | 17
3 | 212.5 | HS2-00002YD7F | Aylesbury Embankment Vehicular Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS04_CL18-000075-ACBOS | P03 | 2024-06-03 | 2024-06-12 | 2024-06-12 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600155 |  | On Hold on 07-June-23 ,after forwarded for JSON check as suggested by DT | [7 empty] | 10 - Complete | Rakesh | bhargavi.saranga@arcadis.com> | 0 | 1 | 9
| 230.04-2 | HS2-00002CTG0 | Lower Thorpe South Cutting Noise Barrier Line | 1MC07-ASC-CV-FRM-CS07_CL26-000113-ACBOS | P02 | 2024-06-04 | 2024-07-03 | 2024-07-04 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600159 | No issues | OS Check - FAIL All SnakeGrids missing for all classes General Comments - For all classes: Snakegrid E/ N all set to Zero (0) All chainage values identical All osgbEasting / Northings identical. GrossVolumes, WidthMn, WidthMx all set as Zero (0). For all classes. GrossPerimeterIExt, GrossPlanAreaExt set as Zero (0) for PLC GrossSurfaceAreaExt - set as Zero (0) for PCE & CLM sent back 14-Jun-24 | 2024-07-03 | [6 empty] | 10 - Complete | Lee | Vasilev, Hristo <hristo.vasilev@arcadis.com> | 1 | 1 | 29
| 229.01-1 | HS2-00002NJ05 | Greatworth Green Tunnel South Portal MPDT | 1MC07-CEK-TN-FRM-CS07_CL25-000009 | P01 | 2024-06-04 | 2024-07-24 | 2024-07-29 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600027 | No issues | Com_typ/Dscrptn issues. Total metrics when combined do not match smartforms 10/6/24 | 2024-06-18 | Uniclass / Ifc mismatch 10 items. 19-jun-24 | 2024-06-26 | DAC check shows many issues. 27-jun-24 | 2024-07-16 | ready to load / test load complete, check metrics in the morning |  | 10 - Complete | Lee | David Pink <dapi@cowi.com> | 3 | 4 | 50
| 229.01-1 | HS2-00002NJ05 | ACBOS – Greatworth Green Tunnel South Portal Earthworks Model Solids | 1MC07-ASC-TN-FRM-CS07_CL25-000008-ACBOS | P02 | 2024-06-04 | 2024-07-24 | 2024-07-29 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600027 | No issues | Total metrics when combined do not match smartforms | 2024-06-18 |  | 2024-06-26 | DAC check shows many issues. 27-jun-24 |  | ready to load / test load complete, check metrics in the morning |  | 10 - Complete | Lee | David Pink <dapi@cowi.com> | 3 | 3 | 50
| 229.01-1 | HS2-00002NJ05 | ACBOS - Greatworth Green Tunnel South Portal | 1MC07-ASC-TN-FRM-CS07_CL25-900015-ACBOS | P01 | 2024-06-04 | 2024-07-24 | 2024-07-29 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600027 | No issues | Total metrics when combined do not match smartforms IFCpresentation / Uniclass mismatch line retunrs on UAID_3 x2 | 2024-06-18 | Uniclass / Ifc mismatch 10 items. 19-jun-24 | 2024-06-26 | DAC check shows many issues. 27-jun-24 |  | ready to load / test load complete, check metrics in the morning |  | 10 - Complete | Lee | David Pink <dapi@cowi.com> | 3 | 4 | 50
| 220.5 | HS2-00002N7W9 | Chetwode Embankment-Ancillary Culvert 084-AC2 | 1MC06-ASC-DR-FRM-CS06_CL10-000077-ACBOS | P03 | 2024-06-04 | 2024-06-12 | 2024-06-14 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600052 | [9 empty] | 10 - Complete | Rakesh | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 2 | 0 | 8
| 218.02 | HS2-00003B931 | Calvert Infrastructure Maintenance Depot Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL09-900031 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600302 | No issues | [8 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 0 | 0
| 218.02 | HS2-00003B932 | Calvert Infrastructure Maintenance Depot Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL09-900032 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600301 | No issues | [8 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 0 | 0
| 218.02 | HS2-00003B933 | Calvert Infrastructure Maintenance Depot Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL09-900033 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600300 | No issues | [8 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 0 | 0
| 218.02 | HS2-00003B92J | Twyford Embankment planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL09-900003 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-05 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600312 | [9 empty] | 10 - Complete | Lee | daniel.slika@arcadis.com> | 1 | 0 | 0
| 218.02 | HS2-00003B92L | Twyford Embankment planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL09-900007 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-05 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600310 | [9 empty] | 10 - Complete | Lee | daniel.slika@arcadis.com> | 1 | 0 | 0
| 218.02 | HS2-00003B92N | Twyford Embankment planting Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL09-900011 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600308 | [9 empty] | 10 - Complete | Lee | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 0 | 0
| 218.02 | HS2-00003B92Q | Twyford Embankment planting Plot 7 | 1MC06-ASC-EV-FRM-CS06_CL09-900015 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600220 |  | uniclass mismatch - in house check Setec MPDT. | fixed 5/6/24 | [6 empty] | 10 - Complete | Lee | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 1 | 0
| 218.02 | HS2-00003B92U | Twyford Embankment planting Plot 11 | 1MC06-ASC-EV-FRM-CS06_CL09-900023 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600306 | [9 empty] | 10 - Complete | Lee | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 0 | 0
| 218.02 | HS2-00003B92W | Twyford Embankment planting Plot 13 | 1MC06-ASC-EV-FRM-CS06_CL10-900023 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600216 | No issues | [8 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 0 | 0
| 218.02 | HS2-00003B92X | Twyford Embankment planting Plot 14 | 1MC06-ASC-EV-FRM-CS06_CL09-900027 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600305 | No issues | [8 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 0 | 0
| 218.02 | HS2-00003B935 | Calvert Cutting Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL09-900001 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600298 | [9 empty] | 10 - Complete | Lee | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 0 | 0
| 218.02 | HS2-00003B938 | Calvert Cutting Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL09-900006 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600295 | [9 empty] | 10 - Complete | Lee | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 0 | 0
| 218.02 | HS2-00003B93A | Calvert Cutting Planting Plot 6 | 1MC06-ASC-EV-FRM-CS06_CL09-900010 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600293 | [9 empty] | 10 - Complete | Lee | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 0 | 0
| 218.02 | HS2-00003B93C | Calvert Cutting Planting Plot 8 | 1MC06-ASC-EV-FRM-CS06_CL09-900014 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600291 |  | zero quantity value 4/6/24 | DT confirm is intended 4/6/24 | [6 empty] | 10 - Complete | Lee | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 1 | 0
| 218.02 | HS2-00003B93G | Calvert Cutting Planting Plot 12 | 1MC06-ASC-EV-FRM-CS06_CL09-900020 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600288 | [9 empty] | 10 - Complete | Lee | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 0 | 0
| 218.02 | HS2-00003B93J | Calvert Cutting Planting Plot 14 | 1MC06-ASC-EV-FRM-CS06_CL09-900024 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600286 |  | zero quantity value 4/6/24 | DT confirm is intended 5/6/24 | [6 empty] | 10 - Complete | Lee | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 1 | 0
| 218.02 | HS2-00003B93M | Calvert Cutting Planting Plot 17 | 1MC06-ASC-EV-FRM-CS06_CL09-900028 | P02 | 2024-06-04 | 2024-06-04 | 2024-06-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600283 | No issues | [8 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 2 | 0 | 0
13 | 213.07-1 | HS2-00003CCK1 |  | 1MC06-ASC-DR-FRM-CS04_CL20-000135-ACBOS | P02 | 2024-06-05 | 2024-06-06 | 2024-06-07 | YES | 1MC06-CEK-IM-DAT-CS04_CL20-600227 |  | OSGB issues, send back on 6-jun-2024 | 2024-06-06 | [6 empty] | 10 - Complete | Lee | Rogers, Andrew <andrew.rogers2@arcadis.com> | 1 | 1 | 1
10 | 233.01-3 | HS2-000025B2P |  | 1MC07-CEK-AR-FRM-CS07_CL13-600002 | P02 | 2024-06-06 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 | No issues | Multi discipline single JSON |  | DT rewoking Zz-zz across all files. 27-Jun-24 |  | Uniclass issues , post L3 works |  |  | Loaded 688 | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>;
10 | 233.01-3 | HS2-000025B2P |  | 1MC07-CEK-FI-FRM-CS07_CL13-000002 | P01 | 2024-06-06 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 | No issues | Multi discipline single JSON |  | DT rewoking Zz-zz across all files. 27-Jun-24 |  |  |  |  | loaded | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>;
10 | 233.01-3 | HS2-000025B2P |  | 1MC07-CEK-ME-FRM-CS07_CL13-000002 | P01 | 2024-06-06 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 | No issues | Multi discipline single JSON |  | DT rewoking Zz-zz across all files. 27-Jun-24 |  |  |  |  | loaded | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>;
10 | 233.01-3 | HS2-000025B2P |  | 1MC07-CEK-ME-FRM-CS07_CL13-000003 | P02 | 2024-06-06 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 | No issues | Multi discipline single JSON |  | DT rewoking Zz-zz across all files. 27-Jun-24 |  |  |  |  | loaded | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>;
| 213.08 | HS2-00002YPE9 |  | 1MC06-ASC-CV-FRM-CS05-000063-ACBOS | P01 | 2024-06-06 | 2024-06-06 | 2024-06-18 |  | 1MC06-CEK-IM-DAT-CS05-600201 | No issues | [8 empty] | 10 - Complete | Lee | Isaac.wong@arcadis.com | 8 | 0 | 0
| 213.08 | HS2-000031B41 |  | 1MC06-ASC-CV-FRM-CS05-000096-ACBOS | P01 | 2024-06-06 | 2024-06-06 | 2024-06-18 |  | 1MC06-CEK-IM-DAT-CS05-600210 | No issues | [8 empty] | 10 - Complete | Lee | Isaac.wong@arcadis.com | 8 | 0 | 0
| UFDR 239.A | HS2-000020CKZ |  | 1MC07-ASC-UT-FRM-CS07_CL24-000031-ACBOS | P02 | 2024-06-07 | 2024-06-07 |  |  | 1MC07-CEK-IM-DAT-CS07_CL24-600014 | No issues | [8 empty] | 99 - Cancelled | Lee | T, Sithrubi <sithrubi.t@arcadis.com>
| UFDR 239.A | HS2-000020CKS |  | 1MC07-ASC-UT-FRM-CS07_CL24-000037-ACBOS | P02 | 2024-06-07 | 2024-06-07 |  |  | 1MC07-CEK-IM-DAT-CS07_CL24-600081 | No issues | [8 empty] | 99 - Cancelled | Lee | T, Sithrubi <sithrubi.t@arcadis.com>
| UFDR 239.A | HS2-00003B2H4 |  | 1MC07-ASC-UT-FRM-CS07_CL24-000075-ACBOS | P02 | 2024-06-07 | 2024-06-07 |  |  | 1MC07-CEK-IM-DAT-CS07_CL24-600118 | No issues | [8 empty] | 99 - Cancelled | Lee | T, Sithrubi <sithrubi.t@arcadis.com>
| UFDR 217.B | HS2-0000245ZF | CSO-04-3125 | 1MC06-ASC-UT-FRM-CS06_CL09-000027-ACBOS | P02 | 2024-06-07 | 2024-06-07 | 2024-06-19 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600087 | No issues | DT have called and have reatgging exercise underway Status set back to "HOLD" - 20-jun-24 | Revised 19-Aug-24 | [6 empty] | 99 - Cancelled | Lee | Bowles, Maya <maya.bowles@arcadis.com>
| UFDR 202.E | HS2-00002NHZ4 |  | 1MC06-ASC-UT-FRM-CS03_CL06-000107-ACBOS | P01 | 2024-06-07 | 2024-06-07 | 2024-06-21 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600060 | [9 empty] | 10 - Complete | Rakesh | Bowles, Maya <maya.bowles@arcadis.com> | 10 | 0 | 0
| UFDR 202.E | HS2-00002NHZ6 |  | 1MC06-ASC-UT-FRM-CS03_CL06-000105-ACBOS | P01 | 2024-06-07 | 2024-07-04 | 2024-07-04 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600069 |  | DT have called and have reatgging exercise underway Status set back to "HOLD" - 20-jun-24 | 2024-07-04 | [6 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com> | 0 | 1 | 27
| UFDR 202.E | HS2-000020CDR |  | 1MC06-ASC-UT-FRM-CS03_CL06-000040-ACBOS | P01 | 2024-06-07 | 2024-07-03 | 2024-07-04 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600083 |  | Chainages in mm? back to 07 status . 20-jun-24 | [7 empty] | 10 - Complete | Rakesh | Bowles, Maya <maya.bowles@arcadis.com> | 1 | 1 | 26
| 233.01 | HS2-00003B93N | Chipping Warden North Portal - DC1 | 1MC07-ASC-CV-FRM-CS07_CL13-000019-ACBOS | P04 | 2024-06-07 | 2024-06-11 | 2024-06-12 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600034 |  | non unique snakegrisd & OS sent back 11/6/24 | 2024-06-11 | [6 empty] | 10 - Complete | Lee | PATIL, APOORVA <apoorva.patil@arcadis.com> | 1 | 1 | 4
| 220.5 | HS2-00002J4YG | Bridleway CHW/24 Link | 1MC06-ASC-HW-FRM-CS06_CL10-000022-ACBOS | P02 | 2024-06-07 | 2024-06-07 | 2024-06-14 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600054 | [9 empty] | 10 - Complete | Rakesh | zakaria.khabouze@setec.com | 5 | 0 | 0
| 220.5 | HS2-00002BJUM | Maintenance Access Road to Pond and MAP (Footpath 225/4 Upgrade) | 1MC06-ASC-HW-FRM-CS06_CL10-000024-ACBOS | P02 | 2024-06-07 | 2024-06-07 | 2024-06-14 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600084 | [9 empty] | 10 - Complete | Rakesh | zakaria.khabouze@setec.com | 5 | 0 | 0
| 220.5 | HS2-00002BJUL | Maintenance Access Road to Pond and MAP (Footpath 225/4 Upgrade) | 1MC06-ASC-HW-FRM-CS06_CL10-900029-ACBOS | P03 | 2024-06-07 | 2024-06-07 | 2024-06-14 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600089 | [9 empty] | 10 - Complete | Rakesh | zakaria.khabouze@setec.com | 5 | 0 | 0
| 220.5 | HS2-000020NLQ | Footpath PBI/9 Diversion | 1MC06-ASC-HW-FRM-CS06_CL10-900011-ACBOS | P02 | 2024-06-07 | 2024-06-18 | 2024-06-18 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600106 | Issue found | Incorrect Com_Type in Pavement Class. | [7 empty] | 10 - Complete | Rakesh | zakaria.khabouze@setec.com | 0 | 1 | 11
| 213.01-01 | HS2-000020NF2 | Station Road Realignment (including Buckingham Road and Fidlers Field Road) | 1MC06-ASC-HW-FRM-CS04_CL20-000013-ACBOS | P05 | 2024-06-10 |  |  |  | 1MC06-CEK-IM-DAT-CS04_CL20-600108 | Issue found | Ifclayer & uniclass ID mismatch,Com_Arsqm 0 , rebar values 0 in FND & LSH . Send back to team on 20 Jun 24. |  |  |  | Cancelled - 13-Jan-25 due to older than 6 months since correspondance |  |  |  | 99 - Cancelled | Rakesh | M, Shambhulinga <Shambhulinga.M@arcadis.com>
| 213.01-01 | HS2-00002BJTJ | Maintenance Access Road to Pond (Off North End of Station Road) 01 Solids Model | 1MC06-ASC-HW-FRM-CS04_CL20-000014-ACBOS | P04 | 2024-06-10 |  |  |  | 1MC06-CEK-IM-DAT-CS04_CL20-600109 | Issue found | Ifc layer & uniclass ID mismatch , send back to team on 20 Jun 2024. | [7 empty] | 99 - Cancelled | Rakesh | M, Shambhulinga <Shambhulinga.M@arcadis.com>
| 235.01 | HS2-00003K85S | Boddington Cutting | 1MC07-ASC-CV-FRM-CS07_CL14-900122-ACBOS | P01 | 2024-06-10 | 2024-06-17 | 2024-06-18 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600216 | No issues | Com_Typ / Dscrptns all incorrect sent back 12-jun-24 | [7 empty] | 10 - Complete | Lee | immanuel.philipose@arcadis.com | 1 | 1 | 7
| 228.2 | HS2-00002CX3J | Bridleway AN37 AN28 and AX1 Drainage System | 1MC07-ASC-DR-FRM-CS07_CL12-000022-ACBOS | P06 | 2024-06-10 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL12-600017 |  | Ifc / Uniclass mismatches. 25-jun-24 |  | DT reworking file as of 12-Jul-24 due to design change |  | Cancelled - 13-Jan-25 due to older than 6 months since correspondance |  |  |  | 99 - Cancelled | Lee | Egan, Conor <Conor.Egan@wsp.com>
| 218.02 | HS2-00002TPZ5 | Portway Culvert and Pond Access | 1MC06-ASC-HW-FRM-CS06_CL09-000071-ACBOS | P05 | 2024-06-10 | 2024-06-11 | 2024-06-12 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600124 | Issue found | IFC / Uniclass mismatches. Send back on 11 June 2024 | [7 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 1 | 1 | 1
| 218.02 | HS2-00003124A | Footpath SCL6 | 1MC06-ASC-HW-FRM-CS06_CL09-000086-ACBOS | P05 | 2024-06-10 | 2024-06-11 | 2024-06-12 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600316 | Issue found | IFC / Uniclass mismatches. Send back on 11 June 2024 | [7 empty] | 10 - Complete | Rakesh | daniel.slika@arcadis.com; romane.leboucher@setec.com | 1 | 1 | 1
| 213.08 | HS2-00002CT7E | Doddershall Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS05-000133-ACBOS | P02 | 2024-06-10 | 2024-06-10 | 2024-06-18 |  | 1MC06-CEK-IM-DAT-CS05-600129 | No issues | [8 empty] | 10 - Complete | Lee | Whyte, William <William.Whyte@arcadis.com> | 6 | 0 | 0
| 213.08 | HS2-00002CT7F | Doddershall Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS05-000135-ACBOS | P02 | 2024-06-10 | 2024-06-10 | 2024-06-18 |  | 1MC06-CEK-IM-DAT-CS05-600130 | No issues | [8 empty] | 10 - Complete | Lee | Whyte, William <William.Whyte@arcadis.com> | 6 | 0 | 0
| 213.05 | HS2-00002CT7D | Bridleway QUA 28A Diversion | 1MC06-ASC-HW-FRM-CS05-000036-ACBOS | P04 | 2024-06-10 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600124 | Issues found | OSGB, Uniclass and other 0's, send back on 24-June-2024 |  |  |  | Cancelled - 13-Jan-25 due to older than 6 months since correspondance |  |  |  | 99 - Cancelled | Supriyan | Yaruva, Praveen Reddy <PraveenReddy.Yaruva@arcadis.com>
| 213.05 | HS2-000020NGC | Footpath QUA 24A 1 Diversion | 1MC06-ASC-HW-FRM-CS05-000051-ACBOS | P04 | 2024-06-10 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600082 | No issues | Com_Typs 25/6/24 |  |  |  | Cancelled - 13-Jan-25 due to older than 6 months since correspondance |  |  |  | 99 - Cancelled | Supriyan | Yaruva, Praveen Reddy <PraveenReddy.Yaruva@arcadis.com>
| 222.6 | HS2-000001326 | Bridleway 213/4 Accommodation Overbridge | 1MC06-ASC-BR-FRM-C002-CL21-000001 | P02 | 2024-06-11 | 2024-07-08 | 2024-07-10 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600062 | No issues | Integer values set for LgnthM - should be NumAttr. | 2024-06-14 | Hghtm now set as mm and with comma seperators on some values. Odd. Sent back 18-jun-24 | 2024-06-18 | Querying several attributes at check stage on 18/06/2024 | 2024-06-19 | Metrics don’t mactch smartforms - 4-jul-24 | 2024-07-08 | 10 - Complete | Lee | DE OLIVEIRA DE ARAUJO Nuno Sergio <sergio.deoliveira@setec.com> | 2 | 4 | 27
| 214.1 | HS2-00002CW17 | SHWBMS | 1MC06-ASC-DR-FRM-CS05-000024-ACBOS | P04 | 2024-06-11 | 2024-07-10 | 2024-07-12 |  | 1MC06-CEK-IM-DAT-CS05-600172 | Issue found | ACBOS PW link is missing .Send back to team on 25 June 24 | 2024-06-25 | Incorrect Uniclass ID OSGB converted coordinates value are more than tolerance value +/-0.005 .Send back to team on 27 -Jun-24 | 03 -July-2024 | OSGB converted coordinates value are more than tolerance value +/-0.005 .Send back to team on 04-July-24 | 09 -July-2024 | OSGB converted coordinates value are more than tolerance value +/-0.005 .Send back to team on 10-July-24 |  | 10 - Complete | Rakesh | Aleksandra Batog <ALBT@COWI.COM> | 2 | 4 | 29
| UFDR 239.A | HS2-000020CKZ | CNO-125-001 | 1MC07-ASC-UT-FRM-CS07_CL24-000031-ACBOS | P03 | 2024-06-12 | 2024-06-12 | 2024-06-18 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600014 | No issues | [8 empty] | 10 - Complete | Lee | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 4 | 0 | 0
| UFDR 239.A | HS2-000020CKS | CNO-125-002 | 1MC07-ASC-UT-FRM-CS07_CL24-000037-ACBOS | P03 | 2024-06-12 | 2024-06-12 | 2024-06-18 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600081 | No issues | [8 empty] | 10 - Complete | Lee | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 4 | 0 | 0
| UFDR 239.A | HS2-00003B2H4 | C23-125-0003 | 1MC07-ASC-UT-FRM-CS07_CL24-000075-ACBOS | P03 | 2024-06-12 | 2024-06-12 | 2024-06-18 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600118 | No issues | [8 empty] | 10 - Complete | Lee | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 4 | 0 | 0
| UFDR 236.A | HS2-000020CJZ | CNO-119-001 | 1MC07-ASC-UT-FRM-CS07_CL23-000005-ACBOS | P03 | 2024-06-12 | 2024-06-12 | 2024-06-25 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600045 | [9 empty] | 10 - Complete | Rakesh | Kamboj, Mohit <mohit.kamboj@arcadis.com> | 9 | 0 | 0
| 204.2-2 | HS2-00002YNHA | Stoke Brook watercourse diversion at Nash Lee Orchard culvert | 1MC06-ASC-DR-FRM-CS03_CL17-000062-ACBOS | P04 | 2024-06-12 | 2024-08-13 | 2024-08-16 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600127 |  | ACBOS link not available, send back on 24-June-2024 | [7 empty] | 10 - Complete | Supriyan | Mallya, Ravikiran <Ravikiran.Mallya@arcadis.com> | 3 | 1 | 62
| 204.2-2 | HS2-00002YNHB | Stoke Brook watercourse diversion at Mill House South culvert | 1MC06-ASC-DR-FRM-CS03_CL17-000064-ACBOS | P03 | 2024-06-12 | 2024-08-13 | 2024-08-16 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600128 | No issues | Com_type wrong, sent back on 24-June-2024 | [7 empty] | 10 - Complete | Supriyan | Mallya, Ravikiran <Ravikiran.Mallya@arcadis.com> | 3 | 1 | 62
| 204.2-2 | HS2-00002YNHC | Stoke Brook watercourse diversion at Mill House North culvert | 1MC06-ASC-DR-FRM-CS03_CL17-000066-ACBOS | P04 | 2024-06-12 | 2024-08-13 | 2024-08-20 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600129 | No issues | Com_type issues, send back on 24-June-2024 | [7 empty] | 10 - Complete | Supriyan | Mallya, Ravikiran <Ravikiran.Mallya@arcadis.com> | 5 | 1 | 62
| 223.8 | HS2-000037YLY | 91-SL1 Mixbury Embankment Pedestrian Slab | 1MC06-ASC-BR-FRM-CS06_CL22-900001 | P02 | 2024-06-12 | 2024-06-20 | 2024-06-21 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600231 | No issues | HghtMn 0.075 set to 0 in house DT to follow on PW file; Sent back 12/6/24. | 2024-06-13 | ready to issue when DT update MPDT | 2024-06-13 | Out of date Uniclass code used. Sent back 17/06/2024 | 2024-06-20 |  |  | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 1 | 3 | 8
| 223.8 | HS2-000037YLZ | 91-SL3 Mixbury Embankment Pedestrian Slab | 1MC06-ASC-BR-FRM-CS06_CL22-900002 | P02 | 2024-06-12 | 2024-06-20 | 2024-06-21 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600230 | No issues | HghtMn 0.075 set to 0 in house DT to follow on PW file; Sent back 12/6/24. | 2024-06-13 | ready to issue when DT update MPDT | 2024-06-13 | Out of date Uniclass code used. Sent back 17/06/2024 | 2024-06-20 |  |  | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 1 | 3 | 8
| 223.8 | HS2-00002YCW9 | 91-SL2 Mixbury Embankment Pedestrian Slab | 1MC06-ASC-BR-FRM-CS06_CL22-900004 | P02 | 2024-06-12 | 2024-06-20 | 2024-06-21 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600232 | No issues | HghtMn 0.075 set to 0 in house DT to follow on PW file; Sent back 12/6/24. | 2024-06-13 | ready to issue when DT update MPDT | 2024-06-13 | Out of date Uniclass code used. Sent back 17/06/2024 | 2024-06-20 | Uniclass / Ifc mismatch on 1 component. 20 - jun-24 | 2024-06-20 | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 1 | 4 | 8
| 222.6 | HS2-00002N7WN | Barton to Mixbury Cutting-Ancillary Culvert 089-AC2 | 1MC06-ASC-DR-FRM-CS06_CL21-000055-ACBOS | P01 | 2024-06-12 | 2024-06-18 | 2024-06-19 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600002 | Issue found | Issue found in Uniclass ID and IfcLayer , send back to team on 18- Jun-24. | [7 empty] | 10 - Complete | Rakesh | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 1 | 1 | 6
| 220.5 | HS2-00002Y0RV | Bridleway CHW/24 Overbridge | 1MC06-ASC-BR-FRM-CS06_CL10-900001 | P02 | 2024-06-12 | 2024-06-26 | 2024-06-26 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600125 | Issue found | lots of zero Lgnth PRP assets. Couple of typos. Sent back 12-jun-24 | 2024-06-26 | [6 empty] | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 0 | 1 | 14
| 214.1 | HS2-000020NJ5 | Footpath CAG/2 Diversion | 1MC06-ASC-HW-FRM-CS05-000030-ACBOS |  | 2024-06-12 | 2024-07-24 | 2024-07-29 |  | 1MC06-CEK-IM-DAT-CS05-600174 |  | ACBOS is not completed with PCRA, send back on 24-June-24 |  | multiple issues, send back on 15-July-2024 |  |  |  | send back during Review, because of ZZ-ZZ asset class issues on 23-July-2024 |  | 10 - Complete | Supriyan | SADV@cowi.com | 3 | 3 | 42
| 214.1 | HS2-00002DRXL | Footpath CAG/2 Realignment | 1MC06-ASC-HW-FRM-CS05-000029-ACBOS |  | 2024-06-12 | 2024-07-24 | 2024-07-29 |  | 1MC06-CEK-IM-DAT-CS05-600173 |  | ACBOS is not completed with PCRA, send back on 24-June-24 |  | multiple issues, send back on 15-July-2024 |  | Krbheight still not correct, send back on 18-July-2024 |  | send back during Review, because of ZZ-ZZ asset class issues on 23-July-2024 |  | 10 - Complete | Supriyan | SADV@cowi.com | 3 | 4 | 42
| 214.1 | HS2-00002BJTZ | Calvert Footpath and Cycle route (south off HS2) - CVT Ctg | 1MC06-ASC-HW-FRM-CS05-000090-ACBOS |  | 2024-06-12 | 2024-07-29 | 2024-07-30 |  | 1MC06-CEK-IM-DAT-CS05-600175 |  | ACBOS is not completed with PCRA, send back on 24-June-24 |  | Angle Slope issues, send back on 18-May-2024 |  |  |  | send back during Review, because of ZZ-ZZ asset class issues on 23-July-2024 |  | 10 - Complete | Supriyan | SADV@cowi.com | 1 | 3 | 47
| 214.1 | HS2-00002CT8K | C2.L.64 Catchment | 1MC06-ASC-DR-FRM-CS06_CL09-000030-ACBOS | P03 | 2024-06-12 | 2024-07-09 | 2024-07-09 |  | 1MC06-CEK-IM-DAT-CS06-CL09-600257 | Issue found | Com_tppe, and co-ordinates issus, send back on 25-June-2024 |  | OSGB conversion issues, and uniclass not in use . Send back on 3-July-2024 |  | Com_type is not as per guidline, 0's found. Send back on 08-July-2024 |  |  |  | 10 - Complete | Supriyan | Anna Kowalewicz <ANKZ@cowi.com> | 0 | 3 | 27
| 204.0-2 | HS2-00002CT4A | B4009 Nash Lee Road Drainage System | 1MC06-ASC-DR-FRM-CS03_CL17-000008-ACBOS | P01 | 2024-06-13 | 2024-07-10 | 2024-07-10 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600059 | Issue found | 0's in InltLvl , Sdslp and osgb & uniclass ID issue. Send back to team on 25 Jun 24 | 2024-06-28 | OSGB converted coordinates value are more than tolerance value +/-0.005 .Send back to team on 02 -July-24 | 02 -July-2024 | Error - UniClassID not on list of compliant values , Send Back to team on 3 July 24. | 09 -July-2024 | OSGB converted coordinates value are more than tolerance value +/-0.005 .Send back to team on 10 -July-24 |  | 10 - Complete | Rakesh | Cordero, Jan <Jan.Cordero@arcadis.com> | 0 | 4 | 27
| 229.01-1 | HS2-000020360 | B4525 Welsh Road | 1MC07-ASC-HW-FRM-CS07_CL25-000022-ACBOS | P01 | 2024-06-14 | 2024-06-18 | 2024-06-24 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600045 | Issue found | SnakeGrid – Osgb Coord conversion checks are showing item outside of +/-0.005 tolerance , Spacing found in GTxtl , Send back to team on 18-Jun-24 . | [7 empty] | 10 - Complete | Rakesh | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 4 | 1 | 4
| 229.01-1 | HS2-000020NVL | Footpath AN40 Diversion | 1MC07-ASC-HW-FRM-CS07_CL25-000023-ACBOS | P01 | 2024-06-14 | 2024-06-18 | 2024-06-24 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600035 | Issue found | SnakeGrid – Osgb Coord conversion checks are showing item outside of +/-0.005 tolerance . Send back to team on 18-Jun-24 . | [7 empty] | 10 - Complete | Rakesh | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 4 | 1 | 4
21 | 214.07 | HS2-00002YXB5 | Edgcott Road NR Access Point Staircase Upmain Ch74200 | 1MC06-ASC-CV-FRM-CS05-000083-ACBOS | P01 | 2024-06-17 | 2024-06-26 | 2024-06-27 |  | 1MC06-CEK-IM-DAT-CS05-600282 |  | Extra/ Duplicate records, send back on 24-June-2024 | [7 empty] | 10 - Complete | Supriyan | isaac.wong@arcadis.com OR anand.parmar@arcadis.com | 1 | 1 | 9
21 | 214.07 | HS2-00002YXB0 | Adams Accommodation Overbridge Access Point Staircase Downmain Ch74540 | 1MC06-ASC-CV-FRM-CS05-000081-ACBOS | P01 | 2024-06-17 | 2024-07-03 | 2024-07-04 |  | 1MC06-CEK-IM-DAT-CS05-600283 |  | Uniclass not in use issue, send back on 01-July-2024 | [7 empty] | 10 - Complete | Supriyan | isaac.wong@arcadis.com OR anand.parmar@arcadis.com | 1 | 1 | 16
21 | 214.07 | HS2-0000300BT | GUN 28 Accommodation Green Overbridge Access Point Staircase Downmain | 1MC06-ASC-CV-FRM-CS05-000089-ACBOS | P01 | 2024-06-17 | 2024-07-03 | 2024-07-09 |  | 1MC06-CEK-IM-DAT-CS05-600280 |  | Uniclass ID not in use issue, send back on 01-July-2024 | [7 empty] | 10 - Complete | Supriyan | isaac.wong@arcadis.com OR anand.parmar@arcadis.com | 4 | 1 | 16
21 | 214.07 | HS2-00003H07G | Greatmoor No.3 Headwall Access Stairs Downmain 76515 | 1MC06-ASC-CV-FRM-CS05-000140-ACBOS | P01 | 2024-06-17 | 2024-07-03 | 2024-08-05 |  | 1MC06-CEK-IM-DAT-CS05-600276 |  | Uniclass ID, not in use error. Send back on 01-July-2024 | [7 empty] | 10 - Complete | Supriyan | isaac.wong@arcadis.com OR anand.parmar@arcadis.com | 23 | 1 | 16
21 | 214.07 | HS2-00003H5JJ | River Ray Culvert Headwall Access Stairs Downmain 74535 | 1MC06-ASC-CV-FRM-CS05-000141-ACBOS | P01 | 2024-06-17 | 2024-07-03 | 2024-07-05 |  | 1MC06-CEK-IM-DAT-CS05-600275 |  | Uniclass ID not in use issue, send back on 01-July-2024 | [7 empty] | 10 - Complete | Supriyan | isaac.wong@arcadis.com OR anand.parmar@arcadis.com | 2 | 1 | 16
21 | 214.07 | HS2-00003HWH3 | QUA-36 Accommodation Green Overbridge Access Stairs Downmain ch75325 | 1MC06-ASC-CV-FRM-CS05-000145-ACBOS | P01 | 2024-06-17 | 2024-07-03 | 2024-07-05 |  | 1MC06-CEK-IM-DAT-CS05-600273 |  | uniclass ID, not is ues error. Send back on 01-July-2024 | [7 empty] | 10 - Complete | Supriyan | isaac.wong@arcadis.com OR anand.parmar@arcadis.com | 2 | 1 | 16
| 228 | HS2-000001338 | Footpath AN22 Accommodation Overbridge | 1MC07-CEK-BR-FRM-CS07_CL12-000007 | P05 | 2024-06-18 | 2024-07-11 | 2024-08-01 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600137 | Issues found | OSGB issues, send back on 25-Apr-2024 |  | OSGB Issues again, send back on 11-July-2024 |  | Issues reported in DAC Check, send back on 12-July-2024 |  | OSGB Issues found again, send back on 30-July-2024 |  | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 15 | 4 | 23
| 222.6 | HS2-00002CW0J | Bridleway 213 4 Drainage System | 1MC06-ASC-DR-FRM-CS06_CL21-000014-ACBOS | P01 | 2024-06-18 | 2024-06-18 | 2024-06-21 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600082 | No issues | Incorrect Uniclass code on Access cover | 2024-06-20 | Nulls in Sdslp - Fixed. 21-jun-20 | [5 empty] | 10 - Complete | Lee | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 3 | 2 | 0
3 | 212.5 | HS2-00002YD79 | Aylesbury Embankment Pedestrian Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS04_CL18-000069-ACBOS | P01 | 2024-06-18 | 2024-06-18 | 2024-06-25 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600152 | No issues | [8 empty] | 10 - Complete | Lee | orlando.sangalang@arcadis.com | 5 | 0 | 0
| 235.01 | HS2-00002TKUY | Boddington Cutting | 1MC07-ASC-CV-FRM-CS07_CL14-900121-ACBOS | P01 | 2024-06-19 | 2024-06-19 | 2024-06-20 | YES | 1MC07-CEK-IM-DAT-CS07_CL14-600215 | No issues | [8 empty] | 10 - Complete | Lee | PHILIPOSE, IMMANUEL <immanuel.philipose@arcadis.com> | 1 | 0 | 0
| 234.05 | HS2-00002N7UN | Ladbroke Cutting Group | 1MC07-ASC-CV-FRM-CS07_CL14-000015-ACBOS | P01 | 2024-06-19 | 2024-07-01 | 2024-07-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600044 |  | conflict of uniclass id, send back on 26-June-24 |  | Com_type issues, send back on 27-June-2024 | [5 empty] | 10 - Complete | Supriyan | PATIL, APOORVA <apoorva.patil@arcadis.com> | 1 | 2 | 12
| 233.01 | HS2-00002YKZ9 | Chipping Warden Green Tunnel | 1MC07-ASC-DR-FRM-CS07_CL13-000008-ACBOS | P03 | 2024-06-19 | 2024-07-01 | 2024-07-02 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600032 |  | Wrong uniclass ID found during DAC Check, send back on 28-June-2024 | [7 empty] | 10 - Complete | Supriyan | B, Gopika <gopika.b@arcadis.com> | 1 | 1 | 12
| 228.1 | HS2-000001340 | Bridleway AN14 Accommodation Overbridge | 1MC07-CEK-BR-FRM-CS07_CL12-000032 | P02 | 2024-06-19 | 2024-07-01 | 2024-08-06 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600133 |  | Angle slope and trailing space issue. Send back on 28-June-2024 |  | Not in use uniclassID's found, send back on 8-July-2024 |  | Issues reported in DAC Check, send back on 12-July-2024 |  | Data type issues, send back on 01-Aug-2024 |  | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 26 | 4 | 12
| 214.1 | HS2-00003CPYS | SWBMS Ancillary Civils | 1MC06-ASC-BR-FRM-CS05_CL09-000001 | P01 | 2024-06-19 | 2024-07-30 | 2024-08-22 |  | 1MC06-CEK-IM-DAT-CS05-600182 | No issues | incorrect JSON filename - 19-jun-24 | 2024-07-11 | Os coordinates all duplicate as are chainages. Returned 16-jul-24 |  | HOLD - DT changing data 22-jul-24 | 2024-07-30 | Com_typs / Descrptns | Revised by DT 14-Aug-24 | 10 - Complete | Lee | Alexander Patrick <alpk@cowi.com> | 17 | 4 | 41
| 214.1 | HS2-000031B3U | SWBMS Emergency Intervention stairs | 1MC06-CEK-BR-FRM-CS05-600045 | P01 | 2024-06-19 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600180 |  | MPDT PCRA is not done, send back on 26-June-2024 | [7 empty] | 99 - Cancelled | Supriyan | Alexander Patrick <alpk@cowi.com>
| 214.1 | HS2-00002NSXM | SWBMS Emergency Access Track West - CVT ctg | 1MC06-ASC-HW-FRM-CS05-000071-ACBOS | P01 | 2024-06-19 | 2024-07-24 | 2024-07-29 |  | 1MC06-CEK-IM-DAT-CS05-600176 |  | Many issues, send back on 26-June-2024 |  | OSGB and other issues, send back on 17-July-2024 |  | Chainage is not correct, send back on 18-July-2024 |  | send back during Review, because of ZZ-ZZ asset class issues on 23-July-2024 |  | 10 - Complete | Supriyan | SADV@cowi.com | 3 | 4 | 35
| 214.1 | HS2-00002NSXL | SWBMS Emergency Access Track East - CVT ctg | 1MC06-ASC-HW-FRM-CS05-000072-ACBOS | P01 | 2024-06-19 | 2024-07-24 | 2024-07-29 |  | 1MC06-CEK-IM-DAT-CS05-600177 |  | Many issues, send back on 27-June-2024 |  | OSGB and other issues, send back on 17-July-2024 |  | Chainage is not correct, send back on 18-July-2024 |  | send back during Review, because of ZZ-ZZ asset class issues on 23-July-2024 |  | 10 - Complete | Supriyan | SADV@cowi.com | 3 | 4 | 35
3 | 212.5 | HS2-000035Q92 | Oxford Road Embankment | 1MC06-ASC-CV-FRM-CS04_CL19-000059-ACBOS | P01 | 2024-06-19 | 2024-06-19 | 2024-06-25 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600081 | No issues | [8 empty] | 10 - Complete | Lee | Rutherford, Max <max.rutherford@arcadis.com> | 4 | 0 | 0
17 | 229.01-2 | HS2-00002EK7T | Greatworth Green Tunnel North Portal UTX | 1MC07-ASC-CV-FRM-CS07_CL25-000018-ACBOS | P01 | 2024-06-20 | 2024-07-03 | 2024-07-04 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600011 | Issue found | 0 value in FnshInvrtLvl , LwstLvl in CHB , HghtMn in BAS , Sdslp in GFL | [7 empty] | 10 - Complete | Rakesh | Reddy, Keshavardhan <keshavardhan.reddy@arcadis.com> | 1 | 1 | 13
| 230.01-3 | HS2-00002CTFN | C3.T.29 Catchment | 1MC07-ASC-DR-FRM-CS07_CL26-000005-ACBOS | P02 | 2024-06-21 | 2024-06-21 | 2024-06-26 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600018 | No issues | [8 empty] | 10 - Complete | Lee | M, Nischitha <nischitha.m@arcadis.com> | 3 | 0 | 0
| 235.01-1 | HS2-000025B3A | Hill Farm Accommodation Access Road | 1MC07-ASC-HW-FRM-CS07_CL14-000035-ACBOS | P02 | 2024-06-24 | 2024-06-24 | 2024-07-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600024 | [9 empty] | 10 - Complete | Rakesh | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 21 | 0 | 0
| 210.2-2 | HS2-00002CW1D | Putlowes Farm Access Drainage System | 1MC06-ASC-DR-FRM-CS04_CL20-000016-ACBOS | P02 | 2024-06-24 | 2024-07-01 |  |  | 1MC06-CEK-IM-DAT-CS04_CL20-600019 | Issues found | OSGB issues, send back on 28-June-2024 |  | 0 in DsgnFlw for PPE, send back to team 0n 03-July-2024 |  | Cancelled - 13-Jan-25 due to older than 6 months since correspondance |  |  |  | 99 - Cancelled | Supriyan | Cordero, Jan <Jan.Cordero@arcadis.com>
| UFDR 227.A | HS2-00002CQQM | Diverted 11kV O H Radstone Road | 1MC07-ASC-UT-FRM-CS07_CL12-000019-ACBOS | P01 | 2024-06-25 | 2024-06-25 | 2024-06-26 | Yes | 1MC07-CEK-IM-DAT-CS07_CL12-600123 | No issues | Ifc / Uniclass mismatch. 25-Jun-24 | 2024-06-25 | [6 empty] | 10 - Complete | Supriyan | Kamboj, Mohit <mohit.kamboj@arcadis.com> | 1 | 1 | 0
| UFDR 227.A | HS2-000020CHN | Diverted 11kV O H Elect Distribution Lines | 1MC07-ASC-UT-FRM-CS07_CL12-000018-ACBOS | P01 | 2024-06-25 | 2024-06-25 | 2024-06-26 | Yes | 1MC07-CEK-IM-DAT-CS07_CL12-600154 | No issues | Ifc / Uniclass mismatch. 25-Jun-24 | 2024-06-25 | [6 empty] | 10 - Complete | Supriyan | Kamboj, Mohit <mohit.kamboj@arcadis.com> | 1 | 1 | 0
| 204.0-2 | HS2-000020NAP | Nash Lee Lane Realignment | 1MC06-ASC-HW-FRM-CS03_CL17-000013-ACBOS | P04 | 2024-06-25 | 2024-07-12 | 2024-07-17 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600057 | Issue found | Spacing issue with 34 UAID_1 " HS2-00002C5SK" 0's in Com_Arsqm Send back to team on 02 July 24. | 2024-07-11 | Com_Typ, OS cords, Uniclass / IFC mismatch sent back 11-jul-24 | 2024-07-12 |  | 2024-07-16 | KrbHghtcm / Com_Typ on FND | 2024-07-17 | 10 - Complete | Lee | Adhikari, Shiksha <shiksha.adhikari@arcadis.com> | 3 | 3 | 17
| 204.0-2 | HS2-00002CT4B | Nash Lee Road Overbridge Realignment | 1MC06-ASC-HW-FRM-CS03_CL17-000005-ACBOS | P04 | 2024-06-25 | 2024-07-12 | 2024-07-17 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600054 | Issue found | Asset count mismatch with smart form.Send back to team on 3 July 24. | 2024-07-11 | Com_Typ, OS cords, Uniclass / IFC mismatch sent back 11-jul-24 | 2024-07-12 | Uniclass issues , MnmmThcknssmm to be integer. 15-jul-24 | 2024-07-16 | KrbHghtcm | 2024-07-17 | 10 - Complete | Lee | Adhikari, Shiksha <shiksha.adhikari@arcadis.com> | 3 | 4 | 17
7 | 215.03 | HS2-00002TUPK | Sheephouse Wood Bat Mitigation Structure Telecoms | 1MC06-ASC-UT-FRM-CS06_CL09-000093-ACBOS | P01 | 2024-06-25 | 2024-08-14 | 2024-08-16 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600223 |  | old LoDM, send back on 28-June-2024 | [7 empty] | 10 - Complete | Supriyan | Bowles, Maya <maya.bowles@arcadis.com> | 2 | 1 | 50
3 | 212.5 | HS2-00002VK4C | Stoke Mandeville Bypass South Pedestrian Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL18-000055-ACBOS | P01 | 2024-06-25 | 2024-06-28 | 2024-07-02 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600160 | Issue found | 0 Rebar Volume/Density in GSL & ABT Com_type & Desc values are interchanged. Send back to team on 28 Jun 24. | [7 empty] | 10 - Complete | Rakesh | Bolton, Christopher <christopher.bolton@arcadis.com> | 2 | 1 | 3
| UFDR 238.G | HS2-000020CKJ | CNO-123-001 | 1MC07-ASC-UT-FRM-CS07_CL24-000011-ACBOS | P01 | 2024-06-26 | 2024-07-03 | 2024-07-04 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600068 | Found issues | OSGB issues, send back on 03-July-2024 | [7 empty] | 10 - Complete | Supriyan | T, Sithrubi <sithrubi.t@arcadis.com> | 1 | 1 | 7
| UFDR 238.G | HS2-000020CKL | CNO-124-003 | 1MC07-ASC-UT-FRM-CS07_CL24-000029-ACBOS | P01 | 2024-06-26 | 2024-06-26 | 2024-07-03 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600062 | [9 empty] | 10 - Complete | Supriyan | T, Sithrubi <sithrubi.t@arcadis.com> | 5 | 0 | 0
| UFDR 238.G | HS2-000020CKM | CNO-124-005 | 1MC07-ASC-UT-FRM-CS07_CL24-000064-ACBOS | P01 | 2024-06-26 | 2024-06-26 | 2024-07-03 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600094 | [9 empty] | 10 - Complete | Supriyan | T, Sithrubi <sithrubi.t@arcadis.com> | 5 | 0 | 0
| 213.01-01 | HS2-00002BJTJ | Maintenance Access Road to Pond (Off North End of Station Road) 01 Solids Model | 1MC06-ASC-HW-FRM-CS04_CL20-000014-ACBOS | P05 | 2024-06-27 | 2024-06-27 | 2024-06-28 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600109 | [9 empty] | 10 - Complete | Rakesh | M, Shambhulinga <Shambhulinga.M@arcadis.com> | 1 | 0 | 0
| 213.01-01 | HS2-00002BJTK | Doddershall House and South Farms Accommodation Access Road Solids Model | 1MC06-ASC-HW-FRM-CS05-000022-ACBOS | P06 | 2024-06-27 | 2024-07-09 | 2024-07-09 |  | 1MC06-CEK-IM-DAT-CS05-600093 | Issue found | Spacing issue found . Send Back to team on 05 July 24. | [7 empty] | 10 - Complete | Rakesh | M, Shambhulinga <Shambhulinga.M@arcadis.com> | 0 | 1 | 12
| 213.01-01 | HS2-00002CT6X | Maintenance Access Road to Pond (Off North End of Station Road) 02 Solids Model | 1MC06-ASC-HW-FRM-CS04_CL20-000015-ACBOS | P03 | 2024-06-27 | 2024-07-05 | 2024-07-09 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600096 | Issue found | Power BI check shows MinThickMm value incorrect.Send Back to team on 05 July 24. | [7 empty] | 10 - Complete | Rakesh | M, Shambhulinga <Shambhulinga.M@arcadis.com> | 2 | 1 | 8
| 213.01-01 | HS2-00002CT6W | Maintenance Access Road to Pond (Off Southern End of Station Road) Solids Model | 1MC06-ASC-HW-FRM-CS04_CL20-000016-ACBOS | P03 | 2024-06-27 | 2024-07-05 | 2024-07-10 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600095 | Issue found | OSGB Conversion outside the tolerance limit . Send back to team on 05 July 24. | [7 empty] | 10 - Complete | Rakesh | M, Shambhulinga <Shambhulinga.M@arcadis.com> | 3 | 1 | 8
| 213.01-01 | HS2-000020NFY | Maintenance Access Road to Pond (Off Fidlers Field Road) Solids Model | 1MC06-ASC-HW-FRM-CS05-000023-ACBOS | P04 | 2024-06-27 | 2024-07-08 | 2024-07-10 |  | 1MC06-CEK-IM-DAT-CS05-600088 | Issue found | OSGB Conversion outside the tolerance limit . Send back to team on 05 July 24. | [7 empty] | 10 - Complete | Rakesh | M, Shambhulinga <Shambhulinga.M@arcadis.com> | 2 | 1 | 11
| 204.2-2 | HS2-00003JQJQ | Risborough Road Underpass Access Stairs No.1 | 1MC06-ASC-CV-FRM-CS03_CL17-000061-ACBOS | P01 | 2024-06-27 | 2024-07-03 | 2024-07-04 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600134 | No issues | one missing Uniclass_ID, send back on 03-July-2024 | [7 empty] | 10 - Complete | Supriyan | U M, Pavana <pavana.um@arcadis.com> | 1 | 1 | 6
| 204.2-2 | HS2-00003JQJR | Risborough Road Underpass Access Stairs No.2 | 1MC06-ASC-CV-FRM-CS03_CL17-000062-ACBOS | P01 | 2024-06-27 | 2024-07-04 | 2024-07-08 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600135 |  | one missing Uniclass_ID, send back on 04-July-2024 | [7 empty] | 10 - Complete | Supriyan | U M, Pavana <pavana.um@arcadis.com> | 2 | 1 | 7
| 204.2-2 | HS2-00003JQJS | Risborough Road Underpass Access Stairs No.3 | 1MC06-ASC-CV-FRM-CS03_CL17-000063-ACBOS | P01 | 2024-06-27 | 2024-07-04 | 2024-07-08 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600136 |  | one missing Uniclass_ID, send back on 04-July-2024 | [7 empty] | 10 - Complete | Supriyan | U M, Pavana <pavana.um@arcadis.com> | 2 | 1 | 7
| 204.2-2 | HS2-00002CT52 | Footpath SMA-5-2 Realignment | 1MC06-ASC-HW-FRM-CS03_CL17-000055-ACBOS | P02.1 | 2024-06-27 | 2024-08-05 | 2024-08-13 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600025 | Issue found | Com_Type in place of 101 other thing issue & IFC and uniclass mismatch . Send back to team on 09 July 24. | 2024-07-24 | Incorrect sheet name ,Send Back to team on 26 July 24 |  | L3 assets ammended by EKFB on 30 july 24. Put on hold as suggested by DT. | 2024-08-02 | Com_Ref value missing . Send back to team on 5 Aug 24. |  | 10 - Complete | Rakesh | Jenkins, Joshua <joshua.jenkins@arcadis.com> | 6 | 4 | 39
| 204.2-2 | HS2-00002BJS4 | Maintenance Access Road to Pond (off Stoke House) | 1MC06-ASC-HW-FRM-CS03_CL17-000056-ACBOS | P02.2 | 2024-06-27 |  | 2024-08-05 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600133 | Issue found | OSGB Conversion outside the tolerance limit & IFC and uniclass mismatch . Send back to team on 09 July 24. | 2024-07-24 | OSGB converted values are not within the tolerance limit(0.005),Send Back to team on 26 July 24 |  | OSGB converted values are not within the tolerance limit(0.005),Send Back to team on 31July 24. | 2024-07-31 | OSGB converted values are not within the tolerance limit(0.005),Send Back to team on 01 Aug 24. |  | 10 - Complete | Rakesh | Jenkins, Joshua <joshua.jenkins@arcadis.com> | 27 | 4
| 204.2-2 | HS2-00002CT4Q | Maintenance Access Road to Pond (off Old Risborough Road) | 1MC06-ASC-HW-FRM-CS03_CL17-000022-ACBOS | P01.3 | 2024-06-27 |  | 2024-08-06 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600014 | Issue found | OSGB Conversion outside the tolerance limit & IFC and uniclass mismatch . Send back to team on 09 July 24. | 2024-07-17 | OSGB issue still found , None values in RdNumber & ThirdPary. Send back to team on 17 -July-24. |  | Issue found with MnmmThckmm ,Send Back to team on 24 July 24 |  | Issue found with Start & End Chainage & MnmmThckmm ,Send Back to team on 26 July 24 |  | 10 - Complete | Rakesh | Jenkins, Joshua <joshua.jenkins@arcadis.com> | 28 | 4
| 222.6 | HS2-00002BJUW | Bridleway 2134 Diversion And Accommodation Overbridge Realignment | 1MC06-ASC-HW-FRM-CS06_CL21-000008-ACBOS | P05 | 2024-06-27 | 2024-07-04 | 2024-07-11 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600025 | Found issues | Com_typs, Uniclass codes - sent back 3-jul-24 | 2024-07-04 | [6 empty] | 10 - Complete | Lee | GOIMARD Thomas <thomas.goimard@setec.com> | 5 | 1 | 7
| 222.6 | HS2-00002VXUD | Maintenance Access Road to GSMR (off Widmore Farm Access) and Compound | 1MC06-ASC-HW-FRM-CS06_CL21-000020-ACBOS | P11 | 2024-06-27 | 2024-07-04 | 2024-07-08 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600095 | No issues | NetVolume set as Zero (0) - sent to DT 3-jul-24 | 2024-07-04 | [6 empty] | 10 - Complete | Lee | GOIMARD Thomas <thomas.goimard@setec.com> | 2 | 1 | 7
| 221.5 | HS2-00002Y4JJ | 087-AC2 Watercourse Diversion | 1MC06-ASC-DR-FRM-CS06_CL21-000088-ACBOS | P01 | 2024-06-27 | 2024-07-02 | 2024-07-02 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600087 |  | UniclassID issue. Send back on 28-June-2024 | [7 empty] | 10 - Complete | Supriyan | Lorusso, Alberto <alberto.lorusso@arcadis.com> | 0 | 1 | 5
3 | 212.5 | HS2-000030TD8 | Hartwell Pond Access Ditch Slab No.2 | 1MC06-ASC-CV-FRM-CS04_CL19-000054-ACBOS | P01 | 2024-06-27 |  | 2024-07-10 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600054 | No issues | Com_Typ & Com_Dscrptn reversed - to DT 3/7/24 - fixed in house DT to update source file. |  | JSON Ready for issue - No MDQC errors.. Will not release JSOn until DT update source file | [5 empty] | 10 - Complete | Lee | Bolton, Christopher <christopher.bolton@arcadis.com> | 9 | 2
3 | 212.5 | HS2-000030TD7 | Hartwell Pond Access Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS04_CL18-000079-ACBOS | P01 | 2024-06-27 | 2024-06-27 | 2024-07-08 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600115 | No issues | [8 empty] | 10 - Complete | Lee | Alagundi, Shreyas <shreyas.alagundi@arcadis.com> | 7 | 0 | 0
| 235.01-1 | HS2-000001456 | Footpath SM101 Green Overbridge | 1MC07-ASC-BR-FRM-CS07_CL14-000002-ACBOS | P03 | 2024-06-28 | 2024-07-01 | 2024-07-02 | YES | 1MC07-CEK-IM-DAT-CS07_CL14-600018 | No issues | CM_CRT & Chg set as P04 - fixed in house, DT to fix PW concurrently. Com_Typs / Dscrptns some changes fixed in house DT fixing PW file concurrently. 28-jun-24 | 2024-07-01 | [6 empty] | 10 - Complete | Lee | jake.marshall@arcadis.com | 1 | 1 | 3
| 214.1 | HS2-00003E24K | SCL 13 Landscape Planting | 1MC06-ASC-EV-REP-CS06_CL09-000002 |  | 2024-06-28 | 2024-07-09 | 2024-07-11 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600318 |  | MPDT file link is not correct | [7 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 1 | 11
| 214.1 | HS2-00003CPYK | SCL 13 Landscape Planting | 1MC06-ASC-EV-REP-CS05_CL09-000002 |  | 2024-06-28 | 2024-07-09 | 2024-07-11 |  | 1MC06-CEK-IM-DAT-CS05-600297 |  | MPDT file link is not correct | [7 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 1 | 11
| 230.05-2 | HS2-00002CTG8 | Lower Thorpe North Embankment Noise Barrier Line | 1MC07-ASC-CV-FRM-CS07_CL26-000112-ACBOS | P01 | 2024-07-01 |  | 2024-10-09 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600157 | No issues | com_typ, incorrect NetVolumes, incorrect HghtMx. - sent back 8-jul-24 | 2024-08-28 | com_typ, incorrect NetVolumes, incorrect HghtMx. - sent back 17-Sep-24 | 2024-09-26 | issues persist sent back 02-oct-24 | 2024-10-07 | issues persist sent back 09-oct-24 |  | 10 - Complete | Lee | Miller, Eluned <eluned.miller@arcadis.com> | 71 | 4
| 202.0-3 | HS2-00002CT2S | Wendover Dean South Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS03_CL05-000031-ACBOS | P01 | 2024-07-02 | 2024-07-09 | 2024-07-10 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600168 |  | uniclass Issue, send back on 9-July-2024 | [7 empty] | 10 - Complete | Supriyan | Le, Michaela <michaela.le@arcadis.com> | 1 | 1 | 7
| 202.0-3 | HS2-00002CT2X | Wendover Dean North Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS03_CL05-000034-ACBOS | P01 | 2024-07-02 | 2024-07-09 | 2024-07-10 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600169 |  | uniclass Issue, send back on 9-July-2024 | [7 empty] | 10 - Complete | Supriyan | Le, Michaela <michaela.le@arcadis.com> | 1 | 1 | 7
| 202.0-3 | HS2-00002CT2Q | Wendover Dean South Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS03_CL05-000038-ACBOS | P01 | 2024-07-02 | 2024-07-09 | 2024-07-10 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600167 |  | Com_type issues, send back on 9-July-2024 | [7 empty] | 10 - Complete | Supriyan | Le, Michaela <michaela.le@arcadis.com> | 1 | 1 | 7
| 202.0-3 | HS2-00002CT2V | Wendover Dean North Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS03_CL05-000040-ACBOS | P01 | 2024-07-02 | 2024-07-09 | 2024-07-10 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600170 |  | Com_type issues, send back on 9-July-2024 | [7 empty] | 10 - Complete | Supriyan | Le, Michaela <michaela.le@arcadis.com> | 1 | 1 | 7
| 202.0-3 | HS2-00002CT2E | C2.L.9 Catchment | 1MC06-ASC-DR-FRM-CS03_CL05-000009-ACBOS | P01 | 2024-07-02 | 2024-07-15 | 2024-07-16 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600165 | Issue found | OSGB conversion , Uniclass ID mismatch & Depricated classes used ,send back to team on 10 July 24. | 2024-07-12 | Spacing found in UAID 1 , send back to team on 15 july 24. | 2024-07-15 |  |  |  |  | 10 - Complete | Rakesh | Hallado, Ruel <Ruel.Hallado@arcadis.com> | 1 | 2 | 13
| 202.0-3 | HS2-00002BVEA | C2.L.10 Catchment | 1MC06-ASC-DR-FRM-CS03_CL05-000010-ACBOS | P01 | 2024-07-02 | 2024-07-15 | 2024-07-16 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600166 | Issue found | Spacing found in AssetName_3-[Optional] in DTC class. Some Sdslp values in GFL not meeting DAC checker criteria (i.e. 1 in x) IFC layer & uniclass ID mismatch Depricated Uniclass values used. Send back to team on 09 July 24. | 2024-07-12 | Spacing found in UAID 1 , send back to team on 15 july 24. | 2024-07-15 |  |  |  |  | 10 - Complete | Rakesh | Hallado, Ruel <Ruel.Hallado@arcadis.com> | 1 | 2 | 13
| 224.6 | HS2-00003D9D1 | 92-SL2 Westbury Viaduct Vehicular Slab | 1MC06-ASC-BR-FRM-CS06_CL22-900005 | P01 | 2024-07-02 | 2024-07-15 | 2024-07-17 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600233 | No issues | Carriage returns in IfcPresentationLayers - fixed in house 10-jul-24 | 2024-07-10 | Hghtm set as mm. PCRA fail. 12-jul-24 | 2024-07-15 |  |  |  | Urgent - Material syntax JSON EDIT - AGP HS2-00003J0PW HS2-00003J0PX | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 2 | 2 | 13
| 224.6 | HS2-000031EF3 | 95-SL1 Turweston Embankment Pedestrian Slab | 1MC07-ASC-BR-FRM-CS07_CL12-900002 | P01 | 2024-07-02 | 2024-07-02 | 2024-07-12 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600292 | No issues | [7 empty] | Urgent - Material syntax JSON EDIT - AGP HS2-00003DPTU HS2-00003DPTV | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 8 | 0 | 0
| 224.6 | HS2-000031EF4 | 95-SL2 Turweston Viaduct Vehicular Bridge | 1MC07-ASC-BR-FRM-CS07_CL12-900004 | P01 | 2024-07-02 |  | 2024-07-26 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600291 | No issues | OS conversions failing - sent back 10-jul-24 | 2024-07-22 | EmbddLgnth need to be integer 24/jul-24 - fix in house | 2024-07-24 | JSON issued with Shear studs retained in model as per DT agreement (Braedon MacGuire) |  |  | Urgent - Material syntax JSON EDIT - AGP HS2-00003GQ1D HS2-00003GQ1E | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 18 | 3
| 238.02_2 | HS2-00002YNH8 | Ladbroke Cutting Culvert 124-AC3 | 1MC07-ASC-CV-FRM-CS07_CL24-000053-ACBOS | P03 | 2024-07-03 | 2024-07-03 | 2024-07-09 | YES | 1MC07-CEK-IM-DAT-CS07_CL24-600113 | No issues | [8 empty] | 10 - Complete | Lee | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 4 | 0 | 0
| 230.01-3 | HS2-00002WUPJ | Thorpe Mandeville Embankment Planting-East Plot 1 | 1MC07-ASC-EV-REP-CS07_CL26-000007 | P01 | 2024-07-03 | 2024-07-03 | 2024-07-17 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600138 | No issues | [8 empty] | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 10 | 0 | 0
| 230.01-3 | HS2-00002WUPK | Thorpe Mandeville Embankment Planting-East Plot 2 | 1MC07-ASC-EV-REP-CS07_CL26-000008 | P01 | 2024-07-03 | 2024-07-03 | 2024-07-17 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600139 | No issues | [8 empty] | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 10 | 0 | 0
| 230.01-3 | HS2-00002WUPL | Thorpe Mandeville Embankment Planting-West Plot 1 | 1MC07-ASC-EV-REP-CS07_CL26-000009 | P01 | 2024-07-03 | 2024-07-03 | 2024-07-17 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600140 | No issues | [8 empty] | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 10 | 0 | 0
| 230.01-3 | HS2-00002WUPM | Thorpe Mandeville Embankment Planting-West Plot 2 | 1MC07-ASC-EV-REP-CS07_CL26-000010 | P01 | 2024-07-03 | 2024-07-03 | 2024-07-17 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600141 | No issues | [8 empty] | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 10 | 0 | 0
| 230.01-3 | HS2-00002WUPN | Lower Thorpe Viaduct Planting - Plot 1 | 1MC07-ASC-EV-REP-CS07_CL26-000001 | P01 | 2024-07-03 | 2024-07-03 | 2024-07-11 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600132 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 230.01-3 | HS2-00002WUPP | Lower Thorpe Viaduct Planting - Plot 2 | 1MC07-ASC-EV-REP-CS07_CL26-000002 | P01 | 2024-07-03 | 2024-07-03 | 2024-07-11 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600133 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 6 | 0 | 0
| 230.01-3 | HS2-00002WUPQ | Lower Thorpe Viaduct Planting - Plot 3 | 1MC07-ASC-EV-REP-CS07_CL26-000003 | P01 | 2024-07-03 | 2024-07-03 | 2024-07-12 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600134 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 7 | 0 | 0
| 230.01-3 | HS2-00002WUPR | Lower Thorpe Viaduct Planting - Plot 4 | 1MC07-ASC-EV-REP-CS07_CL26-000004 | P01 | 2024-07-03 | 2024-07-03 | 2024-07-12 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600135 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 7 | 0 | 0
| 230.01-3 | HS2-00002WUPS | Lower Thorpe Viaduct Planting - Plot 5 | 1MC07-ASC-EV-REP-CS07_CL26-000005 | P01 | 2024-07-03 | 2024-07-03 | 2024-07-12 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600136 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 7 | 0 | 0
| 230.01-3 | HS2-00002WUPT | Lower Thorpe Viaduct Planting - Plot 6 | 1MC07-ASC-EV-REP-CS07_CL26-000006 | P01 | 2024-07-03 | 2024-07-03 | 2024-07-12 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600137 | [9 empty] | 10 - Complete | Rakesh | Clarke, Philip <philip.clarke@arcadis.com> | 7 | 0 | 0
| 224.6 | HS2-0000386UG | 95-SL2 Turweston Viaduct Vehicular Bridge-Earthworks Transition | 1MC07-ASC-BR-FRM-CS07_CL12-000028-ACBOS | P02 | 2024-07-03 | 2024-07-03 | 2024-07-11 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600281 | [9 empty] | 10 - Complete | Rakesh | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 6 | 0 | 0
21 | 214.07 | HS2-00002YXB5 | Edgcott Road NR Access Point Staircase Upmain Ch74200 | 1MC06-ASC-CV-FRM-CS05-000083-ACBOS | P01 | 2024-07-03 | 2024-07-03 | 2024-07-05 |  | 1MC06-CEK-IM-DAT-CS05-600282 | [9 empty] | 10 - Complete | Supriyan | isaac.wong@arcadis.com OR anand.parmar@arcadis.com | 2 | 0 | 0
| UFDR 227.A | HS2-000020CHN |  | 1MC07-ASC-UT-FRM-CS07_CL12-000018-ACBOS | P03 | 2024-07-05 | 2024-07-05 | 2024-07-10 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600154 | No issues | [8 empty] | 10 - Complete | Lee | Kamboj, Mohit <mohit.kamboj@arcadis.com> | 3 | 0 | 0
| UFDR 227.A | HS2-00002CQQM |  | 1MC07-ASC-UT-FRM-CS07_CL12-000019-ACBOS | P03 | 2024-07-05 | 2024-07-05 | 2024-07-10 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600123 | No issues | [8 empty] | 10 - Complete | Lee | Kamboj, Mohit <mohit.kamboj@arcadis.com> | 3 | 0 | 0
| 235.01-1 | HS2-000020NZU |  | 1MC07-ASC-HW-FRM-CS07_CL14-000032-ACBOS | P01 | 2024-07-05 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL14-600016 |  |  |  | Record count issues/send back on 12-Jiuly-2024 |  | Cancelled - 13-Jan-25 due to older than 6 months since correspondance |  |  |  | 99 - Cancelled | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com>
10 | 233.01-3 | HS2-000020NXM |  | 1MC07-ASC-HW-FRM-CS07_CL26-000036-ACBOS | P01 | 2024-07-05 | 2024-07-05 | 2024-07-12 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600021 | [9 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 5 | 0 | 0
10 | 233.01-3 | HS2-000035Q9C |  | 1MC07-ASC-HW-FRM-CS07_CL13-000066-ACBOS | P01 | 2024-07-05 | 2024-07-05 | 2024-07-12 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600038 | [9 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 5 | 0 | 0
| 237.02 | HS2-00002CTJZ |  | 1MC07-ASC-DR-FRM-CS07_CL23-000073-ACBOS | P09 | 2024-07-05 | 2024-07-05 | 2024-07-31 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600062 | No issues | uniclass Issue, send back on 12-July-2024 | 2024-07-26 | [6 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 18 | 1 | 0
| 228.2 | HS2-00002CTEL |  | 1MC07-ASC-HW-FRM-CS07_CL12-000020-ACBOS | P04 | 2024-07-05 | 2024-07-15 | 2024-07-16 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600028 |  | Issues found send bac on 12-July-2024 | [7 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 10
| 228.2 | HS2-000020NUE |  | 1MC07-ASC-HW-FRM-CS07_CL12-000057-ACBOS | P04 | 2024-07-05 | 2024-07-15 | 2024-07-16 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600026 |  | Issues found send bac on 12-July-2024 | [7 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 10
| 218.02 | HS2-000031248 |  | 1MC06-ASC-CV-FRM-CS06_CL10-000090-ACBOS | P03 | 2024-07-05 | 2024-07-10 | 2024-07-11 | YES | 1MC06-CEK-IM-DAT-CS06_CL10-600210 | Done. No Issues | Using Uniclass withdrawn codes - 8/7/24 | [7 empty] | 10 - Complete | Lee | Ul Mashood, Hammad <hammad.mashood@arcadis.com> | 1 | 1
| 234.03 | HS2-00003JN82 | Highfurlong Brook Embankment 113-DC1 | 1MC07-ASC-CV-FRM-CS07_CL14-000110-ACBOS | P01 | 2024-07-08 | 2024-07-08 | 2024-07-15 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600192 | [9 empty] | 10 - Complete | Supriyan | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 5 | 0 | 0
| 234.03 | HS2-00003JN83 | Highfurlong Brook Embankment 113-DC3 | 1MC07-ASC-CV-FRM-CS07_CL14-000112-ACBOS | P01 | 2024-07-08 | 2024-07-08 | 2024-07-15 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600194 | [9 empty] | 10 - Complete | Supriyan | Naik, Vruddhika <vruddhika.naik@arcadis.com> | 5 | 0 | 0
| 222.6 | HS2-00002YGQF | Barton to Mixbury radio compound UTX No2 (GSMR Point 42) | 1MC06-ASC-CV-FRM-CS06_CL21-900011-ACBOS | P01 | 2024-07-08 | 2024-07-10 | 2024-07-11 | YES | 1MC06-CEK-IM-DAT-CS06_CL21-600108 | No issues | HOLD JSON issue until email answered about HghtM zero value 09-jul-24 | 2024-07-10 | [6 empty] | 10 - Complete | Lee | BONICI Alexandra <alexandra.bonici@setec.com> | 1 | 1 | 2
| 216.01 | HS2-00002CT8T | HS2-00002C5T4 - Perry Hill Road Drainage System | 1MC06-ASC-DR-FRM-CS06_CL09-000028-ACBOS | P02 | 2024-07-08 |  |  | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600201 | Fail | Ifc/Uniclass mismatches, OS Coordinates sent back - 12-jul-24 | [7 empty] | 99 - Cancelled | Lee | Rai C, Keerthan <keerthan.raic@arcadis.com>
3 | 212.5 | HS2-00002YD79 | Aylesbury Embankment Pedestrian Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS04_CL18-000069-ACBOS | P02 | 2024-07-08 | 2024-07-08 | 2024-07-09 | YES | 1MC06-CEK-IM-DAT-CS04_CL18-600152 | No issues | This request is in error - PW file P02 to be deleted and revert back to previous revison P01 | [7 empty] | 10 - Complete | Lee | orlando.sangalang@arcadis.com | 1 | 1 | 0
| 238.02_2 | HS2-00003H6PG | Ladbroke Cutting Ancillary Pipe Culvert 2 | 1MC07-ASC-CV-FRM-CS07_CL24-000066-ACBOS | P02 | 2024-07-09 | 2024-07-09 | 2024-07-16 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600119 | No issues | [8 empty] | 10 - Complete | Lee | Chris Gilmour <chris.gilmour@fairhurst.co.uk> | 5 | 0 | 0
| 226.5 | HS2-000031EF6 | 98-SL1 Brackley North Cutting Vehicular Slab | 1MC07-ASC-BR-FRM-CS07_CL12-900001 | P01 | 2024-07-09 | 2024-07-16 | 2024-07-17 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600294 |  | Uniclass ID issue and other isses, send back on 16-July-2024 | [7 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 1 | 1 | 7
| 221.5 | HS2-00002YGQ8 | 84-SL2 Chetwode Embankment Vehicular Slab | 1MC06-ASC-BR-FRM-CS06_CL10-900008 | P01 | 2024-07-09 | 2024-08-14 | 2024-08-19 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600231 |  | Uniclass issue , send back on 23-July-2024 | [7 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 3 | 1 | 36
| 221.5 | HS2-000037YLH | 84-SL3 Chetwode Embankment Vehicular Slab | 1MC06-ASC-BR-FRM-CS06_CL10-900004 | P01 | 2024-07-09 | 2024-08-14 | 2024-08-19 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600228 |  | Uniclass issue , send back on 23-July-2024 | [7 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 3 | 1 | 36
| 221.5 | HS2-00002YGQC | 85-SL1 Chetwode Cutting Vehicular Slab | 1MC06-ASC-BR-FRM-CS06_CL10-900005 | P01 | 2024-07-09 | 2024-08-14 | 2024-08-19 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600230 |  | Uniclass issue , send back on 23-July-2024 | [7 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 3 | 1 | 36
| 221.5 | HS2-000037YLK | 86-SL1 Chetwode Cutting Vehicular Slab | 1MC06-ASC-BR-FRM-CS06_CL10-900006 | P01 | 2024-07-09 | 2024-08-20 | 2024-08-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600227 |  | Uniclass issue , send back on 23-July-2024 | [7 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 3 | 1 | 42
| 221.5 | HS2-00002YGQA | 87-SL1 Barton Hartshorn Embankment Pedestrian Slab | 1MC06-ASC-BR-FRM-CS06_CL21-900001 | P01 | 2024-07-09 | 2024-08-14 | 2024-08-20 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600151 |  | Uniclass issue and OSGB isses, send back on 23-July-2024 | [7 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 4 | 1 | 36
| 221.5 | HS2-000037YLM | 87-SL2 Barton Hartshorn Embankment Pedestrian Slab | 1MC06-ASC-BR-FRM-CS06_CL21-900002 | P01 | 2024-07-09 | 2024-08-14 | 2024-08-20 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600150 |  | Uniclass issue and OSGB isses, send back on 23-July-2024 | [7 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 4 | 1 | 36
| 202.4-2 | HS2-00002CT2Y | C2.L.12 Catchment | 1MC06-ASC-DR-FRM-CS03_CL05-000011-ACBOS | P01 | 2024-07-09 |  | 2024-07-26 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600012 | Issue found | 0's in TtlFldStrgVlmEstmt , FnshInvrtLvl LwstLvl, Hghtm & depricated uniclass value Send back to team 16 July 24 | 2024-07-17 | ComRefNumber blank issue , send back to team on 17-07-2024. | [5 empty] | 10 - Complete | Rakesh | Hallado, Ruel <Ruel.Hallado@arcadis.com> | 13 | 2
| 202.4-2 | HS2-00002CT3Q | C2.L.14 Catchment | 1MC06-ASC-DR-FRM-CS03_CL05-000080-ACBOS | P01 | 2024-07-09 | 2024-07-22 | 2024-07-26 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600033 | Issue found | 0's in FnshInvrtLvl , LwstLvl,Hghtm, DsgnFl , IFC layer and Uniclass ID mismatch , Deprecated Uniclass Send back to team on 16 July 24 | 2024-07-17 | ComRefNumber blank issue , send back to team on 17-07-2024. | [5 empty] | 10 - Complete | Rakesh | Hallado, Ruel <Ruel.Hallado@arcadis.com> | 4 | 2 | 13
| 237.05 | HS2-00003KFPU | Ladbroke Grove Cutting | 1MC07-ASC-CV-FRM-CS07_CL23-000086-ACBOS | P01 | 2024-07-09 | 2024-07-10 | 2024-07-11 | Yes | 1MC07-CEK-IM-DAT-CS07_CL23-600168 |  | Uniclss and other issues, send back on 10-July-2024 | [7 empty] | 10 - Complete | Supriyan | immanuel.philipose@arcadis.com | 1 | 1 | 1
| 237.05 | HS2-00003KFPV | Ladbroke Grove Cutting | 1MC07-ASC-CV-FRM-CS07_CL23-000087-ACBOS | P01 | 2024-07-09 | 2024-07-10 | 2024-07-11 | Yes | 1MC07-CEK-IM-DAT-CS07_CL23-600169 |  | Uniclss and other issues, send back on 10-July-2024 | [7 empty] | 10 - Complete | Supriyan | immanuel.philipose@arcadis.com | 1 | 1 | 1
| 237.05 | HS2-00003KFPW | Ladbroke Grove Cutting | 1MC07-ASC-CV-FRM-CS07_CL23-000088-ACBOS | P01 | 2024-07-09 | 2024-07-10 | 2024-07-11 | Yes | 1MC07-CEK-IM-DAT-CS07_CL23-600170 |  | Uniclss and other issues, send back on 10-July-2024 | [7 empty] | 10 - Complete | Supriyan | immanuel.philipose@arcadis.com | 1 | 1 | 1
| 237.05 | HS2-00003KFPX | Ladbroke Grove Cutting | 1MC07-ASC-CV-FRM-CS07_CL23-000089-ACBOS | P01 | 2024-07-09 | 2024-07-10 | 2024-07-11 | Yes | 1MC07-CEK-IM-DAT-CS07_CL23-600171 |  | Uniclss and other issues, send back on 10-July-2024 | [7 empty] | 10 - Complete | Supriyan | immanuel.philipose@arcadis.com | 1 | 1 | 1
| 226.5 | HS2-000031EF5 | 97-SL2 Brackley Embankment Vehicular Bridge | 1MC07-ASC-BR-FRM-CS07_CL12-900003 | P01 | 2024-07-09 | 2024-07-16 |  |  | 1MC07-CEK-IM-DAT-CS07_CL12-600295 |  | Uniclass ID issue and other isses, send back on 16-July-2024 | [7 empty] | 99 - Cancelled | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
| 221.5 | HS2-000031EF1 | 84-SL1 Godington East Embankment Vehicular Bridge | 1MC06-ASC-BR-FRM-CS06_CL10-900011 | P01 | 2024-07-09 | 2024-08-20 | 2024-08-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600229 |  | Uniclass issue , send back on 23-July-2024 | [7 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 3 | 1 | 42
3 | 212.5 | HS2-00002YD7F | Aylesbury Embankment Vehicular Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS04_CL18-000075-ACBOS | P04 | 2024-07-09 | 2024-07-16 | 2024-07-17 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600155 |  | Maximum Permitted Height Issue, send back on 16-July-2024 | [7 empty] | 10 - Complete | Supriyan | Sangalang, Orlando <orlando.sangalang@arcadis.com> | 1 | 1 | 7
| UFDR 239.E | HS2-000020CKR | CNO-125-007HV | 1MC07-ASC-UT-FRM-CS07_CL24-000023-ACBOS | P01 | 2024-07-11 | 2024-07-11 | 2024-07-16 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600082 | No issues | [8 empty] | 10 - Complete | Lee | T, Sithrubi <sithrubi.t@arcadis.com> | 3 | 0 | 0
| UFDR 239.E | HS2-00002CTKR | CNO-125-007LV | 1MC07-ASC-UT-FRM-CS07_CL24-000025-ACBOS | P01 | 2024-07-11 | 2024-07-11 | 2024-07-16 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600117 | No issues | [8 empty] | 10 - Complete | Lee | T, Sithrubi <sithrubi.t@arcadis.com> | 3 | 0 | 0
| 202.4-2 | HS2-00002CT32 | C2.T.11 Catchment | 1MC06-ASC-DR-FRM-CS03_CL05-000019-ACBOS | P01 | 2024-07-11 | 2024-07-29 | 2024-08-01 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600054 | Issue found | OSGB issue, 0's ,Spacing found.IFC Vs Uniclass mismatch .Send back on 17 July 24. | 2024-07-29 | Com_ISCI value incorrect Send back to team on 30 July 24. | [5 empty] | 10 - Complete | Rakesh | Ramos, Leo <Leomel.Ramos@arcadis.com> | 3 | 2 | 18
| 202.4-2 | HS2-00002BVEK | C2.T.5 Catchment | 1MC06-ASC-DR-FRM-CS03_CL05-000018-ACBOS | P01 | 2024-07-11 | 2024-07-29 | 2024-08-01 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600048 | Issue found | OSGB issue, 0's ,Spacing found. Send back on 17 July 24. | 2024-07-29 | [6 empty] | 10 - Complete | Rakesh | Ramos, Leo <Leomel.Ramos@arcadis.com> | 3 | 1 | 18
| 214.1 | HS2-00003CPYN | SCL 13 Green Overbridge Restraint System | 1MC06-ASC-BR-FRM-CS05_CL09-000002 | P01 | 2024-07-11 | 2024-07-25 | 2024-07-25 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600258 |  | uniclass and other issues, send back on 18-July-2024 |  | Send back during Review on 24-July-2024 | [5 empty] | 10 - Complete | Supriyan | Alexander Patrick <alpk@cowi.com> | 0 | 2 | 14
| 214.1 | HS2-000031B3U | SWBMS Emergency Intervention stairs | 1MC06-CEK-BR-FRM-CS05-600045 | P02 | 2024-07-11 | 2024-07-18 | 2024-07-23 |  | 1MC06-CEK-IM-DAT-CS05-600180 |  | Com_type and other isses, send back on 18-July-2024 | [7 empty] | 10 - Complete | Supriyan | Alexander Patrick <alpk@cowi.com> | 3 | 1 | 7
| 202.1-1 | HS2-000001022 | Small Dean Viaduct | 1MC06-ASC-BR-FRM-CS03_CL06-000004-ACBOS | P01 | 2024-07-12 | 2024-07-30 |  |  | 1MC06-CEK-IM-DAT-CS03_CL06-600056 |  | Wrong ACBOS link, send back on 24-July-2024 |  | Many issues, file send back on 30-July-2024 |  | Cancelled - 13-Jan-25 due to older than 6 months since correspondance |  |  |  | 99 - Cancelled | Supriyan | Mahmood, Qaiser <Qaiser.Mahmood@arcadis.com>
| 235.01 | HS2-00002N7UR | Boddington Cutting | 1MC07-ASC-CV-FRM-CS07_CL14-000018-ACBOS | P03 | 2024-07-12 | 2024-07-12 | 2024-07-15 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600125 | [9 empty] | 10 - Complete | Supriyan | PATIL, APOORVA <apoorva.patil@arcadis.com> | 1 | 0 | 0
| 224.6 | HS2-00002CTDR | Turweston Embankment Boundary Perimeter Fence Line | 1MC07-ASC-CV-FRM-CS07_CL12-000034-ACBOS | P01 | 2024-07-12 | 2024-07-12 | 2024-07-22 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600106 | No issues | [8 empty] | 10 - Complete | Lee | MIRI Youssef <youssef.miri@setec.com> | 6 | 0 | 0
| 224.6 | HS2-00002CTDT | Turweston Embankment Security Fence Line | 1MC07-ASC-CV-FRM-CS07_CL12-000040-ACBOS | P01 | 2024-07-12 | 2024-07-12 | 2024-07-22 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600100 | No issues | [8 empty] | 10 - Complete | Lee | MIRI Youssef <youssef.miri@setec.com> | 6 | 0 | 0
| 224.6 | HS2-00002CTDY | Helmdon Embankment Boundary Perimeter Fence Line | 1MC07-ASC-CV-FRM-CS07_CL12-000033-ACBOS | P01 | 2024-07-12 | 2024-07-12 | 2024-07-22 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600111 | No issues | [8 empty] | 10 - Complete | Lee | MIRI Youssef <youssef.miri@setec.com> | 6 | 0 | 0
| 224.6 | HS2-00002CTE1 | Helmdon Embankment Security Fence Line | 1MC07-ASC-CV-FRM-CS07_CL12-000039-ACBOS | P01 | 2024-07-12 | 2024-07-12 | 2024-07-22 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600113 | No issues | [8 empty] | 10 - Complete | Lee | MIRI Youssef <youssef.miri@setec.com> | 6 | 0 | 0
| 224.6 | HS2-00002CTCM | Turweston Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000019-ACBOS | P01 | 2024-07-12 | 2024-07-12 | 2024-07-22 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600097 | No issues | [8 empty] | 10 - Complete | Lee | MIRI Youssef <youssef.miri@setec.com> | 6 | 0 | 0
| 224.6 | HS2-00002CTCP | Turweston Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000024-ACBOS | P01 | 2024-07-12 | 2024-07-12 | 2024-07-22 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600064 | No issues | [8 empty] | 10 - Complete | Lee | MIRI Youssef <youssef.miri@setec.com> | 6 | 0 | 0
| 224.6 | HS2-00002CTCG | Grovehill Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000016-ACBOS | P01 | 2024-07-12 | 2024-07-12 | 2024-07-22 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600066 | No issues | [8 empty] | 10 - Complete | Lee | MIRI Youssef <youssef.miri@setec.com> | 6 | 0 | 0
| 224.6 | HS2-00002CTCJ | Grovehill Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000021-ACBOS | P01 | 2024-07-12 | 2024-07-12 | 2024-07-22 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600074 | No issues | [8 empty] | 10 - Complete | Lee | MIRI Youssef <youssef.miri@setec.com> | 6 | 0 | 0
| 214.1 | HS2-00003CPYQ | SWBMS Cable routing | 1MC06-ASC-CV-FRM-CS05-000086-ACBOS | P01 | 2024-07-12 | 2024-08-28 | 2024-08-29 |  | 1MC06-CEK-IM-DAT-CS05-600185 |  |  |  |  | Revised 14-Aug-24 | Does not match SmafrtForms. |  | Incorrect HeightMn in Base class , send back to team on 29 Aug 24. |  | 10 - Complete | Rakesh | Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com> | 1 | 2 | 47
| 214.1 | HS2-00002EK75 | SWBMS North UTX | 1MC06-ASC-CV-FRM-CS05-000136-ACBOS | P02 | 2024-07-12 | 2024-08-20 | 2024-08-22 |  | 1MC06-CEK-IM-DAT-CS05-600183 | No issues |  |  |  | Revised 14-Aug-24 | CHB Dpth set as wacky value - sent back 16-Aug-24 |  |  |  | 10 - Complete | Lee | Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com> | 2 | 1 | 39
| 214.1 | HS2-00003CPYP | SWBMS South UTX | 1MC06-ASC-CV-FRM-CS05-000137-ACBOS | P02 | 2024-07-12 | 2024-08-20 | 2024-08-23 |  | 1MC06-CEK-IM-DAT-CS05-600184 | No issues | Com_typ / Uniclass IFC mismatch sent back 29-jul-24 |  |  | Revised 14-Aug-24 | CHB Dpth set as wacky value - sent back 16-Aug-24 | Revised 19-Aug-24 |  |  | 10 - Complete | Lee | Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com> | 3 | 2 | 39
| 214.1 | HS2-00002XQ2Q | SWBMS Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS05-000104-ACBOS | P01 | 2024-07-12 | 2024-07-31 | 2024-08-02 |  | 1MC06-CEK-IM-DAT-CS05-600178 |  | OSGB and com_type issues, send abck on 24-Juy-2024 |  | 0's in Lengthm, send query on 30-July-2024 | [5 empty] | 10 - Complete | Supriyan | Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com> | 2 | 2 | 19
| 214.1 | HS2-00002XQ2R | SWBMS Security Fence Line | 1MC06-ASC-CV-FRM-CS05-000105-ACBOS | P01 | 2024-07-12 | 2024-07-31 | 2024-08-02 |  | 1MC06-CEK-IM-DAT-CS05-600179 |  | OSGB, Uniclass and con_type issues, send back on 24-July-2024 |  | IFC vs uniclass issue,many 0's send back on 30-July-2024 | [5 empty] | 10 - Complete | Supriyan | Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com> | 2 | 2 | 19
3 | 212.5 | HS2-00003BPJH | Oxford Road Embankment Ditch Slab No.11 | 1MC06-ASC-CV-FRM-CS04_CL19-000069-ACBOS | P01 | 2024-07-12 | 2024-07-12 | 2024-07-25 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600103 | [9 empty] | 10 - Complete | Supriyan | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com> | 9 | 0 | 0
3 | 212.5 | HS2-00002ZJQH | SBH-32 Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL19-000051-ACBOS | P01 | 2024-07-12 | 2024-07-12 | 2024-07-25 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600105 | [9 empty] | 10 - Complete | Supriyan | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com> | 9 | 0 | 0
| 226.1 | HS2-00002CTDV | Whitfield ATS | 1MC07-ASC-GT-FRM-CS07_CL12-000028-ACBOS | P01 | 2024-07-15 | 2024-07-15 | 2024-07-24 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600167 | No issues | [8 empty] | 10 - Complete | Lee | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 7 | 0 | 0
| UFDR 208.A | HS2-000020CEX | CSO-02-1211LVP | 1MC06-ASC-UT-FRM-CS04_CL18-000024-ACBOS | P02 | 2024-07-16 | 2024-07-25 | 2024-07-26 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600007 |  | PCRA of ACBOS is pending, send back on 25-July-2024 | [7 empty] | 10 - Complete | Supriyan | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 1 | 1 | 9
| UFDR 208.A | HS2-0000245Z0 | CSO-02-1211HVP | 1MC06-ASC-UT-FRM-CS04_CL18-000022-ACBOS | P02 | 2024-07-16 | 2024-07-25 | 2024-07-26 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600011 |  | PCRA of ACBOS is pending, send back on 25-July-2024 | [7 empty] | 10 - Complete | Supriyan | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 1 | 1 | 9
| UFDR 208.A | HS2-00002SZLT | UKPN Substation Thames Water | 1MC06-ASC-UT-FRM-CS04_CL18-000056-ACBOS | P02 | 2024-07-16 | 2024-07-25 | 2024-07-30 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600097 |  | PCRA of ACBOS is pending, send back on 25-July-2024 | [7 empty] | 10 - Complete | Supriyan | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 3 | 1 | 9
| UFDR 208.A | HS2-00002SZLS | Hartwell Cottages UKPN Substation | 1MC06-ASC-UT-FRM-CS04_CL18-000055-ACBOS | P02 | 2024-07-16 | 2024-07-25 | 2024-07-30 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600096 |  | PCRA of ACBOS is pending, send back on 25-July-2024 | [7 empty] | 10 - Complete | Supriyan | Mainstone, Eloise <eloise.mainstone@arcadis.com> | 3 | 1 | 9
| 202.4-2 | HS2-00002EK6M | Wendover Rail Systems Compound UTX | 1MC06-ASC-CV-FRM-CS03_CL05-000021-ACBOS | P01 | 2024-07-16 | 2024-07-25 | 2024-07-25 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600043 |  | wrong sdslp, send back on 25-July-2024 | [7 empty] | 10 - Complete | Supriyan | T R, Aishwarya <aishwarya.tr@arcadis.com> | 0 | 1 | 9
| 217.03 | HS2-000001314 | Addison Road Overbridge | 1MC06-CEK-BR-FRM-CS06_CL09-000006 | P09 | 2024-07-16 | 2024-07-25 |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600127 |  | PCRA of MPDT is pending, send back on 24-July-2024 |  | Com_type and other issues, send back on 25-July-2024 | [5 empty] | 99 - Cancelled | Supriyan | Whyte, William <William.Whyte@arcadis.com>
| 224.6 | HS2-00003BPLB | Turweston Cutting planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL22-900019 | P01 | 2024-07-17 | 2024-07-19 | 2024-07-22 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600163 | Issue found | Com_Type & Dscrptn missing Sent back 18/07/24. | 2024-07-19 | [6 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 1 | 1 | 2
| 224.6 | HS2-00003BPLD | Turweston Cutting planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL22-900022 | P01 | 2024-07-17 | 2024-07-19 | 2024-07-25 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600167 | Issue found | Com_Type & Dscrptn missing Sent back 18/07/24. | 2024-07-19 | [6 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 4 | 1 | 2
| 224.6 | HS2-00003BPLE | Turweston Cutting planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL22-900023 | P01 | 2024-07-17 | 2024-07-30 | 2024-07-31 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600168 | Issue found | N/A found in DsgnLf send back to team on 22 July 24. | 2024-07-22 | LSH component.need to provide Mtrl and NetVolume ,Send Back to team on 23 July 24 |  | LSH attribution added 30-jul-24 |  |  |  | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 1 | 3 | 13
| 224.6 | HS2-00003BPLG | Turweston Cutting planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL22-900024 | P01 | 2024-07-17 | 2024-07-25 | 2024-07-29 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600169 | Issue found | LSH asset Mtrl and NetVolume blank .Send back to team on 24-July-24. | [7 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 2 | 1 | 8
| 224.6 | HS2-00003BPLN | Turweston Cutting planting Plot 7 | 1MC06-ASC-EV-FRM-CS06_CL22-900026 | P01 | 2024-07-17 | 2024-07-17 | 2024-07-23 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600172 | [9 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 4 | 0 | 0
| 224.6 | HS2-00003BPLF | Turweston Cutting planting Plot 8 | 1MC06-ASC-EV-FRM-CS06_CL22-900027 | P01 | 2024-07-17 | 2024-07-30 | 2024-07-31 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600173 | Issue found | LSH component.need to provide Mtrl and NetVolume ,Sen Back to team on 23 July 24 |  | LSH component.need to provide Mtrl and NetVolume ,Send Back to team on 23 July 24 |  | LSH attribution added 30-jul-24 |  |  |  | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 1 | 3 | 13
| 224.6 | HS2-00003BPLC | Turweston Cutting planting Plot 9 | 1MC06-ASC-EV-FRM-CS06_CL22-900028 | P01 | 2024-07-17 | 2024-07-17 | 2024-07-23 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600174 | [9 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 4 | 0 | 0
| 224.6 | HS2-00003BPLJ | Turweston Cutting planting Plot 10 | 1MC06-ASC-EV-FRM-CS06_CL22-900029 | P01 | 2024-07-17 | 2024-07-24 | 2024-07-26 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600164 | Issue found | CM_StdBL value seems to be incorrect (P15.2) , send back to team on 24-July-24. | [7 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 2 | 1 | 7
| 224.6 | HS2-00003BPLK | Turweston Cutting planting Plot 11 | 1MC06-ASC-EV-FRM-CS06_CL22-900030 | P01 | 2024-07-17 | 2024-07-17 | 2024-07-23 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600165 | [9 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 4 | 0 | 0
| 224.6 | HS2-00003BPLL | Turweston Cutting planting Plot 12 | 1MC06-ASC-EV-FRM-CS06_CL22-900031 | P01 | 2024-07-17 | 2024-07-24 | 2024-07-30 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600166 | Issue found | P06 version found in CM_crt & CM_chg , send back to team on 23 - July-24. | [7 empty] | 10 - Complete | Rakesh | SAAB Hassan <hassan.saab@setec.com> | 4 | 1 | 7
| 224.6 | HS2-00003BPLP | Turweston Cutting planting Plot 13 | 1MC06-ASC-EV-FRM-CS06_CL22-900032 | P01 | 2024-07-17 | 2024-07-17 | 2024-07-24 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600227 | No issues | PW JSON placeholder not at WIP | [7 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 5 | 1 | 0
| 224.6 | HS2-0000386UL | Westbury Viaduct planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL22-900033 | P01 | 2024-07-17 | 2024-07-31 | 2024-07-31 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600138 | No issues | Height, DsgnLf, Areas, incomplete. Sent back 22-jul-24 | 2024-07-24 | LSH Uniclass code incorrect. | 26-jul-24 PM. | LSH attribution added 30-jul-24 |  |  |  | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 0 | 3 | 14
| 224.6 | HS2-0000386UM | Westbury Viaduct planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL22-900034 | P01 | 2024-07-17 | 2024-08-01 | 2024-08-01 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600137 | No issues | Height, DsgnLf, CM_CRT, PlantingType, Quantities incomplete. MTRL and Uniclass does not seem correct for LSH. Sent back 22-jul-24 | 2024-07-24 | LSH Uniclass code incorrect. | 26-jul-24 PM. | LSH attribution added 30-jul-24 |  | DT Altered 3 LSG Lgnthm values |  | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 0 | 4 | 15
| 224.6 | HS2-0000386UP | Westbury Viaduct planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL22-900035 | P01 | 2024-07-17 | 2024-07-25 | 2024-07-26 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600136 | No issues | DsgnLf, CM_CRT, Quantities incomplete. Sent back 22-jul-24 | 2024-07-24 | [6 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 1 | 1 | 8
| 224.6 | HS2-0000386UQ | Westbury Viaduct planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL22-900036 | P01 | 2024-07-17 | 2024-07-25 | 2024-07-26 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600135 | No issues | DsgnLf, CM_CRT, Quantities & height incomplete. Sent back 22-jul-24 | 2024-07-24 | [6 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 1 | 1 | 8
| 224.6 | HS2-00003BPL5 | Grovehill Embankment planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL22-900037 | P01 | 2024-07-17 | 2024-07-25 | 2024-07-26 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600157 | No issues | contains empty Com_Arsqm | 2024-07-24 | [6 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 1 | 1 | 8
| 224.6 | HS2-00003BPL6 | Grovehill Embankment planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL22-900038 | P01 | 2024-07-17 | 2024-07-25 | 2024-07-26 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600158 | No issues |  | 2024-07-24 | [6 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 1 | 0 | 8
| 224.6 | HS2-00003BPL8 | Grovehill Embankment planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL22-900039 | P01 | 2024-07-17 | 2024-07-25 | 2024-07-26 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600159 | No issues | CM_Chg incorrect - fixed in house 22-jul-24 PW file to be updated by DT. | 2024-07-24 | [6 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 1 | 1 | 8
| 224.6 | HS2-00003BPL9 | Grovehill Embankment planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL22-900040 | P01 | 2024-07-17 | 2024-07-30 | 2024-07-31 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600160 | No issues | incomplete. Sent back 22-jul-24 | 2024-07-24 | LSH Uniclass code incorrect. | 26-jul-24 PM. | LSH attribution added 30-jul-24 |  |  |  | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 1 | 3 | 13
| 224.6 | HS2-00003BPLA | Grovehill Embankment planting Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL22-900041 | P01 | 2024-07-17 | 2024-07-17 | 2024-07-24 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600161 | No issues | CM_Chg incorrect - fixed in house 22-jul-24 PW file to be updated by DT. | [7 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 5 | 1 | 0
| 224.6 | HS2-00003BPL7 | Grovehill Embankment planting Plot 6 | 1MC06-ASC-EV-FRM-CS06_CL22-900042 | P01 | 2024-07-17 | 2024-07-25 | 2024-07-30 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600162 |  | DsgnLf, Quantities incomplete. Sent back 23-jul-24 | 2024-07-24 | [6 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 3 | 1 | 8
| 224.6 | HS2-00003BPLS | Turweston Embankment Planting Plot 2 | 1MC07-ASC-EV-FRM-CS07_CL12-900018 | P01 | 2024-07-17 | 2024-07-30 | 2024-07-31 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600215 | No issues | File incomplete missing attributes / UAID's, DsgLf, Uniclass etc. sent back 22-jul-24 | 2024-07-24 | LSH Uniclass code incorrect. | 26-jul-24 PM. | LSH attribution added 30-jul-24 |  |  |  | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 1 | 3 | 13
| 224.6 | HS2-00003BPLU | Turweston Embankment Planting Plot 3 | 1MC07-ASC-EV-FRM-CS07_CL12-900019 | P01 | 2024-07-17 | 2024-07-17 | 2024-07-24 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600216 | No issues | [8 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 5 | 0 | 0
| 224.6 | HS2-00003BPLT | Turweston Embankment Planting Plot 4 | 1MC07-ASC-EV-FRM-CS07_CL12-900020 | P01 | 2024-07-17 | 2024-07-17 | 2024-07-24 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600217 | No issues | [8 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 5 | 0 | 0
| 224.6 | HS2-00003BPLR | Turweston Embankment Planting Plot 5 | 1MC07-ASC-EV-FRM-CS07_CL12-900021 | P01 | 2024-07-17 | 2024-07-25 | 2024-07-30 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600218 | No issues | DsgnLf, Quantities incomplete. Sent back 22-jul-24 | 2024-07-24 | [6 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 3 | 1 | 8
| 224.6 | HS2-00003BPLW | Turweston Viaduct Plot 1 | 1MC07-ASC-EV-FRM-CS07_CL12-900022 | P01 | 2024-07-17 |  | 2024-07-30 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600219 | No issues | DsgnLf, CM_CRT, CM_StdBL, CM_Chg & Quantities incomplete. Sent back 22-jul-24 | 2024-07-24 | UAID_1 contains trailing space - Fixed in house , please update Source MPDT to match. | [5 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 9 | 2
| 224.6 | HS2-00003BPM1 | Turweston Viaduct Plot 2 | 1MC07-ASC-EV-FRM-CS07_CL12-900023 | P01 | 2024-07-17 | 2024-07-30 | 2024-07-31 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600220 | No issues | Height, DsgnLf, CM_CRT, CM_Chg, Cm_StdBL, PlantingType, Quantities incomplete. MTRL and Uniclass does not seem correct for LSH. Sent back 22-jul-24 | 2024-07-24 | LSH Uniclass code incorrect. | 26-jul-24 PM. | LSH attribution added 30-jul-24 |  |  |  | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 1 | 3 | 13
| 224.6 | HS2-00003BPLY | Helmdon Embankment Plot 1 | 1MC07-ASC-EV-FRM-CS07_CL12-900024 | P01 | 2024-07-17 | 2024-07-30 | 2024-07-31 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600209 | No issues | Height, DsgnLf, PlantingType, Quantities incomplete. MTRL and Uniclass does not seem correct for LSH. Sent back 22-jul-24 | 2024-07-24 | LSH Uniclass code incorrect. | 26-jul-24 PM. | LSH attribution added 30-jul-24 |  |  |  | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 1 | 3 | 13
| 224.6 | HS2-00003BPM2 | Helmdon Embankment Plot 2 | 1MC07-ASC-EV-FRM-CS07_CL12-900025 | P01 | 2024-07-17 | 2024-07-30 | 2024-07-31 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600210 | No issues | Height, DsgnLf, PlantingType, Quantities incomplete. MTRL and Uniclass does not seem correct for LSH. Sent back 22-jul-24 | 2024-07-24 | LSH Uniclass code incorrect. | 26-jul-24 PM. | LSH attribution added 30-jul-24 |  |  |  | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 1 | 3 | 13
| 224.6 | HS2-00003BPM3 | Helmdon Embankment Plot 3 | 1MC07-ASC-EV-FRM-CS07_CL12-900026 | P01 | 2024-07-17 | 2024-07-17 | 2024-07-24 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600211 | No issues | [8 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 5 | 0 | 0
| 224.6 | HS2-00003BPM4 | Helmdon Embankment Plot 4 | 1MC07-ASC-EV-FRM-CS07_CL12-900027 | P01 | 2024-07-17 | 2024-07-17 | 2024-07-24 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600212 | No issues | [8 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 5 | 0 | 0
| 224.6 | HS2-00003BPM5 | Helmdon Embankment Plot 5 | 1MC07-ASC-EV-FRM-CS07_CL12-900028 | P01 | 2024-07-17 | 2024-07-25 | 2024-07-30 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600213 | No issues |  | 2024-07-24 | [6 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 3 | 0 | 8
| 224.6 | HS2-00003BPM0 | Helmdon Embankment Plot 6 | 1MC07-ASC-EV-FRM-CS07_CL12-900029 | P01 | 2024-07-17 | 2024-07-25 | 2024-07-30 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600214 | No issues |  | 2024-07-24 | [6 empty] | 10 - Complete | Lee | SAAB Hassan <hassan.saab@setec.com> | 3 | 0 | 8
| 222.2 | HS2-00002UVZ0 | 088-AC1 Watercourse Diversion | 1MC06-CEK-DR-FRM-CS06_CL21-600010 | P01 | 2024-07-17 | 2024-07-31 | 2024-08-01 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600089 |  | 0's and blanks, send back on 30-July-2024 | [7 empty] | 10 - Complete | Supriyan | @Mulholland, Luke | 1 | 1 | 14
| 222.2 | HS2-00002UVYY | Newton Purcell Culvert Watercourse Diversion (downstream channel) | 1MC06-CEK-DR-FRM-CS06_CL21-600009 | P01 | 2024-07-17 | 2024-07-31 | 2024-08-01 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600091 |  | 0's and blanks, send back on 30-July-2024 | [7 empty] | 10 - Complete | Supriyan | @Mulholland, Luke | 1 | 1 | 14
| 213.01-01 | HS2-00002BJTK | Doddershall House and South Farms Accommodation Access Road Solids Model | 1MC06-ASC-HW-FRM-CS05-000022-ACBOS | P07 | 2024-07-18 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600093 |  | Com_Type Issue, send abck on 31-July-2024 |  |  |  | Cancelled - 13-Jan-25 due to older than 6 months since correspondance |  |  |  | 99 - Cancelled | Supriyan | Shabad, Mallikarjun <mallikarjun.shabad@arcadis.com>
| 213.01-01 | HS2-000020NF2 | Station Road Realignment (Including Buckingham Road and Fidlers Field Road) Solids Model | 1MC06-ASC-HW-FRM-CS04_CL20-000013-ACBOS | P07 | 2024-07-18 |  |  |  | 1MC06-CEK-IM-DAT-CS04_CL20-600109 | Issue found | OSGB, Uniclass and Com_Type isses, ACBOS PCRA missing. Send back on 31-July-2024 |  |  |  | Cancelled - 13-Jan-25 due to older than 6 months since correspondance |  |  |  | 99 - Cancelled | Supriyan | Shabad, Mallikarjun <mallikarjun.shabad@arcadis.com>
| 238.01 | HS2-00003KFPM | Ladbroke Grove Embankment | 1MC07-ASC-CV-FRM-CS07_CL24-000067-ACBOS | P01 | 2024-07-18 |  | 2024-08-08 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600120 | Issue found | Incorrect Uniclass ID values Send back on 30 July 24. |  | Com_Ref_Number Values are missing in HND class Send back to team on 06 Aug 24. | [5 empty] | 10 - Complete | Rakesh | Afsal, Muhammed <muhammed.afsal@arcadis.com> | 15 | 2
| 234.05 | HS2-00002N7UN | Lower Boddington Embankment | 1MC07-ASC-CV-FRM-CS07_CL14-000015-ACBOS | P01 | 2024-07-18 |  | 2024-08-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600044 | [9 empty] | 10 - Complete | Supriyan | PATIL, APOORVA <apoorva.patil@arcadis.com> | 11 | 0
| 226.1 | HS2-00002EK7G | Whitfield ATS UTX | 1MC07-ASC-CV-FRM-CS07_CL12-000054-ACBOS | P01 | 2024-07-18 | 2024-07-24 | 2024-07-25 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600011 | No issues | Uniclass / IFC mismatch sen back 23-jul-24 | 2024-07-23 | MDQC is showing odd information - see Alex / Partha | [5 empty] | 10 - Complete | Lee | BONICI Alexandra <alexandra.bonici@setec.com> | 1 | 2 | 6
| 222.2 | HS2-00002UVYZ | Newton Purcell Culvert Watercourse Diversion (upstream channel) | 1MC06-CEK-DR-FRM-CS06_CL21-600008 | P01 | 2024-07-18 | 2024-07-31 | 2024-08-01 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600090 |  | 0's and blanks, send back on 30-July-2024 | [7 empty] | 10 - Complete | Supriyan | @Mulholland, Luke | 1 | 1 | 13
| 214.1 | HS2-00003HWH8 | Sheephouse Wood Bat Mitigation Structure Telecoms Section 2 | 1MC06-ASC-UT-FRM-CS05-000042-ACBOS | P01 | 2024-07-18 | 2024-08-01 | 2024-08-02 |  | 1MC06-CEK-IM-DAT-CS05-600298 |  | Com_Type and other issues, send back on 01-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Alexander Patrick <alpk@cowi.com> | 1 | 1 | 14
| 213.08 | HS2-00002CT7E | Doddershall Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS05-000133-ACBOS | P03 | 2024-07-18 |  | 2024-08-08 |  | 1MC06-CEK-IM-DAT-CS05-600129 | No issues | No other issue OS conversion only - 1 item outside tolerance. Sent back 1-aug-24 | DT have asked to leave as is. | [6 empty] | 10 - Complete | Lee | Whyte, William <William.Whyte@arcadis.com> | 15 | 1
| 238.01 | HS2-00003KFPL | Ladbroke Grove Embankment | 1MC07-ASC-CV-FRM-CS07_CL24-000068-ACBOS | P01 | 2024-07-22 | 2024-07-22 | 2024-08-01 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600121 | No issues | [8 empty] | 10 - Complete | Lee | PATIL, APOORVA <apoorva.patil@arcadis.com> | 8 | 0 | 0
3 | 212.5 | HS2-000035Q95 | Oxford Road Embankment Ditch Slab No.7 | 1MC06-ASC-CV-FRM-CS04_CL19-000062-ACBOS | P01 | 2024-07-22 | 2024-07-22 | 2024-08-02 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600084 | No issues | JSON / MDQC trigger not working - 1806hrs 1-Aug-24 | [7 empty] | 10 - Complete | Lee | Alagundi, Shreyas <shreyas.alagundi@arcadis.com> | 9 | 1 | 0
| UFDR 204.B | HS2-000020CEJ | CSO-02-6205 | 1MC06-ASC-UT-FRM-CS03_CL17-000018-ACBOS | P01 | 2024-07-23 | 2024-07-23 | 2024-07-30 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600039 | No issues | [8 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com> | 5 | 0 | 0
| UFDR 204.B | HS2-000020CEK | CSO-02-6206 | 1MC06-ASC-UT-FRM-CS03_CL17-000019-ACBOS | P01 | 2024-07-23 | 2024-07-23 | 2024-08-01 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600034 | No issues | [8 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com> | 7 | 0 | 0
| 204.2-2 | HS2-00002WULF | Stoke Mandeville South Embankment Planting - East Plot 1 | 1MC06-CEK-EV-FRM-CS03_CL17-000003 | tbc | 2024-07-23 | 2024-07-23 | 2024-08-01 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600082 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 7 | 0 | 0
| 204.2-2 | HS2-00002WULG | Stoke Mandeville South Embankment Planting - East Plot 2 | 1MC06-CEK-EV-FRM-CS03_CL17-000004 | tbc | 2024-07-23 |  | 2024-08-01 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600083 | Issue found | Incorrect version in CM_stdbl ,Send back to team on 31 july 24. | 31 july 24. | [6 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 7 | 1
| 204.2-2 | HS2-00002WULH | Stoke Mandeville South Embankment Planting - East Plot 3 | 1MC06-CEK-EV-FRM-CS03_CL17-000005 | tbc | 2024-07-23 |  | 2024-08-01 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600084 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 7 | 0
| 204.2-2 | HS2-00002WULJ | Stoke Mandeville South Embankment Planting - East Plot 4 | 1MC06-CEK-EV-FRM-CS03_CL17-000006 | tbc | 2024-07-23 |  |  |  | 1MC06-CEK-IM-DAT-CS03_CL17-600085 | Issue found | [8 empty] | 99 - Cancelled | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 204.2-2 | HS2-00002WULK | Stoke Mandeville South Embankment Planting - West Plot 1 | 1MC06-CEK-EV-FRM-CS03_CL17-000007 | tbc | 2024-07-23 |  | 2024-08-02 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600086 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 8 | 0
| 204.2-2 | HS2-00002WULL | Stoke Mandeville South Embankment Planting - West Plot 2 | 1MC06-CEK-EV-FRM-CS03_CL17-000008 | tbc | 2024-07-23 |  | 2024-08-02 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600087 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 8 | 0
| 204.2-2 | HS2-00002WULM | Stoke Mandeville South Embankment Planting - West Plot 3 | 1MC06-CEK-EV-FRM-CS03_CL17-000009 | tbc | 2024-07-23 |  | 2024-08-02 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600088 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 8 | 0
| 204.2-2 | HS2-00002WULN | Stoke Mandeville South Embankment Planting - West Plot 4 | 1MC06-CEK-EV-FRM-CS03_CL17-000010 | tbc | 2024-07-23 |  | 2024-08-02 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600089 | Issue found | Mismatch in L2 asset count in MPDT Vs Smart form.Send back on 1 Aug 24. | [7 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 8 | 1
| 202.4-2 | HS2-00002CT39 | Small Dean South Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS03_CL05-000036-ACBOS | P01 | 2024-07-23 |  | 2024-08-08 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600057 | No issues | Uniclass used is withdrawn. Sent back 1-Aug-24 | [7 empty] | 10 - Complete | Lee | Jennifer McKay <JRMY@COWI.COM> | 12 | 1
| 202.4-2 | HS2-00002CT37 | Small Dean South Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS03_CL05-000042-ACBOS | P01 | 2024-07-23 |  | 2024-08-08 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600055 | No issues | OS coords & CM_CRT set as P04. sent back 1-Aug-24 | 2024-08-06 | [6 empty] | 10 - Complete | Lee | Jennifer McKay <JRMY@COWI.COM> | 12 | 1
| 202.0-3 | HS2-00002WUJM | Wendover Dean South Embankment Planting - Plot 1 | 1MC06-CEK-EV-FRM-CS03_CL05-000049 | tbc | 2024-07-23 | 2024-07-23 | 2024-07-25 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600135 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 2 | 0 | 0
| 202.0-3 | HS2-00002WUJN | Wendover Dean South Embankment Planting - Plot 2 | 1MC06-CEK-EV-FRM-CS03_CL05-000050 | tbc | 2024-07-23 |  | 2024-07-25 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600136 | Issue found | Spacing issue in UAID2 Sendback to team on 24 July 24. | [7 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 2 | 1
| 202.0-3 | HS2-00002WUJP | Wendover Dean South Embankment Planting - Plot 3 | 1MC06-CEK-EV-FRM-CS03_CL05-000051 | tbc | 2024-07-23 | 2024-07-23 | 2024-07-25 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600137 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 2 | 0 | 0
| 202.0-3 | HS2-00002WUJQ | Wendover Dean South Embankment Planting - Plot 4 | 1MC06-CEK-EV-FRM-CS03_CL05-000052 | tbc | 2024-07-23 | 2024-07-23 | 2024-07-25 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600138 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 2 | 0 | 0
| 202.0-3 | HS2-00002WUJR | Wendover Dean Viaduct Planting - Plot 1 | 1MC06-CEK-EV-FRM-CS03_CL05-000053 | tbc | 2024-07-23 | 2024-07-23 | 2024-07-30 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600139 |  | Carriage returns in Com_ctn - Send back to team on 25 july 24. | [7 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 5 | 1 | 0
| 202.0-3 | HS2-00002WUJS | Wendover Dean Viaduct Planting - Plot 2 | 1MC06-CEK-EV-FRM-CS03_CL05-000054 | tbc | 2024-07-23 | 2024-07-23 | 2024-07-26 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600140 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 3 | 0 | 0
| 202.0-3 | HS2-00002WUJT | Wendover Dean Viaduct Planting - Plot 3 | 1MC06-CEK-EV-FRM-CS03_CL05-000055 | tbc | 2024-07-23 |  |  |  | 1MC06-CEK-IM-DAT-CS03_CL05-600141 | Issue found | MPDT with blank column , send back to team on 25 July 24. Withdrawn as per DT comment. | [7 empty] | 99 - Cancelled | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 202.0-3 | HS2-00002WUJU | Wendover Dean North Embankment Planting - East Plot 1 | 1MC06-CEK-EV-FRM-CS03_CL05-000046 | tbc | 2024-07-23 | 2024-07-23 | 2024-07-26 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600142 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 3 | 0 | 0
| 202.0-3 | HS2-00002WUJV | Wendover Dean North Embankment Planting - East Plot 2 | 1MC06-CEK-EV-FRM-CS03_CL05-000045 | tbc | 2024-07-23 |  | 2024-07-29 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600143 | Issue found | Incorrect com_type found . Send back to team on 25 July 24. | [7 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 4 | 1
| 202.0-3 | HS2-00002WUJW | Wendover Dean North Embankment Planting - West Plot 1 | 1MC06-CEK-EV-FRM-CS03_CL05-000047 | tbc | 2024-07-23 |  | 2024-07-29 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600144 | Issue found | Incorrect com_type found . Send back to team on 25 July 24. | [7 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 4 | 1
| 202.0-3 | HS2-00002WUJX | Wendover Dean North Embankment Planting - West Plot 2 | 1MC06-CEK-EV-FRM-CS03_CL05-000048 | tbc | 2024-07-23 |  | 2024-07-29 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600145 | Issue found | Incorrect com_type found . Send back to team on 25 July 24. | [7 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 4 | 1
| 226.1 | HS2-000025B21 | A43 Oxford Road Re-alignment | 1MC07-ASC-HW-FRM-CS07_CL12-000011-ACBOS | P01 | 2024-07-23 | 2024-07-24 | 2024-07-25 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600095 | No issues | Com_typs sent back 23-jul-24 | 2024-07-24 | [6 empty] | 10 - Complete | Lee | zakaria.khabouze@setec.com | 1 | 1 | 1
| 226.1 | HS2-000025B20 | Footpath BD8 Diversion | 1MC07-ASC-HW-FRM-CS07_CL12-000018-ACBOS | P01 | 2024-07-23 | 2024-07-24 | 2024-07-25 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600096 | No issues | Com_Typ, DsgnLf, some confirmations of zero values - sent back 23-jul-24 | 2023-07-24 | [6 empty] | 10 - Complete | Lee | zakaria.khabouze@setec.com | 1 | 1 | 1
| 226.1 | HS2-000025B1Z | Maintenance Access Road to Whitfield ATS and Pond (Off A43 Oxford Road West) | 1MC07-ASC-HW-FRM-CS07_CL12-000015-ACBOS | P01 | 2024-07-23 | 2024-07-23 | 2024-07-24 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600118 | No issues | [8 empty] | 10 - Complete | Lee | zakaria.khabouze@setec.com | 1 | 0 | 0
| 226.1 | HS2-00002Y89A | Brackley South Cuttting – Field Access (off A43 Oxford Road) | 1MC07-ASC-HW-FRM-CS07_CL12-000035-ACBOS | P01 | 2024-07-23 | 2024-07-23 | 2024-07-26 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600166 | No issues | [8 empty] | 10 - Complete | Lee | zakaria.khabouze@setec.com | 3 | 0 | 0
| 226.1 | HS2-00002C3YF | A43 Oxford Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL12-000005-ACBOS | P01 | 2024-07-23 | 2024-07-24 | 2024-07-25 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600094 | No issues | single DsgnFlw set as Zero - sent back 24-jul-24 | 24-jul-24 - Intentional Zero value | [6 empty] | 10 - Complete | Lee | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 1 | 1 | 1
| 226.1 | HS2-00002BVJR | C3.L.7 Catchment | 1MC07-ASC-DR-FRM-CS07_CL12-000025-ACBOS | P01 | 2024-07-23 | 2024-07-25 | 2024-07-26 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600117 | No issues | DT reworking file 24-jul-24 | 2024-07-24 | DT revised overnight | 2024-07-25 |  |  |  |  | 10 - Complete | Lee | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 1 | 2 | 2
| 226.1 | HS2-00002N7WZ | Brackley South Cutting-Ancillary Culvert 096-AC1 | 1MC07-ASC-DR-FRM-CS07_CL12-000074-ACBOS | P01 | 2024-07-23 | 2024-07-25 | 2024-07-26 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600046 | No issues | DT reworking file 24-jul-24 | 2024-07-24 | DT revised overnight | 2024-07-25 |  |  |  |  | 10 - Complete | Lee | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 1 | 2 | 2
| 226.1 | HS2-00002N7X0 | Brackley South Cutting-Ancillary Culvert 096-AC2 | 1MC07-ASC-DR-FRM-CS07_CL12-000075-ACBOS | P01 | 2024-07-23 | 2024-07-25 | 2024-07-26 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600045 | No issues | DT reworking file 24-jul-24 | 2024-07-24 | DT revised overnight | 2024-07-25 |  |  |  |  | 10 - Complete | Lee | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 1 | 2 | 2
3 | 212.5 | HS2-00003H07A | Aylesbury North Cutting Acess Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL18-000086-ACBOS | P01 | 2024-07-23 | 2024-07-23 | 2024-08-06 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600157 | [9 empty] | 10 - Complete | Supriyan | Rutherford, Max <max.rutherford@arcadis.com> | 10 | 0 | 0
3 | 212.5 | HS2-000035Q98 | Oxford Road Embankment Ditch Slab No.10 | 1MC06-ASC-CV-FRM-CS04_CL19-000056-ACBOS | P01 | 2024-07-23 | 2024-07-23 | 2024-08-05 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600104 | [9 empty] | 10 - Complete | Supriyan | Rutherford, Max <max.rutherford@arcadis.com> | 9 | 0 | 0
10 | 233.01-3 | HS2-00003FV0K | Chipping Warden Green Tunnel Access Stairs CH.109.810 | 1MC07-ASC-CV-FRM-CS07_CL13-000141 - ACBOS | P01 | 2024-07-25 | 2024-08-06 | 2024-08-08 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600050 |  | Partial ACBOS, send back on 05-Aug-2024 |  | IFC vs uniclass issue,sent back on 6-Aug-2024 | [5 empty] | 10 - Complete | Supriyan | Martin, Joel <Joel.Martin@arcadis.com> | 2 | 2 | 12
10 | 233.01-3 | HS2-00003B93W | Chipping Warden Green Tunnel Access Stair CH.110.025 | 1MC07-ASC-CV-FRM-CS07_CL13-000139 - ACBOS | P01 | 2024-07-25 | 2024-08-06 | 2024-08-09 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600052 |  | Com_type, Uniclass Isues, send back on 05-Aug-2024 |  | IFC vs uniclass issue,sent back on 6-Aug-2024 | [5 empty] | 10 - Complete | Supriyan | Martin, Joel <Joel.Martin@arcadis.com> | 3 | 2 | 12
| 237.05 | HS2-00003D82S | Ladbroke Grove Cutting | 1MC07-ASC-CV-FRM-CS07_CL23-000061-ACBOS | P02 | 2024-07-25 | 2024-07-25 | 2024-08-02 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600155 | No issues | [8 empty] | 10 - Complete | Lee | PATIL, APOORVA <apoorva.patil@arcadis.com> | 6 | 0 | 0
| 227 | HS2-00002NNHW | Brackley Culvert Watercourse Diversion | 1MC07-ASC-DR-FRM-CS07_CL12-000082-ACBOS | P01 | 2024-07-25 | 2024-07-25 | 2024-08-02 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600042 | No issues | [8 empty] | 10 - Complete | Lee | Tiwari, Devendrakumar <devendrakumar.tiwari@arcadis.com> | 6 | 0 | 0
| 207.2 | HS2-00002CT4W | C2.L.22 Catchment | 1MC06-ASC-DR-FRM-CS04_CL18-000003-ACBOS | P03 | 2024-07-25 | 2024-08-07 | 2024-08-27 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600081 |  | OSGB, uniclass and other issus, send back on 05-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Cordero, Jan <Jan.Cordero@arcadis.com> | 13 | 1 | 13
| 207.2 | HS2-00002CW1B | Oat Close Bridleway (SBH/19) Drainage System | 1MC06-ASC-DR-FRM-CS04_CL18-000015-ACBOS | P03 | 2024-07-25 | 2024-08-06 | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600025 |  | Uniclass conflict, send back on 05-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Cordero, Jan <Jan.Cordero@arcadis.com> | 3 | 1 | 12
| 205.3 | HS2-00002CW1F | Standalls Farm Access (SMA 16) Drainage System | 1MC06-ASC-DR-FRM-CS04_CL18-000013-ACBOS | P05 | 2024-07-25 | 2024-08-06 | 2024-08-13 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600026 |  | Uniclass conflict, send back on 05-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Cordero, Jan <Jan.Cordero@arcadis.com> | 5 | 1 | 12
| 234.02-2 | HS2-00002WUQF | Highfurlong Brook Viaduct Planting-East Plot 1 | 1MC07-ASC-EV-REP-CS07_CL14-000019 | P01 | 2024-07-26 | 2024-07-26 | 2024-08-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600121 | No issues | [8 empty] | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 5 | 0 | 0
| 234.02-2 | HS2-00002WUQG | Highfurlong Brook Viaduct Planting-East Plot 2 | 1MC07-ASC-EV-REP-CS07_CL14-000020 | P01 | 2024-07-26 | 2024-07-26 | 2024-08-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600122 | No issues | [8 empty] | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 5 | 0 | 0
| 234.02-2 | HS2-00002WUQH | Highfurlong Brook Viaduct Planting-West Plot 1 | 1MC07-ASC-EV-REP-CS07_CL14-000021 | P01 | 2024-07-26 | 2024-07-26 | 2024-08-08 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600123 | No issues | [8 empty] | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 9 | 0 | 0
| 234.02-2 | HS2-00002WUQJ | Highfurlong Brook Viaduct Planting-West Plot 2 | 1MC07-ASC-EV-REP-CS07_CL14-000022 | P01 | 2024-07-26 | 2024-07-26 | 2024-08-08 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600124 | No issues |  |  | ZZ-zz CAD layer set as uniclass | [5 empty] | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 9 | 1 | 0
| 234.02-2 | HS2-00002WUQK | Highfurlong Brook Embankment Planting-East Plot 1 | 1MC07-ASC-EV-REP-CS07_CL14-000009 | P01 | 2024-07-26 | 2024-07-26 | 2024-08-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600126 | issues found | OSGB issues, send back on 02-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 5 | 1 | 0
| 234.02-2 | HS2-00002WUQL | Highfurlong Brook Embankment Planting-East Plot 2 | 1MC07-ASC-EV-REP-CS07_CL14-000013 | P01 | 2024-07-26 | 2024-07-26 | 2024-08-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600127 | [9 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 5 | 0 | 0
| 234.02-2 | HS2-00002WUQM | Highfurlong Brook Embankment Planting-West Plot 1 | 1MC07-ASC-EV-REP-CS07_CL14-000010 | P01 | 2024-07-26 | 2024-07-26 | 2024-08-08 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600128 | No issues | Wrong Angleslp, send back on 02-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 9 | 1 | 0
| 234.02-2 | HS2-00002WUQN | Highfurlong Brook Embankment Planting-West Plot 2 | 1MC07-ASC-EV-REP-CS07_CL14-000011 | P01 | 2024-07-26 | 2024-07-26 | 2024-08-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600129 | Issue found | OSGB issues found, send back on 2-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 5 | 1 | 0
| 234.02-2 | HS2-00002WUQP | Highfurlong Brook Embankment Planting-West Plot 3 | 1MC07-ASC-EV-REP-CS07_CL14-000012 | P01 | 2024-07-26 | 2024-07-26 | 2024-08-02 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600130 | [9 empty] | 10 - Complete | Supriyan | Clarke, Philip <philip.clarke@arcadis.com> | 5 | 0 | 0
| 229.01-1 | HS2-00002HQ9E | Welsh Road Mitigation Earthworks | 1MC07-ASC-GT-FRM-CS07_CL25-000007-ACBOS | P01 | 2024-07-26 | 2024-08-09 | 2024-08-13 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600013 | No issues | Uniclass issue and sdslp issue, sent back on 06-Aug-2024 | [7 empty] | 10 - Complete | Lee | Jonathan Clifford <jocd@cowi.com> | 2 | 1 | 14
| 229.01-1 | HS2-000037YM1 | Greatworth North Cutting Transition Earthworks to South Portal | 1MC07-ASC-GT-FRM-CS07_CL12-000030-ACBOS | P01 | 2024-07-26 | 2024-08-09 | 2024-08-16 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600301 | No issues | ACBOS workflow is not completed, sdslp not in format, Not in use uniclass ID used. Sent back on 08-Aug-2024 |  | GFL -Sdslp syntax incorrect, Uniclass issue unresolved. 13-Aug-24 | 2024-08-15 |  |  |  |  | 10 - Complete | Lee | Jonathan Clifford <jocd@cowi.com> | 5 | 2 | 14
| 204.2-2 | HS2-00002CT4R | Footpath SMA-5 Diversion | 1MC06-ASC-HW-FRM-CS03_CL17-000019-ACBOS | P02 | 2024-07-26 | 2024-08-05 | 2024-08-13 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600013 | Issue found | 0's values in Rebar Volume & Density & None in StrctrlT,ThrdPrty , Gtxtl ,Rd_Nmbr , Send back to team on 30 July 24. |  | L3 assets ammended by EKFB on 30 july 24. Put on hold as suggested by DT. | [5 empty] | 10 - Complete | Rakesh | Jenkins, Joshua <joshua.jenkins@arcadis.com> | 6 | 2 | 10
| 204.2-2 | HS2-00002CT4H | Stoke Mandeville Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS03_CL17-000019-ACBOS | P01 | 2024-07-26 | 2024-08-14 | 2024-08-27 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600052 |  | Uniclass and Com_type issues, sent back on 12-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Jennifer McKay <JRMY@COWI.COM> | 8 | 1 | 19
| 204.2-2 | HS2-00002CT4D | Stoke Mandeville Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS03_CL17-000021-ACBOS | P01 | 2024-07-26 | 2024-08-14 | 2024-08-28 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600048 |  | Com_type and OSGB issues, sent back on 12-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Jennifer McKay <JRMY@COWI.COM> | 9 | 1 | 19
3 | 212.5 | HS2-00002VK4B | Stoke Mandeville Bypass North Pedestrian Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL18-000054-ACBOS | P01 | 2024-07-26 | 2024-08-06 | 2024-08-08 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600162 | [9 empty] | 10 - Complete | Supriyan | Sangalang, Orlando <orlando.sangalang@arcadis.com> | 2 | 0 | 11
3 | 212.5 | HS2-00002VK4A | Stoke Mandeville Bypass Vehicular Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL18-000053-ACBOS | P01 | 2024-07-26 | 2024-08-06 | 2024-08-08 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600161 | [9 empty] | 10 - Complete | Supriyan | Sangalang, Orlando <orlando.sangalang@arcadis.com> | 2 | 0 | 11
| 229.01-1 | HS2-00002HCE5 | Greatworth Green Tunnel Low Mileage Portal Mitigation Earthworks | 1MC07-ASC-GT-FRM-CS07_CL25-000011-ACBOS | P01 | 2024-07-29 | 2024-08-09 | 2024-08-14 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600018 | No issues | ACBOS workflow is not completed, OSGB issues, sdslp not in format, send back on 08-Aug-2024 | [7 empty] | 10 - Complete | Lee | Jonathan Clifford <jocd@cowi.com> | 3 | 1 | 11
21 | 214.07 | HS2-00002CT81 | Maintenance Access Road to Pond (Connecting CAG 2 and GUN 28) | 1MC06-ASC-HW-FRM-CS05-000027-ACBOS | P07 | 2024-07-29 | 2024-07-29 | 2024-08-08 |  | 1MC06-CEK-IM-DAT-CS05-600285 | [9 empty] | 10 - Complete | Rakesh | Quirante, Dan <dan.quirante@arcadis.com> | 8 | 0 | 0
10 | 233.01-3 | HS2-00002CX3P | Culworth Road Bridleway and Chipping Warden South Portal Access Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL26-000062-ACBOS | P01 | 2024-07-30 |  | 2024-08-13 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600064 | [9 empty] | 10 - Complete | Supriyan | M, Nischitha <nischitha.m@arcadis.com> | 10 | 0
| 214.02-2 | HS2-000020NH1 | Edgcott Road Realignment | 1MC06-ASC-HW-FRM-CS05-000019-ACBOS | P01 | 2024-07-30 |  | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS05-600125 | No issues | KRB with 1 GrossVolume set as Zero - sent 7-aug-24 | 2024-08-08 | [6 empty] | 10 - Complete | Lee | Ollier, James <james.ollier@arcadis.com> | 8 | 1
| 229.03 | HS2-00003124E | Greatworth North Embankment and Cutting Access Stairs | 1MC07-ASC-CV-FRM-CS07_CL12-000111-ACBOS | P02 | 2024-07-30 | 2024-08-07 | 2024-08-09 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600288 |  | uniclass_id issue sent back on 06-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Behera, Latika <latika.behera@arcadis.com> | 2 | 1 | 8
| 213.08 | HS2-00003CPWX | Doddershall Embankment Planting Plot 1 | 1MC06-CEK-EV-FRM-CS05-600002 | P01 | 2024-07-30 |  | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS05-600211 | No issues | MPDT wont load |  | Rebuild required using Partha's template. | 2024-08-06 |  |  |  |  | 10 - Complete | Lee | CHILLET Sebastien <sebastien.chillet@setec.com> | 8 | 2
| 213.08 | HS2-00003CPWY | Doddershall Embankment Planting Plot 2 | 1MC06-CEK-EV-FRM-CS05-600003 | P01 | 2024-07-30 |  | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS05-600212 | Issue found | Upload failed in L3 DB , issue raised to Dev Team | [7 empty] | 10 - Complete | Rakesh | CHILLET Sebastien <sebastien.chillet@setec.com> | 8 | 1
| 213.08 | HS2-00003CPWZ | Doddershall Embankment Planting Plot 3 | 1MC06-CEK-EV-FRM-CS05-600004 | P01 | 2024-07-30 |  | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS05-600213 | Issue found | Upload failed in L3 DB , issue raised to Dev Team | [7 empty] | 10 - Complete | Rakesh | CHILLET Sebastien <sebastien.chillet@setec.com> | 8 | 1
| 213.08 | HS2-00003CPX1 | Doddershall Embankment Planting Plot 4 | 1MC06-CEK-EV-FRM-CS05-600005 | P01 | 2024-07-30 |  | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS05-600214 | Issue found | Upload failed in L3 DB , issue raised to Dev Team | [7 empty] | 10 - Complete | Rakesh | CHILLET Sebastien <sebastien.chillet@setec.com> | 8 | 1
| 213.08 | HS2-00003CPX2 | Doddershall Embankment Planting Plot 5 | 1MC06-CEK-EV-FRM-CS05-600006 | P01 | 2024-07-30 |  | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS05-600215 | Issue found | Upload failed in L3 DB , issue raised to Dev Team | [7 empty] | 10 - Complete | Rakesh | CHILLET Sebastien <sebastien.chillet@setec.com> | 8 | 1
| 213.08 | HS2-00003CPX3 | Doddershall Embankment Planting Plot 6 | 1MC06-CEK-EV-FRM-CS05-600007 | P01 | 2024-07-30 |  | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS05-600216 | Issue found | Upload failed in L3 DB , issue raised to Dev Team | [7 empty] | 10 - Complete | Rakesh | CHILLET Sebastien <sebastien.chillet@setec.com> | 8 | 1
| 213.08 | HS2-00003CPX4 | Doddershall Embankment Planting Plot 7 | 1MC06-CEK-EV-FRM-CS05-600008 | P01 | 2024-07-30 |  | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS05-600217 | No issues | Rebuild required using Partha's template. | 2024-08-06 | [6 empty] | 10 - Complete | Lee | CHILLET Sebastien <sebastien.chillet@setec.com> | 8 | 1
| 213.08 | HS2-00003CPX6 | Doddershall Embankment Planting Plot 8 | 1MC06-CEK-EV-FRM-CS05-600009 | P01 | 2024-07-30 |  | 2024-08-12 |  | 1MC06-CEK-IM-DAT-CS05-600218 | No issues | Rebuild required using Partha's template. | 2024-08-06 | [6 empty] | 10 - Complete | Lee | CHILLET Sebastien <sebastien.chillet@setec.com> | 9 | 1
| 213.08 | HS2-00003CPX7 | Doddershall Embankment Planting Plot 9 | 1MC06-CEK-EV-FRM-CS05-600010 | P01 | 2024-07-30 |  | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS05-600219 | No issues | Rebuild required using Partha's template. | 2024-08-06 | [6 empty] | 10 - Complete | Lee | CHILLET Sebastien <sebastien.chillet@setec.com> | 8 | 1
| 213.06 | HS2-00002Z6NM | Footpath QUA 26 Diversion Crossing | 1MC06-ASC-CV-FRM-CS05-000067-ACBOS | P02 | 2024-07-30 | 2024-08-19 | 2024-08-20 |  | 1MC06-CEK-IM-DAT-CS05-600166 |  | ACBOS PCRA is pending, send back on 08-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Thambi, Albin <albin.thambi@arcadis.com> | 1 | 1 | 20
3 | 212.5 | HS2-000035Q94 | Oxford Road Embankment Ditch Slab No.6 | 1MC06-ASC-CV-FRM-CS04_CL19-000061-ACBOS | P01 | 2024-07-30 | 2024-07-30 | 2024-08-13 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600083 | [9 empty] | 10 - Complete | Rakesh | Alagundi, Shreyas <shreyas.alagundi@arcadis.com> | 10 | 0 | 0
3 | 212.5 | HS2-00003KFPN | Aylesbury South Cutting Access Ditch Slab No.4 | 1MC06-ASC-CV-FRM-CS04_CL18-000091-ACBOS | P01 | 2024-07-31 |  | 2024-08-14 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600167 | Issue found | Com_Ref_Number value are missing. Send Back to team on 09 Aug 24. | [7 empty] | 10 - Complete | Rakesh | Rutherford, Max <max.rutherford@arcadis.com> | 10 | 1
3 | 212.5 | HS2-00003JKXT | Aylesbury South Cutting Access Ditch Slab No.3 | 1MC06-ASC-CV-FRM-CS04_CL18-000089-ACBOS | P01 | 2024-07-31 |  | 2024-08-14 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600168 | [9 empty] | 10 - Complete | Rakesh | Rutherford, Max <max.rutherford@arcadis.com> | 10 | 0
| UFDR 204.B | HS2-000020CEL | CSO-02-7201 | 1MC06-ASC-UT-FRM-CS03_CL17-000021-ACBOS | P01 | 2024-08-01 | 2024-08-29 | 2024-09-03 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600037 | No issues | old schema Asset Description_2 incomplete | 2024-08-30 | [6 empty] | 10 - Complete | Lee | Anthony Payne <aype@cowi.com> | 3 | 1 | 28
| 230.01-3 | HS2-00002EKZV | Highfurlong Brook Viaduct Planting-East Plot 1 | 1MC07-ASC-EV-REP-CS07_CL26-000011 | P01 | 2024-08-01 |  | 2024-08-05 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600160 | No issues | chainage values are incorrect - 2-aug-24 - Fixed in house for speed. Dt update source | [7 empty] | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 2 | 1
21 | 214.07 | HS2-000031GXR | Grendon Underwood MAS Ditch Crossing-MAS | 1MC06-ASC-CV-FRM-CS05-000101-ACBOS | P01 | 2024-08-01 | 2024-08-20 | 2024-08-22 |  | 1MC06-CEK-IM-DAT-CS05-600279 |  | Com_type and other issues, send back on 12-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Max Hepburn <mxhn@cowi.com> | 2 | 1 | 19
21 | 214.07 | HS2-00002Z3NJ | CAG/2 Realignment Pedestrian Crossing-Pedestrian | 1MC06-ASC-CV-FRM-CS05-000078-ACBOS | P01 | 2024-08-01 | 2024-08-20 | 2024-08-23 |  | 1MC06-CEK-IM-DAT-CS05-600281 |  | Com_type and other issues, send back on 12-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Max Hepburn <mxhn@cowi.com> | 3 | 1 | 19
21 | 214.07 | HS2-00002VK3Y | Greatmoor Crossing MAS-MAS-75+670 | 1MC06-ASC-CV-FRM-CS05-000054-ACBOS | P01 | 2024-08-01 | 2024-08-20 | 2024-08-21 |  | 1MC06-CEK-IM-DAT-CS05-600284 |  | Com_type and other issues, send back on 12-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Max Hepburn <mxhn@cowi.com> | 1 | 1 | 19
3 | 212.5 | HS2-00003H079 | Aylesbury South Cutting Access Ditch Slab No.2 | 1MC06-ASC-CV-FRM-CS04_CL18-000088-ACBOS | P01 | 2024-08-01 |  | 2024-08-13 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600158 | [9 empty] | 10 - Complete | Supriyan | Rutherford, Max <max.rutherford@arcadis.com> | 8 | 0
| UFDR 238.H | HS2-000020CKP | CNO-124-008HV | 1MC07-ASC-UT-FRM-CS07_CL24-000019-ACBOS | P02 | 2024-08-06 |  | 2024-08-09 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600072 | [9 empty] | 10 - Complete | Lee | T, Sithrubi <sithrubi.t@arcadis.com> | 3 | 0
| UFDR 204.A | HS2-000020CEA | CSO-02-1206P | 1MC06-ASC-UT-FRM-CS03_CL17-000026-ACBOS | P01 | 2024-08-06 | 2024-08-06 | 2024-08-13 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600033 | No issues | [8 empty] | 10 - Complete | Lee | Anthony Payne <aype@cowi.com> | 5 | 0 | 0
| UFDR 202.E | HS2-00002NHZ4 | CSO-02-6201P | 1MC06-ASC-UT-FRM-CS03_CL06-000107-ACBOS | P01 | 2024-08-06 | 2024-08-06 | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600060 | No issues | identical chainages - sent back 7-Aug-24 | 2024-08-08 | [6 empty] | 10 - Complete | Lee | Anthony Payne <aype@cowi.com> | 3 | 1 | 0
10 | 233.01-3 | HS2-0000386TE | C3.T.83 Catchment | 1MC07-ASC-DR-FRM-CS07_CL26-000114-ACBOS | P01 | 2024-08-06 | 2024-08-14 | 2024-08-20 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600163 |  | Asset count mismatch with smart form.Send back to team on 14-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | M, Nischitha <nischitha.m@arcadis.com> | 4 | 1 | 8
| 202.4-2 | HS2-00002WUK2 | Small Dean South Embankment Planting - East Plot 1 | 1MC06-CEK-EV-FRM-CS03_CL05-000012 | P01 | 2024-08-06 |  | 2024-08-08 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600176 | No issues | [8 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 2 | 0
| 202.4-2 | HS2-00002WUK3 | Small Dean South Embankment Planting - East Plot 2 | 1MC06-CEK-EV-FRM-CS03_CL05-000013 | P01 | 2024-08-06 |  | 2024-08-08 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600177 | No issues | Zz_80_85 - Trees & Planting CAD layer used | fixed in house with DT call. DT updating PW file in background. | [6 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 2 | 1
| 202.4-2 | HS2-00002WUK4 | Small Dean South Embankment Planting - East Plot 3 | 1MC06-CEK-EV-FRM-CS03_CL05-000014 | P01 | 2024-08-06 |  | 2024-08-08 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600178 | No issues | [8 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 2 | 0
| 202.4-2 | HS2-00002WUK5 | Small Dean South Embankment Planting - East Plot 4 | 1MC06-CEK-EV-FRM-CS03_CL05-000015 | P01 | 2024-08-06 |  | 2024-08-08 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600179 | No issues | Zz_80_85 - Trees & Planting CAD layer used | fixed in house with DT call. DT updating PW file in background. | [6 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 2 | 1
| 202.4-2 | HS2-00002WUK6 | Small Dean South Embankment Planting - West Plot 1 | 1MC06-CEK-EV-FRM-CS03_CL05-000016 | P01 | 2024-08-06 |  | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600180 | No issues | [8 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 3 | 0
| 202.4-2 | HS2-00002WUK7 | Small Dean South Embankment Planting - West Plot 2 | 1MC06-CEK-EV-FRM-CS03_CL05-000017 | P01 | 2024-08-06 |  | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600181 | No issues | [8 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 3 | 0
| 202.4-2 | HS2-00002WUK8 | Small Dean South Embankment Planting - West Plot 3 | 1MC06-CEK-EV-FRM-CS03_CL05-000018 | P01 | 2024-08-06 |  | 2024-08-09 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600182 | No issues | Zz_80_85 - Trees & Planting CAD layer used | fixed in house with DT call. DT updating PW file in background. | [6 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 3 | 1
| 202.4-2 | HS2-00002WUK9 | Small Dean South Embankment Planting - West Plot 4 | 1MC06-CEK-EV-FRM-CS03_CL05-000019 | P01 | 2024-08-06 |  | 2024-08-08 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600183 | No issues | [8 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 2 | 0
| 202.4-2 | HS2-00002WUKA | Small Dean South Embankment Planting - West Plot 5 | 1MC06-CEK-EV-FRM-CS03_CL05-000020 | P01 | 2024-08-06 |  | 2024-08-08 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600184 | No issues | Zz_80_85 - Trees & Planting CAD layer used | fixed in house with DT call. DT updating PW file in background. | [6 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com> | 2 | 1
| 234.05 | HS2-000001375 | Lower Boddington Embankment Group | 1MC07-ASC-CV-FRM-CS07_CL14-000041-ACBOS | P01 | 2024-08-07 | 2024-08-20 | 2024-08-21 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600090 |  | ACBOS workflow is not completed, send back on 14-Aug-2024 |  | Com_Type issus and other 0's. Send back on 16-Aug- 2024 | [5 empty] | 10 - Complete | Supriyan | Afsal, Muhammed <muhammed.afsal@arcadis.com> | 1 | 2 | 13
| 204.2-2 | HS2-00002CT4M | C2.L.19 Catchment | 1MC06-ASC-DR-FRM-CS03_CL17-000003-ACBOS | P01 | 2024-08-07 | 2024-08-07 | 2024-08-14 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600010 | No issues | [8 empty] | 10 - Complete | Lee | Ka, Srinatha <srinatha.ka@arcadis.com> | 5 | 0 | 0
| 204.2-2 | HS2-00002EKX6 | Risborough Road Ecological Mitigation Site (A) | 1MC06-ASC-EV-FRM-CS03_CL17-000002-ACBOS | P01 | 2024-08-07 | 2024-08-20 | 2024-08-22 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600122 | No issues | PND Uniclass withdrawn - sent back 14-Aug-24 |  |  | revised 20-aug-24 |  |  |  |  | 10 - Complete | Lee | Ka, Srinatha <srinatha.ka@arcadis.com> | 2 | 1 | 13
| 204.2-2 | HS2-00002EKX5 | Risborough Road Ecological Mitigation Site (B) | 1MC06-ASC-EV-FRM-CS03_CL17-000004-ACBOS | P01 | 2024-08-07 | 2024-08-20 | 2024-08-22 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600123 | No issues | 2d and point Environmental assets in Smartforms not icluded in modelled dataset. - sent back for clarification. - 13-Aug-24. | 2024-08-14 | Withdrawn Uniclass issue - sent back 15-Aug-24 | revised 20-aug-24 |  |  |  |  | 10 - Complete | Lee | Ka, Srinatha <srinatha.ka@arcadis.com> | 2 | 2 | 13
| 204.2-2 | HS2-00002ZPP6 | Stoke Mandeville South Embankment Flood Compensation Area - 2R | 1MC06-ASC-DR-FRM-CS03_CL17-000076-ACBOS | P01 | 2024-08-07 | 2024-08-20 | 2024-08-22 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600124 | No issues | GFL & PND Uniclass withdrawn - Sent back 14-Aug-24 |  |  | revised 20-aug-24 |  |  |  |  | 10 - Complete | Lee | Ka, Srinatha <srinatha.ka@arcadis.com> | 2 | 1 | 13
| 204.2-2 | HS2-00003E24P | Stoke Mandeville South Embankment Flood Compensation Area - 2L | 1MC06-ASC-DR-FRM-CS03_CL17-000075-ACBOS | P01 | 2024-08-07 |  | 2024-08-22 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600125 | No issues |  |  |  | revised 20-aug-24 |  |  |  |  | 10 - Complete | Lee | Ka, Srinatha <srinatha.ka@arcadis.com> | 11 | 0
| 204.2-2 | HS2-00003E24R | Stoke Mandeville South Embankment Flood Compensation Area – 3R | 1MC06-ASC-DR-FRM-CS03_CL17-000077-ACBOS | P01 | 2024-08-07 | 2024-08-20 | 2024-08-22 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600126 | No issues | Old schema - sent back - 13-Aug-24 |  |  | revised 20-aug-24 |  |  |  |  | 10 - Complete | Lee | Ka, Srinatha <srinatha.ka@arcadis.com> | 2 | 1 | 13
| 214.1 | HS2-00003CPYM | SWBMS HS2 NR Fence | 1MC06-CEK-CV-FRM-CS05-600003 | P01 | 2024-08-08 | 2024-08-27 | 2024-08-28 |  | 1MC06-CEK-IM-DAT-CS05-600181 | Issue found | MPDT file format and blank cells issue , send back to team on 13 Aug 24. |  | OSGB coordinate tolerance issue , send back to team on 22-Aug-24. | 2024-08-28 | Still OSGB coordinate tolerance issue , send back to team on 28-Aug-24. |  |  |  | 10 - Complete | Rakesh | Trine Norsk <trno@cowi.com> | 1 | 3 | 19
| 213.08 | HS2-00002VK43 | P-RAI-0724 Ditch Crossing MAS | 1MC06-CEK-CV-FRM-CS05-000055 | P01 | 2024-08-08 |  | 2024-08-21 |  | 1MC06-CEK-IM-DAT-CS05-600189 | Issue found | Most of the Columns are left blank. Send back to team on 13 -Aug -24. | 14 -Aug -24. | [6 empty] | 10 - Complete | Rakesh | Fowler, Alex <alex.fowler@arcadis.com> | 9 | 1
| 213.08 | HS2-00002VK42 | P-RAI-0725 Ditch Crossing MAS | 1MC06-CEK-CV-FRM-CS05-000056 | P01 | 2024-08-08 | 22-Aug-24. | 2024-08-23 |  | 1MC06-CEK-IM-DAT-CS05-600190 | Issue found | Most of the Columns are left blank. Send back to team on 13 -Aug -24. | 14 -Aug -24. | OSGB coordinate tolerance issue , send back to team on 21-Aug-24. | 22-Aug-24. |  |  |  |  | 10 - Complete | Rakesh | Fowler, Alex <alex.fowler@arcadis.com> | 11 | 2 | #VALUE!
| 213.08 | HS2-00003H6PF | P-RAI-0724 Ditch Pedestrian Crossing | 1MC06-CEK-CV-FRM-CS05-000057 | P01 | 2024-08-08 | 2024-08-20 | 2024-08-21 |  | 1MC06-CEK-IM-DAT-CS05-600222 | No issues | Withdrawn Uniclass used. Insitu / precast conflicting data 2 UAID with incorrect codes Ss_30_16_10_16 - sent back - 15-Aug-24 | revised 20-Aug-24 | [6 empty] | 10 - Complete | Lee | Fowler, Alex <alex.fowler@arcadis.com> | 1 | 1 | 12
| 213.08 | HS2-000031247 | Footpath QUA/26 Diversion Crossing 2 (HS2) | 1MC06-CEK-CV-FRM-CS05-000049 | P01 | 2024-08-08 | 2024-08-20 | 2024-08-21 |  | 1MC06-CEK-IM-DAT-CS05-600203 | No issues | 2 UAID with incorrect codes - sent back 15-Aug-24 | revised 20-Aug-24 | [6 empty] | 10 - Complete | Lee | Fowler, Alex <alex.fowler@arcadis.com> | 1 | 1 | 12
| 213.08 | HS2-00002VK3X | Doddershall 4 Culvert Headwall MAS (HS2) | 1MC06-CEK-CV-FRM-CS05-000050 | P01 | 2024-08-08 | 2024-08-20 | 2024-08-21 |  | 1MC06-CEK-IM-DAT-CS05-600198 | No issues | Withdrawn Uniclass used. 2 UAID with incorrect codes Ss_30_16_10_16 - sent back - 15-Aug-24 | revised 20-Aug-24 | [6 empty] | 10 - Complete | Lee | Fowler, Alex <alex.fowler@arcadis.com> | 1 | 1 | 12
| 213.08 | HS2-00002Z6NL | Doddershall 1 Crossing MAS | 1MC06-CEK-CV-FRM-CS05-000051 | P01 | 2024-08-08 | 2024-08-20 | 2024-08-21 |  | 1MC06-CEK-IM-DAT-CS05-600186 | No issues | Non integer values 2 UAID with incorrect codes Ss_30_16_10_16 - sent back - 15-Aug-24 | revised 20-Aug-24 | [6 empty] | 10 - Complete | Lee | Fowler, Alex <alex.fowler@arcadis.com> | 1 | 1 | 12
| 212.6 | HS2-00002CT54 | Aylesbury South Cutting Noise Barrier Line | 1MC06-CEK-CV-FRM-CS04_CL18-000001 | P04 | 2024-08-08 | 2024-09-03 | 2024-09-05 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600066 | No issues | Identical chainages, Many missing attributes for Com_RfrncNmbr, NetVolume etc. - sent back 9-Aug-24 | revised 20-Aug-24 | EmbdddLngth data type issue, and other queries sent on 22-Aug-2024 |  | Start Chainage > End Chainage , sent back on 29-Aug-2024 |  |  |  | 10 - Complete | Supriyan | Trine Norsk <trno@cowi.com> | 2 | 3 | 26
| 212.6 | HS2-00002CT5B | Aylesbury Embankment Noise Barrier Line | 1MC06-CEK-CV-FRM-CS04_CL18-000002 | P04 | 2024-08-08 | 2024-09-04 | 2024-09-09 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600019 | No issues | Identical chainages, Many missing attributes for Com_RfrncNmbr, NetVolume etc. - sent back 9-Aug-24 | revised 20-Aug-24 | EmbdddLngth data type issue, and other queries sent on 22-Aug-2024 |  | Start Chainage > End Chainage , sent back on 30-Aug-2024 during REVIEW |  |  |  | 10 - Complete | Lee | Trine Norsk <trno@cowi.com> | 3 | 3 | 27
| 212.6 | HS2-00002CT5J | Aylesbury North Cutting Noise Barrier Line | 1MC06-CEK-CV-FRM-CS04_CL18-000003 | P05 | 2024-08-08 | 2024-08-28 | 2024-08-29 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600034 | No issues | Identical chainages, Many missing attributes for Com_RfrncNmbr, NetVolume etc. - sent back 9-Aug-24 | revised 20-Aug-24 | EmbdddLngth data type issue, and other queries sent on 22-Aug-2024 | [5 empty] | 10 - Complete | Supriyan | Trine Norsk <trno@cowi.com> | 1 | 2 | 20
| 212.6 | HS2-00002CT5R | Oxford Road Embankment Noise Barrier Line | 1MC06-CEK-CV-FRM-CS04_CL19-000001 | P05 | 2024-08-08 | 2024-08-28 | 2024-09-02 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600029 | No issues | Identical chainages, Many missing attributes for Com_RfrncNmbr, NetVolume etc. - sent back 9-Aug-24 | revised 20-Aug-24 | EmbdddLngth data type issue, and other queries sent on 22-Aug-2024 | [5 empty] | 10 - Complete | Supriyan | Trine Norsk <trno@cowi.com> | 3 | 2 | 20
| 212.6 | HS2-00002CT5V | Whaddon Hill Cutting Noise Barrier Line | 1MC06-CEK-CV-FRM-CS04_CL19-000002 | P05 | 2024-08-08 | 2024-09-04 | 2024-09-09 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600038 | No issues | Identical chainages, Many missing attributes for Com_RfrncNmbr, NetVolume etc. - sent back 9-Aug-24 | revised 20-Aug-24 | EmbdddLngth data type issue, and other queries sent on 22-Aug-2024 |  | OSGB Issues, sent back on 29-Aug-2024 |  |  |  | 10 - Complete | Lee | Trine Norsk <trno@cowi.com> | 3 | 3 | 27
| 212.6 | HS2-00002CT5Y | Thame Valley South Embankment Noise Barrier Line | 1MC06-CEK-CV-FRM-CS04_CL19-000050 | P01 | 2024-08-08 | 2024-08-27 | 2024-08-29 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600040 | No issues | Identical chainages, Many missing attributes for Com_RfrncNmbr, NetVolume etc. - sent back 9-Aug-24 | revised 20-Aug-24 | EmbdddLgnth to be Integer value. Sent back 21-Aug-24 | [5 empty] | 10 - Complete | Supriyan | Trine Norsk <trno@cowi.com> | 2 | 2 | 19
10 | 233.01-3 | HS2-00003B93X | Chipping Warden Green Tunnel Access Stair | 1MC07-ASC-CV-FRM-CS07_CL13-000140 - ACBOS | P01 | 2024-08-09 |  | 2024-08-15 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600051 | [9 empty] | 10 - Complete | Supriyan | K S, Abhisheka <abhisheka.ks@arcadis.com> | 4 | 0
| 234.03 | HS2-00002TG2Z | Highfurlong Brook Embankment | 1MC07-ASC-CV-FRM-CS07_CL14-000111-ACBOS | P01 | 2024-08-09 | 2024-08-14 | 2024-08-20 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600193 |  | OSGB issues, sent back on 14-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | PHILIPOSE, IMMANUEL <immanuel.philipose@arcadis.com>
| 205.3 | HS2-00002CW1L | Whitethorn Farm Access (SMA 9) Drainage System | 1MC06-ASC-DR-FRM-CS04_CL18-000017-ACBOS | P05 | 2024-08-09 | 2024-08-22 | 2024-08-23 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600028 |  | OSGB issues, uniclass issues send back on 14-Jan-2024 | [7 empty] | 10 - Complete | Supriyan | N, Sudhakara <sudhakara.n@arcadis.com> | 1 | 1 | 13
| 204.2-2 | HS2-00003JQJQ | Risborough Road Underpass Access Stairs No.1 | 1MC06-ASC-CV-FRM-CS03_CL17-000061-ACBOS | P02 | 2024-08-12 | 2024-08-12 | 2024-08-16 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600134 | No issues | [8 empty] | 10 - Complete | Lee | U M, Pavana <pavana.um@arcadis.com> | 4 | 0 | 0
| 204.2-2 | HS2-00003JQJR | Risborough Road Underpass Access Stairs No.2 | 1MC06-ASC-CV-FRM-CS03_CL17-000062-ACBOS | P02 | 2024-08-12 | 2024-08-12 | 2024-08-16 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600135 | No issues | [8 empty] | 10 - Complete | Lee | U M, Pavana <pavana.um@arcadis.com> | 4 | 0 | 0
| 204.2-2 | HS2-00003JQJS | Risborough Road Underpass Access Stairs No.3 | 1MC06-ASC-CV-FRM-CS03_CL17-000063-ACBOS | P02 | 2024-08-12 | 2024-08-12 | 2024-08-16 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600136 | No issues | [8 empty] | 10 - Complete | Lee | U M, Pavana <pavana.um@arcadis.com> | 4 | 0 | 0
| 204.2-2 | HS2-00003K2XQ | Nash Lee Orchard Culvert Access Stairs | 1MC06-ASC-CV-FRM-CS03_CL17-000064-ACBOS | P01 | 2024-08-12 | 2024-08-12 | 2024-08-16 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600137 | No issues | [8 empty] | 10 - Complete | Lee | U M, Pavana <pavana.um@arcadis.com> | 4 | 0 | 0
7 | 215.03 | HS2-00003GL96 | Calvert IMD.22 UTX No. 3 | 1MC06-ASC-CV-FRM-CS06_CL09-000099-ACBOS | P02 | 2024-08-12 |  | 2024-08-23 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600274 | [9 empty] | 10 - Complete | Supriyan | Mehta, Jeet <jeet.mehta@arcadis.com> | 9 | 0
7 | 215.03 | HS2-00003GL97 | Calvert IMD.22 UTX No. 4 | 1MC06-ASC-CV-FRM-CS06_CL09-000100-ACBOS | P02 | 2024-08-12 |  | 2024-08-28 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600275 | [9 empty] | 10 - Complete | Supriyan | Mehta, Jeet <jeet.mehta@arcadis.com> | 11 | 0
7 | 215.03 | HS2-00002Y8VT | East West Rail Overbridge Maintenance Access Point Staircase Downmain Ch80070 | 1MC06-ASC-CV-FRM-CS06_CL09-000056-ACBOS | P02 | 2024-08-12 |  | 2024-08-23 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600345 | [9 empty] | 10 - Complete | Rakesh | Wong, Ka Ho <Isaac.wong@arcadis.com> | 9 | 0
7 | 215.03 | HS2-00002YXB6 | Shepherds Furze Culvert Emergency Access Point Staircase Downmain Ch79340 | 1MC06-ASC-CV-FRM-CS06_CL09-000069-ACBOS | P02 | 2024-08-12 |  | 2024-08-23 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600340 | [9 empty] | 10 - Complete | Rakesh | Wong, Ka Ho <Isaac.wong@arcadis.com> | 9 | 0
7 | 215.03 | HS2-00003D9CF | IMD West Culvert Access staircase Downmain Ch99674 OXD Line | 1MC06-ASC-CV-FRM-CS06_CL09-000093-ACBOS | P02 | 2024-08-12 |  | 2024-08-23 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600337 | [9 empty] | 10 - Complete | Rakesh | Wong, Ka Ho <Isaac.wong@arcadis.com> | 9 | 0
7 | 215.03 | HS2-00002YPE6 | Calvert Green Overbridge Maintenance Access Point Staircase Downmain Ch78400 | 1MC06-ASC-CV-FRM-CS06_CL09-000058-ACBOS | P02 | 2024-08-12 |  | 2024-08-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600343 | [9 empty] | 10 - Complete | Rakesh | Wong, Ka Ho <Isaac.wong@arcadis.com> | 10 | 0
7 | 215.03 | HS2-00002Y8VS | School Hill Green Overbridge Maintenance Access Point Staircase Downmain Ch79020 | 1MC06-ASC-CV-FRM-CS06_CL09-000057-ACBOS | P02 | 2024-08-12 |  | 2024-08-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600346 | [9 empty] | 10 - Complete | Rakesh | Wong, Ka Ho <Isaac.wong@arcadis.com> | 10 | 0
7 | 215.03 | HS2-00003GNA5 | Calvert Green Overbridge NR Access point Downmain Ch21800 | 1MC06-ASC-CV-FRM-CS06_CL09-000097-ACBOS | P02 | 2024-08-12 |  | 2024-08-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600335 | [9 empty] | 10 - Complete | Rakesh | Wong, Ka Ho <Isaac.wong@arcadis.com> | 10 | 0
3 | 212.5 | HS2-000035Q91 | Oxford Road Embankment Ditch Slab No.3 | 1MC06-ASC-CV-FRM-CS04_CL19-000058-ACBOS | P01 | 2024-08-12 |  | 2024-08-23 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600080 | [9 empty] | 10 - Complete | Supriyan | Alagundi, Shreyas <shreyas.alagundi@arcadis.com> | 9 | 0
17 | 229.01-2 | HS2-00002TMF6 | Greatworth Green Tunnel North Portal Building Telecoms | 1MC07-ASC-UT-FRM-CS07_CL25-000073-ACBOS | P02 | 2024-08-13 | 2024-08-13 | 2024-08-22 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600054 | No issues | [8 empty] | 10 - Complete | Lee | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 7 | 0 | 0
17 | 229.01-2 | HS2-00002TMF5 | Greatworth Green Tunnel North Portal Building Fire-fighting Water | 1MC07-ASC-UT-FRM-CS07_CL25-000071-ACBOS | P01 | 2024-08-13 | 2024-08-13 | 2024-08-21 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600049 | No issues | [8 empty] | 10 - Complete | Lee | Lokhande, Juilee <juilee.lokhande@arcadis.com> | 6 | 0 | 0
| 204.2-2 | HS2-000031GXP | ELL 20 Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS03_CL17-000045-ACBOS | P01 | 2024-08-13 | 2024-08-13 |  |  | 1MC06-CEK-IM-DAT-CS03_CL17-600116 | No issues | [8 empty] | 10 - Complete | Lee | Tilici, Andreea <andreea.tilici@arcadis.com>
| 204.2-2 | HS2-000031GXK | Nash Lee Orchard Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS03_CL17-000038-ACBOS | P01 | 2024-08-13 | 2024-08-20 | 2024-08-20 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600120 | No issues | UAID_3 in ABT does not match Smartforms. Sent back 14-Aug-24. | Revise 19-Aug-24 | [6 empty] | 10 - Complete | Lee | Tilici, Andreea <andreea.tilici@arcadis.com> | 0 | 1 | 7
| 204.2-2 | HS2-000031GXL | Nash Lee Orchard Ditch Slab No.2 | 1MC06-ASC-CV-FRM-CS03_CL17-000039-ACBOS | P01 | 2024-08-13 | 2024-08-19 | 2024-09-11 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600119 | No issues | Coordinates incorrect - sent back 14-Aug-24 | Revise 19-Aug-24 | [6 empty] | 10 - Complete | Lee | Tilici, Andreea <andreea.tilici@arcadis.com> | 16 | 1 | 6
| 204.2-2 | HS2-000031GXM | Nash Lee Orchard Ditch Slab No.3 | 1MC06-ASC-CV-FRM-CS03_CL17-000040-ACBOS | P01 | 2024-08-13 | 2024-08-19 | 2024-09-11 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600118 | No issues | Coordinates incorrect - sent back 14-Aug-24 | Revise 19-Aug-24 | [6 empty] | 10 - Complete | Lee | Tilici, Andreea <andreea.tilici@arcadis.com> | 16 | 1 | 6
| 204.2-2 | HS2-000031GXN | Nash Lee Orchard Ditch Slab No.4 | 1MC06-ASC-CV-FRM-CS03_CL17-000041-ACBOS | P01 | 2024-08-13 | 2024-08-19 | 2024-08-20 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600117 | No issues | Coordinates incorrect - sent back 14-Aug-24 | Revise 19-Aug-24 | [6 empty] | 10 - Complete | Lee | Tilici, Andreea <andreea.tilici@arcadis.com> | 1 | 1 | 6
| 204.2-2 | HS2-00003CPYY | Nash Lee Orchard Ditch Slab No.6 | 1MC06-ASC-CV-FRM-CS03_CL17-000056-ACBOS | P01 | 2024-08-13 | 2024-08-19 | 2024-08-21 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600106 | No issues | Coordinates incorrect - sent back 14-Aug-24 | Revise 19-Aug-24 | [6 empty] | 10 - Complete | Lee | Tilici, Andreea <andreea.tilici@arcadis.com> | 2 | 1 | 6
| 204.2-2 | HS2-000031GXQ | Risborough Road Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS03_CL17-000046-ACBOS | P01 | 2024-08-13 | 2024-08-13 | 2024-08-16 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600115 | No issues | [8 empty] | 10 - Complete | Lee | Tilici, Andreea <andreea.tilici@arcadis.com> | 3 | 0 | 0
| 204.2-2 | HS2-00003CPYX | Risborough Road Ditch Slab No.2 | 1MC06-ASC-CV-FRM-CS03_CL17-000058-ACBOS | P01 | 2024-08-13 | 2024-08-13 | 2024-08-16 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600105 | No issues | [8 empty] | 10 - Complete | Lee | Tilici, Andreea <andreea.tilici@arcadis.com> | 3 | 0 | 0
| 204.2-2 | HS2-0000325TJ | SMA 5 Footpath Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS03_CL17-000047-ACBOS | P01 | 2024-08-13 | 2024-08-13 | 2024-08-16 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600114 | No issues | [8 empty] | 10 - Complete | Lee | Tilici, Andreea <andreea.tilici@arcadis.com> | 3 | 0 | 0
| 204.2-2 | HS2-0000325TK | SMA 5 Footpath Ditch Slab No.2 | 1MC06-ASC-CV-FRM-CS03_CL17-000048-ACBOS | P01 | 2024-08-13 | 2024-08-13 | 2024-08-16 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600113 | No issues | [8 empty] | 10 - Complete | Lee | Tilici, Andreea <andreea.tilici@arcadis.com> | 3 | 0 | 0
| 204.2-2 | HS2-00003CPYU | Stoke House Crossing Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS03_CL17-000057-ACBOS | P01 | 2024-08-13 | 2024-08-13 | 2024-08-16 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600111 | No issues | [8 empty] | 10 - Complete | Lee | Tilici, Andreea <andreea.tilici@arcadis.com> | 3 | 0 | 0
| 226.5 | HS2-000031EF5 | 97-SL2 Brackley Embankment Vehicular Bridge | 1MC07-ASC-BR-FRM-CS07_CL12-900003 | P01 | 2024-08-13 |  | 2024-08-22 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600295 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 7 | 0
| 226.5 | HS2-000031EF6 | 98-SL1 Brackley North Cutting Vehicular Slab | 1MC07-ASC-BR-FRM-CS07_CL12-900001 | P01 | 2024-08-13 |  | 2024-08-22 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600294 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 7 | 0
| 213.08 | HS2-00002Y0EX | Doddershall Access Track Crossing 3 | 1MC06-CEK-CV-FRM-CS05-000052 | P01 | 2024-08-14 | 2024-08-20 | 2024-08-21 |  | 1MC06-CEK-IM-DAT-CS05-600289 | No issues | Non-Integer values. Sent back 15-Aug-24 | revised 20-Aug-24 | [6 empty] | 10 - Complete | Lee | Fowler, Alex <alex.fowler@arcadis.com> | 1 | 1 | 6
| 213.08 | HS2-00002VK4D | Doddershall Access Track Crossing 2 | 1MC06-CEK-CV-FRM-CS05-000053 | P01 | 2024-08-14 | 2024-08-20 | 2024-08-21 |  | 1MC06-CEK-IM-DAT-CS05-600288 | No issues | Non-Integer values. Sent back 15-Aug-24 | revised 20-Aug-24 | [6 empty] | 10 - Complete | Lee | Fowler, Alex <alex.fowler@arcadis.com> | 1 | 1 | 6
| 213.08 | HS2-00002VK3Q | Doddershall Access Track Crossing 1 | 1MC06-CEK-CV-FRM-CS05-000054 | P01 | 2024-08-14 | 2024-08-20 | 2024-08-21 |  | 1MC06-CEK-IM-DAT-CS05-600287 | No issues | Non-Integer values. Sent back 15-Aug-24 | revised 20-Aug-24 | [6 empty] | 10 - Complete | Lee | Fowler, Alex <alex.fowler@arcadis.com> | 1 | 1 | 6
17 | 229.01-2 | HS2-00002CTF3 | Greatworth Green Tunnel North Portal Access Road Retaining Wall 1 | 1MC07-ASC-CV-FRM-CS07_CL25-000004-ACBOS | P01 | 2024-08-15 | 2024-09-12 | 2024-09-12 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600052 |  | Uniclass and other issues, send back on 26-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Chelsea Ridge <CHRG@COWI.COM> | 0 | 1 | 28
7 | 215.03 | HS2-00003H07F | Pond Access Road Staircase Downmain 81175 | 1MC06-ASC-CV-FRM-CS06_CL09-000098-ACBOS | P01 | 2024-08-15 | 2024-08-27 | 2024-08-28 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600332 | Issue found | 0 found in Net volume, send back to team on 26 Aug 24. | [7 empty] | 10 - Complete | Rakesh | Isaac.wong@arcadis.com | 1 | 1 | 12
7 | 215.03 | HS2-00002Y8VU | Perry Hill Overbridge Maintenance Access Point Downmain Ch80800 | 1MC06-ASC-CV-FRM-CS06_CL09-000055-ACBOS | P02 | 2024-08-15 |  | 2024-08-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600344 | [9 empty] | 10 - Complete | Rakesh | Isaac.wong@arcadis.com | 7 | 0
7 | 215.03 | HS2-00003D9CD | Perry Hill OB access staircase Upmain Ch80800 | 1MC06-ASC-CV-FRM-CS06_CL09-000092-ACBOS | P01 | 2024-08-15 |  | 2024-08-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600338 | [9 empty] | 10 - Complete | Rakesh | Isaac.wong@arcadis.com | 7 | 0
| 213.08 | HS2-00002BJTN | HS2-00002C5T1-Footpath QUA 26 Diversion | 1MC06-ASC-HW-FRM-CS05-000033-ACBOS | P | 2024-08-15 | 2024-08-20 | 2024-08-21 |  | 1MC06-CEK-IM-DAT-CS05-600080 | No issues | all Com_typs, all Com_dscrptn, all Sdslp, AnglSlp, some zero value GrossVolume, 1 odd value NetVolume. Back on 19-Aug-24 | revised 20-Aug-24 | [6 empty] | 10 - Complete | Lee | Khan, Sal <sal.khan@arcadis.com> | 1 | 1 | 5
| UFDR 217.B | HS2-0000245ZF | CSO-04-3125 | 1MC06-ASC-UT-FRM-CS06_CL09-000027-ACBOS | P02 | 2024-08-19 |  | 2024-08-21 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600087 | No issues | DT have called and have reatgging exercise underway Status set back to "HOLD" - 20-jun-24 | Revised 19-Aug-24 | [6 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com> | 2 | 1
17 | 229.01-2 | HS2-00003FV0F | Greatworth Green Tunnel Access Stairs CH.102.100 | 1MC07-ASC-CV-FRM-CS07_CL25-000136 - ACBOS | P01 | 2024-08-19 | 2024-08-28 | 2024-08-29 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600076 |  | Query sent on various 0's on 25-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Martin, Joel <Joel.Martin@arcadis.com> | 1 | 1 | 9
17 | 229.01-2 | HS2-00003FV0G | Greatworth Green Tunnel Access Stairs CH.104.600 | 1MC07-ASC-CV-FRM-CS07_CL25-000137 - ACBOS | P01 | 2024-08-19 | 2024-08-28 | 2024-08-29 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600075 |  | Sent queries on various 0's on 25-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Martin, Joel <Joel.Martin@arcadis.com> | 1 | 1 | 9
| 218.02-1 | HS2-00002NSXQ | OXD Boundary/ Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL09-000081-ACBOS | P02 | 2024-08-19 | 2024-08-28 | 2024-08-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600181 |  | OSGB issues, other issues. Sent back on 27-Aug-2024 | [7 empty] | 10 - Complete | Supriyan | Whyte, William <William.Whyte@arcadis.com> | 1 | 1 | 9
| 217.03 | HS2-00002CT8S | HS2-00002C5T4-Addison Road Drainage System | 1MC06-ASC-DR-FRM-CS06_CL09-000027-ACBOS | P02 | 2024-08-19 | 2024-08-28 | 2024-08-29 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600110 | Issue found | DsgnLf values are missing .Send back to team on 27 Aug 24. | [7 empty] | 10 - Complete | Rakesh | Rai C, Keerthan <keerthan.raic@arcadis.com> | 1 | 1 | 9
3 | 212.5 | HS2-00003JKXS | Bicester Road Embankment No.6 Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL20-000082-ACBOS | P01 | 2024-08-19 |  | 2024-08-29 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600248 | [9 empty] | 10 - Complete | Rakesh | orlando.sangalang@arcadis.com | 7 | 0
3 | 212.5 | HS2-00003H07B | Whaddon Hill Cutting Ditch Slab No. 1 | 1MC06-ASC-CV-FRM-CS04_CL19-000071-ACBOS | P01 | 2024-08-19 | 2024-08-28 | 2024-08-30 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600102 | Issue found | Carriage return issue in ifc Layer for GSL clas,Send Back to team on 27 Aug 24. | [7 empty] | 10 - Complete | Rakesh | orlando.sangalang@arcadis.com | 2 | 1 | 9
| 230.01-3 | HS2-00002CTFN | C3.T.29 Catchment | 1MC07-ASC-DR-FRM-CS07_CL26-000005-ACBOS | P03 | 2024-08-20 | 2024-08-20 | 2024-08-21 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600018 | No issues | trailing spaces & uniclass withdrawn - sent back 20-aug-24 | [7 empty] | 10 - Complete | Lee | M, Nischitha <nischitha.m@arcadis.com> | 1 | 1 | 0
| 215.02-2 | HS2-00002CX35 | Civil 3D Solids Model - P-RAI-0795 | 1MC06-ASC-DR-FRM-CS06_CL09-000011-ACBOS | P06 | 2024-08-21 | 2024-09-03 | 2024-09-05 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600220 |  | DmtrExtr in PPE asset class need update, sent back on 02-Sept-2024 | [7 empty] | 10 - Complete | Supriyan | SAIHI Thamer <thamer.saihi@setec.com> | 2 | 1 | 13
| 213.08 | HS2-00003HWH0 | Doddershall Embankement Ancillary Earthworks | 1MC06-ASC-HW-FRM-CS05-000099-ACBOS | P01 | 2024-08-21 | 2024-08-27 | 2024-08-28 |  | 1MC06-CEK-IM-DAT-CS05-600291 | Issue found | OSGB Conversion Issue , Send back to team on 23 Aug 24. | [7 empty] | 10 - Complete | Rakesh | Quirante, Dan <dan.quirante@arcadis.com> | 1 | 1 | 6
| UFDR 204.B | HS2-000020CEJ | CSO-02-6205 | 1MC06-ASC-UT-FRM-CS03_CL17-000018-ACBOS | P02 | 2024-08-22 |  | 2024-09-04 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600039 | [9 empty] | 10 - Complete | Rakesh | maya.bowles@arcadis.com> | 8 | 0
| UFDR 204.B | HS2-000020CEK | CSO-02-6206 | 1MC06-ASC-UT-FRM-CS03_CL17-000019-ACBOS | P02 | 2024-08-22 |  | 2024-09-04 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600034 | [9 empty] | 10 - Complete | Rakesh | maya.bowles@arcadis.com> | 8 | 0
| 215.02-2 | HS2-00002CX36 | Civil 3D Solids Model - P-RAI-0799 | 1MC06-ASC-DR-FRM-CS06_CL09-000037-ACBOS | P09 | 2024-08-22 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600209 |  | In-complete tagging, sent back on 02-Sept-2024 | [7 empty] | 99 - Cancelled | Supriyan | thamer.saihi@setec.com>
| 215.02-2 | HS2-00002CT8V | Civil 3D Solids Model - P-RAI-0786 | 1MC06-ASC-DR-FRM-CS06_CL09-000035-ACBOS | P08 | 2024-08-22 | 2024-09-03 | 2024-09-05 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600199 |  | Com_type and other issues, send back on 03-Sept-2024 | [7 empty] | 10 - Complete | Supriyan | thamer.saihi@setec.com> | 2 | 1 | 12
| 228.2 | HS2-000001339 | AN37 Accommodation Overbridge | 1MC07-CEK-BR-FRM-CS07_CL12-000008 | P05 | 2024-08-22 | 2024-10-02 | 2024-10-03 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600136 |  | uniclass_ID issue, sent back on 02-Sept-2024 |  | Data type and insitu/pre cast conflict, sent back on 17-Sept-2024 | [5 empty] | 10 - Complete | Supriyan | anamika.puri@wsp.com> | 1 | 2 | 41
| 228.2 | HS2-000001436 | Helmdon Culvert | 1MC07-CEK-BR-FRM-CS07_CL12-000012 | P07 | 2024-08-22 | 2024-09-24 | 2024-09-25 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600120 |  | IFC Presenation layer missing, sent back on 03-Sept-2024 |  | IFC Presenation layer missing, sent back on 16-Sept-2024 |  | Precast vs insitu error, sent back on 23-09-2024 |  |  |  | 10 - Complete | Supriyan | anamika.puri@wsp.com> | 1 | 3 | 33
| 228.1 | HS2-000001340 | Bridleway AN14 Accommodation Overbridge | 1MC07-CEK-BR-FRM-CS07_CL12-000032 | P02 | 2024-08-22 | 2024-10-02 | 2024-10-04 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600133 |  | Uniclass_ID issue,sent back on 02-Sept-2024 |  | Uniclass_ID issue,sent back on 16-Sept-2024 | [5 empty] | 10 - Complete | Rakesh | anamika.puri@wsp.com> | 2 | 2 | 41
| 213.02-2 | HS2-000001040 | Civil 3D Solids Model - 071-L1-71800-72370 | 1MC06-ASC-GT-FRM-CS05-000010-ACBOS | P04 | 2024-08-26 | 2024-09-03 | 2024-09-05 |  | 1MC06-CEK-IM-DAT-CS05-600098 |  | Com_Type is not correct, sent back on 03-Sept-2024 | [7 empty] | 10 - Complete | Supriyan | thamer.saihi@setec.com> | 2 | 1 | 8
| 234.01 | HS2-00002U4NE | Aston Le Walls Embankment Group | 1MC07-ASC-CV-FRM-CS07_CL14-000079-ACBOS | P03 | 2024-08-26 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL14-600112 | Issue found | NA found in FtRtng , send back on 06 Sep 24. | [7 empty] | 10 - Complete | Rakesh | apoorva.patil@arcadis.com
| 229.03 | HS2-00002CTES | C3.L.20 Catchment | 1MC07-ASC-DR-FRM-CS07_CL12-000016-ACBOS | P01 | 2024-08-26 | 2024-09-04 | 2024-09-10 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600032 | Issue found | Spacing issue found . Send Back to team on 04 Sep 24. | 2024-09-05 | Incorrect com type , send back to team on 6 Sep 24. | 2024-09-09 |  |  |  |  | 10 - Complete | Rakesh | pradeep.s@arcadis.com> | 4 | 2 | 9
| 226.5 | HS2-0000386UJ | 97-SL2 Brackley Embankment Vehicular Bridge - Earthworks Transition | 1MC07-ASC-BR-FRM-CS07_CL12-000030-ACBOS | P01 | 2024-08-26 |  | 2024-09-03 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600282 | [9 empty] | 10 - Complete | Supriyan | zakaria.khabouze@setec.com | 5 | 0
| 230.04-2 | HS2-00002CTG0 | Lower Thorpe South Cutting Noise Barrier Line | 1MC07-ASC-CV-FRM-CS07_CL26-000113-ACBOS | P03 | 2024-08-28 | 2024-09-20 | 2024-09-25 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600159 | No issues | All classes GdMT incomplete. No other issues. Sent back 5-Sep-24 | [7 empty] | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com> | 3 | 1 | 23
| 229.03 | HS2-000001072 | Greatworth North Cutting | 1MC07-ASC-GT-FRM-CS07_CL12-000003-ACBOS | P03 | 2024-08-28 | 2024-09-12 | 2024-09-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600020 |  | ACBOS PCRA is pending, sent back on 09-Sept-2024 |  | Uniclass_ID and OSGB issues, sent back on 9-Sept-2024 | [5 empty] | 10 - Complete | Supriyan | deepak.kp@arcadis.com> | 4 | 2 | 15
| 229.03 | HS2-00002CTET | C3.L.21 Catchment | 1MC07-ASC-DR-FRM-CS07_CL12-000018-ACBOS | P02 | 2024-08-28 | 2024-09-06 | 2024-09-11 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600031 | No issues | Trailing spaces within Com_Dscrptns in CUT and GFL categories. 1 attribute value for Sdslp in GFL contains text “I in 3” and not “1 in 3”. Com_Typ for class Pr_65_52_01_02 is incorrect and should not be Pr_65_52_01_02. sent 5-Sep-24 | revised 6-sep-24 | [6 empty] | 10 - Complete | Lee | pradeep.s@arcadis.com> | 3 | 1 | 9
| 216.01 | HS2-000001318 | West Street Overbridge | 1MC06-CEK-BR-FRM-CS06_CL09-000009 | P08 | 2024-08-28 | 2024-09-10 | 2024-10-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600152 | No issues | Com_Typs for ZZ-ZZ. DT are asking for mitigation? Discuss with Alex / Partha | 2024-09-10 | some integer atts set as reals. 11-sep-24 | 2024-10-10 | Real numbers to remian for RtndHght |  |  |  | 10 - Complete | Lee | William.Whyte@arcadis.com> | 24 | 3 | 13
7 | 215.03 | HS2-00002CT93 | Calvert Cutting Noise Barrier Line | 1MC06-ASC-CV-FRM-CS06_CL09-000060-ACBOS | P01 | 2024-08-28 | 2024-09-09 | 2024-09-10 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600277 |  | ACBOS PCRA is not done, sent back on 06-Sept-2024 | [7 empty] | 10 - Complete | Supriyan | karthiban.sr@arcadis.com> | 1 | 1 | 12
13 | 213.07-1 | HS2-00003JN81 | Tetchwick Brook Flood Compensation Areas Bund Culvert | 1MC06-ASC-CV-FRM-CS04_CL20-000009 | P01 | 2024-08-28 | 2024-09-11 | 2024-09-12 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600246 | No issues | Com_Typ & Com_dscrptn incorrect. Sdslp incorrect. Sent back 5-sep-24 | 2024-09-11 | [6 empty] | 10 - Complete | Lee | jeet.mehta@arcadis.com> | 1 | 1 | 14
13 | 213.07-1 | HS2-000032LLS | NR Flood Relief Culvert 1 | 1MC06-CEK-CV-FRM-CS04_CL20-000057 | P01 | 2024-08-28 | 2024-09-11 | 2024-09-16 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600229 | No issues | Com_Typ & Com_dscrptn incorrect. Sdslp incorrect. Sent back 6-sep-24 | 2024-09-11 | [6 empty] | 10 - Complete | Lee | jeet.mehta@arcadis.com> | 3 | 1 | 14
13 | 213.07-1 | HS2-000032LLT | NR Flood Relief Culvert 2 | 1MC06-CEK-CV-FRM-CS04_CL20-000058 | P01 | 2024-08-28 |  | 2024-09-19 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600230 | Issue found | Com_RfrncNmbr "None" missing ,sdslp ,DsgnFlwBss not in LODM prescribed format , Send back on 6 Sep 24. | 11 Sep 2024 | Extra Spacing found in Com_Desc & Uniclass ID , Send back to team on 12 Sep 24. | [5 empty] | 10 - Complete | Rakesh | jeet.mehta@arcadis.com> | 16 | 2
13 | 213.07-1 | HS2-000032LLU | NR Flood Relief Culvert 3 | 1MC06-CEK-CV-FRM-CS04_CL20-000059 | P01 | 2024-08-28 |  | 2024-09-19 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600231 | Issue found | Com_RfrncNmbr "None" missing ,sdslp ,DsgnFlwBss not in LODM prescribed format , Send back on 6 Sep 24. | 11 Sep 2024 | Extra Spacing found in Com_Desc & Uniclass ID , Send back to team on 12 Sep 24. | [5 empty] | 10 - Complete | Rakesh | jeet.mehta@arcadis.com> | 16 | 2
13 | 213.07-1 | HS2-000032LLV | NR Flood Relief Culvert 4 | 1MC06-CEK-CV-FRM-CS04_CL20-000060 | P01 | 2024-08-28 |  | 2024-09-19 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600232 | Issue found | Com_RfrncNmbr "None" missing ,sdslp ,DsgnFlwBss not in LODM prescribed format , Send back on 6 Sep 24. | 11 Sep 2024 | Extra Spacing found in Com_Desc & Uniclass ID , Send back to team on 12 Sep 24. | [5 empty] | 10 - Complete | Rakesh | jeet.mehta@arcadis.com> | 16 | 2
13 | 213.07-1 | HS2-000032LLW | NR Watercourse Culvert | 1MC06-CEK-CV-FRM-CS04_CL20-000061 | P01 | 2024-08-28 |  | 2024-09-19 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600228 | Issue found | Com_RfrncNmbr "None" missing ,sdslp ,DsgnFlwBss not in LODM prescribed format , Send back on 6 Sep 24. | 11 Sep 2024 | Extra Spacing found in Com_Desc & Uniclass ID , Send back to team on 12 Sep 24. | [5 empty] | 10 - Complete | Rakesh | jeet.mehta@arcadis.com> | 16 | 2
| 230.03-2 | HS2-00002CTFX | Lower Thorpe South Embankment Noise Barrier Line | 1MC07-ASC-CV-FRM-CS07_CL26-000114-ACBOS | P01 | 2024-08-29 |  | 2024-09-06 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600156 | [9 empty] | 10 - Complete | Supriyan | Joel.Martin@arcadis.com> | 6 | 0
3 | 212.5 | HS2-000030TD8 | Hartwell Pond Access Ditch Slab No.2 | 1MC06-ASC-CV-FRM-CS04_CL19-000054-ACBOS | P02 | 2024-08-29 |  |  |  | 1MC06-CEK-IM-DAT-CS04_CL19-600054 | [9 empty] | 10 - Complete | Supriyan | shreyas.alagundi@arcadis.com>
3 | 212.5 | HS2-000030TD7 | Hartwell Pond Access Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS04_CL18-000079-ACBOS | P02 | 2024-08-29 | 2024-09-11 | 2024-09-13 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600115 |  | Com_type is not as per guidline,sent back on 06-Sept-2024 |  | Again com_Type issues found, sent back on 11-Sept-2024 | [5 empty] | 10 - Complete | Supriyan | shreyas.alagundi@arcadis.com> | 2 | 2 | 13
| 204.2-2 | HS2-00002CT4M | C2.L.19 Catchment | 1MC06-ASC-DR-FRM-CS03_CL17-000003-ACBOS | P02 | 2024-09-02 | 2024-09-11 | 2024-09-16 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600010 |  | Queries sent regarding 0's and othe not applicable attributes on 09-Sept-2024 | [7 empty] | 10 - Complete | Lee | srinatha.ka@arcadis.com> | 3 | 1 | 9
7 | 215.03 | HS2-00002YPEG | GSMR Point 37 Access Road Crossing No. 1 | 1MC06-ASC-CV-FRM-CS06_CL09-000063-ACBOS | P01 | 2024-09-02 | 2024-09-24 | 2024-09-26 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600341 |  | ACBOS PCRA is not done, sent back on 09-Sept-2024 |  | Multiple issues, send back on 10-Sept-2024 |  | sdslp not in format, sent back on 16-Sept-2024 |  |  |  | 10 - Complete | Supriyan | mxhn@cowi.com> | 2 | 3 | 22
7 | 215.03 | HS2-00002YPEH | GSMR Point 37 Access Road Crossing No. 2 | 1MC06-ASC-CV-FRM-CS06_CL09-000064-ACBOS | P01 | 2024-09-02 | 2024-09-24 | 2024-09-26 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600342 |  | ACBOS PCRA is not done, sent back on 09-Sept-2024 |  | Multiple issues, send back on 10-Sept-2024 |  | OSGB issue, sdslp format and com_Type issue. Sent back on 16-Sept-2024 |  |  |  | 10 - Complete | Supriyan | mxhn@cowi.com> | 2 | 3 | 22
7 | 215.03 | HS2-00002VK40 | Shepherds Furze Watercourse Crossing MAS | 1MC06-ASC-CV-FRM-CS06_CL09-000039-ACBOS | P01 | 2024-09-02 | 2024-09-24 | 2024-09-26 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600347 | No issues | ACBOS PCRA is not done, sent back on 09-Sept-2024 |  | Multiple issues, send back on 10-Sept-2024 |  | sdslp not in format, osgb issues, sent back on 16-Sept-2024 | 2024-09-26 |  |  | 10 - Complete | Lee | mxhn@cowi.com> | 2 | 3 | 22
7 | 215.03 | HS2-00003GSJY | Shepherds Furze Watercourse Crossing 2 MAS | 1MC06-ASC-CV-FRM-CS06_CL09-000102-ACBOS | P01 | 2024-09-02 | 2024-09-24 | 2024-09-26 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600334 | No issues | ACBOS PCRA is not done, sent back on 09-Sept-2024 |  | OSGB and other issues, send back on 10-Sept-2024 |  |  | 2024-09-26 |  |  | 10 - Complete | Lee | mxhn@cowi.com> | 2 | 2 | 22
7 | 215.03 | HS2-00003GSJZ | C2.OXD.T.522 Catchment MAS Crossing | 1MC06-ASC-CV-FRM-CS06_CL09-000101-ACBOS | P01 | 2024-09-02 | 2024-09-24 | 2024-09-26 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600333 | No issues | ACBOS PCRA is not done, sent back on 09-Sept-2024 |  | OSGB and other issues, send back on 10-Sept-2024 |  |  | 2024-09-26 |  |  | 10 - Complete | Lee | mxhn@cowi.com> | 2 | 2 | 22
14 | UFDR 214.A | HS2-00002TUPJ | FCC Sidings Telecoms | 1MC06-ASC-UT-FRM-CS05-000019-ACBOS | P02 | 2024-09-03 | 2024-09-03 | 2024-09-11 |  | 1MC06-CEK-IM-DAT-CS05-600135 | [9 empty] | 10 - Complete | Rakesh | Bowles, Maya <maya.bowles@arcadis.com> | 6 | 0 | 0
10 | 233.01-3 | HS2-000025B2P | Chipping Warden Tunnel South Portal Building | 1MC07-ASC-CV-FRM-CS07-000002-ACBOS | P02 | 2024-09-03 | 2024-09-03 |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 | No issues | Combined JSON | [6 empty] | Loaded 1420. | 10 - Complete | Lee | Bandi, Venkatesh <venkatesh.bandi@arcadis.com> Shanmugham, Subbarayan <Subbarayan.Shanmugham@arcadis.com>; Harnett, Toby <toby.harnett@arcadis.com>; Foster, Alex <alex.foster@arcadis.com>; Prasad C N, Hari <hari.prasadcn@arcadis.com>; Prerak Agrawal <pkal@cowi.com>; B S, Shashank <shashank.bs@arcadis.com>; Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>; U M, Pavana <pavana.um@arcadis.com>; Maruboyina, Saikumar <saikumar.maruboyina@arcadis.com>; Laxmana, Mahesha <Mahesha.Laxmana@arcadis.com>; J, Akash Mohan <akashmohan.j@arcadis.com>; Reddy Andru, Raghu Vikas <raghuvikas.reddyandru@arcadis.com>; Shukla, Ravi Kumar <ravikumar.shukla@arcadis.com>; Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com>; Andrew Macpherson <a.macpherson@moxonarchitects.com>; Godevenos, Georgios <georgios.godevenos@arcadis.com>; Keeling, Sam <sam.keeling@arcadis.com>
10 | 233.01-3 | HS2-000025B2P | Chipping Warden Tunnel South Portal Building | 1MC07-CEK-CV-FRM-CS07_CL13-000002 | P02 | 2024-09-03 | 2024-09-03 |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 | No issues | Combined JSON | [6 empty] | Loaded 643 | 10 - Complete | Lee | Bandi, Venkatesh <venkatesh.bandi@arcadis.com> Shanmugham, Subbarayan <Subbarayan.Shanmugham@arcadis.com>; Harnett, Toby <toby.harnett@arcadis.com>; Foster, Alex <alex.foster@arcadis.com>; Prasad C N, Hari <hari.prasadcn@arcadis.com>; Prerak Agrawal <pkal@cowi.com>; B S, Shashank <shashank.bs@arcadis.com>; Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>; U M, Pavana <pavana.um@arcadis.com>; Maruboyina, Saikumar <saikumar.maruboyina@arcadis.com>; Laxmana, Mahesha <Mahesha.Laxmana@arcadis.com>; J, Akash Mohan <akashmohan.j@arcadis.com>; Reddy Andru, Raghu Vikas <raghuvikas.reddyandru@arcadis.com>; Shukla, Ravi Kumar <ravikumar.shukla@arcadis.com>; Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com>; Andrew Macpherson <a.macpherson@moxonarchitects.com>; Godevenos, Georgios <georgios.godevenos@arcadis.com>; Keeling, Sam <sam.keeling@arcadis.com>
10 | 233.01-3 | HS2-000025B2P | Chipping Warden Tunnel South Portal Building | 1MC07-CEK-EL-FRM-CS07_CL13-000001 | P03 | 2024-09-03 | 2024-09-03 |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 | No issues | Combined JSON |  | Uniclass issues , post L3 works |  |  |  |  | Loaded 1456 | 10 - Complete | Lee | Bandi, Venkatesh <venkatesh.bandi@arcadis.com> Shanmugham, Subbarayan <Subbarayan.Shanmugham@arcadis.com>; Harnett, Toby <toby.harnett@arcadis.com>; Foster, Alex <alex.foster@arcadis.com>; Prasad C N, Hari <hari.prasadcn@arcadis.com>; Prerak Agrawal <pkal@cowi.com>; B S, Shashank <shashank.bs@arcadis.com>; Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>; U M, Pavana <pavana.um@arcadis.com>; Maruboyina, Saikumar <saikumar.maruboyina@arcadis.com>; Laxmana, Mahesha <Mahesha.Laxmana@arcadis.com>; J, Akash Mohan <akashmohan.j@arcadis.com>; Reddy Andru, Raghu Vikas <raghuvikas.reddyandru@arcadis.com>; Shukla, Ravi Kumar <ravikumar.shukla@arcadis.com>; Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com>; Andrew Macpherson <a.macpherson@moxonarchitects.com>; Godevenos, Georgios <georgios.godevenos@arcadis.com>; Keeling, Sam <sam.keeling@arcadis.com>
10 | 233.01-3 | HS2-000025B2P | Chipping Warden Tunnel South Portal Building | 1MC07-CEK-EL-FRM-CS07_CL13-000002 | P03 | 2024-09-03 | 2024-09-03 |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 | No issues | Combined JSON | [6 empty] | Loaded 192 | 10 - Complete | Lee | Bandi, Venkatesh <venkatesh.bandi@arcadis.com> Shanmugham, Subbarayan <Subbarayan.Shanmugham@arcadis.com>; Harnett, Toby <toby.harnett@arcadis.com>; Foster, Alex <alex.foster@arcadis.com>; Prasad C N, Hari <hari.prasadcn@arcadis.com>; Prerak Agrawal <pkal@cowi.com>; B S, Shashank <shashank.bs@arcadis.com>; Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>; U M, Pavana <pavana.um@arcadis.com>; Maruboyina, Saikumar <saikumar.maruboyina@arcadis.com>; Laxmana, Mahesha <Mahesha.Laxmana@arcadis.com>; J, Akash Mohan <akashmohan.j@arcadis.com>; Reddy Andru, Raghu Vikas <raghuvikas.reddyandru@arcadis.com>; Shukla, Ravi Kumar <ravikumar.shukla@arcadis.com>; Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com>; Andrew Macpherson <a.macpherson@moxonarchitects.com>; Godevenos, Georgios <georgios.godevenos@arcadis.com>; Keeling, Sam <sam.keeling@arcadis.com>
10 | 233.01-3 | HS2-000025B2P | Chipping Warden Tunnel South Portal Building | 1MC07-CEK-EL-FRM-CS07_CL13-000003 | P03 | 2024-09-03 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 | No issues | Combined JSON | [6 empty] | loaded 170 | 10 - Complete | Lee | Bandi, Venkatesh <venkatesh.bandi@arcadis.com> Shanmugham, Subbarayan <Subbarayan.Shanmugham@arcadis.com>; Harnett, Toby <toby.harnett@arcadis.com>; Foster, Alex <alex.foster@arcadis.com>; Prasad C N, Hari <hari.prasadcn@arcadis.com>; Prerak Agrawal <pkal@cowi.com>; B S, Shashank <shashank.bs@arcadis.com>; Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>; U M, Pavana <pavana.um@arcadis.com>; Maruboyina, Saikumar <saikumar.maruboyina@arcadis.com>; Laxmana, Mahesha <Mahesha.Laxmana@arcadis.com>; J, Akash Mohan <akashmohan.j@arcadis.com>; Reddy Andru, Raghu Vikas <raghuvikas.reddyandru@arcadis.com>; Shukla, Ravi Kumar <ravikumar.shukla@arcadis.com>; Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com>; Andrew Macpherson <a.macpherson@moxonarchitects.com>; Godevenos, Georgios <georgios.godevenos@arcadis.com>; Keeling, Sam <sam.keeling@arcadis.com>
10 | 233.01-3 | HS2-000025B2P | Chipping Warden Tunnel South Portal Building | 1MC07-CEK-EL-FRM-CS07_CL13-000004 | P03 | 2024-09-03 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 |  | Combined JSON | [6 empty] | loaded | 10 - Complete | Lee | Bandi, Venkatesh <venkatesh.bandi@arcadis.com> Shanmugham, Subbarayan <Subbarayan.Shanmugham@arcadis.com>; Harnett, Toby <toby.harnett@arcadis.com>; Foster, Alex <alex.foster@arcadis.com>; Prasad C N, Hari <hari.prasadcn@arcadis.com>; Prerak Agrawal <pkal@cowi.com>; B S, Shashank <shashank.bs@arcadis.com>; Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>; U M, Pavana <pavana.um@arcadis.com>; Maruboyina, Saikumar <saikumar.maruboyina@arcadis.com>; Laxmana, Mahesha <Mahesha.Laxmana@arcadis.com>; J, Akash Mohan <akashmohan.j@arcadis.com>; Reddy Andru, Raghu Vikas <raghuvikas.reddyandru@arcadis.com>; Shukla, Ravi Kumar <ravikumar.shukla@arcadis.com>; Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com>; Andrew Macpherson <a.macpherson@moxonarchitects.com>; Godevenos, Georgios <georgios.godevenos@arcadis.com>; Keeling, Sam <sam.keeling@arcadis.com>
10 | 233.01-3 | HS2-000025B2P | Chipping Warden Tunnel South Portal Building | 1MC07-CEK-EL-FRM-CS07_CL13-000005 | P03 | 2024-09-03 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 |  | Combined JSON | [6 empty] | loaded | 10 - Complete | Lee | Bandi, Venkatesh <venkatesh.bandi@arcadis.com> Shanmugham, Subbarayan <Subbarayan.Shanmugham@arcadis.com>; Harnett, Toby <toby.harnett@arcadis.com>; Foster, Alex <alex.foster@arcadis.com>; Prasad C N, Hari <hari.prasadcn@arcadis.com>; Prerak Agrawal <pkal@cowi.com>; B S, Shashank <shashank.bs@arcadis.com>; Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>; U M, Pavana <pavana.um@arcadis.com>; Maruboyina, Saikumar <saikumar.maruboyina@arcadis.com>; Laxmana, Mahesha <Mahesha.Laxmana@arcadis.com>; J, Akash Mohan <akashmohan.j@arcadis.com>; Reddy Andru, Raghu Vikas <raghuvikas.reddyandru@arcadis.com>; Shukla, Ravi Kumar <ravikumar.shukla@arcadis.com>; Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com>; Andrew Macpherson <a.macpherson@moxonarchitects.com>; Godevenos, Georgios <georgios.godevenos@arcadis.com>; Keeling, Sam <sam.keeling@arcadis.com>
10 | 233.01-3 | HS2-000025B2P | Chipping Warden Tunnel South Portal Building | 1MC07-CEK-FI-FRM-CS07_CL13-000001 | P02 | 2024-09-03 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 |  | Combined JSON | [6 empty] | loaded | 10 - Complete | Lee | Bandi, Venkatesh <venkatesh.bandi@arcadis.com> Shanmugham, Subbarayan <Subbarayan.Shanmugham@arcadis.com>; Harnett, Toby <toby.harnett@arcadis.com>; Foster, Alex <alex.foster@arcadis.com>; Prasad C N, Hari <hari.prasadcn@arcadis.com>; Prerak Agrawal <pkal@cowi.com>; B S, Shashank <shashank.bs@arcadis.com>; Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>; U M, Pavana <pavana.um@arcadis.com>; Maruboyina, Saikumar <saikumar.maruboyina@arcadis.com>; Laxmana, Mahesha <Mahesha.Laxmana@arcadis.com>; J, Akash Mohan <akashmohan.j@arcadis.com>; Reddy Andru, Raghu Vikas <raghuvikas.reddyandru@arcadis.com>; Shukla, Ravi Kumar <ravikumar.shukla@arcadis.com>; Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com>; Andrew Macpherson <a.macpherson@moxonarchitects.com>; Godevenos, Georgios <georgios.godevenos@arcadis.com>; Keeling, Sam <sam.keeling@arcadis.com>
10 | 233.01-3 | HS2-000025B2P | Chipping Warden Tunnel South Portal Building | 1MC07-CEK-FI-FRM-CS07_CL13-000003 | P02 | 2024-09-03 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 |  | Combined JSON | [6 empty] | loaded | 10 - Complete | Lee | Bandi, Venkatesh <venkatesh.bandi@arcadis.com> Shanmugham, Subbarayan <Subbarayan.Shanmugham@arcadis.com>; Harnett, Toby <toby.harnett@arcadis.com>; Foster, Alex <alex.foster@arcadis.com>; Prasad C N, Hari <hari.prasadcn@arcadis.com>; Prerak Agrawal <pkal@cowi.com>; B S, Shashank <shashank.bs@arcadis.com>; Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>; U M, Pavana <pavana.um@arcadis.com>; Maruboyina, Saikumar <saikumar.maruboyina@arcadis.com>; Laxmana, Mahesha <Mahesha.Laxmana@arcadis.com>; J, Akash Mohan <akashmohan.j@arcadis.com>; Reddy Andru, Raghu Vikas <raghuvikas.reddyandru@arcadis.com>; Shukla, Ravi Kumar <ravikumar.shukla@arcadis.com>; Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com>; Andrew Macpherson <a.macpherson@moxonarchitects.com>; Godevenos, Georgios <georgios.godevenos@arcadis.com>; Keeling, Sam <sam.keeling@arcadis.com>
10 | 233.01-3 | HS2-000025B2P | Chipping Warden Tunnel South Portal Building | 1MC07-CEK-ME-FRM-CS07_CL13-000001 | P02 | 2024-09-03 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 |  | Combined JSON | [6 empty] | loaded | 10 - Complete | Lee | Bandi, Venkatesh <venkatesh.bandi@arcadis.com> Shanmugham, Subbarayan <Subbarayan.Shanmugham@arcadis.com>; Harnett, Toby <toby.harnett@arcadis.com>; Foster, Alex <alex.foster@arcadis.com>; Prasad C N, Hari <hari.prasadcn@arcadis.com>; Prerak Agrawal <pkal@cowi.com>; B S, Shashank <shashank.bs@arcadis.com>; Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>; U M, Pavana <pavana.um@arcadis.com>; Maruboyina, Saikumar <saikumar.maruboyina@arcadis.com>; Laxmana, Mahesha <Mahesha.Laxmana@arcadis.com>; J, Akash Mohan <akashmohan.j@arcadis.com>; Reddy Andru, Raghu Vikas <raghuvikas.reddyandru@arcadis.com>; Shukla, Ravi Kumar <ravikumar.shukla@arcadis.com>; Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com>; Andrew Macpherson <a.macpherson@moxonarchitects.com>; Godevenos, Georgios <georgios.godevenos@arcadis.com>; Keeling, Sam <sam.keeling@arcadis.com>
10 | 233.01-3 | HS2-000025B2P | Chipping Warden Tunnel South Portal Building | 1MC07-CEK-RC-FRM-CS07_CL13-000001 | P03 | 2024-09-03 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL13-600009 |  | Combined JSON | [6 empty] | loaded | 10 - Complete | Lee | Bandi, Venkatesh <venkatesh.bandi@arcadis.com> Shanmugham, Subbarayan <Subbarayan.Shanmugham@arcadis.com>; Harnett, Toby <toby.harnett@arcadis.com>; Foster, Alex <alex.foster@arcadis.com>; Prasad C N, Hari <hari.prasadcn@arcadis.com>; Prerak Agrawal <pkal@cowi.com>; B S, Shashank <shashank.bs@arcadis.com>; Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>; U M, Pavana <pavana.um@arcadis.com>; Maruboyina, Saikumar <saikumar.maruboyina@arcadis.com>; Laxmana, Mahesha <Mahesha.Laxmana@arcadis.com>; J, Akash Mohan <akashmohan.j@arcadis.com>; Reddy Andru, Raghu Vikas <raghuvikas.reddyandru@arcadis.com>; Shukla, Ravi Kumar <ravikumar.shukla@arcadis.com>; Shettigar, Sushmitha <sushmitha.shettigar@arcadis.com>; Andrew Macpherson <a.macpherson@moxonarchitects.com>; Godevenos, Georgios <georgios.godevenos@arcadis.com>; Keeling, Sam <sam.keeling@arcadis.com>
| 215.02-02 | HS2-00002BJU3 | School Hill Road Realignment | 1MC06-ASC-HW-FRM-CS06_CL09-000045-ACBOS | P8 | 2025-01-29 | 2025-02-07 | 2025-02-10 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600263 |  | com_type and other issues, sent back 04-Feb-2025 | [7 empty] | 10 - Complete | Supriyan | Abedelkareem Alnajajreh <adan@cowi.com> | 1 | 1 | 9
| 215.02-02 | HS2-00002CT8Y | Maintenance Access Road to Pond (Off School Hill Road West) | 1MC06-ASC-HW-FRM-CS06_CL09-000041-ACBOS | P11 | 2025-01-29 | 2025-02-11 | 2025-02-12 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600266 |  | com_type and other issues, sent back 04-Feb-2025 |  | ThcknssM set as 100 PCRA C - Fail 10-feb-24 | 2025-02-11 |  |  |  |  | 10 - Complete | Supriyan | Abedelkareem Alnajajreh <adan@cowi.com> | 1 | 2 | 13
| 229.03 | HS2-00002CTEY | C3.T.22 Catchment | 1MC07-ASC-DR-FRM-CS07_CL12-000017-ACBOS | P01 | 2024-09-03 | 2024-09-10 | 2024-09-11 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600008 |  | Com_type issue, send back on 09-Sept-2024 | [7 empty] | 10 - Complete | Supriyan | S, Pradeep <pradeep.s@arcadis.com> | 1 | 1 | 7
10 | 233.01-3 | HS2-00002NJ07 | Chipping Warden Green Tunnel South Portal | 1MC07-CEK-TN-FRM-CS07_CL13-000009 | P01 | 2024-09-05 |  | 2024-11-08 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600012 | No issues | Multiple issues, sent back on 11-Sept-2024 |  | loaded 8-oct-24 |  | 620 assets | 2024-11-04 | loaded |  | 10 - Complete | Lee | David Pink <dapi@cowi.com> | 46 | 4
10 | 233.01-3 | HS2-00002NJ07 | Chipping Warden Green Tunnel South Portal | 1MC07-ASC-TN-PLN-CS07_CL13-000014-ACBOS | P02 | 2024-09-05 |  | 2024-11-08 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600012 | No issues | Multiple issues, sent back on 11-Sept-2024 |  | loaded 9-oct-24 |  | 40 assets - 660 total | 2024-11-04 | loaded |  | 10 - Complete | Lee | David Pink <dapi@cowi.com> | 46 | 4
10 | 233.01-3 | HS2-00002NJ07 | Chipping Warden Green Tunnel South Portal | 1MC07-ASC-TN-FRM-CS07_CL13-000013-ACBOS | P02 | 2024-09-05 |  | 2024-11-08 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600012 | No issues | Multiple issues, sent back on 11-Sept-2024 |  | loaded 9-oct-24 |  | 358 assets - 1018 total | 2024-11-04 | Loaded |  | 10 - Complete | Lee | David Pink <dapi@cowi.com> | 46 | 4
| UFDR 238.E | HS2-000020CKG | CNO-124-001 | 1MC07-ASC-UT-FRM-CS07_CL24-000015-ACBOS | P01 | 2024-09-06 | 2024-09-06 | 2024-09-11 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600064 | No issues | [8 empty] | 10 - Complete | Lee | T, Sithrubi <sithrubi.t@arcadis.com> | 3 | 0 | 0
| UFDR 205.B | HS2-000020CET | CSO-02-1209 | 1MC06-ASC-UT-FRM-CS04_CL18-000009-ACBOS | P02 | 2024-09-06 |  |  |  | 1MC06-CEK-IM-DAT-CS04_CL18-600047 | [9 empty] | 99 - Cancelled |  | Bowles, Maya <maya.bowles@arcadis.com>
| UFDR 205.B | HS2-000020CEU | CSO-02-1210 | 1MC06-ASC-UT-FRM-CS04_CL18-000010-ACBOS | P02 | 2024-09-06 |  |  |  | 1MC06-CEK-IM-DAT-CS04_CL18-600044 | [9 empty] | 99 - Cancelled |  | Bowles, Maya <maya.bowles@arcadis.com>
| UFDR 205.B | HS2-00002SXNK | Aylesbury South UKPN Substation | 1MC06-ASC-UT-FRM-CS04_CL18-000052-ACBOS | P04 | 2024-09-06 |  |  |  | 1MC06-CEK-IM-DAT-CS04_CL18-600095 | [9 empty] | 99 - Cancelled |  | Bowles, Maya <maya.bowles@arcadis.com>
| UFDR 205.B | HS2-000020CEQ | CSO-02-1208 | 1MC06-ASC-UT-FRM-CS04_CL18-000008-ACBOS | P02 | 2024-09-06 |  |  |  | 1MC06-CEK-IM-DAT-CS04_CL18-600060 | [9 empty] | 99 - Cancelled |  | Bowles, Maya <maya.bowles@arcadis.com>
| 238.01 | HS2-00002BVN8 | C3.L.73 Catchment | 1MC07-ASC-DR-FRM-CS07_CL23-000013-ACBOS | P01 | 2024-09-06 |  | 2024-10-11 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600055 | Fail | OSGB and other issues, sent back on 12-Sept-2024 | 2024-10-09 | HghtMn set as 375 metres?? GTXTL set as yes. Sent back 10-oct-24 | 2024-10-11 |  |  |  |  | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 25 | 2
| 238.01 | HS2-00002CTK8 | Ladbroke Grove Embankment Security Fence Line | 1MC07-ASC-CV-FRM-CS07_CL24-000043-ACBOS | P03 | 2024-09-06 | 2024-09-26 | 2024-09-30 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600046 |  | Uniclass_ID issue, sent back on 17-Sept-2024 |  | PCRA - FAIL - P04 in CM_CRT & Chg - 25-Sep-24 | 2024-09-26 |  |  |  |  | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com> | 2 | 2 | 20
| 238.01 | HS2-00002CTK7 | Ladbroke Grove Embankment Boundary/Perimeter Fence Line | 1MC07-ASC-CV-FRM-CS07_CL24-000023-ACBOS | P04 | 2024-09-06 | 2024-09-24 | 2024-09-25 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600053 |  | OSGB issues, sent back on 17-Sept-2024 | [7 empty] | 10 - Complete | Supriyan | Egan, Conor <Conor.Egan@wsp.com> | 1 | 1 | 18
7 | 215.03 | HS2-00003GEER | C2.L.65 Catchment Model | 1MC06-ASC-DR-FRM-CS06_CL09-000112-ACBOS | P01 | 2024-09-06 | 2024-09-11 | 2024-09-12 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600336 |  | Queries sent regarding 0's and othe not applicable attributes on 11-Sept-2024 | [7 empty] | 10 - Complete | Supriyan | SAIHI Thamer <thamer.saihi@setec.com> | 1 | 1 | 5
3 | 212.5 | HS2-00002VK4B | Stoke Mandeville Bypass North Pedestrian Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL18-000054-ACBOS | P02 | 2024-09-06 |  | 2024-09-17 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600162 | [9 empty] | 10 - Complete | Supriyan | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com> | 7 | 0
3 | 212.5 | HS2-00003BPJH | Oxford Road Embankment Ditch Slab No.11 | 1MC06-ASC-CV-FRM-CS04_CL19-000069-ACBOS | P02 | 2024-09-06 |  | 2024-09-17 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600103 | [9 empty] | 10 - Complete | Supriyan | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com> | 7 | 0
3 | 212.5 | HS2-00003H079 | Aylesbury South Cutting Access Ditch Slab No.2 | 1MC06-ASC-CV-FRM-CS04_CL18-000088-ACBOS | P02 | 2024-09-06 |  | 2024-09-17 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600158 | [9 empty] | 10 - Complete | Supriyan | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com> | 7 | 0
3 | 212.5 | HS2-00003KFPN | Aylesbury South Cutting Access Ditch Slab No.4 | 1MC06-ASC-CV-FRM-CS04_CL18-000091-ACBOS | P02 | 2024-09-06 |  | 2024-09-18 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600167 | [9 empty] | 10 - Complete | Supriyan | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com> | 8 | 0
3 | 212.5 | HS2-00003H07A | Aylesbury North Cutting Access Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL18-000086-ACBOS | P02 | 2024-09-06 |  | 2024-09-17 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600157 | [9 empty] | 10 - Complete | Supriyan | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com> | 7 | 0
3 | 212.5 | HS2-00003H078 | Aylesbury South Cutting Access Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS04_CL18-000087-ACBOS | P01 | 2024-09-06 |  | 2024-09-18 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600159 | [9 empty] | 10 - Complete | Supriyan | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com> | 8 | 0
3 | 212.5 | HS2-00003H07C | Whaddon Hill Cutting Ditch Slab No. 2 | 1MC06-ASC-CV-FRM-CS04_CL19-000072-ACBOS | P01 | 2024-09-06 |  | 2024-09-18 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600101 | [9 empty] | 10 - Complete | Supriyan | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com> | 8 | 0
| UFDR 238.E | HS2-00003L5EE | Ladbroke Grove Farm water supply | 1MC07-ASC-UT-FRM-CS07_CL24-000077-ACBOS | P01 | 2024-09-09 | 2024-09-09 | 2024-09-11 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600122 | No issues | [8 empty] | 10 - Complete | Lee | T, Sithrubi <sithrubi.t@arcadis.com> | 2 | 0 | 0
| 233.01-2 | HS2-00003AQDH | Chipping Warden North Portal - Ditch Crossing 2 | 1MC07-ASC-CV-FRM-CS07_CL13-000018-ACBOS | P03 | 2024-09-09 |  | 2024-09-20 |  | 1MC07-CEK-IM-DAT-CS07_CL13-000002 | [9 empty] | 10 - Complete | Supriyan | PATIL, APOORVA <apoorva.patil@arcadis.com> | 9 | 0
| 218.02-1 | HS2-00002VK47 | EWR culvert watercourse diversion MAS crossing | 1MC06-ASC-CV-FRM-CS06_CL09-000042-ACBOS | P02 | 2024-09-10 | 2024-09-18 | 2024-09-20 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600261 |  | sdslp and OSGB isses, sent back on 18-Sept-2024 | [7 empty] | 10 - Complete | Supriyan | Chakraborty, Ambar <ambar.chakraborty@arcadis.com> | 2 | 1 | 8
| 234.04 | HS2-000001345 | Claydon Road Overbridge | 1MC07-ASC-BR-FRM-CS07_CL14-000004-ACBOS | P01 | 2024-09-11 | 2024-09-12 | 2024-09-16 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600059 | No issues | couple of snake grid missing / Sdslp syntax | 2024-09-12 | [6 empty] | 10 - Complete | Lee | Marshall, Jake <jake.marshall@arcadis.com> | 2 | 1 | 1
10 | 233.01-3 | HS2-00003124M | Chipping Warden Green Tunnel South Portal Mitigation Earthworks | 1MC07-ASC-GT-FRM-CS07_CL13-000005-ACBOS | P03 | 2024-09-12 | 2024-11-19 | 2024-11-25 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600053 |  | Missing assets, sent back on 19-Sept-2024 | 2024-11-19 | [6 empty] | 10 - Complete | Supriyan | J K, Abhishekgowda <abhishekgowda.jk@arcadis.com> | 4 | 1 | 68
10 | 233.01-3 | HS2-000035Q9B | Chipping Warden Green Tunnel - Edgcote Cutting Transition Zone Earthworks | 1MC07-ASC-GT-FRM-CS07_CL26-000012-ACBOS | P01 | 2024-09-12 |  | 2024-11-15 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600164 |  | Com_type, uniclass Isues, send back on 19-Sept-2024 | [7 empty] | 10 - Complete | Supriyan | J K, Abhishekgowda <abhishekgowda.jk@arcadis.com> | 46 | 1
| 204.2-2 | HS2-00002WULG | Stoke Mandeville South Embankment Planting - East Plot 2 | 1MC06-CEK-EV-FRM-CS03_CL17-000004 | tbc | 2024-09-13 |  | 2024-09-16 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600083 | [9 empty] | 10 - Complete | Lee | Clarke, Philip <philip.clarke@arcadis.com> | 1 | 0
| 229.03 | HS2-000020NVF | Footpath AN13 Extension | 1MC07-ASC-HW-FRM-CS07_CL25-000030-ACBOS | P01 | 2024-09-13 |  | 2024-10-04 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600038 | Issue found | Chainge mismatch with SmartForm data. OSGB co-ordinate issues. Send back on 20 Sep 24. | 2024-09-25 | OSGB co-ordinate issues. Send back on 26 Sep 24. | [5 empty] | 10 - Complete | Rakesh | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 15 | 2
| 226.5 | HS2-00002CTE4 | Brackley South Cutting Boundary Fences | 1MC07-ASC-CV-FRM-CS07_CL12-000030-ACBOS | P01 | 2024-09-13 | 2024-09-23 | 2024-09-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600091 | No issues | ACBOS still at WIP; Withdrawn Uniclass, incorrect Com_Typs - sent 17-sep-24 | 2024-09-18 | ACBOS still at WIP; Withdrawn Uniclass, incorrect Com_Typs - sent 18-sep-24 |  | Partha identified some coordinate / legnth anomalies DT to investigate 20-sep-24 | 2024-09-23 |  |  | 10 - Complete | Lee | GOIMARD Thomas <thomas.goimard@setec.com> | 0 | 3 | 10
| 226.5 | HS2-00002CTE9 | Brackley Embankment Boundary Fences | 1MC07-ASC-CV-FRM-CS07_CL12-000028-ACBOS | P02 | 2024-09-13 | 2024-09-20 | 2024-09-20 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600146 | No issues | Partha discovered OS cordinate / IFC mismatch. 19-sep-24 | resolved 19-sep-24 | Snakegrid conversion now has issues on 2 items. Sent back 19-sep-24 | 2024-09-20 |  |  |  |  | 10 - Complete | Lee | GOIMARD Thomas <thomas.goimard@setec.com> | 0 | 2 | 7
| 226.5 | HS2-00002CTEB | Brackley Embankment Security Fences | 1MC07-ASC-CV-FRM-CS07_CL12-000035-ACBOS | P02 | 2024-09-13 | 2024-09-24 | 2024-09-24 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600140 | No issues | Fence Length anomalies identfied reprocess 24-Sep-24 | 2024-09-24 | [6 empty] | 10 - Complete | Lee | GOIMARD Thomas <thomas.goimard@setec.com> | 0 | 1 | 11
| 226.5 | HS2-00002BVK1 | Brackley North Cutting Security Fences | 1MC07-ASC-CV-FRM-CS07_CL12-000036-ACBOS | P01 | 2024-09-13 | 2024-09-13 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600151 | No issues | [8 empty] | 10 - Complete | Lee | GOIMARD Thomas <thomas.goimard@setec.com> | 4 | 0 | 0
| 226.5 | HS2-00002CQQK | Brackley North Cutting Boundary Fences | 1MC07-ASC-CV-FRM-CS07_CL12-000029-ACBOS | P01 | 2024-09-13 | 2024-09-19 | 2024-09-20 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600127 | No issues | Many incomplete cells across all categories - sent back 18-sep-24 | resolved 19-sep-24 | GdMT attribution icomplete on FND - sent back 19-sep-24 | resolved 19-sep-24 |  |  |  |  | 10 - Complete | Lee | GOIMARD Thomas <thomas.goimard@setec.com> | 1 | 2 | 6
| 226.5 | HS2-00002CTE6 | Brackley South Cutting Security Fences | 1MC07-ASC-CV-FRM-CS07_CL12-000037-ACBOS | P01 | 2024-09-13 | 2024-09-19 | 2024-09-24 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600093 | No issues | incorrect UAID_2 for all items - sent back 18-sep-24 | resolved 19-sep-24 |  |  | Partha identified some coordinate / legnth anomalies DT to investigate 20-sep-24 | 2024-09-23 |  |  | 10 - Complete | Lee | GOIMARD Thomas <thomas.goimard@setec.com> | 3 | 2 | 6
| 221.5 | HS2-00002BVHV | C2.L.87 Catchment | 1MC06-ASC-DR-FRM-CS06_CL21-000007-ACBOS | P01 | 2024-09-13 | 2024-09-20 | 2024-09-20 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600058 |  | OSGB and other issues, sent back on 20-Sept-2024 | [7 empty] | 10 - Complete | Supriyan | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 0 | 1 | 7
| 221.5 | HS2-00002CTAX | C2.L.86 Catchment | 1MC06-ASC-DR-FRM-CS06_CL21-000009-ACBOS | P01 | 2024-09-13 |  | 2024-09-20 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600001 | [9 empty] | 10 - Complete | Supriyan | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 5 | 0
| 221.5 | HS2-00002N7WF | Barton Hartshorn Embankment-Ancillary Culvert 087-AC2 | 1MC06-ASC-DR-FRM-CS06_CL21-000047-ACBOS | P01 | 2024-09-13 |  | 2024-09-20 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600015 | [9 empty] | 10 - Complete | Supriyan | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 5 | 0
| 221.5 | HS2-00002YUF9 | Flood Compensation Area-087 | 1MC06-ASC-DR-FRM-CS06_CL21-900060-ACBOS | P01 | 2024-09-13 |  | 2024-09-20 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600084 | [9 empty] | 10 - Complete | Supriyan | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 5 | 0
| 221.5 | HS2-00002EKXU | Godington Ecological Mitigation Site (A) | 1MC06-ASC-EV-FRM-CS06_CL10-000013-ACBOS | P01 | 2024-09-13 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL10-600116 |  | Incomplete ACBOS , sent back on 20-Sept-2024 | [7 empty] | 99 - Cancelled | Supriyan | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com>
| 221.5 | HS2-00003FV0J | Godington West Ecological Pond | 1MC06-ASC-EV-FRM-CS06_CL10-000014-ACBOS | P01 | 2024-09-13 |  | 2024-09-20 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600204 | [9 empty] | 10 - Complete | Supriyan | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 5 | 0
| 221.5 | HS2-0000386UC | 84-SL1 Godington East Embankment Vehicular Bridge-Earthworks Transition | 1MC06-ASC-BR-FRM-CS06_CL10-000028-ACBOS | P01 | 2024-09-13 |  | 2024-09-20 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600206 | [9 empty] | 10 - Complete | Supriyan | KOUEKAM NASSI Gladys Flora <gladys.kouekam-nassi@setec.com> | 5 | 0
| 229.03 | HS2-00002CTEU | Greatworth North Embankment Boundary Perimeter Fence Line | 1MC07-ASC-CV-FRM-CS07_CL12-000109-ACBOS | P01 | 2024-09-16 |  | 2024-09-24 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600034 | [9 empty] | 10 - Complete | Rakesh | Martin, Joel <Joel.Martin@arcadis.com> | 6 | 0
| 229.03 | HS2-00002CTEW | Greatworth North Embankment Security Fence Line | 1MC07-ASC-CV-FRM-CS07_CL12-000110-ACBOS | P01 | 2024-09-16 |  | 2024-10-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600033 | Issue found | Deprecated Uniclass Ss_25_14_67_51 found , Send back to team 23 Sep 24. | 2024-09-25 | Deprecated Uniclass Ss_25_14_67_51 found , Send back to team 27 Sep 24. | [5 empty] | 10 - Complete | Rakesh | Martin, Joel <Joel.Martin@arcadis.com> | 27 | 2
| 229.03 | HS2-00002CTF0 | Greatworth North Cutting Boundary Perimeter Fence Line | 1MC07-ASC-CV-FRM-CS07_CL12-000104-ACBOS | P01 | 2024-09-16 |  | 2024-10-30 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600002 | Issue found | ComType incorrect for BAS class, Send back to team 23 Sep 24. | 2024-09-25 | Multiple ComType for Gate class, Send back to team 23 Sep 24. | 2024-10-18 | Spacing Issue with Com_Type , send back to team on 22 Oct 24. | 28 Oct 24 | Smartform record count mismatch issue , send back to team on 29 Oct 24. |  | 10 - Complete | Rakesh | Martin, Joel <Joel.Martin@arcadis.com> | 32 | 4
| 229.03 | HS2-00002CTF2 | Greatworth North Cutting Security Fence Line | 1MC07-ASC-CV-FRM-CS07_CL12-000108-ACBOS | P01 | 2024-09-16 |  | 2024-10-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600001 | Issue found | Deprecated Uniclass Ss_25_14_67_51 found , Send back to team 23 Sep 24. | 2024-09-25 | Deprecated Uniclass Ss_25_14_67_51 found , Send back to team 27 Sep 24. | [5 empty] | 10 - Complete | Rakesh | Martin, Joel <Joel.Martin@arcadis.com> | 27 | 2
| 226.5 | HS2-00003CPXZ | Brackley South Cutting Planting Plot 1 | 1MC07-ASC-EV-FRM-CS07_CL12-900048 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-16 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600240 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 0 | 0 | 0
| 226.5 | HS2-00003CPY0 | Brackley South Cutting Planting Plot 2 | 1MC07-ASC-EV-FRM-CS07_CL12-900049 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-17 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600241 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 1 | 0 | 0
| 226.5 | HS2-00003CPY1 | Brackley South Cutting Planting Plot 3 | 1MC07-ASC-EV-FRM-CS07_CL12-900050 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-17 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600242 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 1 | 0 | 0
| 226.5 | HS2-00003CPY3 | Brackley South Cutting Planting Plot 4 | 1MC07-ASC-EV-FRM-CS07_CL12-900051 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-17 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600243 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 1 | 0 | 0
| 226.5 | HS2-00003CPY4 | Brackley South Cutting Planting Plot 5 | 1MC07-ASC-EV-FRM-CS07_CL12-900052 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-17 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600244 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 1 | 0 | 0
| 226.5 | HS2-00003CPY5 | Brackley South Cutting Planting Plot 6 | 1MC07-ASC-EV-FRM-CS07_CL12-900053 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600245 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 0 | 0
| 226.5 | HS2-00003CPY6 | Brackley South Cutting Planting Plot 7 | 1MC07-ASC-EV-FRM-CS07_CL12-900054 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600246 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 0 | 0
| 226.5 | HS2-00003CPY8 | Brackley South Cutting Planting Plot 8 | 1MC07-ASC-EV-FRM-CS07_CL12-900055 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600247 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 0 | 0
| 226.5 | HS2-00003CPY9 | Brackley South Cutting Planting Plot 9 | 1MC07-ASC-EV-FRM-CS07_CL12-900056 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600248 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 0 | 0
| 226.5 | HS2-00003CPYA | Brackley South Cutting Planting Plot 10 | 1MC07-ASC-EV-FRM-CS07_CL12-900057 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600249 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 0 | 0
| 226.5 | HS2-00003CPYC | Brackley South Cutting Planting Plot 11 | 1MC07-ASC-EV-FRM-CS07_CL12-900058 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600250 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 0 | 0
| 226.5 | HS2-00003CPYD | Brackley South Cutting Planting Plot 12 | 1MC07-ASC-EV-FRM-CS07_CL12-900059 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600251 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 0 | 0
| 226.5 | HS2-00003CPYE | Brackley South Cutting Planting Plot 13 | 1MC07-ASC-EV-FRM-CS07_CL12-900060 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600252 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 0 | 0
| 226.5 | HS2-00003CPYF | Brackley South Cutting Planting Plot 14 | 1MC07-ASC-EV-FRM-CS07_CL12-900061 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600253 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 0 | 0
| 226.5 | HS2-00003CPYH | Brackley South Cutting Planting Plot 15 | 1MC07-ASC-EV-FRM-CS07_CL12-900062 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600254 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 0 | 0
| 226.5 | HS2-00003CPYJ | Brackley South Cutting Planting Plot 16 | 1MC07-ASC-EV-FRM-CS07_CL12-900063 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-18 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600255 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 2 | 0 | 0
| 226.5 | HS2-00003CPXS | Brackley Embankment Planting Plot 1 | 1MC07-ASC-EV-FRM-CS07_CL12-900043 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600224 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXT | Brackley Embankment Planting Plot 2 | 1MC07-ASC-EV-FRM-CS07_CL12-900044 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600225 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXV | Brackley Embankment Planting Plot 3 | 1MC07-ASC-EV-FRM-CS07_CL12-900064 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600226 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXW | Brackley Embankment Planting Plot 4 | 1MC07-ASC-EV-FRM-CS07_CL12-900046 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600227 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXX | Brackley Embankment Planting Plot 5 | 1MC07-ASC-EV-FRM-CS07_CL12-900047 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600228 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXC | Brackley North Cutting Planting Plot 1 | 1MC07-ASC-EV-FRM-CS07_CL12-900030 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600229 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXD | Brackley North Cutting Planting Plot 2 | 1MC07-ASC-EV-FRM-CS07_CL12-900031 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600230 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXF | Brackley North Cutting Planting Plot 3 | 1MC07-ASC-EV-FRM-CS07_CL12-900032 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600231 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXG | Brackley North Cutting Planting Plot 4 | 1MC07-ASC-EV-FRM-CS07_CL12-900034 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600232 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXH | Brackley North Cutting Planting Plot 5 | 1MC07-ASC-EV-FRM-CS07_CL12-900035 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600233 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXJ | Brackley North Cutting Planting Plot 6 | 1MC07-ASC-EV-FRM-CS07_CL12-900037 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600234 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXL | Brackley North Cutting Planting Plot 7 | 1MC07-ASC-EV-FRM-CS07_CL12-900038 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600235 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXM | Brackley North Cutting Planting Plot 8 | 1MC07-ASC-EV-FRM-CS07_CL12-900039 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600236 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXN | Brackley North Cutting Planting Plot 9 | 1MC07-ASC-EV-FRM-CS07_CL12-900040 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600237 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXQ | Brackley North Cutting Planting Plot 10 | 1MC07-ASC-EV-FRM-CS07_CL12-900041 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600238 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 226.5 | HS2-00003CPXR | Brackley North Cutting Planting Plot 11 | 1MC07-ASC-EV-FRM-CS07_CL12-900042 | P01 | 2024-09-16 | 2024-09-16 | 2024-09-19 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600239 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com> | 3 | 0 | 0
| 234.03 | HS2-00002TGPC | Highfurlong Brook Embankment Access Stair | 1MC07-ASC-CV-FRM-CS07_CL14-000142-ACBOS | P01 | 2024-09-17 |  | 2024-09-20 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600034 | [9 empty] | 10 - Complete | Rakesh | K S, Abhisheka <abhisheka.ks@arcadis.com> | 3 | 0
| 234.03 | HS2-00003E24L | Highfurlong Brook Embankment Access Stair | 1MC07-ASC-CV-FRM-CS07_CL14-000143-ACBOS | P01 | 2024-09-17 |  | 2024-09-20 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600225 | [9 empty] | 10 - Complete | Rakesh | K S, Abhisheka <abhisheka.ks@arcadis.com> | 3 | 0
| 229.03 | HS2-000001071 | Greatworth North Embankment | 1MC07-ASC-GT-FRM-CS07_CL12-000001-ACBOS | P01 | 2024-09-17 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL12-600036 |  | In situ vs precast error, sent back on 23-Sept-2024 | [7 empty] | 99 - Cancelled | Supriyan | K P, Deepak <deepak.kp@arcadis.com>
19 | 202.5-2_2 | HS2-000001363 | Grove Farm Accommodation Underbridge | 1MC06-ASC-BR-FRM-CS03_CL06-000003-ACBOS | P01 | 2024-09-18 |  | 2024-12-17 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600064 | No issues | [8 empty] | 10 - Complete | Lee | L, Surendar <surendar.loganathan@arcadis.com> | 64 | 0
| 201.3-2 | HS2-000001285 | Footpath TLE 2 Accommodation Overbridge | 1MC06-CEK-BR-FRM-CS03_CL05-000037 | P05 | 2024-09-18 |  | 2024-10-04 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600081 | No issues | OS coords fail - many atts set as non integer. Some trailing spaces. Sent back 20-sep-24 | 2024-09-26 | AngSlp still not integer - 2 components set as WTS. Seeking advice. 27-sep-24 | 2024-10-02 | duplication of Components on PLC | 2024-10-03 |  |  | 10 - Complete | Lee | Anne Marie Lauritzen <ANL@cowi.com> | 12 | 3
| 229.03 | HS2-00002CTF5 | Helmdon Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL25-000010-ACBOS | P01 | 2024-09-18 | 2204-09-24 | 2024-10-04 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600006 |  | OSGB issues, sent back on 23-Sept-2024 | [7 empty] | 10 - Complete | Supriyan | S, Pradeep <pradeep.s@arcadis.com> | -46951 | 1 | 65749
10 | 233.01-3 | HS2-000025B2Q | Footpath AE20 & AE21 Reinstatement | 1MC07-ASC-HW-FRM-CS07_CL13-000013-ACBOS | P04 | 2024-09-19 | 2024-11-19 | 2024-11-27 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600008 |  | Trailing space in UAID, sent back on 24-Sept-2024 | 2024-11-19 | [6 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 6 | 1 | 61
10 | 233.01-3 | HS2-00003H5JH | Footpath AE12 | 1MC07-ASC-HW-FRM-CS07_CL13-000003-ACBOS | P01 | 2024-09-19 |  | 2024-10-09 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600042 | [9 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 14 | 0
| 215.01-2 | HS2-00002CT80 | Civil 3D Solids Model - C2.FCC.L.507 Catchment | 1MC06-ASC-DR-FRM-CS05-000032-ACBOS | P01 | 2024-09-19 |  | 2024-10-08 |  | 1MC06-CEK-IM-DAT-CS05-600002 | Issue found | Incorrect values in Com_Type & Sdslp .Send back to team on 24 Sep 24. | 2024-09-24 | OSGB co-ordinate issues. Send back on 26 Sep 24. | 2024-09-27 | OSGB co-ordinate issues. Send back on 27 Sep 24. | 2024-09-27 | OSGB co-ordinate issues. Send back on 30Sep 24. |  | 10 - Complete | Rakesh | SAIHI Thamer <thamer.saihi@setec.com> | 13 | 4
| 235.02 | HS2-000001455 | Banbury Road O/B | 1MC07-ASC-BR-FRM-CS07_CL14-000001-ACBOS | P01 | 2024-09-19 | 2024-09-19 | 2024-09-25 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600017 | No issues | issue with WTS / WPF identified , sent back 24-Sep-24 | 2024-09-24 | [6 empty] | 10 - Complete | Lee | jake.marshall@arcadis.com | 4 | 1 | 0
| 229.03 | HS2-000025B2D | Maintenance Access Road to Pond and MAP (Off Helmdon Road East) and Farm Accommodation Access | 1MC07-ASC-HW-FRM-CS07_CL25-000025-ACBOS | P01 | 2024-09-19 | 2024-09-30 | 2024-10-03 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600041 |  | OSGB and com_Type issues, send abck on 24-Sept-2024 |  | OSGB issues, sent back on 30-Sept-2024 | [5 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 3 | 2 | 11
| 229.03 | HS2-00002CTEZ | Greatworth ATS and South Portal Building Access Road (Off Helmdon Road West) | 1MC07-ASC-HW-FRM-CS07_CL12-000029-ACBOS | P01 | 2024-09-19 | 2024-09-30 | 2024-10-03 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600005 |  | com_Type issues, send abck on 24-Sept-2024 | [7 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com> | 3 | 1 | 11
| 221.5 | HS2-00002EKXU | Godington Ecological Mitigation Site (A) | 1MC06-ASC-EV-REP-CS06_CL10-000001 | P01 | 2024-09-19 |  | 2024-10-11 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600116 |  | COMBINED JSON |  | Chainage / Osgrid issues - sent 26-sep-24 | 2024-10-08 |  |  |  |  | 10 - Complete | Lee | KHABOUZE Zakaria <zakaria.khabouze@setec.com> | 16 | 2
| 221.5 | HS2-00002EKXU | Godington Ecological Mitigation Site (A) | 1MC06-ASC-EV-FRM-CS06_CL10-000013-ACBOS | P01 | 2024-09-19 |  | 2024-10-11 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600116 | No issues | COMBINED JSON |  | combined mteric do not match smartforms ,missing 4 NV-ES-PL-EC sent 26-sep-24 |  |  |  | Loaded 8-oct-24 |  | 10 - Complete | Lee | KHABOUZE Zakaria <zakaria.khabouze@setec.com> | 16 | 3
| 204.2-2 | HS2-00002CT4D | Stoke Mandeville Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS03_CL17-000021-ACBOS | P05 | 2024-09-23 |  | 2024-09-24 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600048 | [9 empty] | 10 - Complete | Rakesh | jrmy@cowi.com | 1 | 0
18 | 222.9 | HS2-00003JYGS | 91-SL4 Tibbetts Farm EFATS UTX Slab | 1MC06-ASC-BR-FRM-CS06_CL21-900012 | P01 | 2024-09-24 |  | 2024-09-27 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600157 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 3 | 0
18 | 222.9 | HS2-00003JYGT | 91-SL5 Tibbetts Farm EFATS UTX Slab | 1MC06-ASC-BR-FRM-CS06_CL21-900013 | P01 | 2024-09-24 |  | 2024-09-27 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600156 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 3 | 0
18 | 222.9 | HS2-00003JYGU | 96-SL1 Whitfield ATS UTX Slab | 1MC07-ASC-BR-FRM-CS07_CL12-900006 | P01 | 2024-09-24 |  | 2024-09-27 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600300 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 3 | 0
18 | 222.9 | HS2-00003JYGV | 96-SL2 Whitfield ATS UTX Slab | 1MC07-ASC-BR-FRM-CS07_CL12-900007 | P01 | 2024-09-24 |  | 2024-09-27 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600299 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 3 | 0
18 | 222.9 | HS2-00003JYGW | 97-SL1 Brackley South Cutting GSMR 47 UTX Slab | 1MC07-ASC-BR-FRM-CS07_CL12-900008 | P01 | 2024-09-24 |  | 2024-09-27 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600298 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 3 | 0
18 | 222.9 | HS2-00003JYGX | 97-SL3 Brackley South Cutting GSMR 47 UTX Slab | 1MC07-ASC-BR-FRM-CS07_CL12-900009 | P01 | 2024-09-24 |  | 2024-10-01 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600297 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 5 | 0
18 | 222.9 | HS2-000037YLR | 88-SL1 Barton to Mixbury Cutting Vehicular Bridge | 1MC06-ASC-BR-FRM-CS06_CL21-900006 | P01 | 2024-09-24 | 2024-10-08 | 2024-10-08 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600154 | Issue found | Embedded length format issue send back to team on 30 Sep 24. | 2024-10-07 | [6 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 0 | 1 | 14
18 | 222.9 | HS2-000037YLS | 88-SL2 Barton to Mixbury Cutting Vehicular Slab | 1MC06-ASC-BR-FRM-CS06_CL21-900005 | P01 | 2024-09-24 |  | 2024-10-03 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600153 | [9 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 7 | 0
18 | 222.9 | HS2-000031EF2 | 92-SL1 Westbury Embankment Pedestrian Slab | 1MC06-ASC-BR-FRM-CS06_CL22-900003 | P01 | 2024-09-24 | 2024-10-10 | 2024-10-15 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600229 |  | Uniclass ID Column BF - incomplete - sent back - 01-10-24 | 2024-10-10 | [6 empty] | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 3 | 1 | 16
18 | 222.9 | HS2-000037YLP | 87-SL4 Barton to Mixbury Cutting Pedestrian Slab | 1MC06-ASC-BR-FRM-CS06_CL21-900007 | P01 | 2024-09-24 |  | 2024-10-04 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600164 | No issues | tiny rebar volume requires clarification. 2-oct-24 | 2024-10-03 | JSON PW placholder not at WIP. | [5 empty] | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 8 | 2
18 | 222.9 | HS2-000037YLT | 88-SL3 Barton to Mixbury Cutting Pedestrian Slab | 1MC06-ASC-BR-FRM-CS06_CL21-900003 | P01 | 2024-09-24 |  | 2024-10-03 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600152 | No issues | [8 empty] | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 7 | 0
18 | 222.9 | HS2-00003JYGN | 89-SL1 Barton to Mixbury Cutting GSMR 42 UTX Slab | 1MC06-ASC-BR-FRM-CS06_CL21-900008 | P01 | 2024-09-24 |  | 2024-10-03 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600158 | No issues | [8 empty] | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 7 | 0
18 | 222.9 | HS2-00003JYGP | 89-SL2 Barton to Mixbury Cutting GSMR 42 UTX Slab | 1MC06-ASC-BR-FRM-CS06_CL21-900009 | P01 | 2024-09-24 |  | 2024-09-30 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600159 | [9 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 4 | 0
18 | 222.9 | HS2-00003JYGQ | 89-SL3 Barton to Mixbury Cutting GSMR 42 UTX Slab | 1MC06-ASC-BR-FRM-CS06_CL21-900010 | P01 | 2024-09-24 |  | 2024-09-30 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600160 | [9 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 4 | 0
18 | 222.9 | HS2-00003JYGR | 89-SL4 Barton to Mixbury Cutting GSMR 42 UTX Slab | 1MC06-ASC-BR-FRM-CS06_CL21-900011 | P01 | 2024-09-24 |  | 2024-09-30 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600161 | [9 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com> | 4 | 0
9 | UFDR 223.A | HS2-000020CH2 | Featherbed Lane | 1MC06-ASC-UT-FRM-CS06_CL22-000048-ACBOS | P01 | 2024-09-25 | 2024-09-30 | 2024-10-08 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600061 |  | ACBOS PCRA missing, and other queries. Sent back on 27-Sept-2024, |  | Asset name mismatch and PCRA of ACBOS, sent back on 01-Oct-2024 |  | 1MC06-ASC-IM-DAT-CS06_CL21-600001 - Incorrect JSON placeholder. Replaced 15-oct-24 |  |  |  | 10 - Complete | Supriyan | Heinen, Richard <richard.heinen@arcadis.com> | 6 | 3 | 5
10 | 233.01-3 | HS2-00003CPYT | Blackgrounds Farm Accommodation Access Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL26-000112-ACBOS | P01 | 2024-09-26 |  | 2024-09-30 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600165 | [9 empty] | 10 - Complete | Supriyan | B, Gopika <gopika.b@arcadis.com>
| 204.0-1 | HS2-000001287 | B4009 Nash Lee Road Overbridge | 1MC06-ASC-BR-FRM-CS03_CL17-000001-ACBOS | P03 | 2024-09-26 | 2024-09-27 | 2024-09-27 | y | 1MC06-CEK-IM-DAT-CS03_CL17-600032 | No issues | 0's found in Rebar valume & Density , HeightMn etc. Waiting for DT for confirmation. Send back on 12 Sep 24. | 12 Sep 2024 | Sdslp & AnglSlp incorrect , send back to team on 13 Sep 24. | 2024-09-26 | Sdslp set as 1 in 0 - purged in house for speed - DT to update PW file in background. | 2024-09-27 |  |  | 10 - Complete | Lee | Lasisi, Adewole <adewole.lasisi@arcadis.com> | 0 | 3 | 1
| 234.03 | HS2-00002TGP3 | ACBOS - Lower Boddington Cutting 113-DC2 | 1MC07-ASC-CV-FRM-CS07_CL14-000126-ACBOS | P01 | 2024-09-26 | 2024-10-07 | 2024-10-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600221 | [9 empty] | 10 - Complete | Supriyan | PATIL, APOORVA <apoorva.patil@arcadis.com> | 0 | 0 | 11
| 234.03 | HS2-00003LAXM | ACBOS - Lower Boddington Cutting 113-DC5 | 1MC07-ASC-CV-FRM-CS07_CL14-000128-ACBOS | P01 | 2024-09-26 | 2024-09-30 | 2024-10-03 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600223 |  | Snake grid co-ordinate are identical, sent back on 27-Sept-2024 | [7 empty] | 10 - Complete | Supriyan | PATIL, APOORVA <apoorva.patil@arcadis.com> | 3 | 1 | 4
| 234.03 | HS2-00003LAXL | ACBOS - Lower Boddington Cutting 113-DC3 | 1MC07-ASC-CV-FRM-CS07_CL14-000127-ACBOS | P01 | 2024-09-26 |  | 2024-09-27 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600222 | [9 empty] | 10 - Complete | Supriyan | Afsal, Muhammed <muhammed.afsal@arcadis.com> | 1 | 0
7 | 215.03 | HS2-00003GNA5 | Calvert Green Overbridge NR Access point Downmain Ch21800 | 1MC06-ASC-CV-FRM-CS06_CL09-000097-ACBOS | P03 | 2024-09-26 |  | 2024-09-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600335 | [9 empty] | 10 - Complete | Supriyan | Wong, Ka Ho <Isaac.wong@arcadis.com> | 1 | 0
| 229.03 | HS2-000020358 | Helmdon Road Realignment | 1MC07-ASC-HW-FRM-CS07_CL25-000019-ACBOS | P02 | 2024-09-30 |  | 2024-10-04 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600039 | No issues | [8 empty] | 10 - Complete | Lee | MarcoAntonio.Tanseco@arcadis.com
| 229.03 | HS2-00002CTET | C3.L.21 Catchment | 1MC07-ASC-DR-FRM-CS07_CL12-000018-ACBOS | P03 | 2024-09-30 |  | 2024-10-04 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600031 | No issues | [8 empty] | 10 - Complete | Lee | S, Pradeep <pradeep.s@arcadis.com>
| 213.02-2 | HS2-00002CT76 | C2.T.49 Catchment | 1MC06-ASC-DR-FRM-CS05-000026-ACBOS | P02 | 2024-10-04 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600122 | Issue found | OSGB issue & Deprecated uniclass found , send back to team on 07 Oct 24. | 2024-10-08 | Deprecated uniclass found , send back to team on 08 Oct 24. | [5 empty] | 99 - Cancelled | Lee | thamer.saihi@setec.com>
| 213.02-2 | HS2-00002CT79 | Civil 3D Solids - P-MCJ-0725-P-MCJ-0728-P-MCJ-0730 | 1MC06-ASC-DR-FRM-CS06_CL09-000002-ACBOS | P02 | 2024-10-04 |  | 2024-10-18 |  | 1MC06-CEK-IM-DAT-CS05-600117 | Issue found | Incorrect Com_Type for Pr_65_52_01_02 .Send Back to team on 08 Oct24. | [7 empty] | 10 - Complete | Rakesh | thamer.saihi@setec.com>
| 204.4-2 | HS2-00002CT38 | Small Dean South Embankment Noise Barrier Line | 1MC06-CEK-CV-FRM-CS03_CL05-000070 | P01 | 2024-10-07 |  | 2024-10-10 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600056 | [9 empty] | 10 - Complete | Supriyan | Trine Norsk <trno@cowi.com>
| 204.4-2 | HS2-00002CT4F | Stoke Mandeville Embankment Noise Barrier Line | 1MC06-CEK-CV-FRM-CS03_CL17-000052 | P01 | 2024-10-07 |  | 2024-10-10 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600050 | [9 empty] | 10 - Complete | Supriyan | Trine Norsk <trno@cowi.com>
10 | 233.01-3 | HS2-00003FV0Q | Chipping Warden Green Tunnel South Portal | 1MC07-ASC-CV-FRM-CS07_CL13-000024-ACBOS | P01 | 2024-10-11 |  | 2024-10-14 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600046 | [9 empty] | 10 - Complete | Rakesh | muhammed.afsal@arcadis.com>
| 230.05-2 | HS2-00002TTH0 | Lower Thorpe North Embankment Ditch Crossing | 1MC07-ASC-CV-FRM-CS07_CL26-000096-ACBOS | P01 | 2024-10-11 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL26-600169 | Issue found | L3 asset count mismatched with EKFB smart form , Send back to team on 14 Oct 24. | 2024-10-15 | DT wants to do some changes in the ACBOS and need a week to hold the process. | [5 empty] | 50 - HOLD | Lee | Devender.Mudiraj@arcadis.com>
| 229.03 | HS2-00002BVKC | Greatworth North Embankment | 1MC07-ASC-GT-FRM-CS07_CL12-000016-ACBOS | P01 | 2024-10-11 | 2024-10-15 | 2024-10-16 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600035 |  | ACBOS PCRA missing,sent back on 14-Oct-2024 | [7 empty] | 10 - Complete | Supriyan | Matthew Coote <mtce@cowi.com>
7 | 215.03 | HS2-00003GEER | C2.L.65 Catchment Model | 1MC06-ASC-DR-FRM-CS06_CL09-000112-ACBOS | P04 | 2024-10-11 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600336 |  | Metrics do not match smartforms Design team are retagging 14-Oct-24 | [7 empty] | 99 - Cancelled | Lee | SAIHI Thamer <thamer.saihi@setec.com>
| 218.02-1 | HS2-0000307ZQ | IMD East Watercourse Pedestrian Crossing 1 | 1MC06-ASC-CV-FRM-CS06_CL09-000073-ACBOS | P02 | 2024-10-14 |  | 2024-10-17 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600259 | [9 empty] | 10 - Complete | Supriyan | albin.thambi@arcadis.com
| 215.02-2 | HS2-00002CX36 | Civil 3D Solids Model - P-RAI-0799 | 1MC06-ASC-DR-FRM-CS06_CL09-000037-ACBOS | P10 | 2024-10-14 |  | 2024-10-18 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600209 | No issues | [8 empty] | 10 - Complete | Lee | SAIHI Thamer <thamer.saihi@setec.com>
| 229.03 | S` | Greatworth North Cutting Landscape Earthworks | 1MC07-ASC-GT-FRM-CS07_CL12-000017-ACBOS | P02 | 2024-10-15 | 2024-10-29 | 2024-10-29 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600009 | Issue found | OSGB issue , Incorrect UAID . Send back to team on 15 Oct 24. | 2024-10-25 | Carriage return issue, send back on 28 Oct 24. | 2024-10-29 |  |  |  |  | 10 - Complete | Rakesh | deepak.kp@arcadis.com>
10 | 233.01-3 | HS2-00003LA5E | Old Airfield Perimeter Track Drainage System | 1MC07-ASC-DR-FRM-CS07_CL13-000010-ACBOS | P01 | 2024-10-15 |  | 2024-10-17 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600054 | Issue found | Carriage return issue in Com_Desc for Cut class,Send Back to team on 16 Oct 24. | [7 empty] | 10 - Complete | Rakesh | B, Gopika <gopika.b@arcadis.com>
13 | 213.07-1 | HS2-00003CCK0 | TB - Flood Compensation Area 071 B | 1MC06-ASC-DR-FRM-CS04_CL20-000133-ACBOS | P04 | 2024-10-15 | 2024-10-16 | 2024-10-18 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600226 |  | OSGB and uniclass_ID issues, sent back on 16-Oct-2024 |  | GRT Com_Rfrnc missing. | [5 empty] | 10 - Complete | Supriyan | Rogers, Andrew <andrew.rogers2@arcadis.com>
11 | 214.06 | HS2-000001309 | SWBMS 3D Model - Foundations | 1MC06-CEK-BR-FRM-CS05-600032 | P01 | 2024-10-15 | 2024-10-25 | 2024-10-25 |  | 1MC06-CEK-IM-DAT-CS05-600113 |  | COMBINED JSON | [7 empty] | 10 - Complete | Supriyan | Bhawna Kathpalia <bhkh@cowi.com>
11 | 214.06 | HS2-000001309 | SHWBMS 3D Model - Superstructure | 1MC06-CEK-BR-FRM-CS05-600033 | P01 | 2024-10-15 | 2024-10-25 | 2024-10-25 |  | 1MC06-CEK-IM-DAT-CS05-600113 |  | COMBINED JSON | [7 empty] | 10 - Complete | Supriyan | Bhawna Kathpalia <bhkh@cowi.com>
11 | 214.06 | HS2-000001309 | Sheephouse Wood Bat Mitigation Structure - Electrical Lightning and Earthing | 1MC06-CEK-EL-FRM-CS05-000003 | P01 | 2024-10-15 | 2024-10-25 | 2024-10-25 |  | 1MC06-CEK-IM-DAT-CS05-600113 |  | COMBINED JSON | [7 empty] | 10 - Complete | Supriyan | Bhawna Kathpalia <bhkh@cowi.com>
| 213.08 | HS2-00002BJTN | HS2-00002C5T1-Footpath QUA 26 Diversion | 1MC06-ASC-HW-FRM-CS05-000033-ACBOS | P01 | 2024-10-15 |  | 2024-10-23 |  | 1MC06-CEK-IM-DAT-CS05-600080 | issue found | OSGB issue found , send back to team on 16 Oct 24. | [7 empty] | 10 - Complete | Supriyan | Khan, Sal <sal.khan@arcadis.com>
3 | 212.5 | HS2-00002EKX8 | Aylesbury Ecological Mitigation Site (B) | 1MC06-ASC-EV-FRM-CS04_CL18-000007-ACBOS | P01 | 2024-10-15 |  | 2024-10-21 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600127 | No issues | [8 empty] | 10 - Complete | Lee | srinatha.ka@arcadis.com
3 | 212.5 | HS2-00002EKXA | Hartwell House Ecological Mitigation Site (A) | 1MC06-ASC-EV-FRM-CS04_CL19-000004-ACBOS | P01 | 2024-10-15 |  | 2024-10-18 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600060 | No issues | [8 empty] | 10 - Complete | Lee | srinatha.ka@arcadis.com
3 | 212.5 | HS2-00002EKXB | Hartwell House Ecological Mitigation Site (B) | 1MC06-ASC-EV-FRM-CS04_CL19-000005-ACBOS | P01 | 2024-10-15 |  | 2024-10-18 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600061 | No issues | [8 empty] | 10 - Complete | Lee | srinatha.ka@arcadis.com
3 | 212.5 | HS2-000035Q98 | Oxford Road Embankment Ditch Slab No.10 | 1MC06-ASC-CV-FRM-CS04_CL19-000056-ACBOS | P01 | 2024-10-16 |  | 2024-10-18 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600104 | [9 empty] | 10 - Complete | Rakesh | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com>
3 | 212.5 | HS2-00003H078 | Aylesbury South Cutting Access Ditch Slab No.1 | 1MC06-ASC-CV-FRM-CS04_CL18-000087-ACBOS | P01 | 2024-10-16 |  | 2024-10-18 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600159 | [9 empty] | 10 - Complete | Rakesh | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com>
3 | 212.5 | HS2-00003H07C | Whaddon Hill Cutting Ditch Slab No. 2 | 1MC06-ASC-CV-FRM-CS04_CL19-000072-ACBOS | P01 | 2024-10-16 |  | 2024-10-18 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600101 | [9 empty] | 10 - Complete | Rakesh | Al Zoubi, Mohamad <mohamad.alzoubi@arcadis.com>
18 | 222.9 | HS2-00003KX2T | 84-SL5 Godington West Embankment Vehicular Bridge (IDB) | 1MC06-ASC-BR-FRM-C002-CL10-900003 | P01 | 2024-10-17 |  | 2024-10-18 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600233 | [9 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003KX2U | 84-SL6 Godington West Embankment Vehicular Bridge (IDB) | 1MC06-ASC-BR-FRM-C002-CL10-900004 | P01 | 2024-10-17 |  | 2024-10-18 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600232 | [9 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
| 218.02-1 | HS2-0000307ZR | IMD East Watercourse Pedestrian Crossing 2 | 1MC06-ASC-CV-FRM-CS06_CL09-000074-ACBOS | P02 | 2024-10-17 |  | 2024-10-24 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600260 | No issues | OS coordinates, withdrawn Uniclass sent back 21-Oct-24 | 2024-10-22 | Dupliacte UAID_3 in GFL - sent back 22-oct-24 | revised 23-oct-24 |  |  |  |  | 10 - Complete | Lee | nagarathinam.pachaiappann@arcadis.com
| 221.5 | HS2-00002CTB3 | Chetwode Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000030-ACBOS | P01 | 2024-10-17 |  | 2024-10-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600012 | No issues | special character found in one com_Typ Fixed in house - waiting for PW ACBOS update before issue. 22-oct-24 |  | Fence length and GIS +10% disparity - DT imply GIS data is at fault. | [5 empty] | 10 - Complete | Lee | zakaria.khabouze@setec.com
| 221.5 | HS2-00002CTB1 | Chetwode Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000024-ACBOS | P01 | 2024-10-17 |  | 2024-10-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600007 | No issues | Com_typ send back 21-oct-24 | revised 21-oct-24 | BRR com_Typ questioned 22-oct-24 | revised 22-oct-24 |  |  |  |  | 10 - Complete | Lee | zakaria.khabouze@setec.com
| 221.5 | HS2-00002CTAT | Chetwode Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000031-ACBOS | P01 | 2024-10-17 |  | 2024-10-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600093 | [9 empty] | 10 - Complete | Rakesh | zakaria.khabouze@setec.com
| 221.5 | HS2-00002CTAR | Chetwode Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000025-ACBOS | P01 | 2024-10-17 |  | 2024-10-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600092 | [9 empty] | 10 - Complete | Rakesh | zakaria.khabouze@setec.com
| 221.5 | HS2-00002CTAH | Godington West Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000034-ACBOS | P01 | 2024-10-17 |  | 2024-10-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600087 | [9 empty] | 10 - Complete | Rakesh | zakaria.khabouze@setec.com
| 221.5 | HS2-00002CTAF | Godington West Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000027-ACBOS | P01 | 2024-10-17 |  | 2024-10-22 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600097 | Issue found | CM_Chg & CM_CRT value is missing , send back to team on 21 Oct 24. | 2024-10-21 | Com_Type incorrect for BRR send back to team on 22 Oct 24. | [5 empty] | 10 - Complete | Rakesh | zakaria.khabouze@setec.com
| 221.5 | HS2-00002CTAA | Godington East Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000033-ACBOS | P01 | 2024-10-17 |  | 2024-10-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600100 | [9 empty] | 10 - Complete | Rakesh | zakaria.khabouze@setec.com
| 221.5 | HS2-00002CTA8 | Godington East Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL10-000029-ACBOS | P01 | 2024-10-17 | 2024-10-28 | 2024-10-30 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600098 |  | Co-ordinate issues found during REVIEW |  | OSGB conversion issues, sent back on 25-Oct-2024 | [5 empty] | 10 - Complete | Supriyan | zakaria.khabouze@setec.com
| 221.5 | HS2-00002CTBB | Barton Hartshorn Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL21-000009-ACBOS | P01 | 2024-10-17 |  | 2024-10-23 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600063 | [9 empty] | 10 - Complete | Supriyan | zakaria.khabouze@setec.com
| 221.5 | HS2-00002CTB9 | Barton Hartshorn Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL21-000006-ACBOS | P01 | 2024-10-17 |  | 2024-10-23 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600055 | [9 empty] | 10 - Complete | Supriyan | zakaria.khabouze@setec.com
20 | 219.1 | HS2-00002CT9Z | Cowley Embankment Noise Barrier Line | 1MC06-ASC-CV-FRM-CS06_CL10-000018-ACBOS | P01 | 2024-10-17 | 2024-10-23 | 2024-10-28 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600061 |  | data type issue, sent back on 22-Oct-2024 | [7 empty] | 10 - Complete | Supriyan | GOIMARD Thomas <thomas.goimard@setec.com>
13 | 213.07-1 | HS2-00003LH5P | Station Road Culvert No.5 and No.16 Headwall Access Stairs Upmain 71825 | 1MC06-ASC-CV-FRM-CS04_CL20-000087-ACBOS | P01 | 2024-10-18 |  | 2024-10-28 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600250 | No issues | [8 empty] | 10 - Complete | Lee | isaac.wong@arcadis.com
| 229.03 | HS2-000001071 | Greatworth North Embankment | 1MC07-ASC-GT-FRM-CS07_CL12-000001-ACBOS | P02 | 2024-10-18 |  | 2024-10-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600036 | No issues | [8 empty] | 10 - Complete | Lee | K P, Deepak <deepak.kp@arcadis.com>
| 221.5 | HS2-00002CTAN | C2.L.83 Catchment | 1MC06-ASC-DR-FRM-CS06_CL10-000028-ACBOS | P01 | 2024-10-18 |  | 2024-10-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600095 | No issues | [8 empty] | 10 - Complete | Lee | youssef.miri@setec.com
| 221.5 | HS2-00002Y0AU | Chetwode Cutting-Ancillary Culvert 085-AC2 | 1MC06-ASC-DR-FRM-CS06_CL10-000068-ACBOS | P01 | 2024-10-18 |  | 2024-10-24 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600131 | No issues | Sdslp set as 0 in 1 - 23-oct-24 | revised 23-oct-24 | [6 empty] | 10 - Complete | Lee | KHABOUZE Zakaria <zakaria.khabouze@setec.com>
7 | 215.03 | HS2-00002CT94 | Calvert Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL09-000091-ACBOS | P02 | 2024-10-18 |  | 2024-10-24 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600193 | Fail | one incorrect uniclass Fence length and GIS +40% disparity - sent back 22-oct-24 | DT have caveats 23-oct-24 | [6 empty] | 10 - Complete | Lee | Whyte, William <William.Whyte@arcadis.com>
7 | 215.03 | HS2-00002CT92 | Calvert Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL09-000089-ACBOS | P02 | 2024-10-18 |  | 2024-10-28 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600198 | No issues | [8 empty] | 10 - Complete | Lee | Whyte, William <William.Whyte@arcadis.com>
17 | 229.01-2 | HS2-00002NJ04 | Greatworth Green Tunnel North Portal | 1MC07-CEK-TN-FRM-CS07_CL25-000008 | P01 | 2024-10-21 |  | 2025-01-08 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600024 | No issues | Combined JSON | 2024-11-27 | 635 assets to load | 2025-01-02 | loaded |  |  |  | 10 - Complete | Lee | David Pink <dapi@cowi.com>
17 | 229.01-2 | HS2-00002NJ04 | Greatworth Green Tunnel North Portal | 1MC07-ASC-TN-FRM-CS07_CL25-000009-ACBOS | P01 | 2024-10-21 |  | 2025-01-08 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600024 | No issues | Combined JSON | 2024-11-27 | 33 assets to load | 2025-01-02 | loaded |  |  |  | 10 - Complete | Lee | David Pink <dapi@cowi.com>
17 | 229.01-2 | HS2-00002NJ04 | Greatworth Green Tunnel North Portal | 1MC07-ASC-TN-FRM-CS07_CL25-000010-ACBOS | P01 | 2024-10-21 |  | 2025-01-08 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600024 | No issues | Combined JSON | 2024-11-27 | 364 to load | 2025-01-02 | loaded |  |  |  | 10 - Complete | Lee | David Pink <dapi@cowi.com>
| 214.03-1 | HS2-00002KRAP | Grendon Underwood Embankment Mitigation Earthworks 3D Model | 1MC06-ASC-GT-FRM-CS05-000022-ACBOS | P01 | 2024-10-21 | 2024-10-28 | 2024-10-30 |  | 1MC06-CEK-IM-DAT-CS05-600143 | No issues | sent back non integer values for MnmmThcknssmm - 25-Oct-24 | 2024-10-28 | MnmmThcknssM is now also integer set as 700. - sent back 28-oct-24 | 2024-10-28 |  |  |  |  | 10 - Complete | Lee | SAIHI Thamer <thamer.saihi@setec.com>
| 213.02-1 | HS2-00002BVGH | Doddershal Embankment Mitigation Earthworks 3D Model | 1MC06-ASC-GT-FRM-CS05-000014-ACBOS | P02 | 2024-10-21 | 2024-10-29 | 2024-10-30 |  | 1MC06-CEK-IM-DAT-CS05-600101 |  | Gtxtl issues and other queries , sent back on 25-Oct-2024 |  | sent back, feedback from CHECK stage on 30-Oct-2024 | [5 empty] | 10 - Complete | Supriyan | SAIHI Thamer <thamer.saihi@setec.com>
| 230.05-2 | HS2-00002TTH0 | Lower Thorpe North Embankment Ditch Crossing | 1MC07-ASC-CV-FRM-CS07_CL26-000096-ACBOS | P02 | 2024-10-22 |  | 2024-10-24 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600169 | [9 empty] | 10 - Complete | Rakesh | Afsal, Muhammed <muhammed.afsal@arcadis.com>
17 | 229.01-2 | HS2-00002CTF6 | Sulgrave Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL25-000003-ACBOS | P02 | 2024-10-22 |  | 2024-10-25 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600005 |  | DT asking for priority | [7 empty] | 10 - Complete | Supriyan | M, Nischitha <nischitha.m@arcadis.com>
| 216.01-2 | HS2-00002CW0B | Sailing Club Access | 1MC06-ASC-HW-FRM-CS06_CL09-000049-ACBOS | P03 | 2024-10-22 |  | 2024-11-12 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600221 | No issues | AnglSlp incorrect in LSS - sent back 28-oct-24 | 2024-11-06 | MnmmTchknss in LSS incorrect syntax. 7-Nov-24 | 2024-11-08 |  |  |  |  | 10 - Complete | Lee | Neglur, Harish <Harish.Neglur@arcadis.com>
| 237.02 | HS2-00003GSK0 | Lower Radbourne Embankment Ecology Pond - 1 | 1MC07-ASC-EV-FRM-CS07_CL23-000002-ACBOS | P03 | 2024-10-22 |  | 2024-10-24 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600149 | [9 empty] | 10 - Complete | Rakesh | B, Gopika <gopika.b@arcadis.com>
| 237.02 | HS2-00003GSK1 | Oxford Canal North Embankment Ecology Pond - 1 | 1MC07-ASC-EV-FRM-CS07_CL23-000003-ACBOS | P03 | 2024-10-22 |  | 2024-10-24 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600150 | [9 empty] | 10 - Complete | Rakesh | B, Gopika <gopika.b@arcadis.com>
| 237.02 | HS2-00003GSK2 | Oxford Canal North Embankment Ecology Pond - 2 | 1MC07-ASC-EV-FRM-CS07_CL23-000004-ACBOS | P03 | 2024-10-22 |  | 2024-10-24 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600151 | [9 empty] | 10 - Complete | Rakesh | B, Gopika <gopika.b@arcadis.com>
| 237.02 | HS2-00003GSK3 | Oxford Canal South Embankment Ecology Pond - 1 | 1MC07-ASC-EV-FRM-CS07_CL23-000005-ACBOS | P03 | 2024-10-22 |  | 2024-10-24 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600152 | [9 empty] | 10 - Complete | Rakesh | B, Gopika <gopika.b@arcadis.com>
| 237.02 | HS2-00003GSK4 | Oxford Canal South Embankment Ecology Pond - 2 | 1MC07-ASC-EV-FRM-CS07_CL23-000006-ACBOS | P03 | 2024-10-22 |  | 2024-10-24 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600154 | [9 empty] | 10 - Complete | Rakesh | B, Gopika <gopika.b@arcadis.com>
| 237.02 | HS2-00003GSK5 | Oxford Canal South Embankment Ecology Pond - 3 | 1MC07-ASC-EV-FRM-CS07_CL23-000007-ACBOS | P03 | 2024-10-22 |  | 2024-10-24 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600153 | [9 empty] | 10 - Complete | Rakesh | B, Gopika <gopika.b@arcadis.com>
| 221.5 | HS2-00003BPJP | Godington East Viaduct Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL10-900030 | P01 | 2024-10-22 |  | 2024-10-29 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600177 | [9 empty] | 10 - Complete | Rakesh | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJQ | Godington East Viaduct Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL10-900031 | P01 | 2024-10-22 |  | 2024-10-29 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600178 | [9 empty] | 10 - Complete | Rakesh | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJM | Godington East Viaduct Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL10-900028 | P01 | 2024-10-22 |  | 2024-10-30 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600179 | [9 empty] | 10 - Complete | Rakesh | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJN | Godington East Viaduct Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL10-900029 | P01 | 2024-10-22 |  | 2024-10-30 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600180 | [9 empty] | 10 - Complete | Rakesh | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJK | Godington East Embankment Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL10-900026 | P01 | 2024-10-22 |  | 2024-10-25 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600174 | [9 empty] | 10 - Complete | Rakesh | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJL | Godington East Embankment Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL10-900027 | P01 | 2024-10-22 |  | 2024-10-30 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600175 | [9 empty] | 10 - Complete | Rakesh | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJJ | Godington East Embankment Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL10-900025 | P01 | 2024-10-22 |  | 2024-10-25 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600176 | [9 empty] | 10 - Complete | Rakesh | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPK2 | Chetwode Embankment Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL10-900044 | P01 | 2024-10-22 |  | 2024-10-29 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600169 | [9 empty] | 10 - Complete | Rakesh | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJY | Chetwode Embankment Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL10-900045 | P01 | 2024-10-22 |  | 2024-10-30 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600170 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJZ | Chetwode Embankment Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL10-900041 | P01 | 2024-10-22 |  | 2024-10-30 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600171 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPK3 | Chetwode Embankment Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL10-900046 | P01 | 2024-10-22 |  | 2024-10-30 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600172 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPK0 | Chetwode Embankment Planting Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL10-900042 | P01 | 2024-10-22 |  | 2024-11-05 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600173 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPK5 | Chetwode Cutting Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL10-900048 | P01 | 2024-10-22 |  | 2024-11-04 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600157 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPK1 | Chetwode Cutting Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL10-900043 | P01 | 2024-10-22 |  | 2024-11-04 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600161 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPK8 | Chetwode Cutting Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL10-900051 | P01 | 2024-10-22 |  | 2024-11-04 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600162 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPKB | Chetwode Cutting Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL10-900054 | P01 | 2024-10-22 |  | 2024-11-04 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600163 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPKD | Chetwode Cutting Planting Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL10-900056 | P01 | 2024-10-22 |  | 2024-11-04 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600164 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPKE | Chetwode Cutting Planting Plot 6 | 1MC06-ASC-EV-FRM-CS06_CL10-900057 | P01 | 2024-10-22 |  | 2024-11-04 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600165 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPK6 | Chetwode Cutting Planting Plot 7 | 1MC06-ASC-EV-FRM-CS06_CL10-900049 | P01 | 2024-10-22 |  | 2024-11-04 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600166 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPK4 | Chetwode Cutting Planting Plot 8 | 1MC06-ASC-EV-FRM-CS06_CL10-900047 | P01 | 2024-10-22 |  | 2024-11-04 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600167 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPK9 | Chetwode Cutting Planting Plot 9 | 1MC06-ASC-EV-FRM-CS06_CL10-900052 | P01 | 2024-10-22 |  | 2024-11-05 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600168 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPK7 | Chetwode Cutting Planting Plot 10 | 1MC06-ASC-EV-FRM-CS06_CL10-900050 | P01 | 2024-10-22 |  | 2024-11-04 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600158 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPKA | Chetwode Cutting Planting Plot 11 | 1MC06-ASC-EV-FRM-CS06_CL10-900053 | P01 | 2024-10-22 |  | 2024-10-28 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600159 | [9 empty] | 10 - Complete | supriyan | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPKC | Chetwode Cutting Planting Plot 12 | 1MC06-ASC-EV-FRM-CS06_CL10-900055 | P01 | 2024-10-22 |  | 2024-10-29 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600160 | [9 empty] | 10 - Complete | Supriyan | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJS | Godington West Embankment Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL10-900033 | P01 | 2024-10-22 |  | 2024-10-29 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600181 | [9 empty] | 10 - Complete | Supriyan | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJT | Godington West Embankment Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL10-900034 | P01 | 2024-10-22 |  | 2024-10-29 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600182 | [9 empty] | 10 - Complete | Supriyan | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJR | Godington West Embankment Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL10-900032 | P01 | 2024-10-22 |  | 2024-10-29 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600183 | [9 empty] | 10 - Complete | Supriyan | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJU | Godington West Embankment Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL10-900035 | P01 | 2024-10-22 |  | 2024-11-05 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600184 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJV | Godington West Viaduct Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL10-900037 | P01.1 | 2024-10-22 |  | 2024-11-05 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600185 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJX | Godington West Viaduct Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL10-900039 | P01.1 | 2024-10-22 |  | 2024-11-05 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600186 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPJW | Godington West Viaduct Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL10-900038 | P01.1 | 2024-10-22 |  | 2024-11-05 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600187 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPKG | Barton Hartshorn Embankment Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL21-900024 | P01 | 2024-10-22 |  | 2024-11-05 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600132 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPKJ | Barton Hartshorn Embankment Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL21-900022 | P01 | 2024-10-22 |  | 2024-11-07 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600109 | [9 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPKH | Barton Hartshorn Embankment Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL21-900021 | P01 | 2024-10-22 |  | 2024-11-07 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600110 | [9 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 221.5 | HS2-00003BPKF | Barton Hartshorn Embankment Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL21-900023 | P01 | 2024-10-22 |  | 2024-11-07 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600111 | [9 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
| 235.01-1 | HS2-00003LGKV | H4a VRS Transition Foundation Banbury Road | 1MC07-ASC-BR-FRM-CS07_CL14-000015-ACBOS | P01 | 2024-10-23 |  | 2024-10-25 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600220 |  | Priority | [7 empty] | 10 - Complete | Lee | liam.addley@arcadis.com
17 | 229.01-2 | HS2-00002CUCC | Banbury Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL25-000004-ACBOS | P01 | 2024-10-23 |  | 2024-11-04 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600004 | [9 empty] | 10 - Complete | Supriyan | M, Nischitha <nischitha.m@arcadis.com>
| 229.01-1 | HS2-00002TMF3 | Greatworth Green Tunnel South Portal Building Electric | 1MC07-ASC-UT-FRM-CS07_CL12-000098-ACBOS | P07 | 2024-10-23 |  | 2024-11-04 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600053 | [9 empty] | 10 - Complete | Supriyan | Lokhande, Juilee <juilee.lokhande@arcadis.com>
| 201.3-2 | HS2-000020134 | Stoneton Lane Green Overbridge | 1MC07-CEK-BR-FRM-CS07_CL14-000003 | P07 | 2024-10-23 | 2024-11-11 | 2024-11-13 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600019 |  | Com_type issue, sent back on 04-Nov-2024 |  | OSGB issues sent back on 06-Nov-2024 | [5 empty] | 10 - Complete | Supriyan | Anne Marie Lauritzen <ANL@cowi.com>
10 | 233.01-3 | HS2-000035Q9A | Footpath AE17 | 1MC07-ASC-HW-FRM-CS07_CL13-000065-ACBOS | P02 | 2024-10-25 |  | 2024-11-05 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600037 | [9 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com>
10 | 233.01-3 | HS2-00003H5JH | Footpath AE12 | 1MC07-ASC-HW-FRM-CS07_CL13-000003-ACBOS | P02 | 2024-10-25 |  | 2024-11-05 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600042 | [9 empty] | 10 - Complete | Supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com>
12 | UFDR 211.A | HS2-00003KUMA | WAD-3 Sub-station Access Road | 1MC06-ASC-HW-FRM-CS04_CL20-000055-ACBOS | P01 | 2024-10-25 | 2024-10-25 | 2024-11-28 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600253 | No issues | OS coordinates. Sent 14-Nov-24 | 2024-11-27 | [6 empty] | 10 - Complete | Lee | Abdelmalik Hassen <ABHS@cowi.com>
10 | 233.01-3 | HS2-00003FV0R | Chipping Warden Green Tunnel South Portal | 1MC07-ASC-CV-FRM-CS07_CL26-000108-ACBOS | P01 | 2024-10-25 |  | 2024-11-05 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600166 | [9 empty] | 10 - Complete | Supriyan | Afsal, Muhammed <muhammed.afsal@arcadis.com>
| 229.03 | HS2-00002CTEU | Greatworth North Embankment Boundary Perimeter Fence Line | 1MC07-ASC-CV-FRM-CS07_CL12-000109-ACBOS | P03 | 2024-10-25 |  | 2024-10-30 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600034 | [9 empty] | 10 - Complete | Rakesh | Joel.Martin@arcadis.com
11 | 214.06 | HS2-000001310 | Footpath SCL13 Green Overbridge3D Model | 1MC06-CEK-BR-FRM-CS06_CL09-000007 | P06 | 2024-10-25 |  | 2024-11-06 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600123 | [9 empty] | 10 - Complete | supriyan | Bhawna Kathpalia <bhkh@cowi.com>
14 | UFDR 214.A | HS2-00002TUPJ | FCC Sidings Telecoms | 1MC06-ASC-UT-FRM-CS05-000019-ACBOS | P03 | 2024-10-25 |  | 2024-10-31 | YES | 1MC06-CEK-IM-DAT-CS05-600135 | No issues | [8 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
14 | UFDR 214.A | HS2-00002TUPF | FCC Sidings Electric | 1MC06-ASC-UT-FRM-CS05-000018-ACBOS | P02 | 2024-10-25 |  | 2024-10-30 | YES | 1MC06-CEK-IM-DAT-CS05-600132 | No issues | [8 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
14 | UFDR 214.A | HS2-00003KFPT | FCC Sidings UKPN 11kV Switch Site | 1MC06-ASC-UT-FRM-CS05-000039-ACBOS | P01 | 2024-10-25 |  | 2024-10-30 | YES | 1MC06-CEK-IM-DAT-CS05-600303 | No issues | AssetName_2 incorrect - sent back 29-oct-24 | [7 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
14 | UFDR 214.A | HS2-00003E24S | BBOWT Water Supply | 1MC06-ASC-UT-FRM-CS05-000040-ACBOS | P01 | 2024-10-25 |  | 2024-10-30 | YES | 1MC06-CEK-IM-DAT-CS05-600307 | No issues | carriage return in AssetName_3 | [7 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
14 | UFDR 214.A | HS2-00002YCLK | DNO Cabinet to FCC Sidings | 1MC06-ASC-UT-FRM-CS05-000036-ACBOS | P01 | 2024-10-25 |  | 2024-10-31 | YES | 1MC06-CEK-IM-DAT-CS05-600302 | No issues | AssetName_2 incorrect - sent back 29-oct-24 | [7 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
14 | UFDR 214.A | HS2-00002TUPG | FCC Sidings Substation | 1MC06-ASC-UT-FRM-CS05-000015-ACBOS | P01 | 2024-10-25 |  | 2024-10-30 | YES | 1MC06-CEK-IM-DAT-CS05-600133 | No issues | rework AsseName_2 inhouse due to defined value with trailing space |  | SQL won't load Partham advises leave as is | [5 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
14 | UFDR 214.A | HS2-00002TUPH | FCC Sidings Water | 1MC06-ASC-UT-FRM-CS05-000017-ACBOS | P02 | 2024-10-31 |  | 2024-11-04 | YES | 1MC06-CEK-IM-DAT-CS05-600134 | No issues | [8 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
| 226.2 | HS2-00002Y4JL | Brackley South Cutting Radio Compound UTX | 1MC07-ASC-CV-FRM-CS07_CL12-000101-ACBOS | P01 | 2024-10-25 |  | 2024-11-05 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600171 | [9 empty] | 10 - Complete | supriyan | BONICI Alexandra <alexandra.bonici@setec.com>
18 | 222.9 | HS2-00003D82W | Access Stairs 82-ST1 | 1MC06-ASC-CV-FRM-CS06_CL10-900027 | P01 | 2024-10-28 |  | 2024-11-07 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600189 |  | Com_dscrptn incorrect on PW JSON | [7 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D82X | Access Stairs 82-ST2 | 1MC06-ASC-CV-FRM-CS06_CL10-900026 | P01 | 2024-10-28 |  | 2024-11-07 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600190 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D82Y | Access Stairs 83-ST1 | 1MC06-ASC-CV-FRM-CS06_CL10-900025 | P01 | 2024-10-28 |  | 2024-11-07 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600191 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D82Z | Access Stairs 83-ST2 | 1MC06-ASC-CV-FRM-CS06_CL10-900024 | P01 | 2024-10-28 |  | 2024-11-07 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600192 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D832 | Access Stairs 84-ST3 | 1MC06-ASC-CV-FRM-CS06_CL10-900021 | P01 | 2024-10-28 |  | 2024-11-11 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600195 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D833 | Access Stairs 84-ST4 | 1MC06-ASC-CV-FRM-CS06_CL10-900018 | P01 | 2024-10-28 |  | 2024-11-08 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600196 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D834 | Access Stairs 84-ST5 | 1MC06-ASC-CV-FRM-CS06_CL10-900020 | P01 | 2024-10-28 |  | 2024-11-11 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600197 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D835 | Access Stairs 84-ST6 | 1MC06-ASC-CV-FRM-CS06_CL10-900019 | P01 | 2024-10-28 |  | 2024-11-11 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600198 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D836 | Access Stairs 84-ST7 | 1MC06-ASC-CV-FRM-CS06_CL10-900015 | P01 | 2024-10-28 |  | 2024-11-11 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600199 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D837 | Access Stairs 84-ST8 | 1MC06-ASC-CV-FRM-CS06_CL10-900014 | P01 | 2024-10-28 |  | 2024-11-11 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600200 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D838 | Access Stairs 85-ST1 | 1MC06-ASC-CV-FRM-CS06_CL10-900013 | P01 | 2024-10-28 |  | 2024-11-11 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600201 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D839 | Access Stairs 85-ST2 | 1MC06-ASC-CV-FRM-CS06_CL10-900012 | P01 | 2024-10-28 |  | 2024-11-11 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600202 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83A | Access Stairs 86-ST1 | 1MC06-ASC-CV-FRM-CS06_CL10-900011 | P01 | 2024-10-28 |  | 2024-11-11 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600133 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83B | Access Stairs 86-ST2 | 1MC06-ASC-CV-FRM-CS06_CL10-900010 | P01 | 2024-10-28 |  | 2024-11-12 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600203 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83C | Access Stairs 87-ST1 | 1MC06-ASC-CV-FRM-CS06_CL21-900002 | P01 | 2024-10-28 |  | 2024-11-12 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600134 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83D | Access Stairs 87-ST2 | 1MC06-ASC-CV-FRM-CS06_CL21-900001 | P01 | 2024-10-28 |  | 2024-11-12 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600135 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83E | Access Stairs 88-ST1 | 1MC06-ASC-CV-FRM-CS06_CL21-900011 | P01 | 2024-10-28 |  | 2024-11-12 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600162 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83F | Access Stairs 88-ST2 | 1MC06-ASC-CV-FRM-CS06_CL21-900010 | P01 | 2024-10-28 |  | 2024-11-13 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600136 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83G | Access Stairs 88-ST3 | 1MC06-ASC-CV-FRM-CS06_CL21-900009 | P01 | 2024-10-28 |  | 2024-11-13 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600137 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83J | Access Stairs 89-ST1 | 1MC06-ASC-CV-FRM-CS06_CL21-900008 | P01 | 2024-10-28 |  | 2024-11-13 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600138 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83K | Access Stairs 89-ST2 | 1MC06-ASC-CV-FRM-CS06_CL21-900007 | P01 | 2024-10-28 | 2025-01-21 | 2025-01-24 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600139 |  | com_Dscrptns incorrect |  | Wrong ifcprsenation layer sent back on 19-Dec-2024 | [5 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83L | Access Stairs 89-ST3 | 1MC06-ASC-CV-FRM-CS06_CL21-900006 | P01 | 2024-10-28 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600140 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83M | Access Stairs 89-ST4 | 1MC06-ASC-CV-FRM-CS06_CL21-900005 | P01 | 2024-10-28 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600141 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83N | Access Stairs 90-ST1 | 1MC06-ASC-CV-FRM-CS06_CL21-900004 | P01 | 2024-10-28 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600142 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83P | Access Stairs 90-ST2 | 1MC06-ASC-CV-FRM-CS06_CL21-900003 | P01 | 2024-10-28 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600143 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83Q | Access Stairs 91-ST1 | 1MC06-ASC-CV-FRM-CS06_CL22-900008 | P01 | 2024-10-28 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600212 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83R | Access Stairs 91-ST2 | 1MC06-ASC-CV-FRM-CS06_CL22-900007 | P01 | 2024-10-28 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600214 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83S | Access Stairs 92-ST3 | 1MC06-ASC-CV-FRM-CS06_CL22-900006 | P01 | 2024-10-28 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600211 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83T | Access Stairs 92-ST4 | 1MC06-ASC-CV-FRM-CS06_CL22-900005 | P01 | 2024-10-28 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600210 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83U | Access Stairs 92-ST5 | 1MC06-ASC-CV-FRM-CS06_CL22-900004 | P01 | 2024-10-28 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600175 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D83V | Access Stairs 92-ST6 | 1MC06-ASC-CV-FRM-CS06_CL22-900003 | P01 | 2024-10-28 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600181 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D84T | Access Stairs 94-ST17 | 1MC06-ASC-CV-FRM-CS06_CL22-900002 | P01 | 2024-10-28 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600207 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D84U | Access Stairs 94-ST18 | 1MC06-ASC-CV-FRM-CS06_CL22-900001 | P01 | 2024-10-28 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600208 | [9 empty] | 10 - Complete | Rakesh | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D84Z | Access Stairs 95-ST4 | 1MC07-ASC-CV-FRM-CS07_CL12-900003 | P01 | 2024-10-28 | 2025-01-21 | 2025-01-24 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600274 |  | com_Dscrptns incorrect |  | Wrong ifcprsenation layer sent back on 19-Dec-2024 | [5 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D850 | Access Stairs 95-ST5 | 1MC07-ASC-CV-FRM-CS07_CL12-900002 | P01 | 2024-10-28 | 2025-01-21 | 2025-01-24 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600273 |  | com_Dscrptns incorrect |  | Wrong ifcprsenation layer sent back on 19-Dec-2024 | [5 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D854 | Access Stairs 97-ST3 | 1MC07-ASC-CV-FRM-C003-CL12-900001 | P01 | 2024-10-28 | 2025-01-21 | 2025-01-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600269 |  | com_Dscrptns incorrect |  | Wrong ifcprsenation layer sent back on 19-Dec-2024 | [5 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003FV0S | Access Stairs 97-ST4 | 1MC07-ASC-CV-FRM-C003-CL12-900002 | P01 | 2024-10-28 | 2025-01-21 | 2025-01-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600303 |  | com_Dscrptns incorrect |  | Wrong ifcprsenation layer sent back on 19-Dec-2024 | [5 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D855 | Access Stair 98-ST1 | 1MC07-ASC-CV-FRM-CS07_CL12-900013 | P01 | 2024-10-28 | 2025-01-21 | 2025-01-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600268 |  | com_Dscrptns incorrect |  | Wrong ifcprsenation layer sent back on 19-Dec-2024 | [5 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D857 | Access Stair 98-ST3 | 1MC07-ASC-CV-FRM-CS07_CL12-900012 | P01 | 2024-10-28 | 2025-01-21 | 2025-01-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600266 |  | com_Dscrptns incorrect |  | Wrong ifcprsenation layer sent back on 19-Dec-2024 | [5 empty] | 10 - Complete | Supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D858 | Access Stair 98-ST4 | 1MC07-ASC-CV-FRM-CS07_CL12-900011 | P01 | 2024-10-28 | 2025-01-21 | 2025-01-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600265 | No issues | com_Dscrptns incorrect |  | Wrong ifcprsenation layer sent back on 19-Dec-2024 | 2025-01-21 |  |  |  |  | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D85A | Access Stairs 99-ST2 | 1MC07-ASC-CV-FRM-CS07_CL12-900010 | P01 | 2024-10-28 | 2025-01-21 | 2025-01-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600263 | No issues | com_Dscrptns incorrect |  | Wrong ifcprsenation layer sent back on 19-Dec-2024 | 2025-01-21 |  |  |  |  | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D85B | Access Stairs 100-ST1 | 1MC07-ASC-CV-FRM-CS07_CL12-900009 | P01 | 2024-10-28 | 2025-01-21 | 2025-01-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600262 | No issues | com_Dscrptns incorrect |  | Wrong ifcprsenation layer sent back on 19-Dec-2024 | 2025-01-21 |  |  |  |  | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D85C | Access Stairs 100-ST2 | 1MC07-ASC-CV-FRM-CS07_CL12-900008 | P01 | 2024-10-28 | 2025-01-21 | 2025-01-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600261 | No issues | com_Dscrptns incorrect |  | Wrong ifcprsenation layer sent back on 19-Dec-2024 | 2025-01-21 |  |  |  |  | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D85D | Access Stairs 100-ST3 | 1MC07-ASC-CV-FRM-CS07_CL12-900007 | P01 | 2024-10-28 | 2025-01-21 | 2025-01-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600260 | No issues | com_Dscrptns incorrect |  | Wrong ifcprsenation layer sent back on 19-Dec-2024 | 2025-01-21 |  |  |  |  | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D85E | Access Stairs 100-ST4 | 1MC07-ASC-CV-FRM-CS07_CL12-900006 | P01 | 2024-10-28 | 2025-01-21 | 2025-01-23 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600259 | No issues | com_Dscrptns incorrect |  | Wrong ifcprsenation layer sent back on 19-Dec-2024 | 2025-01-21 |  |  |  |  | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
10 | 233.01-3 | HS2-00003LCQE | Blackgrounds Farm LV Supply | 1MC07-ASC-UT-FRM-CS07_CL26-000061-ACBOS | P01 | 2024-10-28 | 2024-11-19 | 2024-11-25 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600167 |  | Asset name is wrong, sent back on 06-Nov-2024 | [7 empty] | 10 - Complete | supriyan | T, Sithrubi <sithrubi.t@arcadis.com>
10 | 233.01-3 | HS2-00003LCQD | Blackgrounds Farm Private Water Main | 1MC07-ASC-UT-FRM-CS07_CL26-000063-ACBOS | P01 | 2024-10-28 |  | 2024-11-06 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600168 | [9 empty] | 10 - Complete | supriyan | T, Sithrubi <sithrubi.t@arcadis.com>
18 | 222.9 | HS2-00003KX2V | 84-SL5 Godington West Embankment Vehicular Bridge (IDB) - Earthworks Transition | 1MC06-ASC-BR-FRM-CS06_CL10-000031-ACBOS | P01 | 2024-10-28 | 2024-11-12 | 2024-12-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600235 | [9 empty] | 10 - Complete | supriyan | LABA Dodji <dodji.laba@setec.com>
18 | 222.9 | HS2-00003KX2W | 84-SL6 Godington West Embankment Vehicular Bridge (IDB) - Earthworks Transition | 1MC06-ASC-BR-FRM-CS06_CL10-000033-ACBOS | P01 | 2024-10-28 | 2024-11-12 | 2024-12-23 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600234 | [9 empty] | 10 - Complete | supriyan | LABA Dodji <dodji.laba@setec.com>
18 | 222.9 | HS2-0000386UD | 88-SL1 Barton to Mixbury Cutting Vehicular Bridge - Earthworks Transition | 1MC06-ASC-BR-FRM-CS06_CL21-000022-ACBOS | P01 | 2024-10-28 | 2024-11-12 | 2024-12-23 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600144 | [9 empty] | 10 - Complete | supriyan | LABA Dodji <dodji.laba@setec.com>
| 230.05-2 | HS2-00002CTG8 | Lower Thorpe North Embankment Noise Barrier Line | 1MC07-ASC-CV-FRM-CS07_CL26-000112-ACBOS | P02 | 2024-10-28 |  | 2024-10-30 | Yes | 1MC07-CEK-IM-DAT-CS07_CL26-600157 | No issues | [8 empty] | 10 - Complete | Lee | Miller, Eluned <eluned.miller@arcadis.com> | 2 | 0
7 | 215.03 | HS2-00003GEER | C2.L.65 Catchment Model | 1MC06-ASC-DR-FRM-CS06_CL09-000112-ACBOS | P12 | 2024-10-28 | 2024-11-13 | 2024-11-14 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600336 |  | Asset Count mismatch, sent back on 05-Nov-2024 |  | Incomplete ACBOS, sent back on 13-Nov-2024 | [5 empty] | 10 - Complete | Supriyan | SAIHI Thamer <thamer.saihi@setec.com>
| 208.2 | HS2-00002SZLX | Footpath SBH 32 Overbridge Impact Protection Walls | 1MC06-CEK-CV-FRM-CS04_CL19-000047 | P04 | 2024-10-29 |  |  |  | 1MC06-CEK-IM-DAT-CS04_CL19-600017 |  | Design flow issues, sent back on 30-Oct-2024 |  | Wrong-HS2Class sent back on 26-Nov-2024 | [5 empty] | 30 - Sent back to team | Supriyan | Harry Forbes <HRFO@COWI.COM>
| 206.1-2 | HS2-00002WUTU | Princes Risborough To Aylesbury Line Planting-East Plot 1 | 1MC06-ASC-EV-REP-CS04_CL18-000001 | P01 | 2024-10-29 |  | 2024-11-08 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600173 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 206.1-2 | HS2-00002WUTV | Princes Risborough To Aylesbury Line Planting-East Plot 2 | 1MC06-ASC-EV-REP-CS04_CL18-000002 | P01 | 2024-10-29 |  | 2024-11-08 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600174 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 206.1-2 | HS2-00002WUTW | Princes Risborough To Aylesbury Line Planting-East Plot 3 | 1MC06-ASC-EV-REP-CS04_CL18-000003 | P01 | 2024-10-29 |  | 2024-11-08 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600175 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 206.1-2 | HS2-00002WUTX | Princes Risborough To Aylesbury Line Planting-West Plot 1 | 1MC06-ASC-EV-REP-CS04_CL18-000004 | P01 | 2024-10-29 |  | 2024-11-08 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600176 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 206.1-2 | HS2-00002WUTY | Princes Risborough To Aylesbury Line Planting-West Plot 2 | 1MC06-ASC-EV-REP-CS04_CL18-000005 | P01 | 2024-10-29 |  | 2024-11-08 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600177 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 206.1-2 | HS2-00002WUTZ | Princes Risborough To Aylesbury Line Planting-West Plot 3 | 1MC06-ASC-EV-REP-CS04_CL18-000006 | P01 | 2024-10-29 |  | 2024-11-08 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600178 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 208.2 | HS2-00002CT5P | C2.T.27 Catchment | 1MC06-ASC-DR-FRM-CS04_CL19-000005-ACBOS | P07 | 2024-10-29 | 2024-11-04 | 2024-11-12 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600016 |  | PRIORITY PLEASE |  | coordinates update | 2024-11-04 | one coordinate outside site boundary - 7-nov-24 | 2024-11-08 |  |  | 10 - Complete | Lee | srinatha.ka@arcadis.com
| 215.01-2 | HS2-000001044 | Civil 3D Solids Model - 077-L1-77725-808621 | 1MC06-ASC-GT-FRM-CS06_CL09-000003-ACBOS | P02 | 2024-10-29 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600122 |  | Asset count mismatch and other issues, send back on 11-Nov-2024 | [7 empty] | 99 - Cancelled | supriyan | BENHMIDA Fedi <fedi.benhmida@setec.com>
18 | 222.9 | HS2-00003JAYD | Footpath 308-2 Link | 1MC06-ASC-HW-FRM-CS06_CL21-000023-ACBOS | P01 | 2024-10-29 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600147 | [9 empty] | 10 - Complete | supriyan | youssef.miri@setec.com
18 | 222.9 | HS2-00003JAYE | Footpath 308-3 Link | 1MC06-ASC-HW-FRM-CS06_CL21-000024-ACBOS | P01 | 2024-10-29 |  | 2024-11-13 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600148 | [9 empty] | 10 - Complete | supriyan | youssef.miri@setec.com
10 | 233.01-3 | HS2-00003LGKW | Chipping Warden Green Tunnel South Security Fence | 1MC07-ASC-CV-FRM-CS07_CL13-000144-ACBOS | P01 | 2024-10-30 | 2024-11-07 | 2024-11-11 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600055 |  | sent back. Com_type and other issues on 6-Nov-2024 |  | Problems found again, sent back on 07-Nov-2024 | [5 empty] | 10 - Complete | Supriyan | Martin, Joel <Joel.Martin@arcadis.com>
10 | 233.01-3 | HS2-00003LGKX | Chipping Warden Green Tunnel North Security Fence | 1MC07-ASC-CV-FRM-CS07_CL14-000145-ACBOS | P01 | 2024-10-30 | 2024-11-07 | 2024-11-08 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600227 |  | sent back. Com_type and other issues on 6-Nov-2024 |  | Issues found again, sent abck on 07-Nov-2024 | [5 empty] | 10 - Complete | Supriyan | Martin, Joel <Joel.Martin@arcadis.com>
7 | 215.03 | HS2-00003GNA4 | IMD Ancillary Accesses | 1MC06-ASC-HW-FRM-CS06_CL09-000100-ACBOS | P01 | 2024-10-31 |  | 2024-11-07 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600356 | No issues | Wromg UAID_1, sent back on 05-Oct-2024 | 2024-11-07 | [6 empty] | 10 - Complete | Lee | Ambrose, Shaun <shaun.ambrose@arcadis.com>
7 | 215.03 | HS2-00003GNA3 | OXD Ancillary Accesses | 1MC06-ASC-HW-FRM-CS06_CL09-000102-ACBOS | P01 | 2024-10-31 |  | 2024-11-06 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600355 |  | PRIORITY PLEASE | [7 empty] | 10 - Complete | Supriyan | Ambrose, Shaun <shaun.ambrose@arcadis.com>
7 | 215.03 | HS2-00002TTH1 | Calvert Cutting Ancillary Accesses | 1MC06-ASC-HW-FRM-CS06_CL09-000108-ACBOS | P01 | 2024-10-31 |  | 2024-11-06 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600354 |  | PRIORITY PLEASE | [7 empty] | 10 - Complete | Supriyan | Ambrose, Shaun <shaun.ambrose@arcadis.com>
| 229.03 | HS2-00003JYH5 | Greatworth North Cutting Planting-Plot 1 | 1MC07-ASC-EV-REP-CS07_CL12-000004 | P01 | 2024-10-31 |  | 2024-11-07 |  | 1MC07-CEK-IM-DAT-CS07-600001 | No issues | zz CAD layer used. | 2024-11-07 | [6 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 229.03 | HS2-00003JYH6 | Greatworth North Cutting Planting-Plot 2 | 1MC07-ASC-EV-REP-CS07_CL12-000005 | P01 | 2024-10-31 | 2024-10-31 | 2024-11-07 |  | 1MC07-CEK-IM-DAT-CS07-600002 | No issues | [8 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 229.03 | HS2-00003JYH7 | Greatworth North Cutting Planting-Plot 3 | 1MC07-ASC-EV-REP-CS07_CL12-000006 | P01 | 2024-10-31 | 2024-10-31 | 2024-11-07 |  | 1MC07-CEK-IM-DAT-CS07-600003 | No issues | [8 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 229.03 | HS2-00003JYH2 | Greatworth North Embankment Planting-Plot 1 | 1MC07-ASC-EV-REP-CS07_CL12-000007 | P01 | 2024-10-31 |  | 2024-11-07 |  | 1MC07-CEK-IM-DAT-CS07-600004 | No issues | zz CAD layer used. | 2024-11-07 | [6 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 229.03 | HS2-00003JYH3 | Greatworth North Embankment Planting-Plot 2 | 1MC07-ASC-EV-REP-CS07_CL12-000008 | P01 | 2024-10-31 |  | 2024-11-07 |  | 1MC07-CEK-IM-DAT-CS07-600005 | No issues | zz CAD layer used. | 2024-11-07 | [6 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 229.03 | HS2-00003JYH4 | Greatworth North Embankment Planting-Plot 3 | 1MC07-ASC-EV-REP-CS07_CL12-000009 | P01 | 2024-10-31 | 2024-10-31 | 2024-11-07 |  | 1MC07-CEK-IM-DAT-CS07-600006 | No issues | [8 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00003KFPP | Aylesbury South Cutting Ecology Pond - 1 | 1MC06-ASC-EV-FRM-CS04_CL18-000024-ACBOS | P01 | 2024-10-31 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600169 | [9 empty] | 10 - Complete | supriyan | srinatha.ka@arcadis.com
3 | 212.5 | HS2-00003KFPQ | Aylesbury South Cutting Ecology Pond - 2 | 1MC06-ASC-EV-FRM-CS04_CL18-000026-ACBOS | P01 | 2024-10-31 |  | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600170 | [9 empty] | 10 - Complete | supriyan | srinatha.ka@arcadis.com
3 | 212.5 | HS2-00003KFPR | Aylesbury South Cutting Ecology Pond - 3 | 1MC06-ASC-EV-FRM-CS04_CL18-000028-ACBOS | P01 | 2024-10-31 |  | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600171 | [9 empty] | 10 - Complete | supriyan | srinatha.ka@arcadis.com
3 | 212.5 | HS2-00003KFPS | Aylesbury North Cutting Ecology Pond - 1 | 1MC06-ASC-EV-FRM-CS04_CL18-000022-ACBOS | P01 | 2024-10-31 |  | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600172 | [9 empty] | 10 - Complete | supriyan | srinatha.ka@arcadis.com
15 | UFDR 216.I | HS2-00003GEEP | Portway Farm Slurry Pipe | 1MC06-ASC-UT-FRM-CS06_CL09-000105-ACBOS | P01 | 2024-10-31 |  | 2024-12-03 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600353 |  | 2 AssetDescription_3 not set 4 trailing spaces in AssetDescription_2 All | 2024-11-29 | DT revised overnight | 2024-12-02 |  |  |  |  | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
7 | 215.03 | HS2-00003LGKQ | P-RAI-0786 Ditch Crossing MAS | 1MC06-ASC-CV-FRM-CS06_CL09-000103-ACBOS | P01 | 2024-11-01 |  | 2024-11-11 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600352 | Issue found | Com_type incorrect 07/11/24. | 2024-10-08 | [6 empty] | 10 - Complete | Rakesh | Isaac.wong@arcadis.com
5 | 201.0-1 | HS2-00002CT2G | C2.T.3 Catchment | 1MC06-ASC-DR-FRM-CS03_CL05-000017-ACBOS | P01 | 2024-11-04 | 2024-11-27 | 2024-11-29 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600151 |  | OSGB and Com_type isses, sent back on 25-Nov-2024 | [7 empty] | 10 - Complete | supriyan | srinatha.ka@arcadis.com
3 | 212.5 | HS2-00003KR5H | Ditch slab-1 crossing for HV Cables at GSM-R Compound Point 26 | 1MC06-ASC-CV-FRM-CS04_CL18-000092-ACBOS | P01 | 2024-11-05 |  | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600179 | [9 empty] | 10 - Complete | Rakesh | Rutherford, Max <max.rutherford@arcadis.com>
3 | 212.5 | HS2-00003KR5J | Ditch slab-2 crossing for LV Cables at GSM-R Compound Point 26 | 1MC06-ASC-CV-FRM-CS04_CL18-000093-ACBOS | P01 | 2024-11-05 |  | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600180 | [9 empty] | 10 - Complete | Rakesh | Rutherford, Max <max.rutherford@arcadis.com>
3 | 212.5 | HS2-00003LCQ9 | Ditch slab-3 crossing for HV Cables at GSM-R Compound Point 26 | 1MC06-ASC-CV-FRM-CS04_CL18-000094-ACBOS | P01 | 2024-11-05 |  | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600181 | [9 empty] | 10 - Complete | Rakesh | Rutherford, Max <max.rutherford@arcadis.com>
3 | 212.5 | HS2-00003LCQA | Ditch slab-4 crossing for HV Cables at GSM-R Compound Point 26 | 1MC06-ASC-CV-FRM-CS04_CL18-000095-ACBOS | P01 | 2024-11-05 |  | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600182 | [9 empty] | 10 - Complete | Rakesh | Rutherford, Max <max.rutherford@arcadis.com>
3 | 212.5 | HS2-00003LGKN | Ditch slab-5 crossing for HV Cables at GSM-R Compound Point 32 | 1MC06-ASC-CV-FRM-CS04_CL20-000085-ACBOS | P01 | 2024-11-05 |  | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600251 | [9 empty] | 10 - Complete | Rakesh | Rutherford, Max <max.rutherford@arcadis.com>
3 | 212.5 | HS2-00003LGKP | Ditch slab-6 crossing for HV Cables at GSM-R Compound Point 32 | 1MC06-ASC-CV-FRM-CS04_CL20-000086-ACBOS | P01 | 2024-11-05 |  |  |  | 1MC06-CEK-IM-DAT-CS04_CL20-600252 | issue found | OSGB tolerance issue send back to team on 19 Nov 24. | [7 empty] | 10 - Complete | Rakesh | Rutherford, Max <max.rutherford@arcadis.com>
| 235.01 | HS2-00003LA5C | Boddington Cutting | 1MC07-ASC-CV-FRM-CS07_CL14-000124-ACBOS | P02 | 2024-11-05 |  | 2024-11-12 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600218 |  | PRIORITY PLEASE | [7 empty] | 10 - Complete | supriyan | PHILIPOSE, IMMANUEL <immanuel.philipose@arcadis.com>
| 235.01 | HS2-00003LA5D | Boddington Cutting | 1MC07-ASC-CV-FRM-CS07_CL14-000125-ACBOS | P02 | 2024-11-05 |  | 2024-11-12 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600219 |  | PRIORITY PLEASE | [7 empty] | 10 - Complete | supriyan | PHILIPOSE, IMMANUEL <immanuel.philipose@arcadis.com>
5 | 201.0-1 | HS2-00002CT2D | C2.L.8 Catchment | 1MC06-ASC-DR-FRM-CS03_CL05-000003-ACBOS | P01 | 2024-11-05 | 2024-11-27 | 2024-11-29 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600062 | [9 empty] | 10 - Complete | supriyan | Hallado, Ruel <Ruel.Hallado@arcadis.com>
3 | 212.5 | HS2-00002WULZ | Aylesbury Embankment Planting-East Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL18-000007 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600128 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUM0 | Aylesbury Embankment Planting-East Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL18-000008 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600129 | No issues | L3 Asset scope created. |  | zz-zz Uniclass altered to EF_45_90 - DT amending PW MPDT concurrently - to be checked before issue of JSON | 2024-11-19 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUM1 | Aylesbury Embankment Planting-West Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL18-000009 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600130 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUM2 | Aylesbury Embankment Planting-West Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL18-000010 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-21 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600131 | No issues | L3 Asset scope created. |  | zz-zz Uniclass altered to EF_45_90 - DT amending PW MPDT concurrently - to be checked before issue of JSON | [5 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUM3 | Aylesbury North Cutting Planting-East Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL18-000011 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600132 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUM4 | Aylesbury North Cutting Planting-East Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL18-000012 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600133 | No issues | L3 Asset scope created. |  | zz-zz Uniclass altered to EF_45_90 - DT amending PW MPDT concurrently - to be checked before issue of JSON | 2024-11-19 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUM5 | Aylesbury North Cutting Planting-East Plot 3 | 1MC06-CEK-EV-FRM-CS04_CL18-000013 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600134 | No issues | L3 Asset scope created. |  | zz-zz Uniclass altered to EF_45_90 - DT amending PW MPDT concurrently - to be checked before issue of JSON | 2024-11-19 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUM6 | Aylesbury North Cutting Planting-East Plot 4 | 1MC06-CEK-EV-FRM-CS04_CL18-000014 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-21 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600135 | No issues | L3 Asset scope created. |  | zz-zz Uniclass altered to EF_45_90 - DT amending PW MPDT concurrently - to be checked before issue of JSON | [5 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUM7 | Aylesbury North Cutting Planting-West Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL18-000015 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600136 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUM8 | Aylesbury North Cutting Planting-West Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL18-000016 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-21 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600137 | No issues | L3 Asset scope created. |  | zz-zz Uniclass altered to EF_45_90 - DT amending PW MPDT concurrently - to be checked before issue of JSON Withdrawn Uniclass changed - SL_32_65_59 to En_32_65_59 Open grasslands | [5 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUM9 | Aylesbury North Cutting Planting-West Plot 3 | 1MC06-CEK-EV-FRM-CS04_CL18-000017 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600138 | No issues | L3 Asset scope created. |  | zz-zz Uniclass altered to EF_45_90 - DT amending PW MPDT concurrently - to be checked before issue of JSON | 2024-11-19 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WULP | Aylesbury South Cutting Planting-East Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL18-000018 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600116 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WULQ | Aylesbury South Cutting Planting-East Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL18-000019 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600117 | No issues | L3 Asset scope created. |  | zz-zz Uniclass altered to EF_45_90 - DT amending PW MPDT concurrently - to be checked before issue of JSON | 2024-11-19 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WULR | Aylesbury South Cutting Planting-East Plot 3 | 1MC06-CEK-EV-FRM-CS04_CL18-000020 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-20 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600118 | No issues | L3 Asset scope created. |  | zz-zz Uniclass altered to EF_45_90 - DT amending PW MPDT concurrently - to be checked before issue of JSON | 2024-11-19 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WULS | Aylesbury South Cutting Planting-East Plot 4 | 1MC06-CEK-EV-FRM-CS04_CL18-000021 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600119 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WULT | Aylesbury South Cutting Planting-East Plot 5 | 1MC06-CEK-EV-FRM-CS04_CL18-000022 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-21 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600120 | No issues | L3 Asset scope created. |  | zz-zz Uniclass altered to EF_45_90 - DT amending PW MPDT concurrently - to be checked before issue of JSON | [5 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WULU | Aylesbury South Cutting Planting-West Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL18-000023 | P01 | 2024-11-05 | 2024-11-05 |  |  | 1MC06-CEK-IM-DAT-CS04_CL18-600121 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WULV | Aylesbury South Cutting Planting-West Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL18-000024 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-21 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600122 | No issues | L3 Asset scope created. |  | zz-zz Uniclass altered to EF_45_90 - DT amending PW MPDT concurrently - to be checked before issue of JSON | [5 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WULW | Aylesbury South Cutting Planting-West Plot 3 | 1MC06-CEK-EV-FRM-CS04_CL18-000025 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-21 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600123 | No issues | L3 Asset scope created. |  | zz-zz Uniclass altered to EF_45_90 - DT amending PW MPDT concurrently - to be checked before issue of JSON | [5 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WULX | Aylesbury South Cutting Planting-West Plot 4 | 1MC06-CEK-EV-FRM-CS04_CL18-000026 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-21 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600124 | No issues | L3 Asset scope created. |  | UAID_1 Column BE incorrect - corrected in house MPDT to catch up 19-Nov-24 | 2024-11-20 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WULY | Aylesbury South Cutting Planting-West Plot 5 | 1MC06-CEK-EV-FRM-CS04_CL18-000027 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-25 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600125 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUMA | Oxford Road Embankment Planting-East Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL19-000008 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-25 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600055 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUMB | Oxford Road Embankment Planting-East Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL19-000009 | P01 | 2024-11-05 |  | 2024-11-25 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600056 | No issues | L3 Asset scope created. |  | zz-zz Uniclass altered to EF_45_90 - DT amending PW MPDT concurrently - to be checked before issue of JSON | [5 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUMC | Oxford Road Embankment Planting-West Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL19-000010 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-25 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600057 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUMD | Oxford Road Embankment Planting-West Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL19-000011 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-25 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600058 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUME | Oxford Road Embankment Planting-West Plot 3 | 1MC06-CEK-EV-FRM-CS04_CL19-000012 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-25 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600059 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUMF | Whaddon Hill Cutting Planting-East Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL19-000023 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-28 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600062 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUMG | Whaddon Hill Cutting Planting-East Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL19-000024 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-28 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600063 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUMH | Whaddon Hill Cutting Planting-West Plot 1 | 1MC06-CEK-EV-FRM-CS04_CL19-000025 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-28 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600064 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUMJ | Whaddon Hill Cutting Planting-West Plot 2 | 1MC06-CEK-EV-FRM-CS04_CL19-000026 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-28 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600065 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUMK | Whaddon Hill Cutting Planting-West Plot 3 | 1MC06-CEK-EV-FRM-CS04_CL19-000027 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-28 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600066 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
3 | 212.5 | HS2-00002WUML | Whaddon Hill Cutting Planting-West Plot 4 | 1MC06-CEK-EV-FRM-CS04_CL19-000028 | P01 | 2024-11-05 | 2024-11-05 | 2024-11-28 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600067 | No issues | L3 Asset scope created. | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
7 | 215.03 | HS2-00003KUM9 | HS2-00002C5T4-Addison Road to School Hill FP Drainage | 1MC06-ASC-DR-FRM-CS06_CL09-000113-ACBOS | P01 | 2024-11-05 | 2024-11-12 | 2024-11-14 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600357 | No issues | OS coordinates. Uniclass clarifications. Sent 7-Nov-24 | 2024-11-12 | [6 empty] | 10 - Complete | Lee | Muthappan, Rani <rani.muthappan@arcadis.com>
| UFDR 217.B | HS2-00002C3X7 | CSO-03-6103 | 1MC06-ASC-UT-FRM-CS06_CL09-000026-ACBOS | P02 | 2024-11-05 | 2024-11-05 | 2024-12-04 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600118 | No issues | [8 empty] | 10 - Complete | Lee | maya.bowles@arcadis.com
| 234.05 | HS2-000020351 | Cedars Farm Accommodation Overbridge | 1MC07-ASC-BR-FRM-CS07_CL14-000006-ACBOS | P01 | 2024-11-05 | 2024-12-03 | 2024-12-04 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600081 | No issues | WPF ComTyp fixed in house DT to catch up before JSON issue 22-nov-24 SnakeGrids are all reversed. Sent back 25-Nov-24 |  | 2024-11-26 | [5 empty] | 10 - Complete | Lee | Sherlock, Maura <maura.sherlock@arcadis.com>
7 | 215.03 | HS2-00003124D | Calvert Footpath and Cycleway-north section | 1MC06-ASC-HW-FRM-CS06_CL09-000082-ACBOS | P01 | 2024-11-05 |  | 2024-11-11 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600339 | No issues | FND - MnmmThcknssM set to Zero. Com_Typ for PR code classes fixed inhouse - DT to update ACBOs overnight for resubmission. Sent 7-Nov-24 | 2024-11-08 | [6 empty] | 10 - Complete | Lee | Cooper, Craig <craig.cooper@arcadis.com>
7 | 215.03 | HS2-00003FV0H | IMD East Access Road | 1MC06-ASC-HW-FRM-CS06_CL09-000107-ACBOS | P01 | 2024-11-05 |  | 2024-11-11 | YES | 1MC06-CEK-IM-DAT-CS06_CL09-600273 | No issues | [8 empty] | 10 - Complete | Lee | Cooper, Craig <craig.cooper@arcadis.com>
5 | 201.0-1 | HS2-00002Y849 | South Heath Cutting Perturbation Crossover UTX | 1MC06-ASC-CV-FRM-CS03_CL05-000065-ACBOS | P01 | 2024-11-06 | 2024-11-26 | 2024-11-27 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600185 |  | sdslp not as per format, sent back on 25-Nov-2024 | [7 empty] | 10 - Complete | supriyan | T R, Aishwarya <aishwarya.tr@arcadis.com>
7 | 215.03 | HS2-00003KUM8 | Calvert Bridleway - North Section | 1MC06-ASC-HW-FRM-CS06_CL09-000109-ACBOS | P01 | 2024-11-07 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600358 | No issues | OS coordinates. Sent 14-Nov-24 | 2024-11-14 | [6 empty] | 10 - Complete | Lee | Cooper, Craig <craig.cooper@arcadis.com>
| 223.4 | HS2-000001329 | Bridleway 303/4 Overbridge | 1MC06-CEK-BR-FRM-CS06_CL22-000004 | P06 | 2024-11-07 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL22-600056 |  | HOLD - DT still working RevP09 |  | Multiple issues, sent back on 20-Dec-2024 | [5 empty] | 99 - Cancelled | supriyan | gabin.duport@arcadis.com>
| 220 | HS2-000001050 | Godington East Viaduct | 1MC06-CEK-BR-FRM-CS06_CL10-000001 | P09 | 2024-11-08 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL10-600112 | No issues | Com_typs / OS coords / IFC mismatches / withdrawn Uniclasses - sent back 27-Nov-24 | 2025-01-06 | Com_Typ / Dscrptn not fixed one withdrawn Uniclass still remains 8-Jan-25 |  | ON HOLD - DT reworking Parapets |  |  |  | 50 - HOLD | Lee | Duport, Gabin <gabin.duport@arcadis.com>
| 220 | HS2-000001052 | Godington West Viaduct | 1MC06-CEK-BR-FRM-CS06_CL10-000002 | P04 | 2024-11-08 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL10-600113 | FAIL | Com_typs / OS coords / IFC mismatches / withdrawn Uniclasses - sent back 27-Nov-24 | 2025-01-06 | Com_Typ / Dscrptn not fixed one withdrawn Uniclass still remains 8-Jan-25 |  | ON HOLD - DT reworking Parapets |  |  |  | 50 - HOLD | Lee | Duport, Gabin <gabin.duport@arcadis.com>
10 | 233.01-3 | HS2-00003JRGA | Chipping Warden Green Tunnel North Portal-Evacuation Walkways | 1MC07-ASC-CV-FRM-CS07_CL14-000149-ACBOS | P01 | 2024-11-08 | 2024-11-13 | 2024-11-15 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600195 |  | Wrong Maximum Loading, sent back on 13-Nov-2024 | [7 empty] | 10 - Complete | supriyan | Quinn, Emma <emma.quinn@arcadis.com>
7 | 215.03 | HS2-00003JAYB | Addison Road to School Hill Public Footpath | 1MC06-ASC-HW-FRM-CS06_CL09-000104-ACBOS | P01 | 2024-11-08 |  | 2024-11-15 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600359 | No issues | com_typ / Anglslp - 14-nov-24 |  | fixed in house - wait for DT to update PW version | 2024-11-14 |  |  |  |  | 10 - Complete | Lee | Cooper, Craig <craig.cooper@arcadis.com>
13 | 213.07-1 | HS2-00002CT73 | Quainton Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS05-000123-ACBOS | P02 | 2024-11-11 |  | 2024-12-10 |  | 1MC06-CEK-IM-DAT-CS05-600075 |  | Difference in length, sent back on 10-Dec-2024 | [7 empty] | 10 - Complete | supriyan | William.Whyte@arcadis.com
13 | 213.07-1 | HS2-00002CT72 | Quainton Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS05-000121-ACBOS | P02 | 2024-11-11 |  | 2024-12-10 |  | 1MC06-CEK-IM-DAT-CS05-600096 |  | Difference in length, sent back on 10-Dec-2024 | [7 empty] | 10 - Complete | supriyan | William.Whyte@arcadis.com
| 212.4 | HS2-00002Y47A | Bicester Road Embankment No.3 Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL20-000073-ACBOS | P02 | 2024-11-11 | 2025-01-03 | 2025-01-09 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600238 | No issues | Com_typ in PIL incorrect - 3-dec-24 | 2025-01-03 | [6 empty] | 10 - Complete | Lee | shreyas.alagundi@arcadis.com
3 | 212.5 | HS2-00003JKXR | Bicester Road Embankment No.5 Ditch Slab | 1MC06-ASC-CV-FRM-CS04_CL20-000084-ACBOS | P01 | 2024-11-11 |  | 2024-11-19 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600249 | [9 empty] | 10 - Complete | Rakesh | shreyas.alagundi@arcadis.com
10 | 233.01-3 | HS2-00003JRG9 | Chipping Warden Green Tunnel South Portal-Evacuation Walkways | 1MC07-ASC-CV-FRM-CS07_CL26-000148-ACBOS | P01 | 2024-11-12 | 2024-11-13 | 2024-11-15 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600044 |  | Wrong OSGB co-ordinate, sent back on 13-Nov-2024 | [7 empty] | 10 - Complete | supriyan | emma.quinn@arcadis.com>
| 216.01-2 | HS2-00002VK46 | Twyford East Ditch Crossing MAS | 1MC06-ASC-CV-FRM-CS06_CL10-000044-ACBOS | P02 | 2024-11-12 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL10-600188 | No issues | [8 empty] | 10 - Complete | Lee | Thambi, Albin <albin.thambi@arcadis.com>
| 216.01-2 | HS2-00002ZJQJ | TWY/4 Footpath Crossing-Pedestrian | 1MC06-ASC-CV-FRM-CS06_CL09-000059-ACBOS | P03 | 2024-11-12 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600253 | No issues | [8 empty] | 10 - Complete | Lee | Thambi, Albin <albin.thambi@arcadis.com>
10 | 233.01-3 | HS2-000020NXK | Culworth Road Turning Head | 1MC07-ASC-HW-FRM-CS07_CL26-000035-ACBOS | P02 | 2024-11-12 |  | 2024-12-02 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600023 | [9 empty] | 10 - Complete | Rakesh | MarcoAntonio.Tanseco@arcadis.com
10 | 233.01-3 | HS2-000020NXM | Chipping Warden South Portal Access Road (Off Culworth Road) | 1MC07-ASC-HW-FRM-CS07_CL26-000036-ACBOS | P02 | 2024-11-12 |  | 2024-12-02 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600021 | [9 empty] | 10 - Complete | Rakesh | MarcoAntonio.Tanseco@arcadis.com
10 | 233.01-3 | HS2-000035Q99 | Footpath AE16 | 1MC07-ASC-HW-FRM-CS07_CL13-000017-ACBOS | P02 | 2024-11-12 |  | 2024-12-03 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600036 | [9 empty] | 10 - Complete | Rakesh | MarcoAntonio.Tanseco@arcadis.com
1 | 238.02 | HS2-00002J4YY | Footpath SM33 Diversion - upgrade to bridleway (east of HS2) | 1MC07-ASC-HW-FRM-CS07_CL24-000030-ACBOS | P01 | 2024-11-12 |  | 2024-11-21 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600025 | Issue found | DsgnLf values are missing .Send back to team on 18 Nov 24. | 2024-11-19 | Incorrect UAID 3 , Send back to team on 20 Nov 24. | [5 empty] | 10 - Complete | Rakesh | MarcoAntonio.Tanseco@arcadis.com
7 | 215.03 | HS2-00003H6P1 | Calvert Cutting planting Plot 18 | 1MC06-CEK-EV-FRM-CS06_CL09-600002 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600319 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
7 | 215.03 | HS2-00003H6P2 | Calvert Cutting planting Plot 19 | 1MC06-ASC-EV-FRM-CS06_CL09-900035 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600360 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
7 | 215.03 | HS2-00003H6P3 | Calvert Cutting planting Plot 20 | 1MC06-CEK-EV-FRM-CS06_CL09-600003 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600320 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
7 | 215.03 | HS2-00003H6P4 | Calvert Cutting planting Plot 21 | 1MC06-CEK-EV-FRM-CS06_CL09-600004 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600321 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
7 | 215.03 | HS2-00003H6P5 | Calvert Cutting planting Plot 22 | 1MC06-CEK-EV-FRM-CS06_CL09-600005 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600322 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
7 | 215.03 | HS2-00003H6P6 | Calvert Cutting planting Plot 23 | 1MC06-CEK-EV-FRM-CS06_CL09-600006 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600323 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
7 | 215.03 | HS2-00003H6P7 | Calvert Cutting planting Plot 24 | 1MC06-CEK-EV-FRM-CS06_CL09-600007 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600324 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
7 | 215.03 | HS2-00003H6P8 | Calvert Cutting planting Plot 25 | 1MC06-CEK-EV-FRM-CS06_CL09-600008 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600325 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
7 | 215.03 | HS2-00003H6P9 | Calvert Cutting planting Plot 26 | 1MC06-CEK-EV-FRM-CS06_CL09-600009 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600326 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
7 | 215.03 | HS2-00003H6PA | Calvert Cutting planting Plot 27 | 1MC06-CEK-EV-FRM-CS06_CL09-600010 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600327 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
7 | 215.03 | HS2-00003H6PB | Calvert Cutting planting Plot 28 | 1MC06-CEK-EV-FRM-CS06_CL09-600011 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600328 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
7 | 215.03 | HS2-00003H6PC | Calvert Cutting planting Plot 29 | 1MC06-CEK-EV-FRM-CS06_CL09-600012 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600329 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
7 | 215.03 | HS2-00003H6PD | Calvert Cutting planting Plot 30 | 1MC06-CEK-EV-FRM-CS06_CL09-600013 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600330 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
7 | 215.03 | HS2-00003H6PE | Calvert Cutting planting Plot 31 | 1MC06-CEK-EV-FRM-CS06_CL09-600014 | P01 | 2024-11-12 |  | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600331 | No issues | [8 empty] | 10 - Complete | Lee | louis.knight@setec.com
13 | 213.07-1 | HS2-0000307ZS | Station Road Cycle Track Crossing 2 | 1MC06-ASC-CV-FRM-CS05_CL09-900015 | P01 | 2024-11-12 | 2024-12-16 | 2024-12-19 |  | 1MC06-CEK-IM-DAT-CS05-600188 |  | ACBOS placeholder confusion |  | Krbhgt issue, sent back on 13-Dec-2024 | [5 empty] | 10 - Complete | supriyan | alex.fowler@arcadis.com
13 | 213.07-1 | HS2-00002Z3NH | Station Road MAS Crossing 1 | 1MC06-ASC-CV-FRM-CS05-000069-ACBOS | P01 | 2024-11-12 | 2024-12-16 | 2024-12-19 |  | 1MC06-CEK-IM-DAT-CS05-600187 |  | ACBOS placeholder confusion |  | OSGB issues sent back on 11-Dec-2024 |  | sent back on 13-Dec-2024-Krbhgtcm issues |  |  |  | 10 - Complete | supriyan | alex.fowler@arcadis.com
3 | 212.5 | HS2-00003HWH6 | FMA-1 Accommodation Overbridge | 1MC06-ASC-CV-FRM-CS04_CL20-000083-ACBOS | P01 | 2024-11-13 |  | 2024-11-21 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600247 | [9 empty] | 10 - Complete | Rakesh | Nayak M S, Yogesh <Yogesh.S@arcadis.com>
3 | 212.5 | HS2-00003HWH5 | SBH-32 Overbridge Access Stairs | 1MC06-ASC-CV-FRM-CS04_CL19-000073-ACBOS | P01 | 2024-11-13 |  | 2024-11-21 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600098 | [9 empty] | 10 - Complete | Rakesh | Nayak M S, Yogesh <Yogesh.S@arcadis.com>
3 | 212.5 | HS2-00003HWH4 | SMA-16 Standall’s Farm Footbridge Access Stairs | 1MC06-ASC-CV-FRM-CS04_CL18-000090-ACBOS | P01 | 2024-11-13 |  | 2024-11-21 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600151 | [9 empty] | 10 - Complete | Rakesh | Nayak M S, Yogesh <Yogesh.S@arcadis.com>
3 | 212.5 | HS2-00003LQUL | Thame Valley South Embankment Access Stairs | 1MC06-ASC-CV-FRM-CS04_CL19-000075-ACBOS | P01 | 2024-11-13 |  | 2024-11-22 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600107 | [9 empty] | 10 - Complete | Rakesh | Nayak M S, Yogesh <Yogesh.S@arcadis.com>
3 | 212.5 | HS2-00003LQUM | Thame Valley North Embankment Access Stairs | 1MC06-ASC-CV-FRM-CS04_CL19-000074-ACBOS | P01 | 2024-11-13 |  | 2024-11-22 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600106 | [9 empty] | 10 - Complete | Rakesh | Nayak M S, Yogesh <Yogesh.S@arcadis.com>
| 214.01-2 | HS2-00002BJTY | FCC Sidings Access Road | 1MC06-ASC-HW-FRM-CS05-000026-ACBOS | P01 | 2024-11-13 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600029 |  | Multiple issues, sent back on 06-Jan-2025 | [7 empty] | 30 - Sent back to team | supriyan | Khan, Sal <sal.khan@arcadis.com>
| 214.01-2 | HS2-00002BJTU | Greatmoor Road Realignment | 1MC06-ASC-HW-FRM-CS05-000024-ACBOS | P01 | 2024-11-13 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600032 | [9 empty] | 50 - HOLD | supriyan | Khan, Sal <sal.khan@arcadis.com>
| 214.01-2 | HS2-00002BJTX | Bridleway GUN 28 Diversion | 1MC06-ASC-HW-FRM-CS05-000025-ACBOS | P01 | 2024-11-13 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600034 | [9 empty] | 50 - HOLD | supriyan | Khan, Sal <sal.khan@arcadis.com>
| 214.01-2 | HS2-00002CT82 | Access Road to Greatmoor Sidings NR | 1MC06-ASC-HW-FRM-CS05-000028-ACBOS | P01 | 2024-11-13 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600008 | [9 empty] | 50 - HOLD | supriyan | Khan, Sal <sal.khan@arcadis.com>
17 | 229.01-2 | HS2-00002CTF9 | Greatworth Green Tunnel Boundary Perimeter Fence Line South | 1MC07-ASC-CV-FRM-CS07_CL25-000151-ACBOS | P01 | 2024-11-13 |  | 2024-12-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600080 | No issues | metrics do not match SMRTFRMS - sent back 3-DEC-24 | 2024-12-06 | BRR GIS Length Vs JSON Length mismatch 2610m vs 3588m , Send back to team on 10/12/24 No other issues - could issue with caveat from DT. | [5 empty] | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com>
17 | 229.01-2 | HS2-00003B2GD | Greatworth Green Tunnel Boundary Perimeter Fence Line North | 1MC07-ASC-CV-FRM-CS07_CL25-000150-ACBOS | P01 | 2024-11-13 |  | 2024-12-18 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600078 | FAIL | OS coordinates - sent back 10-dec-24 | [7 empty] | 10 - Complete | supriyan | Martin, Joel <Joel.Martin@arcadis.com>
| 221.5 | HS2-00002Y4JJ | 087-AC2 Watercourse Diversion | 1MC06-ASC-DR-FRM-CS06_CL21-000088-ACBOS | P04 | 2024-11-13 | 2024-11-13 | 2024-11-14 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600087 |  | High Priority | [7 empty] | 10 - Complete | Lee | Rogers, Andrew <andrew.rogers2@arcadis.com>
2 | UFDR 229.D | HS2-000020CJ5 | CSO-04-6105P | 1MC07-ASC-UT-FRM-CS07_CL25-000048-ACBOS | P01 | 2024-11-13 |  | 2024-11-21 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600037 | [9 empty] | 10 - Complete | supriyan | Lokhande, Juilee <juilee.lokhande@arcadis.com>
2 | UFDR 229.D | HS2-000020CJ4 | CSO-04-4300P | 1MC07-ASC-UT-FRM-CS07_CL25-000063-ACBOS | P01 | 2024-11-13 |  | 2024-11-21 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600032 | [9 empty] | 10 - Complete | supriyan | Lokhande, Juilee <juilee.lokhande@arcadis.com>
2 | UFDR 229.D | HS2-000020CJ3 | CSO-04-3110P | 1MC07-ASC-UT-FRM-CS07_CL25-000060-ACBOS | P01 | 2024-11-13 |  | 2024-11-21 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600031 | [9 empty] | 10 - Complete | supriyan | Lokhande, Juilee <juilee.lokhande@arcadis.com>
2 | UFDR 229.D | HS2-00003KLDE | CSO-04-6105T1 | 1MC07-ASC-UT-FRM-CS07_CL25-000082-ACBOS | P01 | 2024-11-13 |  | 2024-11-21 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600074 | [9 empty] | 10 - Complete | supriyan | Lokhande, Juilee <juilee.lokhande@arcadis.com>
2 | UFDR 229.D | HS2-00003KLDD | CSO-04-4300T1 | 1MC07-ASC-UT-FRM-CS07_CL25-000080-ACBOS | P01 | 2024-11-13 |  | 2024-11-21 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600073 | [9 empty] | 10 - Complete | supriyan | Lokhande, Juilee <juilee.lokhande@arcadis.com>
2 | UFDR 229.D | HS2-00003KLDC | CSO-04-3110T1 | 1MC07-ASC-UT-FRM-CS07_CL25-000078-ACBOS | P01 | 2024-11-13 |  | 2024-11-21 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600072 | [9 empty] | 10 - Complete | supriyan | Lokhande, Juilee <juilee.lokhande@arcadis.com>
2 | UFDR 229.D | HS2-00003CPXB | Clean Water Pipe CFA_15_23a | 1MC07-ASC-UT-FRM-CS07_CL14-000037-ACBOS | P01 | 2024-11-13 |  | 2024-11-21 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600228 | [9 empty] | 10 - Complete | supriyan | Lokhande, Juilee <juilee.lokhande@arcadis.com>
| 227 | HS2-00002NNHW | Brackley Culvert Watercourse Diversion | 1MC07-ASC-DR-FRM-CS07_CL12-000082-ACBOS | P02 | 2024-11-15 |  | 2024-12-04 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600042 | No issues | [8 empty] | 10 - Complete | Lee | Bulusu, Sai Sravan Kumar <saisravankumar.bulusu@arcadis.com>
17 | 229.01-2 | HS2-00002WUPB | Greatworth Green Tunnel Planting-Plot 4 | 1MC07-ASC-EV-REP-CS07_CL25-000001 | P01 | 2024-11-15 | 2024-12-11 | 2024-12-11 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600060 |  | Wrong UAID_2, sent back on 10-Dec-2024 | [7 empty] | 10 - Complete | supriyan | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
17 | 229.01-2 | HS2-00002WUPC | Greatworth Green Tunnel Planting-Plot 5 | 1MC07-ASC-EV-REP-CS07_CL25-000002 | P01 | 2024-11-15 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600061 | [9 empty] | 10 - Complete | supriyan | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
17 | 229.01-2 | HS2-00002WUPD | Greatworth Green Tunnel Planting-Plot 6 | 1MC07-ASC-EV-REP-CS07_CL25-000003 | P01 | 2024-11-15 | 2024-12-11 | 2024-12-11 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600062 |  | Wrong UAID_2, sent back on 10-Dec-2024 | [7 empty] | 10 - Complete | supriyan | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
17 | 229.01-2 | HS2-00002WUPE | Greatworth Green Tunnel Planting-Plot 7 | 1MC07-ASC-EV-REP-CS07_CL25-000004 | P01 | 2024-11-15 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600063 |  | No Record in EKFB smartform and in data | [7 empty] | 99 - Cancelled | supriyan | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
17 | 229.01-2 | HS2-00002WUPF | Greatworth Green Tunnel Planting-Plot 8 | 1MC07-ASC-EV-REP-CS07_CL25-000005 | P01 | 2024-11-15 | 2024-12-11 | 2024-12-11 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600064 | [9 empty] | 10 - Complete | supriyan | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
17 | 229.01-2 | HS2-00002WUPG | Greatworth Green Tunnel Planting-Plot 9 | 1MC07-ASC-EV-REP-CS07_CL25-000006 | P01 | 2024-11-15 | 2024-12-11 | 2024-12-11 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600065 | [9 empty] | 10 - Complete | supriyan | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
17 | 229.01-2 | HS2-00002WUPH | Greatworth Green Tunnel Planting-Plot 10 | 1MC07-ASC-EV-REP-CS07_CL25-000007 | P01 | 2024-11-15 | 2024-12-11 | 2024-12-12 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600066 |  | Wrong HS2-Class, sent back on 11-Dec-2024 | [7 empty] | 10 - Complete | supriyan | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
4 | 202.1-3 | HS2-00003H07E | Small Dean Viaduct Network Rail Cutting Reinstatement-East | 1MC06-ASC-GT-FRM-CS03_CL06-000011-ACBOS | P04 | 2024-11-15 |  | 2024-12-10 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600106 | [9 empty] | 10 - Complete | supriyan | SouravKumar.Chatterjee@arcadis.com
4 | 202.1-3 | HS2-00003H07D | Small Dean Viaduct Network Rail Cutting Reinstatement-West | 1MC06-ASC-GT-FRM-CS03_CL06-000012-ACBOS | P04 | 2024-11-15 |  | 2024-12-10 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600105 | [9 empty] | 10 - Complete | supriyan | SouravKumar.Chatterjee@arcadis.com
5 | 201.0-1 | HS2-000001016 | South Heath Cutting | 1MC06-ASC-GT-FRM-CS03_CL05-000004-ACBOS | P07 | 2024-11-15 | 2024-11-27 | 2024-11-29 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600084 | [9 empty] | 10 - Complete | supriyan | SouravKumar.Chatterjee@arcadis.com
5 | 201.0-1 | HS2-00002XQ2N | South Heath Cutting Landscape Earthworks-Bowood Lane East | 1MC06-ASC-GT-FRM-CS03_CL05-000019-ACBOS | P02 | 2024-11-15 | 2024-11-27 | 2024-11-29 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600155 |  | OSGB issues, sent back on 25-Nov-2024 | [7 empty] | 10 - Complete | supriyan | SouravKumar.Chatterjee@arcadis.com
18 | 222.9 | HS2-00003D830 | Access Stairs 84-ST1 | 1MC06-ASC-CV-FRM-CS06_CL10-900023 | P01 | 2024-11-18 |  | 2025-01-03 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600193 | [9 empty] | 10 - Complete | supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D831 | Access Stairs 84-ST2 | 1MC06-ASC-CV-FRM-CS06_CL10-900022 | P01 | 2024-11-18 |  | 2025-01-03 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600194 | [9 empty] | 10 - Complete | supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D84X | Access Stairs 95-ST2 | 1MC07-ASC-CV-FRM-CS07_CL12-900005 | P01 | 2024-11-18 |  | 2025-01-03 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600276 | [9 empty] | 10 - Complete | supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D84Y | Access Stairs 95-ST3 | 1MC07-ASC-CV-FRM-CS07_CL12-900004 | P01 | 2024-11-18 |  | 2025-01-03 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600275 | [9 empty] | 10 - Complete | supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
10 | 233.01-3 | HS2-000020NXG | Blackgrounds Farm Accommodation Access Realignment (off Culworth Road -west of HS2) | 1MC07-ASC-HW-FRM-CS07_CL26-000034-ACBOS | P01 | 2024-11-19 | 2024-12-05 | 2024-12-11 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600022 | No issues | MnmmThcknssM set as 100 PCRA FAIL 4/12/24 | 2024-12-05 | [6 empty] | 10 - Complete | Lee | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com>
6 | UFDR 209.A | HS2-000020CF0 | Aylesbury North Cutting Group | 1MC06-ASC-UT-FRM-CS04_CL18-000037-ACBOS | P01 | 2024-11-19 | 2024-11-27 | 2024-12-02 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600006 |  | ACBOS PCRA is pending, sent back on 27-Nov-2024 | [7 empty] | 10 - Complete | supriyan | Kamboj, Mohit <mohit.kamboj@arcadis.com>
6 | UFDR 209.A | HS2-00002SZLY | Aylesbury North Cutting Group | 1MC06-ASC-UT-FRM-CS04_CL18-000041-ACBOS | P01 | 2024-11-19 | 2024-11-27 | 2024-12-02 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600094 |  | ACBOS PCRA is pending, sent back on 27-Nov-2024 | [7 empty] | 10 - Complete | supriyan | Kamboj, Mohit <mohit.kamboj@arcadis.com>
1 | 238.02 | HS2-00003LCQC | Ladbroke Cutting Landscape Earthwork Tie Ins (below A423 Banbury Road Overbridge) | 1MC07-ASC-CV-FRM-CS07_CL24-900064-ACBOS | P01 | 2024-11-19 | 2024-11-22 |  |  | 1MC07-CEK-IM-DAT-CS07_CL24-600124 | No issues | MnmmTchknssM & MnmmThcknssmm set as M - Fixed in house to expedite. DT updateing PW file. Com_RfrncNmbr set a blank 0 fixed in house - DT updating PW file. 21-nov-24 | 2024-11-21 | [6 empty] | 10 - Complete | Lee | J K, Abhishekgowda <abhishekgowda.jk@arcadis.com>
17 | 229.01-2 | HS2-00003B2GE | Greatworth Green Tunnel Security Fence Line North | 1MC07-ASC-CV-FRM-CS07_CL25-000152-ACBOS | P01 | 2024-11-19 |  | 2024-12-12 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600023 | No issues | [8 empty] | 10 - Complete | Lee | Martin, Joel <Joel.Martin@arcadis.com>
1 | 238.02 | HS2-00002CTKE | Footpath SM33 Diversion (west of HS2) | 1MC07-ASC-HW-FRM-CS07_CL24-000029-ACBOS | P03 | 2024-11-19 | 2024-11-21 | 2024-11-22 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600079 |  | ACBOS PCRA is pending, sent back on 21-Nov-2024 | [7 empty] | 10 - Complete | supriyan | Egan, Conor <Conor.Egan@wsp.com>
1 | 238.02 | HS2-000020P2P | Footpath SM89 Extension | 1MC07-ASC-HW-FRM-CS07_CL24-000024-ACBOS | P05 | 2024-11-19 | 2024-11-21 | 2024-11-25 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600059 |  | OSGB issues, sent back on 21-Nov-2024 | [7 empty] | 10 - Complete | supriyan | Egan, Conor <Conor.Egan@wsp.com>
1 | 238.02 | HS2-00002C3Z1 | A423 Banbury Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL24-000012-ACBOS | P03 | 2024-11-19 | 2024-11-21 | 2024-11-26 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600076 |  | OSGB issues and other queries, sent back on 21-Nov-2024 |  | PCRA FAIL HghtMN. 22-nov-24 | 2024-11-25 |  |  |  |  | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-CV-FRM-CS07_CL25-000006 | P01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | Loaded |  | 657 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-AR-FRM-CS07_CL25-600001 | P03 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | Use P03 as P04 is for post L3 |  | 668 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-ASC-CV-FRM-CS07_CL25-000017-ACBOS | C01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | Loaded |  | 1420 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-ME-FRM-CS07_CL25-000003 | P01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | Loaded |  | 143 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-ME-FRM-CS07_CL25-000002 | P01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | Loaded |  | 325 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-ME-FRM-CS07_CL25-000001 | P01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | Loaded |  | 478 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-FI-FRM-CS07_CL25-000003 | P01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | Loaded |  | 181 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-FI-FRM-CS07_CL25-000002 | P01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | loaded |  | 493 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-FI-FRM-CS07_CL25-000001 | P01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | loaded |  | 257 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-EL-FRM-CS07_CL25-000001 | P01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | Loaded |  | 1455 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-EL-FRM-CS07_CL25-000005 | P01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | loaded |  | 189 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-EL-FRM-CS07_CL25-000004 | P01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | loaded |  | 255 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-EL-FRM-CS07_CL25-000003 | P01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | loaded |  | 170 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-EL-FRM-CS07_CL25-000002 | P01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | loaded |  | 201 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
17 | 229.01-2 | HS2-000025B2F | Greatworth Green Tunnel North portal building | 1MC07-CEK-RC-FRM-CS07_CL25-000003 | P01 | 2024-11-19 | 2024-11-19 |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600056 | No issues | Combined JSON |  | some Uniclass & ZZ-ZZ classifications neede to be confirmed with DT - 18-Dec-24 |  | loaded |  | 36 |  | 10 - Complete | Lee | Lade, Vijaya Krishna <vijayakrishna.lade@arcadis.com>
| 212.4 | HS2-00003B93V | Putlowes Farm Access Road Ditch Slab No.2 | 1MC06-ASC-CV-FRM-CS04_CL20-000080-ACBOS | P02 | 2024-11-20 | 2025-01-03 | 2025-01-08 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600242 | No issues | Com_Typ / Dscrptns incorrect - | 2025-01-03 | [6 empty] | 10 - Complete | Lee | Alagundi, Shreyas <shreyas.alagundi@arcadis.com>
15 | UFDR 216.I | HS2-00002TTR2 | CSO-03-2210P | 1MC06-ASC-UT-FRM-CS06_CL09-000073-ACBOS | P01 | 2024-11-20 |  | 2024-12-02 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600226 |  | 2 AssetDescription_3 not set 4 trailing spaces in AssetDescription_2 All Gas Pipeline route to change to Gas Pressure Route | 2024-11-29 | [6 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
| 216.01-2 | HS2-00002NNHQ | Portway Culvert Watercourse Diversion | 1MC06-ASC-DR-FRM-CS06_CL09-000095-ACBOS | P02 | 2024-11-20 |  | 2024-12-13 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600254 | No issues | Com_Typ / Dscrptns all incorrect Cm_CRT&Chg set to P04 some missing attribution that should be complete sent back 3-dec-24 | 2024-12-06 | [6 empty] | 10 - Complete | Lee | Bulusu, Sai Sravan Kumar <saisravankumar.bulusu@arcadis.com>
| 217.03 | HS2-000001314 | Addison Road Overbridge | 1MC06-CEK-BR-FRM-CS06_CL09-000006 | P12 | 2024-11-20 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600127 | No issues | SdSlp syntax, MnmmThcknssM blank, some ZZ-zz components WTS should be WPF. Sent back 16-dec-24 |  | couple of MTRL / GdMt / Com _Dscrptn concrete inconsistency. Sdslp syntax incorrect and does not macth previous JSON / MPDT works, fixed in house. Talk to Alex / Daniel 8-Jan-25 |  | DT do not need to have JSON issued at this time - HOLD - Possible set for Cancelled status |  |  |  | 50 - HOLD | Lee | Whyte, William <William.Whyte@arcadis.com>
1 | 238.02 | HS2-00003EB33 | Ladbroke Cutting Culvert 124-AC3 Watercourse Tie In | 1MC07-ASC-DR-FRM-CS07_CL24-000056-ACBOS | P01 | 2024-11-20 |  | 2024-11-25 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600123 | Issue found | ComType incorrect , OSGB conversion issue .Send back to team 21 Nov 24. |  | DT have changed data 26-Nov-24 | [5 empty] | 10 - Complete | Rakesh | rhea.duncan@fairhurst.co.uk
3 | 212.5 | HS2-00003LGKP | Ditch slab-6 crossing for HV Cables at GSM-R Compound Point 32 | 1MC06-ASC-CV-FRM-CS04_CL20-000086-ACBOS | P01 | 2024-11-20 |  | 2024-11-22 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600252 | [9 empty] | 10 - Complete | Rakesh | Rutherford, Max <max.rutherford@arcadis.com>
8 | 224.7 | HS2-00003HF3T | C2.L.110 Catchment | 1MC06-ASC-DR-FRM-CS06_CL22-000050-ACBOS | P01 | 2024-11-20 |  | 2024-11-29 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600226 | [9 empty] | 10 - Complete | supriyan | LABA Dodji <dodji.laba@setec.com>
3 | 212.5 | HS2-00002CT5A | Aylesbury Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS04_CL18-000039-ACBOS | P01 | 2024-11-20 |  | 2024-11-27 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600016 | [9 empty] | 10 - Complete | Rakesh | Jennifer McKay <JRMY@COWI.COM>
3 | 212.5 | HS2-00002CT5C | Aylesbury Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS04_CL18-000035-ACBOS | P01 | 2024-11-20 |  | 2024-11-26 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600022 | [9 empty] | 10 - Complete | Rakesh | Jennifer McKay <JRMY@COWI.COM>
3 | 212.5 | HS2-00002CT5H | Aylesbury North Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS04_CL18-000040-ACBOS | P01 | 2024-11-20 |  | 2024-12-05 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600041 | Issue found | Com_Type incorrect .Send back to team on 26 Nov 24. | 3-dec-24 @1600 | [6 empty] | 10 - Complete | Lee | Jennifer McKay <JRMY@COWI.COM>
3 | 212.5 | HS2-00002GUW0 | Aylesbury North Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS04_CL18-000036-ACBOS | P01 | 2024-11-20 |  | 2024-11-26 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600001 | [9 empty] | 10 - Complete | Rakesh | Jennifer McKay <JRMY@COWI.COM>
3 | 212.5 | HS2-00002NL60 | Stoke Mandeville Bypass Fencing | 1MC06-ASC-CV-FRM-CS03_CL17-000028-ACBOS | P01 | 2024-11-20 |  | 2024-12-03 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600070 | [9 empty] | 10 - Complete | Rakesh | Jennifer McKay <JRMY@COWI.COM>
3 | 212.5 | HS2-00002CT5Q | Oxford Road Embankment Boundary Perimeter Line | 1MC06-ASC-CV-FRM-CS04_CL19-000023-ACBOS | P01 | 2024-11-20 |  | 2024-11-26 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600030 | [9 empty] | 10 - Complete | Rakesh | Jennifer McKay <JRMY@COWI.COM>
3 | 212.5 | HS2-00002CT5S | Oxford Road Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS04_CL19-000017-ACBOS | P01 | 2024-11-20 |  | 2024-11-26 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600028 | [9 empty] | 10 - Complete | Rakesh | Jennifer McKay <JRMY@COWI.COM>
3 | 212.5 | HS2-00002CT5U | Whaddon Hill Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS04_CL19-000031-ACBOS | P01 | 2024-11-20 |  | 2024-11-28 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600039 | [9 empty] | 10 - Complete | Rakesh | Jennifer McKay <JRMY@COWI.COM>
3 | 212.5 | HS2-00002CT5W | Whaddon Hill Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS04_CL19-000018-ACBOS | P01 | 2024-11-20 |  | 2024-11-27 |  | 1MC06-CEK-IM-DAT-CS04_CL19-600037 | [9 empty] | 10 - Complete | Rakesh | Jennifer McKay <JRMY@COWI.COM>
1 | 238.02 | HS2-000020P2N | Maintenance Access Road to Pond (Off A423 Banbury Road North) | 1MC07-ASC-HW-FRM-CS07_CL24-000023-ACBOS | P02 | 2024-11-21 | 2024-11-21 |  |  | 1MC07-CEK-IM-DAT-CS07_CL24-600058 | No issues | [8 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com>
1 | 238.02 | HS2-000025B3T | Accommodation Access Road (Off A423 Banbury Road) | 1MC07-ASC-HW-FRM-CS07_CL24-000027-ACBOS | P05 | 2024-11-21 | 2024-11-21 | 2024-11-22 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600066 | No issues | [8 empty] | 10 - Complete | Lee | Phillips, Steve <steve.phillips@wsp.com>
1 | 238.02 | HS2-000025B3V | A423 Banbury Road Realignment | 1MC07-ASC-HW-FRM-CS07_CL24-000031-ACBOS | P05 | 2024-11-21 |  | 2024-11-26 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600067 | No issues | zz-zz classifications. | 2024-11-25 | [6 empty] | 10 - Complete | Lee | Phillips, Steve <steve.phillips@wsp.com>
13 | 213.07-1 | HS2-00003CPW1 | Quainton Cutting Planting Plot 1 | 1MC06-CEK-EV-FRM-CS05-600013 | P01 | 2024-11-21 | 2024-11-21 |  |  | 1MC06-CEK-IM-DAT-CS05-600250 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPW2 | Quainton Cutting Planting Plot 2 | 1MC06-CEK-EV-FRM-CS05-600014 | P01 | 2024-11-21 | 2024-11-21 |  |  | 1MC06-CEK-IM-DAT-CS05-600251 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPW4 | Quainton Cutting Planting Plot 3 | 1MC06-CEK-EV-FRM-CS05-600015 | P01 | 2024-11-21 | 2024-11-21 |  |  | 1MC06-CEK-IM-DAT-CS05-600252 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPW5 | Quainton Cutting Planting Plot 4 | 1MC06-CEK-EV-FRM-CS05-600016 | P01 | 2024-11-21 | 2024-11-21 |  |  | 1MC06-CEK-IM-DAT-CS05-600253 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPW6 | Quainton Cutting Planting Plot 5 | 1MC06-CEK-EV-FRM-CS05-600017 | P01 | 2024-11-21 | 2024-11-21 | 2024-12-12 |  | 1MC06-CEK-IM-DAT-CS05-600254 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPW9 | Quainton Cutting Planting Plot 7 | 1MC06-CEK-EV-FRM-CS05-600019 | P01 | 2024-11-21 | 2024-11-21 | 2024-12-12 |  | 1MC06-CEK-IM-DAT-CS05-600256 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPWA | Quainton Cutting Planting Plot 8 | 1MC06-CEK-EV-FRM-CS05-600020 | P01 | 2024-11-21 | 2024-11-21 | 2024-12-12 |  | 1MC06-CEK-IM-DAT-CS05-600257 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPWB | Quainton Cutting Planting Plot 9 | 1MC06-CEK-EV-FRM-CS05-600021 | P01 | 2024-11-21 | 2024-11-21 | 2024-12-12 |  | 1MC06-CEK-IM-DAT-CS05-600258 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPWE | Quainton Cutting Planting Plot 11 | 1MC06-CEK-EV-FRM-CS05-600023 | P01 | 2024-11-21 | 2024-11-21 |  |  | 1MC06-CEK-IM-DAT-CS05-600260 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPWF | Quainton Cutting Planting Plot 12 | 1MC06-CEK-EV-FRM-CS05-600024 | P01 | 2024-11-21 | 2024-11-21 |  |  | 1MC06-CEK-IM-DAT-CS05-600261 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPWG | Quainton Cutting Planting Plot 13 | 1MC06-CEK-EV-FRM-CS05-600025 | P01 | 2024-11-21 | 2024-11-21 |  |  | 1MC06-CEK-IM-DAT-CS05-600262 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPWJ | Quainton Cutting Planting Plot 14 | 1MC06-CEK-EV-FRM-CS05-600026 | P01 | 2024-11-21 | 2024-11-21 | 2024-12-12 |  | 1MC06-CEK-IM-DAT-CS05-600263 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPWL | Quainton Cutting Planting Plot 16 | 1MC06-CEK-EV-FRM-CS05-600028 | P01 | 2024-11-21 | 2024-11-21 | 2024-12-12 |  | 1MC06-CEK-IM-DAT-CS05-600265 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPWN | Quainton Cutting Planting Plot 17 | 1MC06-CEK-EV-FRM-CS05-600029 | P01 | 2024-11-21 | 2024-11-21 | 2024-12-12 |  | 1MC06-CEK-IM-DAT-CS05-600266 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPWQ | Quainton Cutting Planting Plot 19 | 1MC06-CEK-EV-FRM-CS05-600031 | P01 | 2024-11-21 | 2024-11-21 | 2024-12-12 |  | 1MC06-CEK-IM-DAT-CS05-600268 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPWS | Quainton Cutting Planting Plot 20 | 1MC06-CEK-EV-FRM-CS05-600032 | P01 | 2024-11-21 | 2024-11-21 |  |  | 1MC06-CEK-IM-DAT-CS05-600269 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
13 | 213.07-1 | HS2-00003CPWV | Quainton Cutting Planting Plot 23 | 1MC06-CEK-EV-FRM-CS05-600035 | P01 | 2024-11-21 | 2024-11-21 |  |  | 1MC06-CEK-IM-DAT-CS05-600272 | No issues | [8 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
3 | 212.5 | HS2-00002CT53 | Aylesbury South Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS04_CL18-000038-ACBOS | P01 | 2024-11-21 |  | 2024-11-28 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600073 | [9 empty] | 10 - Complete | Rakesh | Jennifer McKay <JRMY@COWI.COM>
3 | 212.5 | HS2-00002CT55 | Aylesbury South Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS04_CL18-000034-ACBOS | P01 | 2024-11-21 |  | 2024-11-28 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600067 | [9 empty] | 10 - Complete | Rakesh | Jennifer McKay <JRMY@COWI.COM>
10 | 233.01-3 | HS2-000035Q9C | Old Airfield Perimeter Track | 1MC07-ASC-HW-FRM-CS07_CL13-000066-ACBOS | P02 | 2024-11-21 |  | 2024-12-04 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600038 | [9 empty] | 10 - Complete | Rakesh | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com>
| 215.01-2 | HS2-000001044 | Civil 3D Solids Model - 077-L1-77725-808621 | 1MC06-ASC-GT-FRM-CS06_CL09-000003-ACBOS | P03 | 2024-11-21 | 2024-11-21 | 2025-01-07 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600122 | No issues | [8 empty] | 10 - Complete | Lee | BENHMIDA Fedi <fedi.benhmida@setec.com>
8 | 224.7 | HS2-00003HF3P | Turweston cutting Additional Landscape Earthworks 1 | 1MC06-ASC-GT-FRM-CS06_CL22-000016-ACBOS | P01 | 2024-11-21 | 2024-11-28 | 2024-12-03 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600217 |  | Minimum Thickenss issue, sent back on 28-Nov-2024 | [7 empty] | 10 - Complete | supriyan | LABA Dodji <dodji.laba@setec.com>
8 | 224.7 | HS2-00003HF3Q | Turweston cutting Additional Landscape Earthworks 2 | 1MC06-ASC-GT-FRM-CS06_CL22-000017-ACBOS | P01 | 2024-11-21 | 2024-11-28 | 2024-12-03 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600218 | [9 empty] | 10 - Complete | supriyan | LABA Dodji <dodji.laba@setec.com>
8 | 224.7 | HS2-00003HF3R | Turweston cutting Additional Landscape Earthworks 3 | 1MC06-ASC-GT-FRM-CS06_CL22-000018-ACBOS | P01 | 2024-11-21 | 2024-11-28 | 2024-12-03 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600219 | [9 empty] | 10 - Complete | supriyan | LABA Dodji <dodji.laba@setec.com>
8 | 224.7 | HS2-00003HF3S | Turweston cutting Additional Landscape Earthworks 4 | 1MC06-ASC-GT-FRM-CS06_CL22-000019-ACBOS | P01 | 2024-11-21 | 2024-11-28 | 2024-12-03 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600220 | [9 empty] | 10 - Complete | supriyan | LABA Dodji <dodji.laba@setec.com>
4 | 202.1-3 | HS2-00003J169 | MCJ2 Network Rail Boundary Fencing (East) - Fencing 3D Model - DM3 | 1MC06-ASC-CV-FRM-CS03_CL06-000060-ACBOS | P01 | 2024-11-21 |  |  |  | 1MC06-CEK-IM-DAT-CS03_CL06-600107 | No issues | [8 empty] | 10 - Complete | Lee | Jennifer McKay <JRMY@COWI.COM>
4 | 202.1-3 | HS2-00003J16A | MCJ2 Network Rail Boundary Fencing (West) - Fencing 3D Model - DM3 | 1MC06-ASC-CV-FRM-CS03_CL06-000062-ACBOS | P01 | 2024-11-21 |  |  |  | 1MC06-CEK-IM-DAT-CS03_CL06-600108 | No issues | [8 empty] | 10 - Complete | Lee | Jennifer McKay <JRMY@COWI.COM>
| 220.3 | HS2-00002EK7A | Cowley Embankment UTX | 1MC06-ASC-CV-FRM-CS06_CL10-000038-ACBOS | P01 | 2024-11-22 | 2024-11-22 | 2024-12-10 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600047 | No issues | [8 empty] | 10 - Complete | Lee | BONICI Alexandra <alexandra.bonici@setec.com>
| 229.01 | HS2-00002BVKJ | Greatworth Green Tunnel High Mileage Portal Mitigation Earthworks | 1MC07-ASC-GT-FRM-CS07_CL25-000009-ACBOS | P01 | 2024-11-22 |  | 2024-12-12 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600047 | No issues | MnmmThcknssM set as 500 Trailing GFL Sdslp space sent back 6/12/24 | [7 empty] | 10 - Complete | Lee | Matthew Coote <mtce@cowi.com>
17 | 229.01-2 | HS2-00003JRG8 | Greatworth Green Tunnel North Portal-Evacuation Walkways | 1MC07-ASC-CV-FRM-CS07_CL25-000147-ACBOS | P01 | 2024-11-22 |  | 2024-12-19 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600069 | [9 empty] | 10 - Complete | supriyan | Quinn, Emma <emma.quinn@arcadis.com>
| 237.05 | HS2-000032216 | Maintenance Access Road to Switch and Crossing MS2.11 | 1MC07-ASC-HW-FRM-CS07_CL23-000046-ACBOS | P04 | 2024-11-26 | 2024-11-06 | 2025-01-10 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600077 |  | ZZ-zz classifications issue, sent back on 06-Jan-2025 |  | OSGB Issue, sent back on 07-Jan-2025 | [5 empty] | 10 - Complete | supriyan | Matthew Coote <mtce@cowi.com>
6 | UFDR 209.A | HS2-000020CF1 | Aylesbury North Cutting Group - CSO-02-6210 | 1MC06-ASC-UT-FRM-CS04_CL18-000021-ACBOS | P02 | 2024-11-26 | 2024-12-06 | 2024-12-10 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600009 |  | ACBOS PCRA is pending, sent back on 27-Nov-2024 |  | AssetDescription_3 is missing for Pr_65_52_01_02, sent back on 02-Dec-2024 | [5 empty] | 10 - Complete | supriyan | Kamboj, Mohit <mohit.kamboj@arcadis.com>
5 | 201.0-1 | HS2-00003JN84 | Access Road to Bowood Lane Radio Compound | 1MC06-ASC-HW-FRM-CS03_CL05-000062-ACBOS | P01 | 2024-11-26 | 2024-11-28 | 2024-12-02 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600161 |  | OSGB and com_type issues,sent back on 27-Nov-2024 | [7 empty] | 10 - Complete | supriyan | Metzaki Burgham-Malin, Chrysi <Chrysi.Burgham.Malin@arcadis.com>
5 | 201.0-1 | HS2-000020N9Q | Maintenance Access Road to Bowood Lane Drop Inlet Culvert | 1MC06-ASC-HW-FRM-CS03_CL05-000020-ACBOS | P01 | 2024-11-26 | 2024-11-28 | 2024-11-29 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600068 |  | OSGB and other issues,sent back on 27-Nov-2024 | [7 empty] | 10 - Complete | supriyan | Metzaki Burgham-Malin, Chrysi <Chrysi.Burgham.Malin@arcadis.com>
5 | 201.0-1 | HS2-00002CT2K | Maintenance Access Road to Pond-0504 | 1MC06-ASC-HW-FRM-CS03_CL05-900028-ACBOS | P01 | 2024-11-26 | 2024-11-28 | 2024-12-02 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600157 |  | OSGB and other issues,sent back on 27-Nov-2024 | [7 empty] | 10 - Complete | supriyan | Metzaki Burgham-Malin, Chrysi <Chrysi.Burgham.Malin@arcadis.com>
5 | 201.0-1 | HS2-00002CT2L | South Heath Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS03_CL05-000037-ACBOS | P01 | 2024-11-26 |  |  |  | 1MC06-CEK-IM-DAT-CS03_CL05-600018 |  | GIS Length Vs SQL DB Length mismatch , Send back to team on 28 Nov 24. |  |  |  | Push To JSON - expecting confirmation for fencing 4/12/24 | 2024-12-06 |  |  | 10 - Complete | Lee | Danish Sanwal <dnsw@cowi.com>
5 | 201.0-1 | HS2-00002CT2N | South Heath Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS03_CL05-000052-ACBOS | P01 | 2024-11-26 |  |  |  | 1MC06-CEK-IM-DAT-CS03_CL05-600023 | Issue found | 0's found in LengthM , send back to team on 27 Nov 24. | 2024-11-28 | GIS Length Vs SQL DB Length mismatch , Send back to team on 28 Nov 24. |  | Push To JSON - expecting confirmation for fencing 4/12/24 | 2024-12-06 |  |  | 10 - Complete | Lee | Danish Sanwal <dnsw@cowi.com>
| 237.05 | HS2-000020P0N | Maintenance Access Road to Pond (Off Lower Radbourne Farm Access Road East) | 1MC07-ASC-HW-FRM-CS07_CL23-000035-ACBOS | P01 | 2024-11-26 | 2025-01-06 | 2025-01-10 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600008 |  | OSGB Issues, sent back on 06-Jan-2025 | [7 empty] | 10 - Complete | supriyan | Matthew Coote <mtce@cowi.com>
1 | 238.02 | HS2-000001463 | Windmill Lane Green Overbridge | 1MC07-CEK-BR-FRM-CS07_CL24-000016. | P01 | 2024-11-28 |  | 2024-11-29 | yes | 1MC07-CEK-IM-DAT-CS07_CL24-600048 | No issues | TEMP ROW for ANDY BARNES / EKFB error finding exercise | [7 empty] | 10 - Complete | Lee
1 | 238.02 | HS2-00002YNH8 | Ancillary Culvert 124-AC3 | 1MC07-ASC-CV-FRM-CS07_CL24-000053-ACBOS | P01 | 2024-11-26 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL24-600113 |  | TEMP ROW for ANDY BARNES / EKFB error finding exercise |  | PW JSON reloaded to DAC check - No issues | [5 empty] | 10 - Complete | Lee
1 | 238.02 | HS2-00003H6PG | Ancillary Culvert 124-AC3 | 1MC07-ASC-CV-FRM-CS07_CL24-000066-ACBOS | P01 | 2024-11-26 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL24-600119 |  | TEMP ROW for ANDY BARNES / EKFB error finding exercise |  | PW JSON reloaded to DAC check - No issues | [5 empty] | 10 - Complete | Lee
5 | 201.0-1 | HS2-00002WUJ5 | South Heath Cutting Planting-East Plot 9 | 1MC06-CEK-EV-FRM-CS03_CL05-000032 | P01 | 2024-11-28 |  | 2024-12-03 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600119 | [9 empty] | 10 - Complete | Rakesh | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
5 | 201.0-1 | HS2-00002WUJ6 | South Heath Cutting Planting-East Plot 10 | 1MC06-CEK-EV-FRM-CS03_CL05-000022 | P01 | 2024-11-28 |  | 2024-12-04 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600120 | [9 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
5 | 201.0-1 | HS2-00002WUJ7 | South Heath Cutting Planting-East Plot 11 | 1MC06-CEK-EV-FRM-CS03_CL05-000023 | P01 | 2024-11-28 |  | 2024-12-04 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600121 | [9 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
5 | 201.0-1 | HS2-00002WUJ8 | South Heath Cutting Planting-East Plot 12 | 1MC06-CEK-EV-FRM-CS03_CL05-000024 | P01 | 2024-11-28 |  | 2024-12-04 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600122 | [9 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
5 | 201.0-1 | HS2-00002WUJH | South Heath Cutting Planting-West Plot 9 | 1MC06-CEK-EV-FRM-CS03_CL05-000044 | P01 | 2024-11-28 | 2024-11-28 | 2024-12-04 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600131 | No issues | [8 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
5 | 201.0-1 | HS2-00002WUJJ | South Heath Cutting Planting-West Plot 10 | 1MC06-CEK-EV-FRM-CS03_CL05-000034 | P01 | 2024-11-28 | 2024-11-28 | 2024-12-04 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600132 | No issues | [8 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
5 | 201.0-1 | HS2-00002WUJK | South Heath Cutting Planting-West Plot 11 | 1MC06-CEK-EV-FRM-CS03_CL05-000035 | P01 | 2024-11-28 | 2024-11-28 | 2024-12-04 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600133 | No issues | [8 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
5 | 201.0-1 | HS2-00002WUJL | South Heath Cutting Planting-West Plot 12 | 1MC06-CEK-EV-FRM-CS03_CL05-000036 | P01 | 2024-11-28 | 2024-11-28 | 2024-12-04 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600134 | No issues | [8 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
8 | 224.7 | HS2-00003BPLH | Turweston Cutting Planting Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL22-900020 | P01 | 2024-11-28 |  | 2024-12-06 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600170 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
8 | 224.7 | HS2-00003BPLM | Turweston Cutting Planting Plot 6 | 1MC06-ASC-EV-FRM-CS06_CL22-900021 | P01 | 2024-11-28 |  | 2024-12-06 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600171 | No issues | [8 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
8 | 224.7 | HS2-00003BPLQ | Turweston Embankment Planting Plot 1 | 1MC07-ASC-EV-FRM-CS07_CL12-900017 | P01 | 2024-11-28 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL12-600289 | No issues | Trailing spaces found and fixed in house for 2 UAID_1 - DT to update before JSON Issued - 6-Dec-24 | 2024-12-06 | [6 empty] | 10 - Complete | Lee | GEORGESCU Tamara <tamara.georgescu@setec.com>
8 | 224.7 | HS2-00003HF3W | Turweston Cutting Additional Landscape Earthworks 1-Boundary-Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000072-ACBOS | P01 | 2024-11-28 |  | 2024-12-10 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600223 | No issues | Snakegrid coordinates reversed E/N back to front - not assured items, DT notified for future works |  | No entry for this UAID_2 within Boundary or Security Fencing GIS data. BRR vs GIS comparison cannot be completed at this time | [5 empty] | 10 - Complete | Lee | slim.trabelsi@setec.com
18 | 222.9 | HS2-00002CTBS | Barton to Mixbury Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL21-000007-ACBOS | P01 | 2024-11-28 | 2025-01-06 | 2025-01-07 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600067 |  | Not in a valid format. Sent back on 03-Jan-2025 | [7 empty] | 10 - Complete | supriyan | slim.trabelsi@setec.com
18 | 222.9 | HS2-00002CTBU | Barton to Mixbury Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL21-000008-ACBOS | P01 | 2024-11-28 | 2025-01-06 | 2025-01-07 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600069 |  | Com_type and other isses, send back on 03-Jan-2025 | [7 empty] | 10 - Complete | supriyan | slim.trabelsi@setec.com
17 | 229.01-2 | HS2-00002EK7T | Greatworth Green Tunnel North Portal UTX | 1MC07-ASC-CV-FRM-CS07_CL25-000018-ACBOS | P01 | 2024-11-29 |  | 2024-12-17 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600011 | [9 empty] | 10 - Complete | supriyan | Quinn, Emma <emma.quinn@arcadis.com>
5 | 201.0-1 | HS2-00002XQ2P | South Heath Cutting Landscape Earthworks-Bowood Lane West | 1MC06-ASC-GT-FRM-CS03_CL05-000018-ACBOS | P01 | 2024-11-29 |  | 2024-12-03 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600174 | [9 empty] | 10 - Complete | supriyan | SouravKumar.Chatterjee@arcadis.com
21 | 214.07 | HS2-00003L0M2 | Woodlands Farm Ecological Mitigation Site | 1MC06-ASC-EV-FRM-CS05-000002-ACBOS | P01 | 2024-12-02 |  | 2025-01-08 |  | 1MC06-CEK-IM-DAT-CS05-600308 | [9 empty] | 10 - Complete | supriyan | Ka, Srinatha <srinatha.ka@arcadis.com>
| 216.01 | HS2-00002BJUG | Perry Hill Road Realignment Solids Model | 1MC06-ASC-HW-FRM-CS06_CL09-000025-ACBOS | P03 | 2024-12-02 | 2025-01-17 | 2025-01-20 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600113 | No issues | SmartFroms / JSON metrics mismatch. Single OS grid coordinate fail - HS2-00003M0HU | 2025-01-17 | [6 empty] | 10 - Complete | Lee | Shabad, Mallikarjun <mallikarjun.shabad@arcadis.com>
| 216.01 | HS2-00002BJUF | IMD Access off Perry Hill Solids Model | 1MC06-ASC-HW-FRM-CS06_CL09-000026-ACBOS | P04 | 2024-12-02 | 2025-01-03 | 2025-01-09 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600116 | No issues | Com_RfrncNmbr trailing space - fixed in house | [7 empty] | 10 - Complete | Lee | Shabad, Mallikarjun <mallikarjun.shabad@arcadis.com>
| 216.01 | HS2-00002BJUE | Maintenance Access Road to Pond 01 (Off IMD access) Solids Model | 1MC06-ASC-HW-FRM-CS06_CL09-000027-ACBOS | P03 | 2024-12-02 | 2025-01-03 | 2025-01-09 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600115 | No issues | Com_RfrncNmbr trailing space - fixed in house | [7 empty] | 10 - Complete | Lee | Shabad, Mallikarjun <mallikarjun.shabad@arcadis.com>
| 216.01 | HS2-00002CT90 | Charndon Lodge Pumping Station and Pond Access Road Solids Model | 1MC06-ASC-HW-FRM-CS06_CL09-000028-ACBOS | P04 | 2024-12-02 | 2025-01-03 | 2025-01-09 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600203 | No issues | Sdslp 1 in 0 to be removed sent back 12/dec/24 | 2025-01-03 | [6 empty] | 10 - Complete | Lee | Shabad, Mallikarjun <mallikarjun.shabad@arcadis.com>
| 216.01 | HS2-000020NKK | Portway Farm ATS Access Road off Perry Hill Road Solids Model | 1MC06-ASC-HW-FRM-CS06_CL09-000029-ACBOS | P04 | 2024-12-02 | 2025-01-03 | 2025-01-08 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600095 | No issues | [8 empty] | 10 - Complete | Lee | Shabad, Mallikarjun <mallikarjun.shabad@arcadis.com>
10 | 233.01-3 | HS2-00003J16B | Chipping Warden North Portal-Ditch Crossing 3 | 1MC07-ASC-CV-FRM-CS07_CL13-000027-ACBOS | P01 | 2024-12-02 | 2024-12-02 | 2024-12-09 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600045 | No issues | [8 empty] | 10 - Complete | Lee | Lok, Terry <terry.lok@arcadis.com>
| 229.01-1 | HS2-00003JRG7 | Greatworth Green Tunnel South Portal-Evacuation Walkways | 1MC07-ASC-CV-FRM-CS07_CL12-000146-ACBOS | P01 | 2024-12-02 | 2025-01-16 | 2025-01-17 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600296 |  | ACBOS Workflow pending and other queries. Sent back on 08-Jan-2025 | [7 empty] | 10 - Complete | supriyan | Quinn, Emma <emma.quinn@arcadis.com>
| 238.03 | HS2-000001464 | A423 Banbury Road Overbridge | 1MC07-CEK-BR-FRM-CS07_CL24-000003 | P08 | 2024-12-03 | 2025-01-10 | 2024-01-14 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600047 |  | OSGB issues, sent back on 08-Jan-2025 | [7 empty] | 10 - Complete | supriyan | ANL@COWI.Com
12 | UFDR 211.A | HS2-00003KFPK | Waddesdon Sewage Treatment Water Supply | 1MC06-ASC-UT-FRM-CS04_CL20-000098-ACBOS | P02 | 2024-12-03 |  | 2024-12-12 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600254 | No issues | incorrect JSON filename. DT informed 3-dec-24 | 2024-12-09 | [6 empty] | 10 - Complete | Lee | Kamboj, Mohit <mohit.kamboj@arcadis.com>
5 | 201.0-1 | HS2-00002WUJ1 | South Heath Cutting Planting-East Plot 5 | 1MC06-CEK-EV-FRM-CS03_CL05-000028 | P01 | 2024-11-29 |  | 2024-12-05 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600115 | No issues | DT previously descoped - now reinstated files 4-dec-24 | [7 empty] | 10 - Complete | Lee | gdmc@cowi.com
5 | 201.0-1 | HS2-00002WUJ3 | South Heath Cutting Planting-East Plot 7 | 1MC06-CEK-EV-FRM-CS03_CL05-000030 | P01 | 2024-11-29 |  | 2024-12-05 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600117 | No issues | DT previously descoped - now reinstated files 4-dec-24 | [7 empty] | 10 - Complete | Lee | gdmc@cowi.com
5 | 201.0-1 | HS2-00002WUJD | South Heath Cutting Planting-West Plot 5 | 1MC06-CEK-EV-FRM-CS03_CL05-000040 | P01 | 2024-11-29 |  | 2024-12-05 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600127 | No issues | DT previously descoped - now reinstated files 4-dec-24 | [7 empty] | 10 - Complete | Lee | gdmc@cowi.com
5 | 201.0-1 | HS2-00002WUJE | South Heath Cutting Planting-West Plot 6 | 1MC06-CEK-EV-FRM-CS03_CL05-000041 | P01 | 2024-11-29 |  | 2024-12-05 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600128 | No issues | DT previously descoped - now reinstated files 4-dec-24 | [7 empty] | 10 - Complete | Lee | gdmc@cowi.com
5 | 201.0-1 | HS2-00002WUJF | South Heath Cutting Planting-West Plot 7 | 1MC06-CEK-EV-FRM-CS03_CL05-000042 | P01 | 2024-11-29 |  | 2024-12-05 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600129 | No issues | DT previously descoped - now reinstated files 4-dec-24 | [7 empty] | 10 - Complete | Lee | gdmc@cowi.com
5 | 201.0-1 | HS2-00002WUJG | South Heath Cutting Planting-West Plot 8 | 1MC06-CEK-EV-FRM-CS03_CL05-000043 | P01 | 2024-11-29 |  | 2024-12-05 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600130 | No issues | DT previously descoped - now reinstated files 4-dec-24 | [7 empty] | 10 - Complete | Lee | gdmc@cowi.com
| 216.01 | HS2-00002CT8T | HS2-00002C5T4-Perry Hill Road Drainage System | 1MC06-ASC-DR-FRM-CS06_CL09-000028-ACBOS | P02 | 2024-12-05 | 2025-01-22 | 2025-01-24 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600201 | No issues | OS coords incorrect 9-Jan-25 | 2025-01-20 | still 3 coords incorrect - 20-jan-25 | temp load overnight for early DAC check 20-jan-25 | DAC checked - No issues. 21-jan-24 - waitingo n Dt for coordinate change | 2024-01-22 |  |  | 10 - Complete | Lee | rani.muthappan@arcadis.com
| 214.01 | HS2-00002CW0M | HS2-00002C5T3-Bridleway GUN 28 Drainage System | 1MC06-CEK-DR-FRM-CS05-000065 | P | 2024-12-05 | 2024-12-05 | 2024-01-14 |  | 1MC06-CEK-IM-DAT-CS05-600010 | No issues | [8 empty] | 10 - Complete | Lee | rani.muthappan@arcadis.com
| 237.05 | HS2-000020P1F | Ladbroke Grove Farm Accommodation Access Realignment | 1MC07-ASC-HW-FRM-CS07_CL23-000038-ACBOS | P05 | 2024-12-05 | 2025-01-10 | 2024-01-14 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600006 |  | ACBOS Link not correct. Sent back on 08-Jan-2025 | [7 empty] | 10 - Complete | supriyan | Matthew Coote <mtce@cowi.com>
20 | 219.1 | HS2-00002CT9Z | Cowley Embankment Noise Barrier Line | 1MC06-ASC-CV-FRM-CS06_CL10-000018-ACBOS | P01 | 2024-12-06 |  | 2024-12-18 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600061 | [9 empty] | 10 - Complete | supriyan | GOIMARD Thomas <thomas.goimard@setec.com>
10 | 233.01-3 | HS2-00002CTH6 | Culworth Road Bridleway and Footpath AE28 Realignment | 1MC07-ASC-HW-FRM-CS07_CL26-000043-ACBOS | P03 | 2024-12-06 |  | 2024-12-11 | yes | 1MC07-CEK-IM-DAT-CS07_CL26-600032 | No issues | cannot load to L3 SQL as UAID_1 in SQL needs change - Monday | 2024-12-10 | [6 empty] | 10 - Complete | Lee | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com>
| 234.01 | HS2-00002CTHK | C3.L.57 Catchment | 1MC07-ASC-DR-FRM-CS07_CL14-000013-ACBOS | P02 | 2024-12-09 |  | 2025-01-09 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600076 | [9 empty] | 10 - Complete | supriyan | B, Gopika <gopika.b@arcadis.com>
16 | 202.5-2 | HS2-000001023 | Small Dean North Embankment | 1MC06-ASC-GT-FRM-CS03_CL06-000001-ACBOS | P06 | 2024-12-10 |  | 2024-12-13 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600063 | No issues | [8 empty] | 10 - Complete | Lee | Siva Sankari Parimalam <sipm@cowi.com>
| 218.02-1 | HS2-00002NSXP | OXD Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL09-000083-ACBOS | P02 | 2024-12-10 | 2025-01-17 | 2024-01-21 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600180 |  | OSGB and other issues. Sent back on 09-Jan-2025 |  | Com_Issues , sent back on 17-Jan-2025 |  | fence length Sum does not match GIS data - 20-jan-25. CK |  |  |  | 10 - Complete | supriyan | Ibrahim, Abdurrahman <abdurrahman.ibrahim@arcadis.com>
| 218.02-1 | HS2-00002NSXQ | OXD Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL09-000081-ACBOS | P04 | 2024-12-10 |  | 2025-01-09 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600181 | [9 empty] | 10 - Complete | supriyan | Ibrahim, Abdurrahman <abdurrahman.ibrahim@arcadis.com>
| 233.01-2 | HS2-00002TMFA | Chipping Warden Green Tunnel North Portal Building Fire Fighting Water | 1MC07-ASC-UT-FRM-CS07_CL13-000038-ACBOS | P04 | 2024-12-12 | 2025-01-13 | 2024-01-14 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600024 |  | Com_type issue, sent back on 09-Jan-2025 | [7 empty] | 10 - Complete | supriyan | T, Sithrubi <sithrubi.t@arcadis.com>
| 233.01-2 | HS2-00002TMFB | Chipping Warden Green Tunnel North Portal Building Telecoms | 1MC07-ASC-UT-FRM-CS07_CL13-000034-ACBOS | P04 | 2024-12-12 | 2025-01-21 | 2025-01-22 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600043 |  | Com_type issue, sent back on14-Jan-2025 | [7 empty] | 10 - Complete | supriyan | T, Sithrubi <sithrubi.t@arcadis.com>
| 233.01-2 | HS2-00002TMFC | Chipping Warden MPATS Telecoms | 1MC07-ASC-UT-FRM-CS07_CL13-000036-ACBOS | P03 | 2024-12-12 | 2025-01-13 | 2024-01-14 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600022 | [9 empty] | 10 - Complete | supriyan | T, Sithrubi <sithrubi.t@arcadis.com>
12 | UFDR 211.A | HS2-000031J4L | Waddesdon Compact Substation | 1MC06-ASC-UT-FRM-CS04_CL20-000091-ACBOS | P02 | 2024-12-12 |  | 2024-12-16 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600245 | No issues | trailing spaces in various places sent back 12-dec-24 | [7 empty] | 10 - Complete | Lee | eloise.mainstone@arcadis.com
12 | UFDR 211.A | HS2-000020CFE | CSO-02-1216 | 1MC06-ASC-UT-FRM-CS04_CL20-000016-ACBOS | P02 | 2024-12-12 | 2024-12-12 | 2024-12-13 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600113 | No issues | [8 empty] | 10 - Complete | Lee | eloise.mainstone@arcadis.com
12 | UFDR 211.A | HS2-00003KUMA | WAD-3 Sub-station Access Road | 1MC06-ASC-HW-FRM-CS04_CL20-000055-ACBOS | P02 | 2024-12-12 | 2024-12-12 | 2024-12-13 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600253 | No issues | [8 empty] | 10 - Complete | Lee | eloise.mainstone@arcadis.com
| 237.05 | HS2-00002CTK4 | Radbourne ATS Access Road | 1MC07-ASC-HW-FRM-CS07_CL23-000040-ACBOS | P02 | 2024-12-12 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL23-600031 | No issues | OS coords issues 10-jan-25 | 2025-01-10 | DAC check fail - Duplicate record - 13-jan-25 | 2025-01-22 | OS coords issues 22-jan-25 | 2025-02-11 | file same as previous- sent back 12-feb-25 |  | 30 - Sent back to team | Lee | Matthew Coote <mtce@cowi.com>
17 | 229.01-2 | HS2-000020361 | Sulgrave Road Reinstatement | 1MC07-ASC-HW-FRM-CS07_CL25-000021-ACBOS | P01 | 2024-12-12 |  | 2024-12-17 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600046 | [9 empty] | 10 - Complete | supriyan | MarcoAntonio.Tanseco@arcadis.com
17 | 229.01-2 | HS2-00003JAYC | Deans Barn Access Track (off Sulgrave Road) | 1MC07-ASC-HW-FRM-CS07_CL25-000002 - ACBOS | P01 | 2024-12-12 | 2024-12-23 | 2025-01-02 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600071 | [9 empty] | 10 - Complete | supriyan | MarcoAntonio.Tanseco@arcadis.com
18 | 222.9 | HS2-00003K85R | Featherbed Lane Realignment retaining wall | 1MC06-ASC-CV-FRM-CS06_CL21-000028-ACBOS | P01 | 2024-12-16 | 2024-01-06 | 2025-01-08 |  | 1MC06-CEK-IM-DAT-CS06_CL21-000009 |  | Queries sent back on 03-Jan-2025 |  | com_dscrptn set as M-Handrail. Found at Check stage. 7-jan-25 | [5 empty] | 10 - Complete | supriyan | TRABELSI Slim <slim.trabelsi@setec.com>
6 | UFDR 209.A | HS2-000020CF1 | CSO-02-6210 | 1MC06-ASC-UT-FRM-CS04_CL18-000021-ACBOS | P05 | 2024-12-18 | 2024-12-18 | 2024-12-20 | YES | 1MC06-CEK-IM-DAT-CS04_CL18-600009 | No issues | [8 empty] | 10 - Complete | supriyan | maya.bowles@arcadis.com
| 229.01 | HS2-00002BVKJ | Greatworth Green Tunnel High Mileage Portal Mitigation Earthworks | 1MC07-ASC-GT-FRM-CS07_CL25-000009-ACBOS | P03 | 2024-12-18 |  | 2025-01-10 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600047 | No issues | [8 empty] | 10 - Complete | Lee | mtce@cowi.com>
| 214.01-1 | HS2-000001308 | Bridleway GUN 28 Accommodation Green Overbridge | 1MC06-CEK-BR-FRM-CS05-000003 | P12 | 2024-12-19 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600116 |  | 101 other things in Com_Typ sdslp syntax ZZ- classifications | [7 empty] | 30 - Sent back to team | Lee | william.whyte@arcadis.com
18 | 222.9 | HS2-000039DS9 | Finmere (Bat Licence) Ecological Mitigation Site | 1MC06-ASC-EV-FRM-CS06_CL21-000007-ACBOS | P01 | 2024-12-19 |  | 2025-01-03 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600145 | [9 empty] | 10 - Complete | supriyan | mate.markus@setec.com>
| UFDR 211.B | HS2-000020CFD | CSO-02-1215 | 1MC06-ASC-UT-FRM-CS04_CL20-000017-ACBOS | P02 | 2024-12-20 |  | 2025-01-10 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600150 | [9 empty] | 10 - Complete | supriyan | eloise.mainstone@arcadis.com>
| UFDR 211.B | HS2-000020CFC | CSO-02-1221P | 1MC06-ASC-UT-FRM-CS04_CL20-000038-ACBOS | P02 | 2024-12-20 |  | 2025-01-10 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600149 | [9 empty] | 10 - Complete | supriyan | eloise.mainstone@arcadis.com>
| 217.04 | HS2-000031NVA | HS2-00002C5T4-Footpath SCL/8 Drainage | 1MC06-CEK-DR-FRM-CS06_CL09-000053 | P01 | 2024-12-20 |  | 2025-01-10 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600248 | [9 empty] | 10 - Complete | supriyan | rani.muthappan@arcadis.com
| 230.01-3 | HS2-00002CTFN | C3.T.29 Catchment | 1MC07-ASC-DR-FRM-CS07_CL26-000005-ACBOS | P04 | 2024-12-21 | 2025-01-15 | 2025-01-17 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600018 | No issues | incorrect coordinate for 2 assets identified by Partha at review stage - 12-Jan-25 | 2025-01-15 | [6 empty] | 10 - Complete | Lee | gopika.b@arcadis.com
| 229.01-1 | HS2-00002TMF4 | Greatworth Green Tunnel South Portal Building Telecoms | 1MC07-ASC-UT-FRM-CS07_CL12-000096-ACBOS | P05 | 2024-12-23 | 2024-12-23 | 2025-01-17 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600052 | No issues | [8 empty] | 10 - Complete | Lee | juilee.lokhande@arcadis.com>
| 229.01-1 | HS2-00002TMF2 | Greatworth Green Tunnel South Portal Building Fire-fighting Water | 1MC07-ASC-UT-FRM-CS07_CL12-000092-ACBOS | P03 | 2024-12-23 |  | 2025-01-15 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600050 | No issues | [8 empty] | 10 - Complete | Lee | juilee.lokhande@arcadis.com>
| 229.01-1 | HS2-00002TMF1 | Greatworth ATS Telecoms | 1MC07-ASC-UT-FRM-CS07_CL12-000094-ACBOS | P04 | 2024-12-23 | 2024-12-23 | 2025-01-14 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600051 | No issues | [8 empty] | 10 - Complete | Lee | juilee.lokhande@arcadis.com>
| 229.01-1 | HS2-00002TMF3 | Greatworth Green Tunnel South Portal Building Electric | 1MC07-ASC-UT-FRM-CS07_CL12-000098-ACBOS | P08 | 2024-12-23 | 2024-12-23 | 2025-01-17 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600053 | No issues | [8 empty] | 10 - Complete | Lee | juilee.lokhande@arcadis.com>
24 | 214.08 | HS2-00002TZT8 | FCC Sidings Foul Water Drainage | 1MC06-ASC-UT-FRM-CS05-000016-ACBOS | P01 | 2025-01-03 |  | 2025-01-15 |  | 1MC06-CEK-IM-DAT-CS05-600136 | [9 empty] | 10 - Complete | supriyan | Bowles, Maya <maya.bowles@arcadis.com>
| 233.01-2 | HS2-00002CX3A | Appletree Lane Drainage System | 1MC07-ASC-DR-FRM-CS07_CL13-000002-ACBOS | P06 | 2025-01-08 | 2025-01-15 | 2025-01-17 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600003 |  | 0's found depth, sent back on 15-Jan-2025 | [7 empty] | 10 - Complete | supriyan | B, Gopika <gopika.b@arcadis.com>
| 234.01 | HS2-00002U4NE | Aston Le Walls Embankment Group | 1MC07-ASC-CV-FRM-CS07_CL14-000079-ACBOS | P04 | 2025-01-09 |  | 2025-01-16 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600112 | [9 empty] | 10 - Complete | supriyan | PATIL, APOORVA <apoorva.patil@arcadis.com>
| 237.05 | HS2-000020P0W | Maintenace Acess Road to Pond (Off Radbourne Lane South) | 1MC07-ASC-HW-FRM-CS07_CL23-000037-ACBOS | P01 | 2025-01-09 |  | 2025-01-16 |  | 1MC07-CEK-IM-DAT-CS07_CL23-600037 | [9 empty] | 10 - Complete | supriyan | Matthew Coote <mtce@cowi.com>
| 213.05 | HS2-00002CW0N | HS2-00002C5T1-Bridleway QUA 28A Drainage System | 1MC06-ASC-DR-FRM-CS05-000021-ACBOS | P | 2025-01-10 | 2025-01-10 | 2025-01-17 |  | 1MC06-CEK-IM-DAT-CS05-600009 | No issues | [8 empty] | 10 - Complete | Lee | Muthappan, Rani <rani.muthappan@arcadis.com>
| 215.02-2 | HS2-00002CX36 | Civil 3D Solids Model - P-RAI-0799 | 1MC06-ASC-DR-FRM-CS06_CL09-000037-ACBOS | P11 | 2025-01-10 |  | 2025-01-17 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600209 | No issues | TNK Com_Dscrptn contains Ifcpresentation Layer prefix 16-jan-25 edited in house - check PW file before JSON issue. | [7 empty] | 10 - Complete | Lee | BENHMIDA Fedi <fedi.benhmida@setec.com>
17 | 229.01-2 | HS2-000020NW0 | Footpath BB3 Diversion | 1MC07-ASC-HW-FRM-CS07_CL25-000024-ACBOS | P01 | 2025-01-13 | 2025-01-13 | 2025-01-15 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600036 | No issues | [8 empty] | 10 - Complete | Lee | veenadhari.bavanam@arcadis.com
17 | 229.01-2 | HS2-000025B2E | Greatworth Green Tunnel North Portal Buildings Access Road | 1MC07-ASC-HW-FRM-CS07_CL25-000026-ACBOS | P01 | 2025-01-13 | 2025-01-13 | 2025-01-15 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600058 | No issues | [8 empty] | 10 - Complete | Lee | veenadhari.bavanam@arcadis.com
17 | 229.01-2 | HS2-000025B2G | Banbury Road (Thorpe Mandeville) Reinstatement | 1MC07-ASC-HW-FRM-CS07_CL25-000027-ACBOS | P02 | 2025-01-13 | 2025-01-13 | 2025-01-16 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600048 | No issues | [8 empty] | 10 - Complete | Lee | veenadhari.bavanam@arcadis.com
17 | 229.01-2 | HS2-000039DSF | Greatworth Park Bat House (Bat licence) Ecological Site Management Plan | 1MC07-ASC-EV-REP-CS07_CL25-000008 |  | 2025-01-13 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL25-600070 |  | Company name is worng in EKFB smartform, sent back on 16-Jan-2025 |  | EKFB asset, no need to create JSON | [5 empty] | 99 - Cancelled | supriyan | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 213.02-1 | HS2-00002BVGF | Civil 3D Solids Model | 1MC06-ASC-DR-FRM-CS05-000027-ACBOS | P02 | 2025-01-15 | 2025-01-24 | 2025-02-04 |  | 1MC06-CEK-IM-DAT-CS05-600081 | No issues | OS coordinate issues 17-jan-25 | 2025-01-21 | waiting for DT to load to PW - 22-jan-25 | 2025-01-24 |  |  |  |  | 10 - Complete | Lee | BENHMIDA Fedi <fedi.benhmida@setec.com>
| 213.02-1 | HS2-00002CT77 | Civil 3D Solids - P-RAI-0730 | 1MC06-ASC-DR-FRM-CS05-000003-ACBOS | P02 | 2025-01-15 | 2025-01-21 | 2025-01-22 |  | 1MC06-CEK-IM-DAT-CS05-600123 |  | sent back with queries on 17-Jan-2025 | [7 empty] | 10 - Complete | supriyan | BENHMIDA Fedi <fedi.benhmida@setec.com>
| 213.02-1 | HS2-00002CT7S | Civil 3D Solids Model - P-RAI-0737 | 1MC06-ASC-DR-FRM-CS05-000006-ACBOS | P02 | 2025-01-15 | 2025-01-20 | 2025-01-21 |  | 1MC06-CEK-IM-DAT-CS05-600031 | No issues | Please choose in FlwDrctn | 2025-01-20 | [6 empty] | 10 - Complete | Lee | BENHMIDA Fedi <fedi.benhmida@setec.com>
| 213.02-1 | HS2-00002CT7A | Civil 3D Solids - P-MCJ-0734-P-MCJ-0735-P-MCJ-0736-P-MCJ-0738-P-MCJ-0744 | 1MC06-ASC-DR-FRM-CS05-000013-ACBOS | P02 | 2025-01-15 | 2025-01-15 | 2025-01-20 |  | 1MC06-CEK-IM-DAT-CS05-600118 | No issues | [8 empty] | 10 - Complete | Lee | BENHMIDA Fedi <fedi.benhmida@setec.com>
| 213.02-1 | HS2-00002CT78 | Civil 3D Solids - P-RAI-0736 | 1MC06-ASC-DR-FRM-CS05-000005-ACBOS | P02 | 2025-01-15 | 2025-01-24 | 2025-02-04 |  | 1MC06-CEK-IM-DAT-CS05-600120 | No issues | commas used as numeric seperators DmtrExtr for PPE has zero (0) set on many. 17-jan-24 |  |  | 2025-01-24 |  |  |  |  | 10 - Complete | Lee | BENHMIDA Fedi <fedi.benhmida@setec.com>
17 | 229.01-2 | HS2-00003AQDA | Thorpe Mandeville Embankment Transition Zone Earthworks | 1MC07-ASC-GT-FRM-CS07_CL25-000012-ACBOS | P01 | 2025-01-16 | 2025-01-17 | 2025-01-20 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600077 | No issues | Couple of coordinate conversion issues 16-Jan-25 | 2025-01-17 | [6 empty] | 10 - Complete | Lee | K P, Deepak <deepak.kp@arcadis.com>
| UFDR 213.A | HS2-00002NHZ9 | CSO-02-6213T | 1MC06-ASC-UT-FRM-CS05-000006-ACBOS | P03 | 2025-01-17 | 2025-01-17 | 2025-01-21 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600067 | No issues | [8 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
| UFDR 210.B | HS2-00002TU6N | C23-069-0002 | 1MC06-ASC-UT-FRM-CS04_CL20-000072-ACBOS | P02 | 2025-01-17 |  | 2025-01-20 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600154 | [9 empty] | 10 - Complete | supriyan | Bowles, Maya <maya.bowles@arcadis.com>
22 | UFDR 202.B | HS2-000020CDN | CSO-02-1203HV | 1MC06-ASC-UT-FRM-CS03_CL05-000015-ACBOS | P02 | 2025-01-22 | 2025-01-22 | 2025-01-24 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600052 | No issues | [8 empty] | 10 - Complete | Lee | Supreetha.ChidanandUrs@arcadis.com
22 | UFDR 202.B | HS2-00002CT3A | CSO-02-1203LV | 1MC06-ASC-UT-FRM-CS03_CL05-000018-ACBOS | P02 | 2025-01-22 | 2025-01-22 | 2025-01-24 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600036 | No issues | [8 empty] | 10 - Complete | Lee | Supreetha.ChidanandUrs@arcadis.com
22 | UFDR 202.B | HS2-000020CDQ | CSO-02-6200 | 1MC06-ASC-UT-FRM-CS03_CL05-000022-ACBOS | P02 | 2025-01-22 | 2025-01-22 | 2025-01-24 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600050 | No issues | [8 empty] | 10 - Complete | Lee | Supreetha.ChidanandUrs@arcadis.com
22 | UFDR 202.B | HS2-00002TG2R | Rocky Lane Substation | 1MC06-ASC-UT-FRM-CS03_CL05-000017-ACBOS | P02 | 2025-01-22 | 2025-01-22 | 2025-01-24 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600098 | No issues | possible coordinate issue showing in DAC check Easting / nothing screen. DT have been asked to confirm. | [7 empty] | 10 - Complete | Lee | Supreetha.ChidanandUrs@arcadis.com
| UFDR 235.A | HS2-000020CJW | CSO-04-3120 | 1MC07-ASC-UT-FRM-CS07_CL14-000009-ACBOS | P03 | 2025-01-22 |  | 2025-01-28 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600014 | [9 empty] | 10 - Complete | supriyan | Bowles, Maya <maya.bowles@arcadis.com>
| 214.01-2 | HS2-00002Z6BC | Bridleway GUN 28 Diversion - Slab Crossing | 1MC06-ASC-CV-FRM-CS05-000076-ACBOS | P01 | 2025-01-22 | 2025-01-27 | 2025-01-28 |  | 1MC06-CEK-IM-DAT-CS05-600142 |  | OSGB Co-ordinate issues, send back on 27-Jan-2025 | [7 empty] | 10 - Complete | supriyan | Sundharam, Karthick <karthick.s2@arcadis.com>
| UFDR 210.B | HS2-00002V04E | C23-068-001 | 1MC06-ASC-UT-FRM-CS04_CL20-000082-ACBOS | P02 | 2025-01-23 |  | 2025-01-28 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600155 | [9 empty] | 10 - Complete | supriyan | Bowles, Maya <maya.bowles@arcadis.com>
21 | 214.07 | HS2-00003H5JK | Grendon Underwood Embankment Planting-Plot 1 | 1MC06-ASC-EV-REP-CS05-000010 | P01 | 2025-01-23 | 2025-01-27 | 2025-01-28 |  | 1MC06-CEK-IM-DAT-CS05-600223 | No issues | All UAID_1 in MPDT contain trailing space |  | fixed in house 24-jan-25 - check PW file before JSON release | DT PW fix - 27-jan-25 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JL | Grendon Underwood Embankment Planting-Plot 2 | 1MC06-ASC-EV-REP-CS05-000005 | P01 | 2025-01-23 | 2025-01-27 | 2025-01-28 |  | 1MC06-CEK-IM-DAT-CS05-600224 | No issues | All UAID_1 in MPDT contain trailing space |  | fixed in house 24-jan-25 - check PW file before JSON release | DT PW fix - 27-jan-25 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JM | Grendon Underwood Embankment Planting-Plot 3 | 1MC06-ASC-EV-REP-CS05-000006 | P01 | 2025-01-23 | 2025-01-27 | 2025-01-28 |  | 1MC06-CEK-IM-DAT-CS05-600225 | No issues | All UAID_1 & UAID_2 in MPDT contain trailing space |  | fixed in house 24-jan-25 - check PW file before JSON release | DT PW fix - 27-jan-25 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JN | Grendon Underwood Embankment Planting-Plot 4 | 1MC06-ASC-EV-REP-CS05-000007 | P01 | 2025-01-23 | 2025-01-27 | 2025-01-28 |  | 1MC06-CEK-IM-DAT-CS05-600226 | No issues | All UAID_1 & UAID_2 in MPDT contain trailing space |  | fixed in house 24-jan-25 - check PW file before JSON release | DT PW fix - 27-jan-25 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JP | Grendon Underwood Embankment Planting-Plot 5 | 1MC06-ASC-EV-REP-CS05-000008 | P01 | 2025-01-23 | 2025-01-27 | 2025-01-28 |  | 1MC06-CEK-IM-DAT-CS05-600227 | No issues | All UAID_1 in MPDT contain trailing space |  | fixed in house 24-jan-25 - check PW file before JSON release | DT PW fix - 27-jan-25 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JQ | Grendon Underwood Embankment Planting-Plot 6 | 1MC06-ASC-EV-REP-CS05-000009 | P01 | 2025-01-23 | 2025-01-27 | 2025-01-28 |  | 1MC06-CEK-IM-DAT-CS05-600228 | No issues | All UAID_1 in MPDT contain trailing space |  | fixed in house 24-jan-25 - check PW file before JSON release | DT PW fix - 27-jan-25 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JR | Grendon Underwood Embankment Planting-Plot 7 | 1MC06-ASC-EV-REP-CS05-000011 | P01 | 2025-01-23 | 2025-01-23 | 2025-01-27 |  | 1MC06-CEK-IM-DAT-CS05-600229 | No issues | no issues | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JS | Grendon Underwood Embankment Planting-Plot 8 | 1MC06-ASC-EV-REP-CS05-000012 | P01 | 2025-01-23 | 2025-01-27 | 2025-01-28 |  | 1MC06-CEK-IM-DAT-CS05-600230 | No issues | All UAID_1 & UAID_2 in MPDT contain trailing space |  | fixed in house 24-jan-25 - check PW file before JSON release | DT PW fix - 27-jan-25 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JT | Grendon Underwood Embankment Planting-Plot 9 | 1MC06-ASC-EV-REP-CS05-000013 | P01 | 2025-01-23 | 2025-01-23 | 2025-01-29 |  | 1MC06-CEK-IM-DAT-CS05-600231 | No issues | no issues | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JU | Grendon Underwood Embankment Planting-Plot 10 | 1MC06-ASC-EV-REP-CS05-000014 | P01 | 2025-01-23 | 2025-01-27 | 2025-01-29 |  | 1MC06-CEK-IM-DAT-CS05-600232 | No issues | All UAID_2 in MPDT contain trailing space |  | fixed in house 27-Jan-25 - check PW file before JSON release | DT PW fix - 27-jan-25 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JV | Grendon Underwood Embankment Planting-Plot 11 | 1MC06-ASC-EV-REP-CS05-000015 | P01 | 2025-01-23 | 2025-01-27 | 2025-01-29 |  | 1MC06-CEK-IM-DAT-CS05-600233 | No issues | All UAID_1 - Column BE in MPDT contain trailing space |  | fixed in house 27-Jan-25 - check PW file before JSON release | DT PW fix - 27-jan-25 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JW | Grendon Underwood Embankment Planting-Plot 12 | 1MC06-ASC-EV-REP-CS05-000016 | P01 | 2025-01-23 | 2025-01-27 | 2025-01-29 |  | 1MC06-CEK-IM-DAT-CS05-600234 | No issues | All UAID_1 - Column BE in MPDT contain trailing space |  | fixed in house 27-Jan-25 - check PW file before JSON release | DT PW fix - 27-jan-25 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JX | Woodlands Cutting Planting-Plot 1 | 1MC06-ASC-EV-REP-CS05-000001 | P01 | 2025-01-23 | 2025-01-23 | 2025-01-29 |  | 1MC06-CEK-IM-DAT-CS05-600235 | No issues | All UAID_1 - Column BE in MPDT contain trailing space |  | fixed in house 27-Jan-25 - check PW file before JSON release | DT PW fix - 27-jan-25 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JY | Woodlands Cutting Planting-Plot 2 | 1MC06-ASC-EV-REP-CS05-000004 | P01 | 2025-01-27 | 2025-01-27 | 2025-01-29 |  | 1MC06-CEK-IM-DAT-CS05-600236 | No issues | no issues | [7 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5JZ | Woodlands Cutting Planting-Plot 3 | 1MC06-ASC-EV-REP-CS05-000002 | P01 | 2025-01-23 | 2025-01-27 | 2025-01-29 |  | 1MC06-CEK-IM-DAT-CS05-600237 | No issues | All UAID_1 - Column BE in MPDT contain trailing space |  | fixed in house 27-Jan-25 - check PW file before JSON release | DT PW fix - 27-jan-25 |  |  |  |  | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
21 | 214.07 | HS2-00003H5K0 | Woodlands Cutting Planting-Plot 4 | 1MC06-ASC-EV-REP-CS05-000003 | P01 | 2025-01-23 | 2025-01-27 | 2025-01-29 |  | 1MC06-CEK-IM-DAT-CS05-600238 | No issues | All UAID_1 - Column BE in MPDT contain trailing space |  | fixed in house 27-Jan-25 - check PW file before JSON release | [5 empty] | 10 - Complete | Lee | Jeewa, Ebrahim <ebrahim.jeewa@arcadis.com>
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-AR-FRM-CS07_CL14-600001 | P05 | 2025-01-23 |  | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | Trailing Space on one Uniclass ID |  | fixed in house 28-Jan-25 - check PW file before JSON release | 2025-01-29 |  |  | loaded 668 - 6-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-ASC-CV-FRM-CS07_CL13-000010-ACBOS | P11 | 2025-01-23 | 2025-01-23 | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues |  |  | confrimation of zero values required. 29-jan-25 | 2025-01-29 |  |  | loaded 1420 - 5-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-CV-FRM-CS07_CL14-000034 | P03 | 2025-01-23 |  | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | trailing space on some Com_Dscrptn - 29-jan-25 |  | fixed in house - DT to follow pre issue. |  | Accsscvr MTRL - sntbck 30-jan-25 | fixed 31-jan-25 | loaded 668 - 5-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-EL-FRM-CS07_CL14-000001 | P03 | 2025-01-23 |  | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | Trailing space in some Com_Dscrptn - 29-jan-25 |  | fixed in house - DT to follow pre issue. | 2025-01-30 |  |  | loaded 1453 - DsgnLf 5-feb-25 | change to 2 Dpth and 2 Hght atts 7-feb-25 pm | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-EL-FRM-CS07_CL14-000002 | P03 | 2025-01-23 |  | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | UAID_1 with trailing space Column BE |  | fixed in house - DT to follow pre issue. | 2025-01-30 |  |  | loaded 194 5-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-EL-FRM-CS07_CL14-000003 | P04 | 2025-01-23 | 2025-01-23 | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | no issues | [5 empty] | loaded 170 5-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-EL-FRM-CS07_CL14-000004 | P03 | 2025-01-23 | 2025-01-23 | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | no issues | [5 empty] | loaded 250 - DsgnLf 4-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-EL-FRM-CS07_CL14-000005 | P03 | 2025-01-23 |  | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | Trailing spaces on all UAID_1 column BE Leading spaces on some Com_dscrptn. 29-jan-25 |  | fixed in house - DT to follow pre issue. | 2025-01-30 |  |  | loaded 187 5-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-FI-FRM-CS07_CL14-000001 | P02 | 2025-01-23 | 2025-01-23 | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | No Issues | [5 empty] | loaded 257 5-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-FI-FRM-CS07_CL14-000002 | P02 | 2025-01-23 | 2025-01-23 | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | No Issues | [5 empty] | loaded 493 5-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-FI-FRM-CS07_CL14-000003 | P02 | 2025-01-23 | 2025-01-23 | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | no issues | [5 empty] | loaded 184 5-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-ME-FRM-CS07_CL14-000001 | P03 | 2025-01-23 | 2025-01-23 | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | no issues | [5 empty] | loaded 478 5-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-ME-FRM-CS07_CL14-000002 | P03 | 2025-01-23 |  | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | Trailing spaces on all UAID_1 column BE Leading spaces on some Com_dscrptn. 30-jan-25 |  | fixed in house - DT to follow pre issue. 30-jan-25 | fixed |  |  | loaded 325 5-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-ME-FRM-CS07_CL14-000003 | P04 | 2025-01-23 | 2025-01-23 | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | no issues | [5 empty] | loaded 141 5-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 233.01-2 | HS2-00002CTHF | Chipping Warden Green Tunnel North portal building | 1MC07-CEK-RC-FRM-CS07_CL14-000001 | P04 | 2025-01-23 |  | 2025-02-07 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600119 | No issues | Pedesstal vehicle ACS - Spelling wthdrwn Uniclass used - Pr_60_75_86_10 30-jan-25 |  |  | fixed 31-jan-25 |  |  | Loaded 41 5-feb-25 |  | 10 - Complete | Lee | shashank.bs@arcadis.com
| 221.5 | HS2-00002EK7C | Chetwode ATS UTX | 1MC06-ASC-CV-FRM-CS06_CL10-000036-ACBOS | P01 | 2025-01-23 | 2025-01-29 | 2025-01-30 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600043 |  | Com_type not correct,sent back on 28-Jan-2025 | [7 empty] | 10 - Complete | supriyan | BONICI Alexandra <alexandra.bonici@setec.com>
| 226.2 | HS2-00002Y4JL | Brackley South Cutting Radio Compound UTX | 1MC07-ASC-CV-FRM-CS07_CL12-000101-ACBOS | P01 | 2025-01-24 | 2025-01-29 | 2025-01-30 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600171 |  | Com_type not correct,sent back on 28-Jan-2025 |  | Com_type not correct,sent back on30-Jan-2025 | [5 empty] | 10 - Complete | supriyan | BONICI Alexandra <alexandra.bonici@setec.com>
| UFDR 210.B | HS2-000020CFA | CSO-02-3114P | 1MC06-ASC-UT-FRM-CS04_CL20-000035-ACBOS | P02 | 2025-01-27 |  | 2025-01-29 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600143 | [9 empty] | 10 - Complete | supriyan | Bowles, Maya <maya.bowles@arcadis.com>
| UFDR 210.B | HS2-000020CF9 | CSO-02-3113 | 1MC06-ASC-UT-FRM-CS04_CL20-000033-ACBOS | P02 | 2025-01-27 |  | 2025-01-29 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600127 | [9 empty] | 10 - Complete | supriyan | Bowles, Maya <maya.bowles@arcadis.com>
24 | 214.08 | HS2-00002TZT8 | FCC Sidings Foul Water Drainage | 1MC06-ASC-UT-FRM-CS05-000016-ACBOS | P03 | 2025-01-27 |  | 2025-01-30 |  | 1MC06-CEK-IM-DAT-CS05-600136 | [9 empty] | 10 - Complete | supriyan | Bowles, Maya <maya.bowles@arcadis.com>
| UFDR 235.A | HS2-000020CJX | CSO-04-6108 | 1MC07-ASC-UT-FRM-CS07_CL14-000003-ACBOS | P03 | 2025-01-27 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL14-600015 |  | DT asked to HOLD 28-Jan-25 | [7 empty] | 50 - HOLD |  | T, Sithrubi <sithrubi.t@arcadis.com>
| 226.2 | HS2-000001334 | Bridleway AX16 Accommodation Overbridge | 1MC07-CEK-BR-FRM-CS07_CL12-000006 | P07 | 2025-01-28 |  | 2025-02-12 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600085 | Fail | OS coordinates outside tolerance 5 Nos. 7-Feb-25 | 2025-02-10 | [6 empty] | 10 - Complete | Lee | DE OLIVEIRA DE ARAUJO Nuno Sergio <sergio.deoliveira@setec.com>
21 | 214.07 | HS2-00002CT85 | Grendon Underwood Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS05-000119-ACBOS | P02 | 2025-01-29 | 2025-01-31 | 2025-02-03 |  | 1MC06-CEK-IM-DAT-CS05-600014 |  | Extra spaces with uniclass_ID, sent back on 31-Jan-2025 | [7 empty] | 10 - Complete | supriyan | Ibrahim, Abdurrahman <abdurrahman.ibrahim@arcadis.com>
21 | 214.07 | HS2-00002CT83 | Grendon Underwood Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS05-000117-ACBOS | P02 | 2025-01-29 |  | 2025-02-03 |  | 1MC06-CEK-IM-DAT-CS05-600015 | [9 empty] | 10 - Complete | supriyan | Ibrahim, Abdurrahman <abdurrahman.ibrahim@arcadis.com>
21 | 214.07 | HS2-00002CT7M | Woodlands Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS05-000129-ACBOS | P02 | 2025-01-29 |  | 2025-02-03 |  | 1MC06-CEK-IM-DAT-CS05-600104 | [9 empty] | 10 - Complete | supriyan | Ibrahim, Abdurrahman <abdurrahman.ibrahim@arcadis.com>
21 | 214.07 | HS2-00002CT7P | Woodlands Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS05-000131-ACBOS | P02 | 2025-01-29 |  | 2025-02-03 |  | 1MC06-CEK-IM-DAT-CS05-600109 | [9 empty] | 10 - Complete | supriyan | Ibrahim, Abdurrahman <abdurrahman.ibrahim@arcadis.com>
| 215.02-02 | HS2-000020NK2 | Maintenance Access Road to Pond (Off School Hill Road East) | 1MC06-ASC-HW-FRM-CS06_CL09-000038-ACBOS | P05 | 2025-01-29 | 2025-02-07 | 2025-02-10 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600265 |  | com_type and other issues, sent back 04-Feb-2025 | [7 empty] | 10 - Complete | supriyan | Abedelkareem Alnajajreh <adan@cowi.com>
| 214.03-1 | HS2-00002BVGJ | Civil 3D Surface - P-LAN-0744 | 1MC06-ASC-DR-FRM-CS05-000007-ACBOS | P01 | 2025-01-31 | 2205-02-10 | 2025-02-12 |  | 1MC06-CEK-IM-DAT-CS05-600155 |  | sent with queries on 06-Feb-2025 | [7 empty] | 10 - Complete | supriyan | BENHMIDA Fedi <fedi.benhmida@setec.com>
| 214.03-1 | HS2-00002CT7H | C2.L.59 Catchment Model | 1MC06-ASC-DR-FRM-CS05-000029-ACBOS | P02 | 2025-01-31 | 2025-02-10 | 2025-02-12 |  | 1MC06-CEK-IM-DAT-CS05-600154 |  | sent with queries on 06-Feb-2025 | [7 empty] | 10 - Complete | supriyan | BENHMIDA Fedi <fedi.benhmida@setec.com>
23 | 204.1-1 | HS2-000020NAE | Wendover Green Tunnel North Portal Access Road | 1MC06-ASC-HW-FRM-CS03_CL17-000002-ACBOS | P01 | 2025-02-03 | 2025-02-14 | 2025-02-19 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600054 | No issues | waiting for email confirmation of GrossVolume zero values 11-Feb-25 | Confirmation rcvd 13-feb-25 | OS check fail | 2025-02-13 |  | 2025-02-14 |  |  | 10 - Complete | Lee | Abdelmalik Hassen <ABHS@cowi.com>
| UFDR 235.A | HS2-00002UMHK | C23-115-0002 | 1MC07-ASC-UT-FRM-CS07_CL14-000026-ACBOS | P03 | 2025-02-03 |  | 2025-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600114 | [9 empty] | 10 - Complete | supriyan | Bowles, Maya <maya.bowles@arcadis.com>
| 226.1 | HS2-00002EK7G | Whitfield ATS UTX | 1MC07-ASC-CV-FRM-CS07_CL12-000054-ACBOS | P01 | 2025-02-03 | 2025-02-03 | 2025-02-17 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600011 | No issues | Metrics pass. All pass | [7 empty] | 10 - Complete | Lee | BONICI Alexandra <alexandra.bonici@setec.com>
| UFDR 210.B | HS2-00002ZH4F | C23-069-003 | 1MC06-ASC-UT-FRM-CS04_CL20-000090-ACBOS | P02 | 2025-02-03 | 2025-02-03 | 2025-02-17 |  | 1MC06-CEK-UT-DAT-CS04_CL20-000001 | No issues | metrics pass. All pass | [7 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
| 222.6 | HS2-00002YGQF | Barton to Mixbury radio compound UTX No2 (GSMR Point 42) | 1MC06-ASC-CV-FRM-CS06_CL21-900011-ACBOS | P01 | 2025-02-03 | 2025-02-03 | 2025-02-17 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600108 | No issues | metrics pass. All pass | [7 empty] | 10 - Complete | Lee | BONICI Alexandra <alexandra.bonici@setec.com>
18 | 222.9 | HS2-00003BPKL | Barton to Mixbury Cutting Planting Plot 1 | 1MC06-ASC-EV-FRM-CS06_CL21-900002 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-06 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600130 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKM | Barton to Mixbury Cutting Planting Plot 2 | 1MC06-ASC-EV-FRM-CS06_CL21-900003 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-06 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600129 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKR | Barton to Mixbury Cutting Planting Plot 3 | 1MC06-ASC-EV-FRM-CS06_CL21-900007 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-06 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600125 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKS | Barton to Mixbury Cutting Planting Plot 4 | 1MC06-ASC-EV-FRM-CS06_CL21-900008 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-07 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600124 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKU | Barton to Mixbury Cutting Planting Plot 5 | 1MC06-ASC-EV-FRM-CS06_CL21-900010 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-06 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600122 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKV | Barton to Mixbury Cutting Planting Plot 6 | 1MC06-ASC-EV-FRM-CS06_CL21-900011 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-06 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600121 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKZ | Barton to Mixbury Cutting Planting Plot 7 | 1MC06-ASC-EV-FRM-CS06_CL21-900015 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-06 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600117 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKY | Barton to Mixbury Cutting Planting Plot 8 | 1MC06-ASC-EV-FRM-CS06_CL21-900014 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-06 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600118 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPL3 | Barton to Mixbury Cutting Planting Plot 9 | 1MC06-ASC-EV-FRM-CS06_CL21-900019 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-06 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600113 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPL2 | Barton to Mixbury Cutting Planting Plot 10 | 1MC06-ASC-EV-FRM-CS06_CL21-900018 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-07 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600114 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPL4 | Barton to Mixbury Cutting Planting Plot 11 | 1MC06-ASC-EV-FRM-CS06_CL21-900020 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-07 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600112 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKN | Barton to Mixbury Cutting Planting Plot 12 | 1MC06-ASC-EV-FRM-CS06_CL21-900004 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-07 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600128 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKK | Barton to Mixbury Cutting Planting Plot 13 | 1MC06-ASC-EV-FRM-CS06_CL21-900001 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-07 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600131 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKP | Barton to Mixbury Cutting Planting Plot 14 | 1MC06-ASC-EV-FRM-CS06_CL21-900005 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-07 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600127 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKQ | Barton to Mixbury Cutting Planting Plot 15 | 1MC06-ASC-EV-FRM-CS06_CL21-900006 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-07 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600126 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKT | Barton to Mixbury Cutting Planting Plot 16 | 1MC06-ASC-EV-FRM-CS06_CL21-900009 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-10 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600123 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKW | Barton to Mixbury Cutting Planting Plot 17 | 1MC06-ASC-EV-FRM-CS06_CL21-900012 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-10 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600120 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPKX | Barton to Mixbury Cutting Planting Plot 18 | 1MC06-ASC-EV-FRM-CS06_CL21-900013 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-10 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600119 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPL0 | Barton to Mixbury Cutting Planting Plot 19 | 1MC06-ASC-EV-FRM-CS06_CL21-900016 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-10 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600116 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
18 | 222.9 | HS2-00003BPL1 | Barton to Mixbury Cutting Planting Plot 20 | 1MC06-ASC-EV-FRM-CS06_CL21-900017 | P01 | 2025-02-03 | 2025-02-03 | 2025-02-10 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600115 | No issues | L3 SQL updated | [7 empty] | 10 - Complete | Lee | KNIGHT Louis <louis.knight@setec.com>
| UFDR 213.A | HS2-000020CFP | CSO-02-3118 | 1MC06-ASC-UT-FRM-CS04_CL20-000086-ACBOS | P03 | 2025-02-06 | 2025-02-06 | 2025-02-11 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600107 | No issues | [8 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
| UFDR 213.A | HS2-000020CFL | CSO-02-3116 | 1MC06-ASC-UT-FRM-CS04_CL20-000084-ACBOS | P02 | 2025-02-06 | 2025-02-06 | 2025-02-11 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600082 | No issues | [8 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
| 238.01 | HS2-00002BVN8 | C3.L.73 Catchment | 1MC07-ASC-DR-FRM-CS07_CL23-000013-ACBOS | P03 | 2025-02-06 | 2025-02-06 | 2025-02-12 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600055 | No issues | [8 empty] | 10 - Complete | Lee | Egan, Conor <Conor.Egan@wsp.com>
| 218.02 | HS2-000035UXF | HS2-00002CTDB-IMD Access Road Drainage System | 1MC06-CEK-DR-FRM-CS06_CL09-000054 | P | 2025-02-06 | 2025-03-27 | 2025-03-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600313 |  | In PPE Dsgnflow with 0.0, sent back on 17-Feb-2025 | [7 empty] | 10 - Complete | supriyan | Muthappan, Rani <rani.muthappan@arcadis.com>
| UFDR 213.A | HS2-00002PRWZ | Station Road DNO Cabinet | 1MC06-ASC-UT-FRM-CS04_CL20-000062-ACBOS | P02 | 2025-02-06 | 2025-02-06 | 2025-02-11 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600052 | No issues | [8 empty] | 10 - Complete | Lee | Bowles, Maya <maya.bowles@arcadis.com>
| 230.01-3 | HS2-00002CTFN | C3.T.29 Catchment | 1MC07-ASC-DR-FRM-CS07_CL26-000005-ACBOS | P07 | 2025-02-06 |  | 2025-02-20 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600018 | No issues | InltPnt - incorrect , no Osgb coords 14-feb-25 | 2025-02-19 | [6 empty] | 10 - Complete | Lee | gopika.b@arcadis.com
| 233.01-2 | HS2-000020364 | Appletree Lane Reinstatement | 1MC07-ASC-HW-FRM-CS07_CL13-000011-ACBOS | P03 | 2025-02-06 |  | 2025-02-12 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600020 | [9 empty] | 10 - Complete | supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com>
| 233.01-2 | HS2-000020NXY | Chipping Warden Green Tunnel North Portal Midpoint ATS Pond and Accommodation Access Road (Off Appletree Lane) | 1MC07-ASC-HW-FRM-CS07_CL13-000012-ACBOS | P02 | 2025-02-06 |  | 2025-02-12 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600026 | [9 empty] | 10 - Complete | supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com>
| 233.01-2 | HS2-00002J4YT | Reinstatement of accommodation access road to Valley View Farm | 1MC07-ASC-HW-FRM-CS07_CL13-000014-ACBOS | P02 | 2025-02-06 | 2025-02-13 | 2025-02-13 |  | 1MC07-CEK-IM-DAT-CS07_CL13-600013 |  | sdslp format issue, sent back on 12-Feb-2025 | 2025-02-13 | [6 empty] | 10 - Complete | supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com>
| 217.02 | HS2-00002CT8N | C2.OXD.L.512 Catchment Model | 1MC06-ASC-DR-FRM-CS06_CL09-000033-ACBOS | P02 | 2025-02-07 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600108 | No issues | Com_Typ & Com_Dscrptns set as "Null" on all classes. DsgnLf set as "please choose" on all classes Com_RfrncNmbr set as "Null" on all classes CHB - zero (0) values set for Dpth, FnshInvrtLvl, LwstLvl, WidthAvrgm CUT – Dpth set to Zero (0) values, Sdslp set as "Null" values DTC – GDMt set as "please choose", WidthAvrgm & DpthAvg set as Zero (0). HDW - GDMt set as "please choose", WidthAvrgm & DpthAvg set as Zero (0). Hghtm set as Zero(0). HND – Mntng set as "please choose", Hghtm set as Zero(0) PPE – GDMt, PPTyp, MtrPp, SrrndMtrl, FlwDrctn, all set as "please choose." DsgnFlw, DpthMn, DmtrExtr, set as Zero (0), DsgnFlwBss, DpthMx, DmtrIntr, all set as "Null" UEF – AngSlp, Dpth, HghtM all set as Zer(0), BckFllMtrl set as "Null" | DT have informed us this may not be required for minor TLC5 changes..set to HOLD 18-Feb-25 | Not required set to cancelled. | [5 empty] | 99 - Cancelled | Lee | BENHMIDA Fedi <fedi.benhmida@setec.com>
18 | 222.9 | HS2-00003MM31 | Box culvert 89-BC1 | 1MC06-ASC-CV-FRM-CS06_CL21-000030-ACBOS | P01 | 2025-02-19 | 2025-02-19 | 2025-02-20 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600166 | No issues | DT reworked - 19-Feb-25 | [7 empty] | 10 - Complete | Lee | MARKUS Mate <mate.markus@setec.com>
18 | 222.9 | HS2-00003MM33 | Box culvert 89-BC2 | 1MC06-ASC-CV-FRM-CS06_CL21-000032-ACBOS | P01 | 2025-02-19 | 2025-02-19 | 2025-02-20 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600168 | No issues | DT reworked - 19-Feb-25 | [7 empty] | 10 - Complete | Lee | MARKUS Mate <mate.markus@setec.com>
18 | 222.9 | HS2-00003MM32 | Box culvert 89-BC3 | 1MC06-ASC-CV-FRM-CS06_CL21-000031-ACBOS | P01 | 2025-02-19 |  | 2025-02-20 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600167 | No issues | DT reworked - 19-Feb-25 | [7 empty] | 10 - Complete | Lee | MARKUS Mate <mate.markus@setec.com>
18 | 222.9 | HS2-00003MM30 | Box culvert 88-BC3 | 1MC06-ASC-CV-FRM-CS06_CL21-000029-ACBOS | P01 | 2025-02-19 |  | 2025-02-20 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600165 | No issues | DT reworked - 19-Feb-25 | [7 empty] | 10 - Complete | Lee | MARKUS Mate <mate.markus@setec.com>
23 | 204.1-1 | HS2-00002CW1J | Wendover North cutting Access Drainage System | 1MC06-ASC-DR-FRM-CS03_CL17-000014-ACBOS | P01 | 2025-02-10 | 2025-02-17 | 2025-02-19 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600029 | No issues | Com_typs, InltPnt, leading spaces, MNH zero value NetSurfaceAreaExt CM_ISCI set as yes - Confirmations rqrd. 13-Feb-25 | 2025-02-17 | [6 empty] | 10 - Complete | Lee | Ramos, Leo <Leomel.Ramos@arcadis.com>
| 204.3-3 | HS2-00002CT4S | Risborough Road Footpath | 1MC06-ASC-HW-FRM-CS03_CL17-000022-ACBOS | P05 | 2025-02-11 |  |  |  | 1MC06-CEK-IM-DAT-CS03_CL17-600014 | Fail | Couple of Lgnthm set as Zero on LSS / GFL. DT asked to confirm OS check fail 17-Feb-25 | No reply from DT | [6 empty] | 30 - Sent back to team | Lee | Mundada, Suraj <suraj.mundada@arcadis.com>
20 | 219.1 | HS2-00002CTBT | Barton to Mixbury Cutting Noise Barrier Line | 1MC06-ASC-CV-FRM-CS06_CL21-000010-ACBOS | P02 | 2025-02-19 |  | 2025-02-25 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600066 | No issues | Many Many incomplete attributes across all classes. V. Poor lots set as null, and many columns of zero values 14-Feb-25 | 2025-02-17 | DT reworking files for Piling - 18-Feb-25 | revised file request rcvd 19-Feb-25 |  |  |  |  | 10 - Complete | Lee | MARKUS Mate <mate.markus@setec.com>
20 | 219.1 | HS2-00002CTDS | Turweston Embankment Noise Barrier Line | 1MC07-ASC-CV-FRM-CS07_CL12-000021-ACBOS | P01 | 2025-02-11 | 2025-02-20 | 2025-03-03 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600101 | No issues | metrics pass. Pass all. Fence check to do once loaded to SQL |  | DT reworking files for Piling - 18-Feb-25 | revised file request rcvd 20-Feb-25 |  |  |  |  | 10 - Complete | Lee | KHABOUZE Zakaria <zakaria.khabouze@setec.com>
20 | 219.1 | HS2-00002CTBA | Barton Hartshorn Embankment Noise Barrier Line | 1MC06-ASC-CV-FRM-CS06_CL21-000005-ACBOS | P01 | 2025-02-11 |  | 2025-02-24 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600059 | No issues | metrics pass. Pass all. Fence check to do once loaded to SQL |  | DT reworking files for Piling - 18-Feb-25 | revised file request rcvd 20-Feb-25 |  |  |  |  | 10 - Complete | Lee | TRABELSI Slim <slim.trabelsi@setec.com>
20 | 219.1 | HS2-00002CTCN | Turweston Cutting Noise Barrier Line | 1MC06-ASC-CV-FRM-CS06_CL22-000015-ACBOS | P01 | 2025-02-11 | 2025-02-11 | 2025-02-24 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600098 | No issues | metrics pass. Pass all. Fence check to do once loaded to SQL |  | DT reworking files for Piling - 18-Feb-25 | revised file request rcvd 20-Feb-25 |  |  |  |  | 10 - Complete | Lee | TRABELSI Slim <slim.trabelsi@setec.com>
23 | 204.1-1 | HS2-00002BJS1 | Stoke Grove ATS Maintenance Sidings Northern (Off Nash Lee Lane) | 1MC06-ASC-HW-FRM-CS03_CL17-000027-ACBOS | P02 | 2025-02-13 | 2025-02-18 | 2025-02-19 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600036 | No issues | Coordinates outside tolerance many com_typ incorrect MnmmThcknssmm set as 0.1 some Com_Dscrptn incorrect 13-Feb-25 | 2025-02-14 | Cannot access PW file likely set to WIP, DT notified 14-Feb-25 | 2025-02-17 | Com_typ for Pr_40_10_77 still incorrect. | 2025-02-18 |  |  | 10 - Complete | Lee | Abdelmalik Hassen <ABHS@cowi.com>
| 235.01 | HS2-000020NZU | Boddington ATS Access Road | 1MC07-ASC-HW-FRM-CS07_CL14-000032-ACBOS | P02 | 2025-02-14 | 2025-02-17 | 2025-02-18 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600016 |  | OGGB issue, sent back on 17-Feb-2025 | [7 empty] | 10 - Complete | supriyan | MarcoAntonio.Tanseco@arcadis.com
| 235.01 | HS2-000025B3A | Hill Farm Accommodation Access Road | 1MC07-ASC-HW-FRM-CS07_CL14-000035-ACBOS | P05 | 2025-02-14 | 2025-02-17 | 2025-02-18 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600024 |  | Extra carriage return, sent back on 17-Feb-2025 | [7 empty] | 10 - Complete | supriyan | MarcoAntonio.Tanseco@arcadis.com
| 235.01 | HS2-00002J4YX | Maintenance Access Road to Pond (off Realigned Banbury Road (East side of HS2)) | 1MC07-ASC-HW-FRM-CS07_CL14-000042-ACBOS | P03 | 2025-02-14 |  | 2025-02-18 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600026 | [9 empty] | 10 - Complete | supriyan | MarcoAntonio.Tanseco@arcadis.com
| 235.01 | HS2-00002J4YV | Stoneton Lane Realignment | 1MC07-ASC-HW-FRM-CS07_CL14-000040-ACBOS | P01 | 2025-02-14 |  | 2025-02-18 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600008 | [9 empty] | 10 - Complete | supriyan | MarcoAntonio.Tanseco@arcadis.com
| 229.01-1 | HS2-00002C3YS | B4525 Welsh Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL25-000008-ACBOS | P03 | 2025-02-17 | 2025-02-17 | 2025-02-20 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600053 | No issues | DT have asked for some zero's to be removed for BAS & BRR - 19-Feb-25 |  | Done | [5 empty] | 10 - Complete | Lee | gopika.b@arcadis.com>
21 | 214.07 | HS2-00002CT81 | Maintenance Access Road to Pond (Connecting CAG-2 and GUN-28) | 1MC06-ASC-HW-FRM-CS05-000027-ACBOS | P08 | 2025-02-17 |  | 2025-02-19 |  | 1MC06-CEK-IM-DAT-CS05-600285 | No issues | Os LSS snakegrids showing duplicate of Osgrids. 18-feb-25 JSON created to test. |  | all coords seem correct in DAC viewer. | [5 empty] | 10 - Complete | Lee | Shabad, Mallikarjun <mallikarjun.shabad@arcadis.com>
| 237.02 | HS2-00002YNH5 | Crossing of Bridleway SM229 to River Itchen Tributary | 1MC07-ASC-CV-FRM-CS07_CL23-000049-ACBOS | P06 | 2025-02-18 | 2025-03-21 |  |  | 1MC07-CEK-IM-DAT-CS07_CL23-600076 |  | Queries and Uniclass_ID issues. Sent back on 24-Feb-2025 |  | multiple comments, sent back on 24-Mar-2025 | [5 empty] | 30 - Sent back to team | supriyan | Martin, Joel <Joel.Martin@arcadis.com>
| 214.03-1 | HS2-00002CT7T | Civil 3D Solids Model - P-RAI-0746 | 1MC06-ASC-DR-FRM-CS05-000001-ACBOS | P01 | 2025-02-18 | 2025-02-25 | 2025-02-26 |  | 1MC06-CEK-IM-DAT-CS05-600148 |  | Few queries, sent back file on 24-Feb-2025 | [7 empty] | 10 - Complete | supriyan | BENHMIDA Fedi <fedi.benhmida@setec.com>
| 214.03-1 | HS2-00002CT7G | C2.L.57 Catchment Model | 1MC06-ASC-DR-FRM-CS05-000028-ACBOS | P01 | 2025-02-18 | 2025-02-24 | 2025-03-05 |  | 1MC06-CEK-IM-DAT-CS05-600153 |  | Few queries, sent back file on 24-Feb-2025 | [7 empty] | 10 - Complete | supriyan | BENHMIDA Fedi <fedi.benhmida@setec.com>
18 | 222.9 | HS2-00003D841 | Access Stair 93-ST6 | 1MC06-ASC-CV-FRM-CS06_CL22-900009 | P01 | 2025-01-22 |  | 2025-02-20 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600181 | No issues | JSON request missed somehow. |  | couple of Uniclass code look sequential. 19-Feb-25 | Fixed in house, check PW file before issuing |  |  |  |  | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D846 | Access Stair 93-ST11 | 1MC06-ASC-CV-FRM-CS06_CL22-900010 | P01 | 2025-01-22 |  | 2025-02-20 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600186 | No issues | JSON request missed somehow. | [7 empty] | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D849 | Access Stair 93-ST14 | 1MC06-ASC-CV-FRM-CS06_CL22-900011 | P01 | 2025-01-22 |  | 2025-02-20 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600189 | No issues | JSON request missed somehow. | [7 empty] | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D84A | Access Stair 93-ST15 | 1MC06-ASC-CV-FRM-CS06_CL22-900012 | P01 | 2025-01-22 |  | 2025-02-19 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600190 |  | JSON request missed somehow. | [7 empty] | 10 - Complete | supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D84E | Access Stair 94-ST4 | 1MC06-ASC-CV-FRM-CS06_CL22-900013 | P01 | 2025-01-22 |  | 2025-02-20 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600194 |  | JSON request missed somehow. | [7 empty] | 10 - Complete | supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D84M | Access Stair 94-ST11 | 1MC06-ASC-CV-FRM-CS06_CL22-900014 | P01 | 2025-01-22 |  | 2025-02-20 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600201 |  | JSON request missed somehow. | [7 empty] | 10 - Complete | supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D84R | Access Stair 94-ST15 | 1MC06-ASC-CV-FRM-CS06_CL22-900015 | P01 | 2025-01-22 |  | 2025-02-20 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600205 |  | JSON request missed somehow. |  | Wrong JSON placeholder | [5 empty] | 10 - Complete | supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D84S | Access Stair 94-ST16 | 1MC06-ASC-CV-FRM-CS06_CL22-900016 | P01 | 2025-01-22 | 2025-02-19 | 2025-02-20 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600206 |  | JSON request missed somehow. |  | Wrong UAID_2, sent back on 19-Feb-2025 | [5 empty] | 10 - Complete | supriyan | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-ASC-CV-FRM-CS07-000003-ACBOS | P01 | 2025-02-19 | 2025-02-19 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  |  |  | 725 assets |  | loaded |  | 10 - Complete | Lee | alex.foster@arcadis.com; Subbarayan.Shanmugham@arcadis.com; venkatesh.bandi@arcadis.com; ravikumar.shukla@arcadis.com; toby.harnett@arcadis.com; pkal@cowi.com; saikumar.maruboyina@arcadis.com; Konde, AnilMohan.K@arcadis.com; akashmohan.j@arcadis.com; shashank.bs@arcadis.com;Mahesha.Laxmana@arcadis.com; raghuvikas.reddyandru@arcadis.com; sam.keeling@arcadis.com; a.macpherson@moxonarchitects.com; vipin.tk@arcadis.com; pavana.um@arcadis.com
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-ASC-CV-FRM-CS07-000001-ACBOS | P04 | 2025-02-19 | 2025-02-19 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  |  |  | 1420 assets |  | loaded |  | 10 - Complete | Lee | AS ABOVE
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-CEK-RC-FRM-CS07_CL25-000006 | P04 | 2025-02-19 | 2025-02-25 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  | Couple of spelling mistake in Com_Typ / Dscrptn. Fixed in house 24-Feb-25 DT to follow in PW file. Withdrawn and incorrect Uniclass used. | rcvd 25-feb-25 | 41 assets |  | loaded |  | 10 - Complete | Lee | AS ABOVE
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-CEK-EL-FRM-CS07_CL25-000007 | P02 | 2025-02-19 | 2025-02-19 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  |  |  | 199 |  | loaded |  | 10 - Complete | Lee | AS ABOVE
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-CEK-EL-FRM-CS07_CL25-000010 | P02 | 2025-02-19 | 2025-02-19 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  |  |  | 187 |  | loaded |  | 10 - Complete | Lee | AS ABOVE
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-CEK-EL-FRM-CS07_CL25-000009 | P02 | 2025-02-19 | 2025-02-19 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  |  |  | 247 |  | loaded |  | 10 - Complete | Lee | AS ABOVE
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-CEK-EL-FRM-CS07_CL25-000008 | P02 | 2025-02-19 | 2025-02-19 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  |  |  | 170 |  | loaded |  | 10 - Complete | Lee | AS ABOVE
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-CEK-EL-FRM-CS07_CL25-000006 | P02 | 2025-02-19 | 2025-02-19 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  |  |  | 1457 |  | loaded |  | 10 - Complete | Lee | AS ABOVE
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-CEK-FI-FRM-CS07_CL25-000004 | P02 | 2025-02-19 | 2025-02-19 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  | ZZ-ZZ layers found DT saying that this is correct 26-Feb-25 |  | 257 |  | loaded |  | 10 - Complete |  | AS ABOVE
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-CEK-FI-FRM-CS07_CL25-000005 | P02 | 2025-02-19 | 2025-02-19 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  |  |  | 492 |  | loaded |  | 10 - Complete |  | AS ABOVE
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-CEK-FI-FRM-CS07_CL25-000006 | P02 | 2025-02-19 | 2025-02-19 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  | ZZ-ZZ layers found DT saying that this is correct 26-Feb-25 |  | 170 |  | loaded |  | 10 - Complete |  | AS ABOVE
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-CEK-ME-FRM-CS07_CL25-000004 | P02 | 2025-02-19 | 2025-02-26 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  | Reversed Snakewgrid and OS coordinates - Fixed in house - DT to update IFC etc concurrently 26-Feb-26 | rcvd 26-Feb-25 | 478 |  | loaded |  | 10 - Complete |  | AS ABOVE
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-CEK-ME-FRM-CS07_CL25-000005 | P02 | 2025-02-19 | 2025-02-19 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  |  |  | 325 |  | loaded |  | 10 - Complete |  | AS ABOVE
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-CEK-ME-FRM-CS07_CL25-000006 | P02 | 2025-02-19 | 2025-02-19 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  | Missing MTRL on HS2-00002T2NV 26-Feb-25 | rcvd 26-Feb-25 | 141 |  | loaded |  | 10 - Complete |  | AS ABOVE
| 229.01-1 | HS2-000025B2C | Greatworth Green Tunnel South portal building | 1MC07-CEK-AR-FRM-CS07_CL25-600002 | P03 | 2025-02-19 | 2025-02-19 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600057 | No issues | COMBINED DISCIPLINE JSON WORKS |  |  |  | 668 |  | loaded |  | 10 - Complete |  | AS ABOVE
| 233.01-1 | HS2-000020360 | B4525 Welsh Road | 1MC07-ASC-HW-FRM-CS07_CL25-000022-ACBOS | P03 | 2025-02-19 |  | 2025-02-24 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600045 | [9 empty] | 10 - Complete | supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com>
| 233.01-1 | HS2-000020359 | Greatworth Park Access Reinstatement | 1MC07-ASC-HW-FRM-CS07_CL25-000020-ACBOS | P03 | 2025-02-19 | 2025-02-24 | 2025-02-26 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600040 |  | wronf Angle slope, send back on 24-Feb-2025 | [7 empty] | 10 - Complete | supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com>
18 | 222.9 | HS2-00003D83V | Access Stairs 92-ST6 | 1MC06-ASC-CV-FRM-CS06_CL22-900003 | P02 | 2025-02-20 |  | 2025-02-24 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600176 | [9 empty] | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
18 | 222.9 | HS2-00003D84S | Access Stairs 94-ST16 | 1MC06-ASC-CV-FRM-CS06_CL22-900016 | P02 | 2025-02-20 |  | 2025-02-25 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600206 | No issues | [8 empty] | 10 - Complete | Lee | HERVOCHES Guillaume <guillaume.hervoches@setec.com>
| 229.01-1 | HS2-00003B5FS | Greatworth Access Road Drainage System | 1MC07-ASC-DR-FRM-CS07_CL25-000025-ACBOS | P03 | 2025-02-20 |  | 2025-02-21 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600068 | [9 empty] | 10 - Complete | supriyan | B, Gopika <gopika.b@arcadis.com>
| 215.02 | HS2-00002T427 | ACBOS - Calvert Green Overbridge Embankments Solids Model | 1MC06-ASC-HW-FRM-CS06_CL09-000069-ACBOS | P01 | 2025-02-20 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600178 |  | OSGB errors, sent back on 27-Feb-2028 | [7 empty] | 30 - Sent back to team | supriyan | Shabad, Mallikarjun <mallikarjun.shabad@arcadis.com>
| 235.01 | HS2-000025B3B | Banbury Road/Warwick Road (Boddington) Realignment | 1MC07-ASC-HW-FRM-CS07_CL14-000044-ACBOS | P01 | 2025-02-21 | 2025-03-05 | 2025-03-05 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600025 |  | Issues found send bak on 27-Feb-2025 |  | 0's found in IFC presentation layer |  | Wrong co-ordinate for one asset |  |  |  | 10 - Complete | supriyan | Tanseco, Marco <MarcoAntonio.Tanseco@arcadis.com>
| 214.03-1 | HS2-00002CT7X | Civil 3D Solids Model - P-MCJ-0756 | 1MC06-ASC-DR-FRM-CS06_CL09-000005-ACBOS | P02 | 2025-02-21 | 2025-04-03 | 2025-04-04 |  | 1MC06-CEK-IM-DAT-CS05-600150 |  | OSGB and other issues, sent back on 03-Mar-2025 | [7 empty] | 10 - Complete | supriyan | BENHMIDA Fedi <fedi.benhmida@setec.com>
20 | 219.1 | HS2-00002CT9Z | Cowley Embankment Noise Barrier Line | 1MC06-ASC-CV-FRM-CS06_CL10-000018-ACBOS | P02 | 2025-02-24 | 2025-02-24 | 2025-02-25 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600061 | No issues | [8 empty] | 10 - Complete | Lee | TRABELSI Slim <slim.trabelsi@setec.com>
20 | 219.1 | HS2-00002CTB2 | Chetwode Cutting Noise Barrier Line | 1MC06-ASC-CV-FRM-CS06_CL10-000023-ACBOS | P01 | 2025-02-24 | 2025-02-27 | 2025-03-05 |  | 1MC06-CEK-IM-DAT-CS06_CL10-600011 | No issues | DT making changes - 24-Feb-25 | 2025-02-28 | single ACBOS load fail. Split into 5 files to load Please check Monday 3/3/25 that data has fully loaded. | [5 empty] | 10 - Complete | supriyan | MARKUS Mate <mate.markus@setec.com>
20 | 219.1 | HS2-00002CTEA | Brackley Embankment Noise Barrier Line | 1MC07-ASC-CV-FRM-CS07_CL12-000024-ACBOS | P01 | 2025-02-25 | 2025-02-25 | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600143 | No issues | [8 empty] | 10 - Complete | Lee | MARKUS Mate <mate.markus@setec.com>
20 | 219.1 | HS2-00002CTE5 | Brackley South Cutting Noise Barrier Line | 1MC07-ASC-CV-FRM-CS07_CL12-000023-ACBOS | P01 | 2025-02-25 |  | 2025-02-28 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600090 | No issues | PIL Com_rfrnNmbr set as null. Fixed in house DT to update Pwfile 26-Feb-25 | [7 empty] | 10 - Complete | Lee | TRABELSI Slim <slim.trabelsi@setec.com>
20 | 219.1 | HS2-00002CTDZ | Helmdon Embankment Noise Barrier Line | 1MC07-ASC-CV-FRM-CS07_CL12-000022-ACBOS | P01 | 2025-02-26 | 2025-03-04 |  |  | 1MC07-CEK-IM-DAT-CS07_CL12-600110 | No issues | CLM - GdMt set as natural stone kerb? DT to confirm 26-feb-25 | 2025-02-28 | metrics mismatch Smrtfrms v ACBOS PLC All other issues resolved 28-Feb-25 |  | DT have fixed late Friday. Please re export from PW Monday 3/3/25 |  |  |  | 10 - Complete | supriyan | MARKUS Mate <mate.markus@setec.com>
20 | 219.1 | HS2-00002CQQL | Brackley North Cutting Noise Barrier Line | 1MC07-ASC-CV-FRM-CS07_CL12-000025-ACBOS | P01 | 2025-02-27 | 2025-03-04 | 2025-03-05 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600126 |  | Incomplete ACBOS, sent back on 04-March-2025 | [7 empty] | 10 - Complete | supriyan | TRABELSI Slim <slim.trabelsi@setec.com>
| 238.01 | HS2-00002BVN8 | C3.L.73 Catchment | 1MC07-ASC-DR-FRM-CS07_CL23-000013-ACBOS | P04 | 2025-03-03 | 2025-03-06 | 2025-03-07 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600055 |  | Extra asset, OSGB issues and queries, sent back 0n 05-Mar-2025 | [7 empty] | 10 - Complete | supriyan | Conor.Egan@wsp.com>
| 234.01 | HS2-00002CTHL | C3.T.56 Catchment | 1MC07-ASC-DR-FRM-CS07_CL14-000004-ACBOS | P02 | 2025-03-03 |  | 2025-03-05 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600071 | [9 empty] | 10 - Complete | supriyan | gopika.b@arcadis.com>
| 214.06 | HS2-00002BJU2 | Sheephouse Wood Bat Mitigation Structure Detailed Design Footpath SCL13 Realignment | 1MC06-ASC-HW-FRM-CS06_CL09-000030-ACBOS | P03 | 2025-03-05 | 2025-03-11 | 2025-03-18 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600089 |  | Multiple issues, sent back on 06-Mar-2025 |  | missing asset, sent back on 10-Mar-2025 | CM_CHG wrong, sent back on 12-Mar-2025 |  |  |  |  | 10 - Complete | supriyan | Abedelkareem Alnajajreh <adan@cowi.com>
| 238.03 | HS2-00003MHBZ | Ladbroke Cutting Banbury Road OB Access Stairs 1 | 1MC07-ASC-CV-FRM-CS07_CL24-000153-ACBOS | P01 | 2025-03-06 |  | 2023-03-07 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600125 | [9 empty] | 10 - Complete | supriyan | joel.martin@arcadis.com
| 238.03 | HS2-00003MHC0 | Ladbroke Cutting Banbury Road OB Access Stairs 2 | 1MC07-ASC-CV-FRM-CS07_CL24-000154-ACBOS | P01 | 2025-03-06 | 2025-04-09 | 2025-04-09 |  | 1MC07-CEK-IM-DAT-CS07_CL24-600126 |  | OSGB Issue, sent back on 07-Mar-2025 |  | UAID_3 issue, sent back on 07-Mar-2025 | [5 empty] | 10 - Complete | supriyan | joel.martin@arcadis.com
| IDR 224.2 | HS2-000001331 | A422 Brackley Road Overbridge | 1MC06-ASC-BR-FRM-CS06_CL22-000002-ACBOS | P04 | 2025-03-06 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL22-600071 |  | Multiple issues, sent back on 07-Mar-2025 | [7 empty] | 99 - Cancelled |  | sergio.deoliveira@setec.com>
| IDR 213.02-1 | HS2-00002CT7A | Civil 3D Solids - P-MCJ-0734-P-MCJ-0735-P-MCJ-0736-P-MCJ-0738-P-MCJ-0744 | 1MC06-ASC-DR-FRM-CS05-000013-ACBOS | P03 | 2025-03-07 | 2025-03-11 | 2025-03-13 |  | 1MC06-CEK-IM-DAT-CS05-600118 |  | Multiple Issue, sent back on 10-Mar-2025 | [7 empty] | 10 - Complete | supriyan | BENHMIDA Fedi <fedi.benhmida@setec.com>
| 213.02-1 | HS2-00002CT7S | Civil 3D Solids Model - P-RAI-0737 | 1MC06-ASC-DR-FRM-CS05-000006-ACBOS | P03 | 2025-03-07 | 2025-03-11 | 2025-03-13 |  | 1MC06-CEK-IM-DAT-CS05-600031 |  | Multiple Issue, sent back on 10-Mar-2025 | [7 empty] | 10 - Complete | supriyan | fedi.benhmida@setec.com
| 235.01_1 | HS2-000001456 | Footpath SM101 Green Overbridge | 1MC07-ASC-BR-FRM-CS07_CL14-000002-ACBOS | P04 | 2025-03-07 | 2025-03-19 | 2025-03-19 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600018 |  | Multiple Queires, sent back on 10-Mar-2025 |  | sdslp with 1 in 999, sent back on 17-Mar-2025 |  | Lengthm issue found during Review, sent back on 18-Mar-2025 |  |  |  | 10 - Complete | supriyan | jake.marshall@arcadis.com
| UFDR 235.A | HS2-00002UMHK | C23-115-0002 | 1MC07-ASC-UT-FRM-CS07_CL14-000026-ACBOS | P04 | 2025-03-07 |  | 2025-03-11 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600114 | [9 empty] | 10 - Complete | supriyan | Bowles, Maya <maya.bowles@arcadis.com>
| UFDR 235.A | HS2-000020CJX | CSO-04-6108 | 1MC07-ASC-UT-FRM-CS07_CL14-000003-ACBOS | P04 | 2025-03-11 |  | 2025-03-11 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600015 | [9 empty] | 10 - Complete |  | sithrubi.t@arcadis.com>
| UFDR 235.A | HS2-000020CJW | CSO-04-3120 | 1MC07-ASC-UT-FRM-CS07_CL14-000009-ACBOS | P04 | 2025-03-11 |  | 2025-03-12 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600014 | [9 empty] | 10 - Complete | supriyan | sithrubi.t@arcadis.com>
| 213.05 | HS2-000020NGC | Footpath QUA 24A 1 Diversion Solids Model | 1MC06-ASC-HW-FRM-CS05-000051-ACBOS | P05 | 2025-03-14 | 2025-03-21 | 2025-03-21 |  | 1MC06-CEK-IM-DAT-CS05-600082 |  | OSGB issue, sent back on 17-Mar-2025 |  | OSGB issue, sent back on 20-Mar-2025 | [5 empty] | 10 - Complete | supriyan | mallikarjun.shabad@arcadis.com>
| 213.05 | HS2-00002CT7D | Bridleway QUA 28A Diversion Solids Model | 1MC06-ASC-HW-FRM-CS05-000036-ACBOS | P05 | 2025-03-14 | 2025-03-19 | 2025-03-20 |  | 1MC06-CEK-IM-DAT-CS05-600124 |  | OSGB issue, sent back on 17-Mar-2025 | [7 empty] | 10 - Complete | supriyan | mallikarjun.shabad@arcadis.com>
| IDR 213.02-1 | HS2-00002CT7S | Civil 3D Solids Model - P-RAI-0737 | 1MC06-ASC-DR-FRM-CS05-000006-ACBOS | P05 | 2025-03-18 | 2025-03-25 | 2025-03-25 |  | 1MC06-CEK-IM-DAT-CS05-600031 |  | queries on 0's and null sent back on 19-Mar-2025 | [7 empty] | 10 - Complete | supriyan | fedi.benhmida@setec.com
| IDR 213.02-1 | HS2-00002CT7A | Civil 3D Solids - P-MCJ-0734-P-MCJ-0735-P-MCJ-0736-P-MCJ-0738-P-MCJ-0744 | 1MC06-ASC-DR-FRM-CS05-000013-ACBOS | P06 | 2025-03-18 | 2025-03-25 | 2025-03-25 |  | 1MC06-CEK-IM-DAT-CS05-600118 |  | queries on 0's and null sent back on 19-Mar-2025 | [7 empty] | 10 - Complete | supriyan | BENHMIDA Fedi <fedi.benhmida@setec.com>
| IDR 214.03-1 | HS2-00002CT7W | Civil 3D Solids Model - P-MCJ-0749 | 1MC06-ASC-DR-FRM-CS06_CL09-000004-ACBOS | P01 | 2025-03-18 | 2025-03-25 | 2025-03-25 |  | 1MC06-CEK-IM-DAT-CS05-600146 |  | queries on 0's and null sent back on 19-Mar-2025 | [7 empty] | 10 - Complete | supriyan | BENHMIDA Fedi <fedi.benhmida@setec.com>
| IDR 214.08 | HS2-00002CT7Z | Civil 3D Solids Model - P-FCC-0766 | 1MC06-ASC-DR-FRM-CS05-000018-ACBOS | P02 | 2025-03-18 | 2025-04-04 | 2025-04-08 |  | 1MC06-CEK-IM-DAT-CS05-600310 |  | queries on 0's and null sent back on 19-Mar-2025 |  | sent back at review stage on 26th March | [5 empty] | 10 - Complete | supriyan | BENHMIDA Fedi <fedi.benhmida@setec.com>
| IDR 214.08 | HS2-00002CT7K | C2.L.62 Catchment Model | 1MC06-ASC-DR-FRM-CS05-000031-ACBOS | P02 | 2025-03-18 | 2025-04-03 | 2025-04-08 |  | 1MC06-CEK-IM-DAT-CS05-600309 |  | UAID_1 is not correct, sent back on 21-Mar-2025 |  | comas as decimal seperator sent back 28-Mar-2025 | [5 empty] | 10 - Complete | supriyan | BENHMIDA Fedi <fedi.benhmida@setec.com>
| IDR 214.03-1 | HS2-00002CT7U | Civil 3D Solids Model - P-RAI-0753 | 1MC06-ASC-DR-FRM-CS05-000009-ACBOS |  | 2025-03-18 | 2025-03-27 | 2025-03-28 |  | 1MC06-CEK-IM-DAT-CS05-600149 |  | queries on 0's and null sent back on 19-Mar-2025 |  | Comas as decimal seperator | [5 empty] | 10 - Complete | supriyan | fedi.benhmida@setec.com>
| IDR 214.03-1 | HS2-00002CT7J | C2.L.61 Catchment Model | 1MC06-ASC-DR-FRM-CS05-000030-ACBOS |  | 2025-03-18 |  | 2025-03-21 |  | 1MC06-CEK-IM-DAT-CS05-600156 | [9 empty] | 10 - Complete | supriyan | fedi.benhmida@setec.com>
| IDR 224.2 | HS2-000001331 | A422 Brackley Road Overbridge | 1MC06-CEK-BR-FRM-CS06_CL22-000020 | P04 | 2025-03-19 | 2025-03-25 | 2025-04-02 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600071 |  | MxmmPrmttdWght with 9999 , sent back on 20-Mar-2025 | [7 empty] | 10 - Complete | supriyan | sergio.deoliveira@setec.com>
| 214.06 | HS2-00003LH5N | Muxwell Brook Crossing Slab | 1MC06-ASC-CV-FRM-CS05-000147-ACBOS | P01 | 2025-03-25 | 2025-04-02 | 2025-04-03 |  | 1MC06-CEK-IM-DAT-CS05-600304 |  | Assetclass wrong mapping, sent back on 26-Mar-2025 | [7 empty] | 10 - Complete | supriyan | Pachaiappann, Nagarathinam <nagarathinam.pachaiappann@arcadis.com>
| UFDR 209.A | HS2-00002SZLY | Aylesbury North Cutting Group | 1MC06-ASC-UT-FRM-CS04_CL18-000041-ACBOS | P03 | 2025-03-26 |  | 2025-03-27 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600094 | [9 empty] | 10 - Complete | supriyan | mohit.kamboj@arcadis.com>
| UFDR 209.A | HS2-000020CF1 | Aylesbury North Cutting Group | 1MC06-ASC-UT-FRM-CS04_CL18-000021-ACBOS | P07 | 2025-03-25 |  | 2025-03-27 |  | 1MC06-CEK-IM-DAT-CS04_CL18-600009 | [9 empty] | 10 - Complete | supriyan | Kamboj, Mohit <mohit.kamboj@arcadis.com>
| 216.01-2 | HS2-00002CT8U | HS2-00002C5T4-West Street Drainage System | 1MC06-ASC-DR-FRM-CS06_CL09-000029-ACBOS | P02 | 2025-03-26 |  | 2025-03-27 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600255 | [9 empty] | 10 - Complete | supriyan | Muthappan, Rani <rani.muthappan@arcadis.com>
| 213.02-1 | HS2-00002NNJ2 | Doddershall Highway Access Solids Model | 1MC06-ASC-HW-FRM-CS05-000066-ACBOS | P02 | 2025-03-27 |  | 2025-04-01 |  | 1MC06-CEK-IM-DAT-CS05-600050 | [9 empty] | 10 - Complete | supriyan | mallikarjun.shabad@arcadis.com>
| 218.02 | HS2-00003B93M | Calvert Cutting Planting Plot 17 | 1MC06-ASC-EV-FRM-CS06_CL09-900028 | P03 | 2025-03-27 |  | 2025-04-01 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600283 | [9 empty] | 10 - Complete | supriyan | louis.knight@setec.com>
| 214.06 | HS2-00002KRAJ | Greatmoor No.4 Watercourse Diversion | 1MC06-ASC-DR-FRM-CS05-000107-ACBOS | P04 | 2025-03-28 | 2025-04-04 | 2025-04-08 |  | 1MC06-CEK-IM-DAT-CS05-600064 |  | OSGB issue, sent back on 28-Mar-2025 | [7 empty] | 10 - Complete | supriyan | Bulusu, Sai Sravan Kumar <saisravankumar.bulusu@arcadis.com>
| 223.4 | HS2-000001329 | Bridleway 303-4 Overbridge | 1MC06-CEK-BR-FRM-CS06_CL22-000004 | P09 | 2025-03-28 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL22-600056 |  | old LoMD related fields, sent back on 03Apr2025 | [7 empty] | 30 - Sent back to team | supriyan | Eschard, Pierre <pierre.eschard@arcadis.com>
| IDR 202.5-3 | HS2-00002CT3C | Small Dean Lane Drainage System | 1MC06-ASC-DR-FRM-CS03_CL06-000007-ACBOS | P01 | 2025-03-31 |  | 2025-04-08 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600038 | [9 empty] | 10 - Complete | supriyan | Cordero, Jan
| 214.06 | HS2-00003LH5M | Mega Ditch Retaining Wall Access Steps | 1MC06-ASC-CV-FRM-CS05-000146-ACBOS | P01 | 2025-03-31 |  | 2025-04-03 |  | 1MC06-CEK-IM-DAT-CS05-600306 | [9 empty] | 10 - Complete | supriyan | karthiban.sr@arcadis.com>
| 214.06 | HS2-000001309 | Sheephouse Wood Bat Mitigation Structure | 1MC06-CEK-BR-FRM-CS05-600033 | P01 | 2025-04-03 | 2025-04-08 | 2025-04-09 |  | 1MC06-CEK-IM-DAT-CS05-600113 |  | Extra assets, sent back on 08-Apr-2025 | [7 empty] | 10 - Complete | supriyan | alpk@cowi.com>
| 214.06 | HS2-000001309 | Sheephouse Wood Bat Mitigation Structure | 1MC06-CEK-BR-FRM-CS05-600032 | P1 | 2025-04-08 |  | 2025-04-09 |  | 1MC06-CEK-IM-DAT-CS05-600113 | [9 empty] | 10 - Complete | supriyan | alpk@cowi.com>
| IDR 235.01-01-2 | HS2-00002UU9P | Accommodation Access Road (Off Diverted Claydon Road) | 1MC07-ASC-HW-FRM-CS07_CL14-000048-ACBOS | P01 | 2025-04-08 | 2025-04-10 | 2025-04-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600120 |  | Angle Slope issue, sent back on 10-Apr-2025 | [7 empty] | 10 - Complete | supriyan | veenadhari.bavanam@arcadis.com>
| UFDR 213.B | HS2-00002FE9J | CSO-02-1217P | 1MC06-ASC-UT-FRM-CS04_CL20-000042-ACBOS | P01 | 2025-04-10 |  | 2025-04-15 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600017 | [9 empty] | 10 - Complete | supriyan | maya.bowles@arcadis.com>
| UFDR 213.B | HS2-000020CFS | CSO-02-3119P | 1MC06-ASC-UT-FRM-CS05-000033-ACBOS | P01 | 2025-04-10 |  | 2025-04-15 |  | 1MC06-CEK-IM-DAT-CS05-600097 | [9 empty] | 10 - Complete | supriyan | maya.bowles@arcadis.com>
| UFDR 213.B | HS2-000020CFQ | CSO-02-6213P | 1MC06-ASC-UT-FRM-CS04_CL20-000040-ACBOS | P01 | 2025-04-10 |  | 2025-04-15 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600104 | [9 empty] | 10 - Complete | supriyan | maya.bowles@arcadis.com>
| IDR 235.01-01-2 | HS2-000025B3B | Banbury Road/Warwick Road (Boddington) Realignment | 1MC07-ASC-HW-FRM-CS07_CL14-000044-ACBOS | P06 | 2025-04-10 | 2025-04-21 | 2025-04-23 |  | 1MC07-CEK-IM-DAT-CS07_CL14-600025 |  | OSGB Issues and few other queries,sent back on 15-Apr-2025 | [7 empty] | 10 - Complete | supriyan | veenadhari.bavanam@arcadis.com>
| 216.01 | HS2-000020RM2 | West Street Realignment Solids Model | 1MC06-ASC-HW-FRM-CS06_CL09-000022-ACBOS | P04 | 2025-04-16 | 2025-04-23 | 2025-04-25 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600100 |  | Com_type issues, send back on 17-Apr-2025 | [7 empty] | 10 - Complete | supriyan | grahith.ravikiran@arcadis.com>
| 216.01 | HS2-000020NL1 | Access Road to Field (Off West Street) Solids Model | 1MC06-ASC-HW-FRM-CS06_CL09-000023-ACBOS | P05 | 2025-04-16 | 2025-04-23 | 2025-04-25 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600102 |  | Com_type issues, send back on 17-Apr-2025 | [7 empty] | 10 - Complete | supriyan | grahith.ravikiran@arcadis.com>
| 216.01 | HS2-000020356 | Sewage Works Accommodation and Pond Access Road Solids Model | 1MC06-ASC-HW-FRM-CS06_CL09-000024-ACBOS | P05 | 2025-04-16 | 2025-04-23 | 2025-04-25 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600156 |  | OSGB Issues, sent back on 17-Apr-2025 | [7 empty] | 10 - Complete | supriyan | grahith.ravikiran@arcadis.com>
| IDR 225_1 | HS2-000001064 | Turweston Viaduct | 1MC07-CEK-BR-FRM-CS07_CL12-000010 | P06 | 2025-04-17 | 2025-04-23 | 2025-04-25 |  | 1MC07-CEK-IM-DAT-CS07_CL12-600103 |  | Com_type issue, sent back on 21-April-2024 |  | HS2 class issues, sent back on 23-April-2025 | [5 empty] | 10 - Complete | supriyan | sergio.deoliveira@setec.com
| IDR 214.03-1 | HS2-00002CT7Y | Civil 3D Solids Model - P-MCJ-0766 | 1MC06-ASC-DR-FRM-CS06_CL09-000006-ACBOS | P02 | 2025-04-17 | 2025-04-22 |  |  | 1MC06-CEK-IM-DAT-CS05-600152 |  | Queries sent on 21-Apr-2025 | [7 empty] | 10 - Complete | supriyan | fedi.benhmida@setec.com
| 213.01-1 | HS2-00002CW1G | HS2-00002C5SZ-Station Road Drainage System | 1MC06-ASC-DR-FRM-CS04_CL20-000014-ACBOS | P02 | 2025-04-24 | 2025-06-25 | 2025-06-27 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600007 |  | OSGB issues, sent back on 28-Apr-2025 |  | Put on hold on 25-June-2025, as suggested by team |  | OSGB issues, sent back on 26-June-2025 |  |  |  | 10 - Complete | supriyan | Muthappan, Rani <rani.muthappan@arcadis.com>
| 214.06 | HS2-00002BJU2 | Sheephouse Wood Bat Mitigation Structure Detailed Design Footpath SCL13 Realignment | 1MC06-ASC-HW-FRM-CS06_CL09-000030-ACBOS | P08 | 2025-04-25 | 2025-05-08 | 2025-05-14 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600089 |  | OSGB isues, sent back on 28-Apr-2025 |  | sdslp and other issues, sent back on 09-May-2025 | [5 empty] | 10 - Complete | supriyan | Abedelkareem Alnajajreh <adan@cowi.com>
| IDR 214.10 | HS2-00002DRXL | Footpath CAG 2 Realignment | 1MC06-ASC-HW-FRM-CS05-000029-ACBOS |  | 2025-04-29 | 2025-05-28 | 2025-05-29 |  | 1MC06-CEK-IM-DAT-CS05-600061 |  | Sent back at Review stage | [7 empty] | 10 - Complete | supriyan | adan@cowi.com>
| IDR 214.10 | HS2-00002BJTZ | Calvert Footpath and Cycle route (south off HS2) | 1MC06-ASC-HW-FRM-CS05-000090-ACBOS |  | 2025-04-29 | 2025-05-20 | 2025-05-21 |  | 1MC06-CEK-IM-DAT-CS05-600175 |  | Classification and other issues, sent back on 30-Apr-2025 | [7 empty] | 10 - Complete | supriyan | adan@cowi.com
| 217.03 | HS2-00002CT8S | HS2-00002C5T4-Addison Road Drainage System | 1MC06-ASC-DR-FRM-CS06_CL09-000027-ACBOS | P03 | 2025-05-01 |  | 2025-05-02 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600110 | [9 empty] | 10 - Complete | supriyan | rani.muthappan@arcadis.com>
| 204.1 | HS2-00002XQ2Q | SWBMS Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS05-000104-ACBOS | P04 | 2025-05-01 | 2025-05-03 |  |  | 1MC06-CEK-IM-DAT-CS05-600178 |  | OSGB issues, sent back on 02-May-2025 | [7 empty] | 10 - Complete | supriyan | neeraj.bhandari@arcadis.com>
| 204.01 | HS2-00002XQ2R | SWBMS Security Fence Line | 1MC06-ASC-CV-FRM-CS05-000105-ACBOS | P04 | 2025-05-02 |  | 2025-05-02 |  | 1MC06-CEK-IM-DAT-CS05-600179 | [9 empty] | 10 - Complete | supriyan | neeraj.bhandari@arcadis.com>
| IDR 202.5-3 | HS2-00002BJRH | ACBOS - Grove Farm Access Track Accommodation Underbridge Realignment 3D Model | 1MC06-ASC-HW-FRM-CS03_CL06-000006-ACBOS | P03 | 2025-05-07 | 2025-05-27 | 2025-05-30 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600009 |  | OSGB issues, and other issees, sent back on 07-May-2025 | [7 empty] | 10 - Complete | supriyan | prashanth.kl@arcadis.com>
| IDR 202.5-3 | HS2-000020NA5 | ACBOS - Small Dean Lane Realignment 3D Model | 1MC06-ASC-HW-FRM-CS03_CL06-000004-ACBOS | P03 | 2025-05-07 | 2025-05-27 | 2025-05-29 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600067 |  | OSGB issues, and other issees, sent back on 07-May-2025 | [7 empty] | 10 - Complete | supriyan | prashanth.kl@arcadis.com>
| IDR 231.01 | HS2-00002RE02 | 107-AC5 | 1MC07-ASC-CV-FRM-CS07_CL26-000073-ACBOS | P01 | 2025-05-07 |  | 2025-05-09 |  | 1MC07-CEK-IM-DAT-CS07_CL26-600049 | [9 empty] | 10 - Complete | supriyan | Priya.Thangavel@arcadis.com>
| IDR 202.1-2 | HS2-00002C3W6 | A413 London Road Drainage System | 1MC06-ASC-DR-FRM-CS03_CL05-000020-ACBOS | P01 | 2025-05-08 |  | 2025-05-13 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600062 | [9 empty] | 10 - Complete | supriyan | Jan.Cordero@arcadis.com>
| 201.3-2 | HS2-000001285 | Footpath TLE 2 Accommodation Overbridge | 1MC06-CEK-BR-FRM-CS03_CL05-000037 | P13 | 2025-05-12 |  | 2025-05-22 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600081 |  | Assets class needs to be updated in smartform | [7 empty] | 10 - Complete | supriyan | ANL@cowi.com>
| IDR 214.03-1 | HS2-00002CT7V | Civil 3D Solids Model - P-RAI-0766 | 1MC06-ASC-DR-FRM-CS05-000008-ACBOS | P02 | 2025-05-13 |  | 2025-05-14 |  | 1MC06-CEK-IM-DAT-CS05-600151 | [9 empty] | 10 - Complete | supriyan | fedi.benhmida@setec.com>
| 224.6 | HS2-00002CTCM | Turweston Cutting Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000019-ACBOS | P03 | 2025-05-16 |  | 2025-05-21 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600097 | [9 empty] | 10 - Complete | supriyan | TRABELSI Slim <slim.trabelsi@setec.com>
| 224.6 | HS2-00002CTCP | Turweston Cutting Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000024-ACBOS | P03 | 2025-05-16 |  | 2025-05-20 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600064 | [9 empty] | 10 - Complete | supriyan | TRABELSI Slim <slim.trabelsi@setec.com>
| 224.6 | HS2-00002CTCG | Grovehill Embankment Boundary Perimeter Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000016-ACBOS | P03 | 2025-05-16 |  | 2025-05-20 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600066 | [9 empty] | 10 - Complete | supriyan | TRABELSI Slim <slim.trabelsi@setec.com>
| 224.6 | HS2-00002CTCJ | Grovehill Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000021-ACBOS | P03 | 2025-05-16 |  | 2025-05-21 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600074 | [9 empty] | 10 - Complete | supriyan | TRABELSI Slim <slim.trabelsi@setec.com>
| 223.8 | HS2-00002CTCA | Westbury Embankment Boundary Perimeter Line | 1MC06-ASC-CV-FRM-CS06_CL22-000020-ACBOS | P02 | 2025-05-21 |  | 2025-05-27 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600083 | [9 empty] | 10 - Complete | supriyan | TRABELSI Slim <slim.trabelsi@setec.com>
| 223.8 | HS2-00002CTCC | Westbury Embankment Security Fence Line | 1MC06-ASC-CV-FRM-CS06_CL22-000025-ACBOS | P03 | 2025-05-21 | 2025-05-23 | 2025-05-27 |  | 1MC06-CEK-IM-DAT-CS06_CL22-600084 |  | UniclassID issue. Send back on 23-05-2025 | [7 empty] | 10 - Complete | supriyan | TRABELSI Slim <slim.trabelsi@setec.com>
| 214.06 | HS2-000001370 | Muxwell Brook Culvert | 1MC06-ASC-CV-FRM-CS05-000148-ACBOS | P01 | 2025-05-22 | 2025-05-27 | 2025-05-28 |  | 1MC06-CEK-IM-DAT-CS05-600305 |  | Comments on Rebar during Review Stage, sent back on 23-May-2025 | [7 empty] | 10 - Complete | supriyan | karthiban.sr@arcadis.com>
| IDR 214.10 | HS2-00002CW17 | HWDR Ch:76.65 Footpath CAG 2 Underbridge Drainage Solids Model | 1MC06-ASC-DR-FRM-CS05-000024-ACBOS | P12 | 2025-05-22 |  | 2025-05-28 |  | 1MC06-CEK-IM-DAT-CS05-600172 | [9 empty] | 10 - Complete | supriyan | BENHMIDA Fedi <fedi.benhmida@setec.com>
| 202.1-2 | HS2-00003KFQ1 | C2.L.14A Catchment | 1MC06-ASC-DR-FRM-CS03_CL06-000043-ACBOS | P01 | 2025-05-23 |  | 2025-05-27 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600110 | [9 empty] | 10 - Complete | supriyan | RyanAdriel.Fortuno@arcadis.com>
| IDR 229.01-2 | HS2-000025B2E | Greatworth Green Tunnel North Portal Buildings Access Road | 1MC07-ASC-HW-FRM-CS07_CL25-000026-ACBOS | P01 | 2025-05-23 |  | 2025-05-28 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600058 | [9 empty] | 10 - Complete | supriyan | veenadhari.bavanam@arcadis.com>
| IDR 229.01-2 | HS2-000025B2G | Banbury Road (Thorpe Mandeville) Realignment | 1MC07-ASC-HW-FRM-CS07_CL25-000027-ACBOS | P01 | 2025-05-23 | 2025-05-30 | 2025-06-02 |  | 1MC07-CEK-IM-DAT-CS07_CL25-600048 |  | Wrong asset location, sent back on 28-May-2025 | [7 empty] | 10 - Complete | supriyan | veenadhari.bavanam@arcadis.com
| IDR 202.5-3 | HS2-00002CT3C | Small Dean Lane Drainage System | 1MC06-ASC-DR-FRM-CS03_CL06-000007-ACBOS | P02 | 2025-05-28 |  | 2025-05-30 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600038 | [9 empty] | 10 - Complete | supriyan | Cordero, Jan
| 216.01 | HS2-00002NKPA | OXD 28 Charndon Lodge Highway Access | 1MC06-ASC-HW-FRM-CS06_CL09-000048-ACBOS | P02 | 2025-05-29 |  | 2025-05-30 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600188 | [9 empty] | 10 - Complete | supriyan | mallikarjun.shabad@arcadis.com>
| 216.01 | HS2-00002CT8T | HS2-00002CT8T - Perry Hill Road Drainage System | 1MC06-ASC-DR-FRM-CS06_CL09-000028-ACBOS | P08 | 2025-05-30 |  | 2025-06-04 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600201 |  | OSGB Issues, sent back on 30-May-2025 | 2025-05-30 | [6 empty] | 10 - Complete | Partha | nischitha.m@arcadis.com>
| IDR 214.10 | HS2-00002NSXM | SWBMS Emergency Access Track West | 1MC06-ASC-HW-FRM-CS05-000071-ACBOS | P10 | 2025-06-04 |  | 2025-06-06 |  | 1MC06-CEK-IM-DAT-CS05-600176 | [9 empty] | 10 - Complete | supriyan | adan@cowi.com>
| 214.1 | HS2-00003CPYK | SWBMS Landscape Planting | 1MC06-ASC-EV-REP-CS05_CL09-000002 |  | 2025-06-06 |  | 2025-06-17 |  | 1MC06-CEK-IM-DAT-CS05-600297 | [9 empty] | 10 - Complete | supriyan | liu.yang2@arcadis.com
| IDR 214.10 | HS2-00003E24K | SWBMS Landscape Planting | 1MC06-ASC-EV-REP-CS06_CL09-000002 |  | 2025-06-06 |  | 2025-06-17 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600318 | [9 empty] | 10 - Complete | supriyan | liu.yang2@arcadis.com>
| IDR-202.1-2 | HS2-000031CVR | Hale Bridge Parapet Extension | 1MC06-ASC-BR-FRM-CS03_CL06-000006-ACBOS | P01 | 2025-06-11 |  |  |  | 1MC06-CEK-IM-DAT-CS03_CL06-600086 |  | OSGB Issues, sent back on 16-June-2025 | [7 empty] | 30 - Sent back to team | supriyan | adewole.lasisi@arcadis.com>
| 202.1-2 | HS2-00002WUKB | Small Dean Viaduct Planting-Plot 1 | 1MC06-CEK-EV-FRM-CS03_CL06-000015 |  | 2025-06-19 | 2025-06-24 | 2025-06-25 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600117 |  | PCRA is pending for MPDT, sent back on 23-June-2025 | [7 empty] | 10 - Complete | supriyan | ebrahim.jeewa@arcadis.com>
| 202.1-2 | HS2-00002WUKC | Small Dean Viaduct Planting-Plot 2 | 1MC06-CEK-EV-FRM-CS03_CL06-000016 |  | 2025-06-19 | 2025-06-24 | 2025-06-26 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600118 |  | PCRA is pending for MPDT, sent back on 23-June-2025 | [7 empty] | 10 - Complete | supriyan | ebrahim.jeewa@arcadis.com>
| 202.1-2 | HS2-00002WUKD | Small Dean Viaduct Planting-Plot 3 | 1MC06-CEK-EV-FRM-CS03_CL06-000017 |  | 2025-06-19 | 2025-06-24 | 2025-06-26 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600119 |  | PCRA is pending for MPDT, sent back on 23-June-2025 | [7 empty] | 10 - Complete | supriyan | ebrahim.jeewa@arcadis.com>
| 202.1-2 | HS2-00002WUKE | Small Dean Viaduct Planting-Plot 4 | 1MC06-CEK-EV-FRM-CS03_CL06-000018 |  | 2025-06-19 | 2025-06-24 | 2025-06-26 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600120 |  | PCRA is pending for MPDT, sent back on 23-June-2025 | [7 empty] | 10 - Complete | supriyan | ebrahim.jeewa@arcadis.com>
| 202.1-2 | HS2-00002WUKF | Small Dean Viaduct Planting-Plot 5 | 1MC06-CEK-EV-FRM-CS03_CL06-000031 |  | 2025-06-19 | 2025-06-24 | 2025-06-26 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600121 |  | PCRA is pending for MPDT, sent back on 23-June-2025 | [7 empty] | 10 - Complete | supriyan | ebrahim.jeewa@arcadis.com>
| 202.1-2 | HS2-00003D9CH | Small Dean Viaduct Landscape Terracing 3D Solid Model (East of A413) | 1MC06-ASC-GT-FRM-CS03_CL06-000028-ACBOS | P01 | 2025-06-20 | 2025-06-23 | 2025-06-24 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600102 |  | JSON placeholder is missing sent back on 23-June-2025 | [7 empty] | 10 - Complete | supriyan | Patil, Kiran <kiran.patil@arcadis.com>
| 202.1-2 | HS2-00003D9CM | Small Dean Viaduct Landscape Terracing 3D Solid Model (North) | 1MC06-ASC-GT-FRM-CS03_CL06-000029-ACBOS | P01 | 2025-06-20 | 2025-06-23 | 2025-06-24 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600104 |  | JSON placeholder is missing sent back on 23-June-2025 | [7 empty] | 10 - Complete | supriyan | Patil, Kiran <kiran.patil@arcadis.com>
| 202.1-2 | HS2-00003D9CK | Small Dean Viaduct Landscape Terracing 3D Solid Model (West of A413) | 1MC06-ASC-GT-FRM-CS03_CL06-000030-ACBOS | P02 | 2025-06-20 | 2025-06-23 | 2025-06-24 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600103 |  | JSON placeholder is missing sent back on 23-June-2025 | [7 empty] | 10 - Complete | supriyan | Patil, Kiran <kiran.patil@arcadis.com>
| IDR 203.02-2 | HS2-00002TMES | Wendover Green Tunnel North Portal Building Telecoms | 1MC06-ASC-UT-FRM-CS03_CL17-000038-ACBOS | P01 | 2025-06-23 |  | 2025-06-25 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600072 | [9 empty] | 10 - Complete | supriyan | juilee.lokhande@arcadis.com>
| IDR 202.1-2 | HS2-00002C3W6 | A413 London Road Drainage System | 1MC06-ASC-DR-FRM-CS03_CL05-000020-ACBOS | P02 | 2025-06-25 |  | 2025-06-25 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600062 | [9 empty] | 10 - Complete | supriyan | Jan.Cordero@arcadis.com>
| 202.1-2 | HS2-00003FV0M | A413 London Road Realignment ,Bosswell Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | 1MC06-ASC-CV-FRM-CS03_CL06-000059-ACBOS | P01 | 2025-06-25 |  | 2025-06-27 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600113 | [9 empty] | 10 - Complete | supriyan | Meka, Mouneesh <mouneesh.meka@arcadis.com>
| 202.1-2 | HS2-00003FV0L | A413 London Road Realignment ,Bosswell Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | 1MC06-ASC-CV-FRM-CS03_CL06-000056-ACBOS | P01 | 2025-06-25 |  | 2025-06-27 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600112 | [9 empty] | 10 - Complete | supriyan | Meka, Mouneesh <mouneesh.meka@arcadis.com>
| 213.01-1 | HS2-00002BJTK | Doddershall House and South Farms Accommodation Access Road | 1MC06-ASC-HW-FRM-CS05-000022-ACBOS | P08 | 2025-06-27 |  | 2025-07-01 |  | 1MC06-CEK-IM-DAT-CS05-600093 | [9 empty] | 10 - Complete | supriyan | mallikarjun.shabad@arcadis.com>
| 213.01-1 | HS2-000020NF2 | Station Road Realignment (Including Buckingham Road and Fidlers Field Road) | 1MC06-ASC-HW-FRM-CS04_CL20-000013-ACBOS | P08 | 2025-06-27 | 2025-07-04 | 2025-07-08 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600108 |  | OSGB issues, sent back on 30-June-2025 |  | Sent back at review stage on 1st July | [5 empty] | 10 - Complete | supriyan | mallikarjun.shabad@arcadis.com>
| 213.01-1 | HS2-00002BJTJ | Maintenance Access Road to Pond (Off North End of Station Road) 01 | 1MC06-ASC-HW-FRM-CS04_CL20-000014-ACBOS | P06 | 2025-06-27 |  | 2025-07-01 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600109 | [9 empty] | 10 - Complete | supriyan | mallikarjun.shabad@arcadis.com>
| 213.01-1 | HS2-00002CT6X | Maintenance Access Road to Pond (Off North End of Station Road) 02 | 1MC06-ASC-HW-FRM-CS04_CL20-000015-ACBOS | P04 | 2025-06-27 |  | 2025-07-02 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600096 | [9 empty] | 10 - Complete | supriyan | mallikarjun.shabad@arcadis.com>
| 213.01-1 | HS2-00002CT6W | Maintenance Access Road to Pond (Off Southern End of Station Road) | 1MC06-ASC-HW-FRM-CS04_CL20-000016-ACBOS | P04 | 2025-06-27 |  | 2025-07-01 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600095 | [9 empty] | 10 - Complete | supriyan | mallikarjun.shabad@arcadis.com>
| 213.01-1 | HS2-000020NFY | Maintenance Access Road to Pond (Off Fidlers Field Road) | 1MC06-ASC-HW-FRM-CS05-000023-ACBOS | P05 | 2025-06-27 | 2025-07-01 |  |  | 1MC06-CEK-IM-DAT-CS05-600088 | [9 empty] | 10 - Complete | supriyan | mallikarjun.shabad@arcadis.com>
| IDR 202.1-2 | HS2-00003LA5B | Small Dean Viaduct (Pier P4) Access Stairs | 1MC06-ASC-CV-FRM-CS03_CL06-000054-ACBOS | P01 | 2025-06-27 | 2025-07-03 | 2025-07-04 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600111 |  | Unwanted 0's sent back on 03-July-2025 | [7 empty] | 10 - Complete | supriyan | L, Surendar <surendar.loganathan@arcadis.com>
| 216.01 | HS2-00002BJUG | Perry Hill Road Realignment | 1MC06-ASC-HW-FRM-CS06_CL09-000025-ACBOS | P05 | 2025-06-27 |  | 2025-07-02 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600113 | [9 empty] | 10 - Complete | supriyan | mallikarjun.shabad@arcadis.com>
| 216.01 | HS2-00002BJUF | IMD Access off Perry Hill | 1MC06-ASC-HW-FRM-CS06_CL09-000026-ACBOS | P05 | 2025-06-27 |  | 2025-07-02 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600116 | [9 empty] | 10 - Complete | supriyan | mallikarjun.shabad@arcadis.com>
| IDR 202.1-2 | HS2-00003M54H | Small Dean Viaduct Terracing (North) | 1MC06-ASC-CV-FRM-CS03_CL06-900060-ACBOS | P01 | 2025-06-30 |  | 2025-07-04 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600123 | [9 empty] | 10 - Complete | supriyan | L, Surendar <surendar.loganathan@arcadis.com>
| IDR 202.1-2 | HS2-00003M54J | Small Dean Viaduct Terracing (West of A413) | 1MC06-ASC-CV-FRM-CS03_CL06-000061-ACBOS | P01 | 2025-06-30 |  | 2025-07-04 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600124 | [9 empty] | 10 - Complete | supriyan | L, Surendar <surendar.loganathan@arcadis.com>
| IDR 202.1-2 | HS2-00003M54K | Small Dean Viaduct Terracing (East of A413) | 1MC06-ASC-CV-FRM-CS03_CL06-900059-ACBOS | P01 | 2025-06-30 |  | 2025-07-04 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600125 | [9 empty] | 10 - Complete | supriyan | L, Surendar <surendar.loganathan@arcadis.com>
| 213.01-1 | HS2-00002N7Y6 | Station Road Watercourse Culvert No. 3 | 1MC06-ASC-DR-FRM-CS04_CL20-000048-ACBOS | P01 | 2025-07-01 |  | 2025-07-08 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600074 | [9 empty] | 10 - Complete | supriyan | nagarathinam.pachaiappann@arcadis.com>
| 213.01-1 | HS2-00002N7Y8 | Station Road Watercourse Culvert No. 5 | 1MC06-ASC-DR-FRM-CS04_CL20-000087-ACBOS | P01 | 2025-07-01 |  | 2025-07-08 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600068 | [9 empty] | 10 - Complete | supriyan | nagarathinam.pachaiappann@arcadis.com>
| 213.01-1 | HS2-0000316C6 | Station Road Watercourse Ancillary Culvert No. 7 | 1MC06-ASC-DR-FRM-CS05-000113-ACBOS | P01 | 2025-07-01 |  | 2025-07-08 |  | 1MC06-CEK-IM-DAT-CS05-600169 | [9 empty] | 10 - Complete | supriyan | nagarathinam.pachaiappann@arcadis.com>
| 213.01-1 | HS2-00002N7XV | Station Road Highway Drainage Culvert No. 12 | 1MC06-ASC-DR-FRM-CS04_CL20-000085-ACBOS | P01 | 2025-07-01 |  | 2025-07-08 |  | 1MC06-CEK-IM-DAT-CS04_CL20-600073 | [9 empty] | 10 - Complete | supriyan | nagarathinam.pachaiappann@arcadis.com>
| 213.01-1 | HS2-000033XXM | Station Road Highway Drainage Culvert No. 16 | 1MC06-ASC-DR-FRM-CS05-000115-ACBOS | P01 | 2025-07-01 |  | 2025-07-16 |  | 1MC06-CEK-IM-DAT-CS05-600170 | [9 empty] | 10 - Complete | supriyan | nagarathinam.pachaiappann@arcadis.com>
| IDR 202.1-2 | HS2-00003D9CJ | Small Dean Viaduct Landscape Paving (East of A413) | 1MC06-ASC-CV-FRM-CS03_CL06-900056-ACBOS | P01 | 2025-07-01 |  | 2025-07-04 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600114 | [9 empty] | 10 - Complete | supriyan | L, Surendar <surendar.loganathan@arcadis.com>
| IDR 202.1-2 | HS2-00003D9CL | Small Dean Viaduct Landscape Paving (West of A413) | 1MC06-ASC-CV-FRM-CS03_CL06-000058-ACBOS | P01 | 2025-07-01 |  | 2025-07-04 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600116 | [9 empty] | 10 - Complete | supriyan | L, Surendar <surendar.loganathan@arcadis.com>
| IDR 202.1-2 | HS2-00003D9CN | Small Dean Viaduct Landscape Paving (North) | 1MC06-ASC-CV-FRM-CS03_CL06-000057-ACBOS | P01 | 2025-07-01 |  | 2025-07-04 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600115 | [9 empty] | 10 - Complete | supriyan | L, Surendar <surendar.loganathan@arcadis.com>
| IDR 202.1-2 | HS2-00002BJRC | A413 London Road Realignment | 1MC06-ASC-HW-FRM-CS03_CL06-000002-ACBOS | P01 | 2025-07-01 | 2025-07-03 | 2025-07-04 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600037 |  | Few issues, sent back on 1st July 2025 | [7 empty] | 10 - Complete | supriyan | Iftikhar Rahman <ifra@cowi.com>
| IDR 202.1-2 | HS2-00002CT3E | Maintenance Access Road to Pond (P-RAI-0522) | 1MC06-ASC-HW-FRM-CS03_CL05-000047-ACBOS | P01 | 2025-07-01 |  | 2025-07-02 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600035 | [9 empty] | 10 - Complete | supriyan | Iftikhar Rahman <ifra@cowi.com>
| IDR 202.5-3 | HS2-00003KLDB | Grove Farm Attenuation Pipe | 1MC06-ASC-CV-FRM-CS03_CL06-000064 | P01 | 2025-07-01 | 2025-07-16 | 2025-07-16 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600127 |  | Data type issues in DmtrExtr sent back on 9th July-2025 | [7 empty] | 10 - Complete | supriyan | jadd@cowi.com>
| IDR 202.5-3 | HS2-000031G3S | Grove Farm Culvert Inlet System-South | 1MC06-ASC-CV-FRM-CS03_CL06-900037-ACBOS | P01 | 2025-07-01 |  | 2025-07-23 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600101 |  | Many issues sent back on 09-July-2025 | [7 empty] | 10 - Complete | supriyan | jadd@cowi.com>
| IDR 202.5-3 | HS2-000031G3R | Grove Farm Culvert Inlet System-North | 1MC06-ASC-CV-FRM-CS03_CL06-900036-ACBOS | P01 | 2025-07-01 | 2025-07-18 | 2025-07-21 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600100 |  | Many issues sent back on 09-July-2025 | [7 empty] | 10 - Complete | supriyan | jadd@cowi.com>
| 216.01 | HS2-000001317 | Perry Hill Overbridge | 1MC06-CEK-BR-FRM-CS06_CL09-000010 | P01 | 2025-07-01 |  | 2025-07-04 |  | 1MC06-CEK-IM-DAT-CS06_CL09-600151 |  | Com_type issues, sent back on 03-July-2025 | [7 empty] | 10 - Complete | supriyan | William.Whyte@arcadis.com>
| UFDR 222.G | HS2-000020CGW | CSO-03-2202P | 1MC06-ASC-UT-FRM-CS06_CL21-000048-ACBOS | P02 | 2025-07-02 | 2025-07-23 | 2025-07-29 |  | 1MC06-CEK-IM-DAT-CS06_CL21-600033 |  | Wrong asset name, sent back on 09-July-2025 | [7 empty] | 10 - Complete | supriyan | maya.bowles@arcadis.com>
| 214.06 | HS2-00003LH5N | Muxwell Brook Crossing Slab | 1MC06-ASC-CV-FRM-CS05-000147-ACBOS | P02 | 2025-07-04 |  | 2025-07-04 |  | 1MC06-CEK-IM-DAT-CS05-600304 | [9 empty] | 10 - Complete | supriyan | Michelle Miller <mcmi@cowi.com>
| 202.1-2 | HS2-00003FV0L | A413 London Road Realignment ,Bosswell Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | 1MC06-ASC-CV-FRM-CS03_CL06-000056-ACBOS | P01 | 2025-07-07 |  | 2025-07-09 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600112 | [9 empty] | 10 - Complete | supriyan | Meka, Mouneesh <mouneesh.meka@arcadis.com>
| 201.3-3 | HS2-00002BJQU | Dutch Lands Farm to Rushmoor Wood (TLE/2) Footpath Realignment | 1MC06-ASC-HW-FRM-CS03_CL05-000004-ACBOS | P07 | 2025-07-11 |  | 2025-07-16 |  | 1MC06-CEK-IM-DAT-CS03_CL05-600107 | [9 empty] | 10 - Complete | supriyan | Chrysi.Burgham.Malin@arcadis.com>
| IDR 204.1-2 | HS2-00002VBQD | Nash Lee Access Road Ditch Slab | 1MC06-ASC-CV-FRM-CS03_CL17-000031-ACBOS | P01 | 2025-07-18 |  | 2025-07-22 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600144 | [9 empty] | 10 - Complete | supriyan | K S, Abhisheka <abhisheka.ks@arcadis.com>
| IDR 204.1-2 | HS2-00003CCK7 | Footpath ELL 25 1 Ditch Slab 2 | 1MC06-ASC-CV-FRM-CS03_CL17-000052-ACBOS | P01 | 2025-07-18 |  | 2025-07-22 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600146 | [9 empty] | 10 - Complete | supriyan | K S, Abhisheka <abhisheka.ks@arcadis.com>
| IDR 204.1-2 | HS2-00003CCK8 | Footpath ELL 25 1 Ditch Slab 3 | 1MC06-ASC-CV-FRM-CS03_CL17-000054-ACBOS | P01 | 2025-07-18 |  | 2025-07-22 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600145 | [9 empty] | 10 - Complete | supriyan | K S, Abhisheka <abhisheka.ks@arcadis.com>
| 201.3-3 | HS2-00002BJQU | Dutch Lands Farm to Rushmoor Wood (TLE/2) Footpath Realignment | 1MC06-ASC-HW-FRM-CS03_CL05-000004-ACBOS | P08 | 2025-07-25 |  |  |  | 1MC06-CEK-IM-DAT-CS03_CL05-600107 | [9 empty] | 10 - Complete | supriyan | CEPY@cowi.com>
| IDR 203.02-4 | HS2-00002TMEQ | Wendover Green Tunnel South Portal Building Telecoms | 1MC06-ASC-UT-FRM-CS03_CL06-000118-ACBOS | P01 | 2025-07-31 | 2025-08-01 | 2025-08-12 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600045 |  | GdMt is misisng, sent back on 01-Aug-2025 | [7 empty] | 10 - Complete | supriyan | juilee.lokhande@arcadis.com>
| IDR-203.02-4 | HS2-00002TMEP | Wendover Green Tunnel South Portal Building Fire fighting water | 1MC06-ASC-UT-FRM-CS03_CL06-000116-ACBOS | P01 | 2025-07-31 |  | 2025-08-05 |  | 1MC06-CEK-IM-DAT-CS03_CL06-600046 | [9 empty] | 10 - Complete | supriyan | <mohit.kamboj@arcadis.com>
| IDR 204.1-2 | HS2-00002EK6U | Stoke Grove Rail Systems Compound (ATS) UTX | 1MC06-ASC-CV-FRM-CS03_CL17-000007-ACBOS | P01 | 2025-08-05 |  | 2025-08-05 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600017 | [9 empty] | 10 - Complete | supriyan | emma.quinn@arcadis.com>
| IDR 203.2-2 | HS2-00003MVER | Wendover North Cutting Access Stairs | 1MC06-ASC-CV-FRM-CS03_CL17-000067-ACBOS | P01 | 2025-08-06 |  | 2025-08-13 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600139 | [9 empty] | 10 - Complete | supriyan | K S, Abhisheka <abhisheka.ks@arcadis.com>
| IDR 203.02-2 | HS2-00002TMES | Wendover Green Tunnel North Portal Building Telecoms | 1MC06-ASC-UT-FRM-CS03_CL17-000038-ACBOS | P02 | 2025-08-06 |  | 2025-08-13 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600072 | [9 empty] | 10 - Complete | supriyan | juilee.lokhande@arcadis.com>
| IDR 204.1-2 | HS2-00002BJRW | Footpath ELL-25-1 Diversion | 1MC06-ASC-HW-FRM-CS03_CL17-000007-ACBOS | P01 | 2025-08-13 |  | 2025-08-14 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600055 | [9 empty] | 10 - Complete | supriyan | craig.cooper@arcadis.com>
| IDR 204.1-2 | HS2-000020NAR | Maintenance Access Road to Pond (Off Nash Lee Road) | 1MC06-ASC-HW-FRM-CS03_CL17-000016-ACBOS | P01 | 2025-08-13 |  | 2025-08-14 |  | 1MC06-CEK-IM-DAT-CS03_CL17-600056 | [9 empty] | 10 - Complete | supriyan | craig.cooper@arcadis.com>
| IDR 204.1-2 | HS2-000039J1M | Maintenance Access Road to Ponds REG-0562-1 to REG-0562-3 | 1MC06-ASC-HW-FRM-CS03_CL17-000031-ACBOS | P01 | 2025-08-13 |  | 2025-08-14 |  | 1MC06-CEK-IM-DAT-CS03_CL17-000004 | [9 empty] | 10 - Complete | supriyan | craig.cooper@arcadis.com>
| UFDR 239.E | HS2-000020CKR | CNO-125-007HV | 1MC07-ASC-UT-FRM-CS07_CL24-000023-ACBOS | P02 | 2025-08-26 |  |  |  | 1MC07-CEK-IM-DAT-CS07_CL24-600082 | [9 empty] | 08 - Checker to check | supriyan | maya.bowles@arcadis.com>
| IDR 204.0-2 | HS2-00002CT4B | B4009 Nash Lee Road Realignment | 1MC06-ASC-HW-FRM-CS03_CL17-000005-ACBOS | p05 | 2025-08-26 |  |  |  | 1MC06-CEK-IM-DAT-CS03_CL17-600054 |  | Few, queries sent back on 27-Aug-2025 | [7 empty] | 30 - Sent back to team | supriyan | CEPY@cowi.com>
| IDR 204.0-2 | HS2-000020NAP | Nash Lee Lane Realignment | 1MC06-ASC-HW-FRM-CS03_CL17-000013-ACBOS | p05 | 2025-08-26 |  |  |  | 1MC06-CEK-IM-DAT-CS03_CL17-600057 |  | OSGB Issues, and other issees, sent back on 27-Aug-2025 | [7 empty] | 30 - Sent back to team | supriyan | CEPY@cowi.com>
| 217.03 | HS2-00002N7XY | Addison Road Land Drainage-Ancillary Culvert No. 1 | 1MC06-ASC-DR-FRM-CS06_CL09-000078-ACBOS | P02 | 2025-09-25 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600163 | [9 empty] | 08 - Checker to check | Rakesh | <barbara.marquesgomes@setec.com>
| 217.03 | HS2-000020NKE | Addison Road Realignment | 1MC06-ASC-HW-FRM-CS06_CL09-000020-ACBOS | P02 | 2025-09-25 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600098 | [9 empty] | 08 - Checker to check | Rakesh | <barbara.marquesgomes@setec.com>
| 217.03 | HS2-00002CT8Z | WPD Electrical Substation Access Road | 1MC06-ASC-HW-FRM-CS06_CL09-000021-ACBOS | P02 | 2025-09-25 |  |  |  | 1MC06-CEK-IM-DAT-CS06_CL09-600204 | [9 empty] | 08 - Checker to check | Rakesh | <barbara.marquesgomes@setec.com>
| 214.1 | HS2-00003CPYQ | SWBMS Cable Routing | 1MC06-ASC-CV-FRM-CS05-000086-ACBOS | P03 | 2025-09-26 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600185 |  | Incorrect Com_Type for PRL class.Send back on 07/10/25. | [7 empty] | 30 - Sent back to team | Rakesh | alpk@cowi.com>
| 214.1 | HS2-00003CPYQ | SWBMS Cable Routing | 1MC06-CEK-EL-FRM-CS05-600003 | P01 | 2025-09-26 | [13 empty] | 00 - To Start | Rakesh | alpk@cowi.com>
| 214.1 | HS2-00003CPYP | SWBMS South UTX | 1MC06-ASC-CV-FRM-CS05-000137-ACBOS | P04 | 2025-09-26 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600184 | [9 empty] | 10 - Complete | Rakesh | alpk@cowi.com>
| 214.1 | HS2-00003CPYP | SWBMS South UTX | 1MC06-CEK-EL-FRM-CS05-600002 | p01 | 2025-09-26 | [13 empty] | 10 - Complete | Rakesh | alpk@cowi.com>
| 214.1 | HS2-00003CPYS | SWBMS Ancillary Civils | 1MC06-ASC-BR-FRM-CS05_CL09-000001 | P06 | 2025-09-26 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600182 |  | Snakegrid to OSGB conversion inaccuracies . Send back to team on 07/10/25 | [7 empty] | 30 - Sent back to team | Rakesh | alpk@cowi.com>
| 214.1 | HS2-00002EK75 | SWBMS South UTX | 1MC06-ASC-CV-FRM-CS05-000136-ACBOS | P04 | 2025-10-01 |  |  |  | 1MC06-CEK-IM-DAT-CS05-600183 | [9 empty] | 09 - Reviewer to check | Rakesh | Alexander Patrick <alpk@cowi.com>
| 214.1 | HS2-00002EK75 | SWBMS South UTX | 1MC06-CEK-EL-FRM-CS05-600001 | P01 | 2025-10-01 | [13 empty] | 09 - Reviewer to check | Rakesh | Alexander Patrick <alpk@cowi.com>
| 203.2-2 | HS2-00002EK6T | Wendover Green Tunnel North Portal UTX | 1MC06-ASC-CV-FRM-CS03_CL17-900008-ACBOS | P01 | 2025-10-07 |  |  |  | 1MC06-CEK-IM-DAT-CS03_CL17-000003 | [9 empty] | 01 - Ongoing | Rakesh | emma.quinn@arcadis.com
Note on B1004: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Corrected. Incorrectly communicated on request (was 204.2-2)
Note on B1005: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Corrected. Incorrectly communicated on request (was 204.2-2)

## List_Values
Statuses |  | Holidays
00 - To Start |  | 2023-12-25
01 - Ongoing |  | 2023-12-26
03 - MDQC | Pre-IDR | 2023-12-27 | UFDR = Utilities Final Design Review
04 - SQL Upload / JSON creation | Post-IDR | 2023-12-28
05 - JSON produced and in checker |  | 2023-12-29
07 - Producer to check |  | 2024-01-01
08 - Checker to check |  | 2024-03-29
09 - Reviewer to check |  | 2024-04-01
10 - Complete |  | 2024-05-06
30 - Sent back to team |  | 2024-05-27
50 - HOLD |  | 2024-08-26
99 - Cancelled |  | 2024-12-25
2024-12-26

## MS_DAC_Team
IDR / UFDR | L2 Asset and UAID_2 | JSON File in PW | Comments
224.1 | HS2-000001062 - Turweston Cutting | 1MC06-CEK-IM-DAT-CS06_CL22-600075 | Review completed by Central Team
224.1 | HS2-00002BVJJ - Turweston Cutting Landscape Earthworks | 1MC06-CEK-IM-DAT-CS06_CL22-600090 | Review completed by Central Team
215.01 | HS2-00002BJUC - Calvert Cutting Retaining Wall | 1MC06-CEK-IM-DAT-CS06_CL09-600091 | Review completed by Central Team
215.01 | HS2-000001425 - Shepherds Furze Culvert | 1MC06-CEK-IM-DAT-CS06_CL09-600153 | Review completed by Central Team
214.01-1 | HS2-000001308 - Bridleway GUN/28 Accommodation Green Overbridge | 1MC06-CEK-IM-DAT-CS05-600116 | Review completed by Central Team

## WIP-ReportBack
WorkPackage | UAID_2 | Package | Cleansed_UAID_2 | Request Date | Status | CompletedDate | Work Packages | Assets | L3 (Last Work Package only) | Package | L2 | Date received | Status | CompletedDate
233.01-2 | HS2-00002NJ06 | IDR 233.01-2 | HS2-00002NJ06 | 2024-04-10 | 10 - Complete | 2024-05-02 | UFDR 238.E - A423 Banbury Road Overbridge Main Works (NGED) | HS2-00003L5EE - Ladbroke Grove Farm Water Supply | UFDR 238.E - A423 Banbury Road Overbridge Main Works (NGED) | UFDR 238.E | HS2-00003L5EE | 2024-09-09 | 10 - Complete | 2024-09-11
236.01 | HS2-00002XCBC | IDR 236.01 | HS2-00002XCBC | 2023-10-31 | 10 - Complete | 2023-11-10 |  | HS2-000020CKR - CNO-125-007HV | UFDR 239.E - B4451 Kineton Road Overbridge NGED Diversions | UFDR 239.E | HS2-000020CKR | 2024-07-11 | 10 - Complete | 2024-07-16
216.01 | HS2-00002CT9B | IDR 216.01 | HS2-00002CT9B | 2023-10-31 | 10 - Complete | 2024-12-13 |  | HS2-00002CTKR - CNO-125-007LV | UFDR 239.E - B4451 Kineton Road Overbridge NGED Diversions | UFDR 239.E | HS2-00002CTKR | 2024-07-11 | 10 - Complete | 2024-07-16
216.01 | HS2-00002CT9B | IDR 216.01 | HS2-00002CT9B | 2023-10-31 | 10 - Complete | 2024-12-13 |  | HS2-000020CKX - CNO-125-012 | UFDR 239.D - Southam Cutting Utilities (NGED) | UFDR 239.D | HS2-000020CKX | #N/A | #N/A | #N/A
216.01 | HS2-00002CT9B | IDR 216.01 | HS2-00002CT9B | 2023-10-31 | 10 - Complete | 2024-12-13 |  | HS2-00002H9MN - CNO-126-020 | UFDR 239.B - Southam Cutting Utilities | UFDR 239.B | HS2-00002H9MN | #N/A | #N/A | #N/A
216.01 | HS2-00002CT9B | IDR 216.01 | HS2-00002CT9B | 2023-10-31 | 10 - Complete | 2024-12-13 |  | HS2-000020CKS - CNO-125-002 | UFDR 239.A - B4451 Kineton Road Overbridge Utilities | UFDR 239.A | HS2-000020CKS | 2024-06-12 | 10 - Complete | 2024-06-18
204.3-1 | HS2-00002BJS0 | IDR 204.3-1 | HS2-00002BJS0 | 2024-02-28 | 10 - Complete | 2024-03-05 |  | HS2-000020CKZ - CNO-125-001 | UFDR 239.A - B4451 Kineton Road Overbridge Utilities | UFDR 239.A | HS2-000020CKZ | 2024-06-12 | 10 - Complete | 2024-06-18
236.01 | HS2-00003B585 | IDR 236.01 | HS2-00003B585 | 2023-11-01 | 10 - Complete | 2023-11-10 |  | HS2-00003B2H4 - C23-125-0003 | UFDR 239.A - B4451 Kineton Road Overbridge Utilities | UFDR 239.A | HS2-00003B2H4 | 2024-06-12 | 10 - Complete | 2024-06-18
216.01-2 | HS2-00002CT8U | IDR 216.01-2 | HS2-00002CT8U | 2025-03-26 | 10 - Complete | 2025-03-27 |  | HS2-000020CKP - CNO-124-008HV | UFDR 238.H - Banbury Rd Overbridge Main Works (NGED) | UFDR 238.H | HS2-000020CKP | 2024-08-06 | 10 - Complete | 2024-08-09
230.01 | HS2-00002PRWV | IDR 230.01 | HS2-00002PRWV | 2023-11-02 | 10 - Complete | 2023-11-07 |  | HS2-000020CKJ - CNO-123-001 | UFDR 238.G - A423 Banbury Road Overbridge Multi-Utility Permanent Diversions | UFDR 238.G | HS2-000020CKJ | 2024-06-26 | 10 - Complete | 2024-07-04
223.4 | HS2-00002BJV0 | IDR 223.4 | HS2-00002BJV0 | 2023-11-24 | 10 - Complete | 2023-11-27 |  | HS2-000020CKL - CNO-124-003 | UFDR 238.G - A423 Banbury Road Overbridge Multi-Utility Permanent Diversions | UFDR 238.G | HS2-000020CKL | 2024-06-26 | 10 - Complete | 2024-07-03
223.4 | HS2-00002BJV1 | IDR 223.4 | HS2-00002BJV1 | 2023-11-24 | 10 - Complete | 2023-11-27 |  | HS2-000020CKM - CNO-124-005 | UFDR 238.G - A423 Banbury Road Overbridge Multi-Utility Permanent Diversions | UFDR 238.G | HS2-000020CKM | 2024-06-26 | 10 - Complete | 2024-07-03
223.4 | HS2-00002BJV2 | IDR 223.4 | HS2-00002BJV2 | 2023-11-24 | 10 - Complete | 2023-11-27 |  | HS2-000020CKG - CNO-124-001 | UFDR 238.E - A423 Banbury Road Overbridge Main Works (NGED) | UFDR 238.E | HS2-000020CKG | 2024-09-06 | 10 - Complete | 2024-09-11
223.4 | HS2-00002BJV3 | IDR 223.4 | HS2-00002BJV3 | 2023-11-02 | 10 - Complete | 2023-11-09 |  | HS2-00002TMEV - CNO-123-001T | UFDR 238.D - A423 Banbury Road Advanced Utilities | UFDR 238.D | HS2-00002TMEV | #N/A | #N/A | #N/A
223.4 | HS2-00002J4YM | IDR 223.4 | HS2-00002J4YM | 2023-11-02 | 10 - Complete | 2023-11-29 |  | HS2-00002TMEW - CNO-124-003T | UFDR 238.D - A423 Banbury Road Advanced Utilities | UFDR 238.D | HS2-00002TMEW | #N/A | #N/A | #N/A
235.01-1 | HS2-000001456 | IDR 235.01-1 | HS2-000001456 | 2025-03-07 | 10 - Complete | 2025-03-19 |  | HS2-000020CKE - CNO-122-002P | UFDR 238.C - Windmill Lane Temporary Utilities - [WSP] | UFDR 238.C | HS2-000020CKE | #N/A | #N/A | #N/A
237.02 | HS2-00002EL0S | IDR 237.02 | HS2-00002EL0S | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-000020CKN - CNO-124-007 | UFDR 238.B - A423 Banbury Road Overbridge Main Works | UFDR 238.B | HS2-000020CKN | #N/A | #N/A | #N/A
237.02 | HS2-00002CTJT | IDR 237.02 | HS2-00002CTJT | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-000020CKA - CNO-122-003 | UFDR 238.A - Windmill Lane Utilities [WSP] | UFDR 238.A | HS2-000020CKA | #N/A | #N/A | #N/A
218.02-1 | HS2-00002KRAM | IDR 218.02-1 | HS2-00002KRAM | 2023-11-21 | 10 - Complete | 2023-11-21 |  | HS2-00002CTKH - CNO-122-002T | UFDR 238.A - Windmill Lane Utilities [WSP] | UFDR 238.A | HS2-00002CTKH | #N/A | #N/A | #N/A
220.5 | HS2-00002BJUL | IDR 220.5 | HS2-00002BJUL | 2024-06-07 | 10 - Complete | 2024-06-14 |  | HS2-000020CK7 - CNO-121-003 | UFDR 237.C - Ladbroke Grove Farm Accommodation Overbridge Main Works (NGED) | UFDR 237.C | HS2-000020CK7 | 2024-03-28 | 10 - Complete | 2024-04-02
220.5 | HS2-00002BJUM | IDR 220.5 | HS2-00002BJUM | 2024-06-07 | 10 - Complete | 2024-06-14 |  | HS2-000020CK5 - CNO-121-001 | UFDR 237.B - Ladbroke Grove Farm Accommodation Overbridge Main Works | UFDR 237.B | HS2-000020CK5 | #N/A | #N/A | #N/A
220.5 | HS2-00002J4YG | IDR 220.5 | HS2-00002J4YG | 2024-06-07 | 10 - Complete | 2024-06-14 |  | HS2-000020CK8 - CNO-121-004 | UFDR 237.B - Ladbroke Grove Farm Accommodation Overbridge Main Works | UFDR 237.B | HS2-000020CK8 | #N/A | #N/A | #N/A
209.2-3 | HS2-00002CT64 | IDR 209.2-3 | HS2-00002CT64 | 2023-11-09 | 10 - Complete | 2023-11-17 |  | HS2-000020CK2 - CNO-120-003 | UFDR 237.A - Lower Radbourne Utilities (NGED) | UFDR 237.A | HS2-000020CK2 | #N/A | #N/A | #N/A
202.4-4 | HS2-00002U7JY | IDR 202.4-4 | HS2-00002U7JY | 2023-11-09 | 10 - Complete | 2023-11-14 |  | HS2-000020CJZ - CNO-119-001 | UFDR 236.A - Wills Pastures Road Utilities | UFDR 236.A | HS2-000020CJZ | 2024-06-12 | 10 - Complete | 2024-06-25
223.4 | HS2-00002VNJ2 | IDR 223.4 | HS2-00002VNJ2 | 2023-11-09 | 10 - Complete | 2023-11-14 |  | HS2-00002BVPZ - C23-115-0001 | UFDR 235.D - Banbury Road Overbridge (Boddington) | UFDR 235.D | HS2-00002BVPZ | #N/A | #N/A | #N/A
223.4 | HS2-00002BVJ7 | IDR 223.4 | HS2-00002BVJ7 | 2023-11-10 | 10 - Complete | 2023-11-29 |  | HS2-000020CJU - CSO-04-1326 | UFDR 235.C - Boddington Road Utilities (NGED) | UFDR 235.C | HS2-000020CJU | 2024-04-05 | 10 - Complete | 2024-04-08
214.04 | HS2-000001307 | IDR 214.04 | HS2-000001307 | 2023-11-10 | 99 - Cancelled | 0 |  | HS2-000020CJV - CSO-04-1327 | UFDR 235.C - Boddington Road Utilities (NGED) | UFDR 235.C | HS2-000020CJV | 2024-04-05 | 10 - Complete | 2024-04-08
236.03 | HS2-000020P08 | IDR 236.03 | HS2-000020P08 | 2023-11-13 | 10 - Complete | 2023-11-22 |  | HS2-000020CJY - CNO-117-001 | UFDR 235.B - Stoneton Utilities (NGED) | UFDR 235.B | HS2-000020CJY | #N/A | #N/A | #N/A
236.03 | HS2-000025B3J | IDR 236.03 | HS2-000025B3J | 2023-11-13 | 10 - Complete | 2023-11-16 |  | HS2-000020CJW - CSO-04-3120 | UFDR 235.A - Boddington Road Utilities | UFDR 235.A | HS2-000020CJW | #N/A | #N/A | #N/A
235.01-2 | HS2-00002CX3F | IDR 235.01-2 | HS2-00002CX3F | 2024-02-05 | 10 - Complete | 2024-02-13 |  | HS2-000020CJX - CSO-04-6108 | UFDR 235.A - Boddington Road Utilities | UFDR 235.A | HS2-000020CJX | #N/A | #N/A | #N/A
218.02-1 | HS2-00002NSXP | IDR 218.02-1 | HS2-00002NSXP | 2024-04-17 | 99 - Cancelled | 0 |  | HS2-00002UMHK - C23-115-0002 | UFDR 235.A - Boddington Road Utilities | UFDR 235.A | HS2-00002UMHK | #N/A | #N/A | #N/A
218.02-1 | HS2-00002NSXQ | IDR 218.02-1 | HS2-00002NSXQ | 2024-08-19 | 10 - Complete | 2024-08-29 |  | HS2-000020CJN - CSO-04-1325P | UFDR 234.E - Appletree Lane Utilities (NGED) | UFDR 234.E | HS2-000020CJN | #N/A | #N/A | #N/A
202.5-4 | HS2-00002Y8VP | IDR 202.5-4 | HS2-00002Y8VP | 2023-11-14 | 10 - Complete | 2023-11-20 |  | HS2-00002CTHG - CSO-04-1325T | UFDR 234.E - Appletree Lane Utilities (NGED) | UFDR 234.E | HS2-00002CTHG | #N/A | #N/A | #N/A
220.5 | HS2-00002Y4JH | IDR 220.5 | HS2-00002Y4JH | 2024-05-01 | 10 - Complete | 2024-05-10 |  | HS2-00002VZUE - C23-113-0001P | UFDR 234.D - Claydon Road Overbridge Main Works | UFDR 234.D | HS2-00002VZUE | #N/A | #N/A | #N/A
211.1 | HS2-00002BVG2 | IDR 211.1 | HS2-00002BVG2 | 2023-11-14 | 10 - Complete | 2023-11-20 |  | HS2-000020CJR - CSO-04-3118P | UFDR 234.D - Claydon Road Overbridge Main Works | UFDR 234.D | HS2-000020CJR | #N/A | #N/A | #N/A
215.02-2 | HS2-00002CX36 | IDR 215.02-2 | HS2-00002CX36 | 2025-01-10 | 10 - Complete | 2025-01-17 |  | HS2-00002VZUD - C23-113-0001T | UFDR 234.C - Cedars Farm Accommodation Overbridge Main Works | UFDR 234.C | HS2-00002VZUD | #N/A | #N/A | #N/A
215.02-2 | HS2-00002CT8V | IDR 215.02-2 | HS2-00002CT8V | 2024-08-22 | 10 - Complete | 2024-09-05 |  | HS2-00002CTJ3 - CSO-04-3117T | UFDR 234.C - Cedars Farm Accommodation Overbridge Main Works | UFDR 234.C | HS2-00002CTJ3 | #N/A | #N/A | #N/A
215.02-2 | HS2-00002CX35 | IDR 215.02-2 | HS2-00002CX35 | 2024-08-21 | 10 - Complete | 2024-09-05 |  | HS2-00002CTJ6 - CSO-04-3118T | UFDR 234.C - Cedars Farm Accommodation Overbridge Main Works | UFDR 234.C | HS2-00002CTJ6 | #N/A | #N/A | #N/A
211.1 | HS2-000001036 | IDR 211.1 | HS2-000001036 | 2023-11-16 | 10 - Complete | 2023-11-17 |  | HS2-000020CJM - CSO-04-3115P | UFDR 233.B - A361 Byfield Road Utilities | UFDR 233.B | HS2-000020CJM | #N/A | #N/A | #N/A
209.2-2 | HS2-00002Y0AS | IDR 209.2-2 | HS2-00002Y0AS | 2023-11-17 | 10 - Complete | 2023-11-29 |  | HS2-00002FEA8 - CSO-04-2200P | UFDR 233.B - A361 Byfield Road Utilities | UFDR 233.B | HS2-00002FEA8 | #N/A | #N/A | #N/A
236.01 | HS2-00003B5AL | IDR 236.01 | HS2-00003B5AL | 2023-11-17 | 10 - Complete | 2023-11-21 |  | HS2-000020CJD - CSO-04-1322 | UFDR 232.D - Trafford Bridge Stage 2 Utilities (NGED) | UFDR 232.D | HS2-000020CJD | #N/A | #N/A | #N/A
236.01 | HS2-00002V04G | IDR 236.01 | HS2-00002V04G | 2023-11-17 | 10 - Complete | 2023-11-21 |  | HS2-000020CJE - CSO-04-3124 | UFDR 232.C - Culworth Road Main Works | UFDR 232.C | HS2-000020CJE | 2024-03-08 | 10 - Complete | 2024-03-11
230.01 | HS2-000020NW9 | IDR 230.01 | HS2-000020NW9 | 2023-11-17 | 10 - Complete | 2023-11-23 |  | HS2-000020CJF - CSO-04-3113 | UFDR 232.C - Culworth Road Main Works | UFDR 232.C | HS2-000020CJF | 2024-03-08 | 10 - Complete | 2024-03-11
204.2 | HS2-000001399 | IDR 204.2 | HS2-000001399 | 2023-11-17 | 10 - Complete | 2023-11-21 |  | HS2-00002FEA3 - C23-109-0003 | UFDR 232.C - Culworth Road Main Works | UFDR 232.C | HS2-00002FEA3 | 2024-03-08 | 10 - Complete | 2024-03-11
218.02-1 | HS2-00002TMWU | IDR 218.02-1 | HS2-00002TMWU | 2023-11-20 | 10 - Complete | 2023-11-22 |  | HS2-000020CJH - CSO-04-6107 | UFDR 232.C - Culworth Road Main Works | UFDR 232.C | HS2-000020CJH | 2024-03-18 | 10 - Complete | 2024-03-19
218.02-1 | HS2-00002TMWV | IDR 218.02-1 | HS2-00002TMWV | 2023-11-20 | 10 - Complete | 2023-11-23 |  | HS2-000020CJG - CSO-04-1323 | UFDR 232.B - Culworth Road Utilities (NGED) | UFDR 232.B | HS2-000020CJG | 2024-02-13 | 10 - Complete | 2024-02-16
218.02-1 | HS2-00002TMWW | IDR 218.02-1 | HS2-00002TMWW | 2023-11-20 | 10 - Complete | 2023-11-23 |  | HS2-000020CJ6 - CSO-04-1319 | UFDR 230.C - Banbury Lane Utilities (NGED) | UFDR 230.C | HS2-000020CJ6 | 2024-03-22 | 10 - Complete | 2024-03-27
213.01-1 | HS2-00002CW1G | IDR 213.01-1 | HS2-00002CW1G | 2025-04-24 | 10 - Complete | 2025-06-27 |  | HS2-000020CJA - CSO-04-1321 | UFDR 230.B - Culworth Grounds Accommodation Overbridge | UFDR 230.B | HS2-000020CJA | 2024-03-12 | 10 - Complete | 2024-03-14
218.02-1 | HS2-00002KRAM | IDR 218.02-1 | HS2-00002KRAM | 2023-11-21 | 10 - Complete | 2023-11-21 |  | HS2-00002FEA1 - C23-105-0001 | UFDR 230.A - Banbury Lane Utilities | UFDR 230.A | HS2-00002FEA1 | #N/A | #N/A | #N/A
218.02-1 | HS2-00002KRAL | IDR 218.02-1 | HS2-00002KRAL | 2023-11-21 | 10 - Complete | 2023-11-27 |  | HS2-000020CJ8 - CSO-04-3111 | UFDR 230.A - Banbury Lane Utilities | UFDR 230.A | HS2-000020CJ8 | #N/A | #N/A | #N/A
236.01 | HS2-00003B5AM | IDR 236.01 | HS2-00003B5AM | 2023-11-21 | 10 - Complete | 2023-11-23 |  | HS2-000020CJ9 - CSO-04-6109 | UFDR 230.A - Banbury Lane Utilities | UFDR 230.A | HS2-000020CJ9 | #N/A | #N/A | #N/A
236.01 | HS2-00003B5AP | IDR 236.01 | HS2-00003B5AP | 2023-11-21 | 10 - Complete | 2023-11-23 |  | HS2-000020CJ3 - CSO-04-3110P | UFDR 229.D - Banbury Road Main Works | UFDR 229.D | HS2-000020CJ3 | 2024-11-13 | 10 - Complete | 2024-11-21
236.01 | HS2-00003B5AR | IDR 236.01 | HS2-00003B5AR | 2023-11-21 | 10 - Complete | 2023-11-23 |  | HS2-000020CJ4 - CSO-04-4300P | UFDR 229.D - Banbury Road Main Works | UFDR 229.D | HS2-000020CJ4 | 2024-11-13 | 10 - Complete | 2024-11-21
236.01 | HS2-00003B5AU | IDR 236.01 | HS2-00003B5AU | 2023-11-21 | 10 - Complete | 2023-11-23 |  | HS2-000020CJ5 - CSO-04-6105P | UFDR 229.D - Banbury Road Main Works | UFDR 229.D | HS2-000020CJ5 | 2024-11-13 | 10 - Complete | 2024-11-21
209.2-3 | HS2-000020C0Z | IDR 209.2-3 | HS2-000020C0Z | 2023-11-22 | 10 - Complete | 2023-11-24 |  | HS2-00003CPXB - Clean Water Pipe CFA_15_23a | UFDR 229.D - Banbury Road Main Works | UFDR 229.D | HS2-00003CPXB | 2024-11-13 | 10 - Complete | 2024-11-21
209.1 | HS2-00002CT5T | IDR 209.1 | HS2-00002CT5T | 2023-11-22 | 10 - Complete | 2023-11-22 |  | HS2-00003KLDC - CSO-04-3110T1 | UFDR 229.D - Banbury Road Main Works | UFDR 229.D | HS2-00003KLDC | 2024-11-13 | 10 - Complete | 2024-11-21
218.02-1 | HS2-00002VK47 | IDR 218.02-1 | HS2-00002VK47 | 2024-09-10 | 10 - Complete | 2024-09-20 |  | HS2-00003KLDD - CSO-04-4300T1 | UFDR 229.D - Banbury Road Main Works | UFDR 229.D | HS2-00003KLDD | 2024-11-13 | 10 - Complete | 2024-11-21
218.02-1 | HS2-0000307ZQ | IDR 218.02-1 | HS2-0000307ZQ | 2024-10-14 | 10 - Complete | 2024-10-17 |  | HS2-00003KLDE - CSO-04-6105T1 | UFDR 229.D - Banbury Road Main Works | UFDR 229.D | HS2-00003KLDE | 2024-11-13 | 10 - Complete | 2024-11-21
218.02-1 | HS2-0000307ZR | IDR 218.02-1 | HS2-0000307ZR | 2024-10-17 | 10 - Complete | 2024-10-24 |  | HS2-00002CTFH - CSO-04-3110T | UFDR 229.C - Banbury Road Early Works | UFDR 229.C | HS2-00002CTFH | #N/A | #N/A | #N/A
223.4 | HS2-00002BJV0 | IDR 223.4 | HS2-00002BJV0 | 2023-11-24 | 10 - Complete | 2023-11-27 |  | HS2-00002CTFD - CSO-04-6105T | UFDR 229.C - Banbury Road Early Works | UFDR 229.C | HS2-00002CTFD | #N/A | #N/A | #N/A
223.4 | HS2-00002BJV1 | IDR 223.4 | HS2-00002BJV1 | 2023-11-24 | 10 - Complete | 2023-11-27 |  | HS2-00002CTFJ - CSO-04-4300T | UFDR 229.C - Banbury Road Early Works | UFDR 229.C | HS2-00002CTFJ | #N/A | #N/A | #N/A
223.4 | HS2-00002BJV2 | IDR 223.4 | HS2-00002BJV2 | 2023-11-24 | 10 - Complete | 2023-11-27 |  | HS2-000020CHZ - CSO-04-3107P | UFDR 229.B - Welsh Rd Stage 2 Utilities | UFDR 229.B | HS2-000020CHZ | 2024-04-05 | 10 - Complete | 2024-04-08
226.1 | HS2-00002TMF0 | IDR 226.1 | HS2-00002TMF0 | 2023-11-28 | 10 - Complete | 2023-12-04 |  | HS2-00002FE9X - C23-102-0002P | UFDR 229.B - Welsh Rd Stage 2 Utilities | UFDR 229.B | HS2-00002FE9X | 2024-04-05 | 10 - Complete | 2024-04-09
236.03 | HS2-000020P0F | IDR 236.03 | HS2-000020P0F | 2023-11-29 | 10 - Complete | 2023-12-05 |  | HS2-00002FE9Z - C23-102-0003P | UFDR 229.B - Welsh Rd Stage 2 Utilities | UFDR 229.B | HS2-00002FE9Z | 2024-04-05 | 10 - Complete | 2024-04-09
236.03 | HS2-00002U6LN | IDR 236.03 | HS2-00002U6LN | 2023-11-29 | 10 - Complete | 2023-12-05 |  | HS2-000020CJ0 - CSO-04-3108P | UFDR 229.B - Welsh Rd Stage 2 Utilities | UFDR 229.B | HS2-000020CJ0 | 2024-04-05 | 10 - Complete | 2024-04-09
224.4 | HS2-000020NPE | IDR 224.4 | HS2-000020NPE | 2023-11-30 | 10 - Complete | 2023-12-06 |  | HS2-000020CJ1 - CSO-04-6104P | UFDR 229.B - Welsh Rd Stage 2 Utilities | UFDR 229.B | HS2-000020CJ1 | 2024-04-05 | 10 - Complete | 2024-04-09
224.4 | HS2-000020RNJ | IDR 224.4 | HS2-000020RNJ | 2023-11-30 | 99 - Cancelled | 0 |  | HS2-000020CJ2 - CSO-04-3109P | UFDR 229.B - Welsh Rd Stage 2 Utilities | UFDR 229.B | HS2-000020CJ2 | 2024-04-05 | 10 - Complete | 2024-04-09
224.4 | HS2-00002BJV5 | IDR 224.4 | HS2-00002BJV5 | 2023-11-30 | 10 - Complete | 2023-12-06 |  | HS2-00002CTFE - CSO-04-3107T | UFDR 229.A - Welsh Rd Stage 1 Utilities | UFDR 229.A | HS2-00002CTFE | #N/A | #N/A | #N/A
217.03 | HS2-00002CT8S | IDR 217.03 | HS2-00002CT8S | 2025-05-01 | 10 - Complete | 2025-05-02 |  | HS2-00002FE9Y - C23-102-0002T | UFDR 229.A - Welsh Rd Stage 1 Utilities | UFDR 229.A | HS2-00002FE9Y | #N/A | #N/A | #N/A
222.2 | HS2-00002N7WG | IDR 222.2 | HS2-00002N7WG | 2024-01-09 | 10 - Complete | 2024-01-11 |  | HS2-00002FEA0 - C23-102-0003T | UFDR 229.A - Welsh Rd Stage 1 Utilities | UFDR 229.A | HS2-00002FEA0 | #N/A | #N/A | #N/A
222.2 | HS2-00002N7WH | IDR 222.2 | HS2-00002N7WH | 2024-01-08 | 10 - Complete | 2024-01-10 |  | HS2-00002CTFF - CSO-04-3108T | UFDR 229.A - Welsh Rd Stage 1 Utilities | UFDR 229.A | HS2-00002CTFF | #N/A | #N/A | #N/A
222.2 | HS2-00002N7WJ | IDR 222.2 | HS2-00002N7WJ | 2024-01-08 | 10 - Complete | 2024-01-11 |  | HS2-00002CTFC - CSO-04-6104T | UFDR 229.A - Welsh Rd Stage 1 Utilities | UFDR 229.A | HS2-00002CTFC | #N/A | #N/A | #N/A
220.5 | HS2-00002Y0RV | IDR 220.5 | HS2-00002Y0RV | 2024-06-12 | 10 - Complete | 2024-06-26 |  | HS2-00002CTFG - CSO-04-3109T | UFDR 229.A - Welsh Rd Stage 1 Utilities | UFDR 229.A | HS2-00002CTFG | 2024-02-01 | 10 - Complete | 2024-02-02
236.03 | HS2-00002CTJN | IDR 236.03 | HS2-00002CTJN | 2023-12-05 | 10 - Complete | 2023-12-06 |  | HS2-00003CFCL - CSO-100-0002 | UFDR 228.F - Greatworth Reservoir - Drain pipe Permanent Diversion | UFDR 228.F | HS2-00003CFCL | 2024-04-08 | 10 - Complete | 2024-04-09
236.03 | HS2-00002CTJP | IDR 236.03 | HS2-00002CTJP | 2023-12-05 | 10 - Complete | 2023-12-06 |  | HS2-000020CHQ - CSO-04-6103 | UFDR 228.E - Greatworth Reservoir - Permanent Diversions | UFDR 228.E | HS2-000020CHQ | #N/A | #N/A | #N/A
235.01 | HS2-00002N7UR | IDR 235.01 | HS2-00002N7UR | 2023-12-05 | 10 - Complete | 2023-12-13 |  | HS2-000020CHS - CSO-04-3105P | UFDR 228.D - Bridleways AN14 Accommodation - Permanent Diversions | UFDR 228.D | HS2-000020CHS | #N/A | #N/A | #N/A
226.3 | HS2-00002N7X1 | IDR 226.3 | HS2-00002N7X1 | 2024-01-08 | 10 - Complete | 2024-01-11 |  | HS2-00002CTEQ - CSO-04-3105T | UFDR 228.C - Bridleways AN14 Accommodation - Temporary Diversions | UFDR 228.C | HS2-00002CTEQ | #N/A | #N/A | #N/A
222.4 | HS2-00002N7WQ | IDR 222.4 | HS2-00002N7WQ | 2024-01-09 | 10 - Complete | 2024-01-11 |  | HS2-000020CHR - CSO-04-1313 | UFDR 228.B - Greatworth Reservoir - NGED Permanent Diversions | UFDR 228.B | HS2-000020CHR | #N/A | #N/A | #N/A
236.03 | HS2-00003D9CV | IDR 236.03 | HS2-00003D9CV | 2023-12-06 | 10 - Complete | 2023-12-07 |  | HS2-00002TTH9 - 1314 Greatworth Hall Ground Mounted Substation | UFDR 228.A - Greatworth Green Tunnel and Sulgrave Utilities (NGED) | UFDR 228.A | HS2-00002TTH9 | 2024-03-25 | 10 - Complete | 2024-03-28
236.03 | HS2-00003D9CW | IDR 236.03 | HS2-00003D9CW | 2023-12-06 | 10 - Complete | 2023-12-07 |  | HS2-000020CHT - CSO-04-1314 | UFDR 228.A - Greatworth Green Tunnel and Sulgrave Utilities (NGED) | UFDR 228.A | HS2-000020CHT | 2024-03-25 | 10 - Complete | 2024-03-27
236.03 | HS2-00003D9CX | IDR 236.03 | HS2-00003D9CX | 2023-12-06 | 10 - Complete | 2023-12-07 |  | HS2-000020CHU - CSO-04-1315 | UFDR 228.A - Greatworth Green Tunnel and Sulgrave Utilities (NGED) | UFDR 228.A | HS2-000020CHU | 2024-03-25 | 10 - Complete | 2024-03-27
236.03 | HS2-00003D9CY | IDR 236.03 | HS2-00003D9CY | 2023-12-06 | 10 - Complete | 2023-12-07 |  | HS2-000020CHV - CSO-04-1316 | UFDR 228.A - Greatworth Green Tunnel and Sulgrave Utilities (NGED) | UFDR 228.A | HS2-000020CHV | 2024-03-25 | 10 - Complete | 2024-03-27
236.03 | HS2-00003GEF2 | IDR 236.03 | HS2-00003GEF2 | 2023-12-06 | 10 - Complete | 2023-12-08 |  | HS2-00002FE9V - CSO-04-1317 | UFDR 228.A - Greatworth Green Tunnel and Sulgrave Utilities (NGED) | UFDR 228.A | HS2-00002FE9V | 2024-03-25 | 10 - Complete | 2024-03-27
236.03 | HS2-00003GEF3 | IDR 236.03 | HS2-00003GEF3 | 2023-12-06 | 10 - Complete | 2023-12-08 |  | HS2-00002PW6B - CSO-04-3104T | UFDR 227.C - Radstone Rd - Temporary Diversions | UFDR 227.C | HS2-00002PW6B | #N/A | #N/A | #N/A
236.03 | HS2-00003GEF4 | IDR 236.03 | HS2-00003GEF4 | 2023-12-06 | 10 - Complete | 2023-12-08 |  | HS2-00002FE9N - CSO-04-6102T | UFDR 227.C - Radstone Rd - Temporary Diversions | UFDR 227.C | HS2-00002FE9N | #N/A | #N/A | #N/A
236.03 | HS2-00003GEF5 | IDR 236.03 | HS2-00003GEF5 | 2023-12-06 | 10 - Complete | 2023-12-08 |  | HS2-000020CHM - CSO-04-3104 Diverted Telecoms Cables | UFDR 227.B - Bridleway AX18 + Radstone Rd OB - Permanent Diversions | UFDR 227.B | HS2-000020CHM | 2024-04-12 | 10 - Complete | 2024-04-19
235.01 | HS2-000020134 | IDR 235.01 | HS2-000020134 | 2024-10-23 | 10 - Complete | 2024-11-13 |  | HS2-0000245Z9 - CSO-04-2201 Diverted Gas Main | UFDR 227.B - Bridleway AX18 + Radstone Rd OB - Permanent Diversions | UFDR 227.B | HS2-0000245Z9 | 2024-04-12 | 10 - Complete | 2024-04-19
216.01-2 | HS2-00003D82Q | IDR 216.01-2 | HS2-00003D82Q | 2023-12-07 | 10 - Complete | 2023-12-09 |  | HS2-00002FE9M - CSO-04-6102P | UFDR 227.B - Bridleway AX18 + Radstone Rd OB - Permanent Diversions | UFDR 227.B | HS2-00002FE9M | 2024-04-12 | 10 - Complete | 2024-04-15
237.03 | HS2-00003D9CP | IDR 237.03 | HS2-00003D9CP | 2023-12-11 | 10 - Complete | 2024-01-16 |  | HS2-00002FE9P - CSO-04-2202 | UFDR 227.B - Bridleway AX18 + Radstone Rd OB - Permanent Diversions | UFDR 227.B | HS2-00002FE9P | 2024-04-12 | 10 - Complete | 2024-04-19
237.03 | HS2-00003D9CQ | IDR 237.03 | HS2-00003D9CQ | 2023-12-11 | 10 - Complete | 2024-01-16 |  | HS2-00002CQQM - CSO-04-1312 Diverted 11kV O H Radstone Road | UFDR 227.A - Bridleway AX18 + Radstone Rd OB - NGED Permanent Diversions | UFDR 227.A | HS2-00002CQQM | 2024-07-05 | 10 - Complete | 2024-07-10
237.03 | HS2-00003D9CR | IDR 237.03 | HS2-00003D9CR | 2023-12-11 | 10 - Complete | 2024-01-17 |  | HS2-000020CHN - CSO-04-1311 Diverted 11kV O H Elect Distribution Lines | UFDR 227.A - Bridleway AX18 + Radstone Rd OB - NGED Permanent Diversions | UFDR 227.A | HS2-000020CHN | 2024-07-05 | 10 - Complete | 2024-07-10
237.03 | HS2-00003D9CS | IDR 237.03 | HS2-00003D9CS | 2023-12-11 | 10 - Complete | 2024-01-16 |  | HS2-00002CTE2 - CSO-04-3103T | UFDR 226.C - A43 Oxford Rd - Temporary Diversions | UFDR 226.C | HS2-00002CTE2 | #N/A | #N/A | #N/A
237.03 | HS2-00003D9CT | IDR 237.03 | HS2-00003D9CT | 2023-12-11 | 10 - Complete | 2024-01-16 |  | HS2-000020CHE - CSO-04-3103P | UFDR 226.B - A43 Oxford Rd OB - Permanent Diversions | UFDR 226.B | HS2-000020CHE | #N/A | #N/A | #N/A
237.03 | HS2-00003D9CU | IDR 237.03 | HS2-00003D9CU | 2023-12-11 | 10 - Complete | 2024-01-17 |  | HS2-000020CHD - CSO-04-1306 | UFDR 226.A - A43 Oxford Rd OB - NGED Permanent Diversions | UFDR 226.A | HS2-000020CHD | 2024-05-14 | 10 - Complete | 2024-05-15
234.02 | HS2-00002CTHS | IDR 234.02 | HS2-00002CTHS | 2024-02-28 | 10 - Complete | 2024-02-28 |  | HS2-00002TTH7 - A43 Oxford Road Switching Station | UFDR 226.A - A43 Oxford Rd OB - NGED Permanent Diversions | UFDR 226.A | HS2-00002TTH7 | 2024-05-01 | 10 - Complete | 2024-05-07
208.2 | HS2-00002CT5F | IDR 208.2 | HS2-00002CT5F | 2023-12-11 | 10 - Complete | 2023-12-14 |  | HS2-000020CHF - CSO-04-1307 | UFDR 226.A - A43 Oxford Rd OB - NGED Permanent Diversions | UFDR 226.A | HS2-000020CHF | 2024-02-23 | 10 - Complete | 2024-02-27
237.03 | HS2-00002CTJV | IDR 237.03 | HS2-00002CTJV | 2023-12-12 | 10 - Complete | 2023-12-14 |  | HS2-000020CHA - CSO-04-1302P | UFDR 224.H - Turweston Green OB - NGED Permanent Diversion | UFDR 224.H | HS2-000020CHA | 2024-02-02 | 10 - Complete | 2024-02-07
237.03 | HS2-00002CTJW | IDR 237.03 | HS2-00002CTJW | 2023-12-12 | 10 - Complete | 2023-12-14 |  | HS2-00002CTCS - CSO-04-1302T | UFDR 224.G - Turweston - NGED Temporary Diversion | UFDR 224.G | HS2-00002CTCS | #N/A | #N/A | #N/A
208.2 | HS2-00002BVFD | IDR 208.2 | HS2-00002BVFD | 2023-12-12 | 10 - Complete | 2023-12-20 |  | HS2-000020CH8 - CSO-04-1301P | UFDR 224.F - A422 Brackley Rd OB - NGED Permanent Diversions | UFDR 224.F | HS2-000020CH8 | 2024-03-07 | 10 - Complete | 2024-03-08
208.2 | HS2-00002CT5N | IDR 208.2 | HS2-00002CT5N | 2023-12-12 | 10 - Complete | 2023-12-20 |  | HS2-00002BVPQ - C23-093-0002P | UFDR 224.E - A422 Brackley Rd TOB - NGED Temporary Diversion | UFDR 224.E | HS2-00002BVPQ | #N/A | #N/A | #N/A
215.02-2 | HS2-00002CX36 | IDR 215.02-2 | HS2-00002CX36 | 2025-01-10 | 10 - Complete | 2025-01-17 |  | HS2-00002CTCR - CSO-04-1301T | UFDR 224.E - A422 Brackley Rd TOB - NGED Temporary Diversion | UFDR 224.E | HS2-00002CTCR | #N/A | #N/A | #N/A
201.3-3 | HS2-00002BJQU | IDR 201.3-3 | HS2-00002BJQU | 2023-12-14 | 10 - Complete | 2024-01-12 |  | HS2-000020CHB - CSO-04-3102P | UFDR 224.D - Turweston Green OB - Permanent Diversions | UFDR 224.D | HS2-000020CHB | #N/A | #N/A | #N/A
215.02-2 | HS2-00002Y8VF | IDR 215.02-2 | HS2-00002Y8VF | 2023-12-15 | 10 - Complete | 2023-12-20 |  | HS2-00002CTCV - CSO-04-3102T | UFDR 224.C - Turweston - Temporary Diversions | UFDR 224.C | HS2-00002CTCV | #N/A | #N/A | #N/A
215.02-2 | HS2-00002CT8V | IDR 215.02-2 | HS2-00002CT8V | 2024-08-22 | 10 - Complete | 2024-09-05 |  | HS2-000020CH4 - CSO-04-3101P | UFDR 224.B - A422 Brackley Rd OB - Permanent Diversions | UFDR 224.B | HS2-000020CH4 | #N/A | #N/A | #N/A
215.02-2 | HS2-00002CX35 | IDR 215.02-2 | HS2-00002CX35 | 2024-08-21 | 10 - Complete | 2024-09-05 |  | HS2-000020CH5 - CSO-04-6100P | UFDR 224.B - A422 Brackley Rd OB - Permanent Diversions | UFDR 224.B | HS2-000020CH5 | #N/A | #N/A | #N/A
215.02-2 | HS2-00002EK76 | IDR 215.02-2 | HS2-00002EK76 | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-000020CH6 - CNO-163-015P | UFDR 224.B - A422 Brackley Rd OB - Permanent Diversions | UFDR 224.B | HS2-000020CH6 | #N/A | #N/A | #N/A
215.02-2 | HS2-00002TMWR | IDR 215.02-2 | HS2-00002TMWR | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-00002CTCQ - CSO-04-6100T | UFDR 224.A - A422 Brackley Rd TOB - Temporary Diversions | UFDR 224.A | HS2-00002CTCQ | #N/A | #N/A | #N/A
215.02-2 | HS2-00002TMWS | IDR 215.02-2 | HS2-00002TMWS | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-00002CTCU - CSO-04-3101T | UFDR 224.A - A422 Brackley Rd TOB - Temporary Diversions | UFDR 224.A | HS2-00002CTCU | #N/A | #N/A | #N/A
215.02-2 | HS2-00002Y8VG | IDR 215.02-2 | HS2-00002Y8VG | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-00002CTCW - CNO-163-015T | UFDR 224.A - A422 Brackley Rd TOB - Temporary Diversions | UFDR 224.A | HS2-00002CTCW | #N/A | #N/A | #N/A
215.02-2 | HS2-00002Y8VH | IDR 215.02-2 | HS2-00002Y8VH | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-000020CH3 - CSO-03-1308 | UFDR 223.B - Westbury Viaduct - Permanent Diversions | UFDR 223.B | HS2-000020CH3 | #N/A | #N/A | #N/A
215.02-2 | HS2-00002Y8VJ | IDR 215.02-2 | HS2-00002Y8VJ | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-000020CH2 - CSO-03-7101 | UFDR 223.A - Featherbed Lane - Permanent Diversions | UFDR 223.A | HS2-000020CH2 | 2024-09-25 | 10 - Complete | 2024-10-08
215.02-2 | HS2-00002Y8VM | IDR 215.02-2 | HS2-00002Y8VM | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-000020CGW - CSO-03-2202P | UFDR 222.G - SGN Featherbed Lane OBs | UFDR 222.G | HS2-000020CGW | #N/A | #N/A | #N/A
215.02-2 | HS2-00002Y8VN | IDR 215.02-2 | HS2-00002Y8VN | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-00002CTC1 - CSO-03-2202T | UFDR 222.F - A421 London Rd + Featherbed Lane - Temporary Diversions | UFDR 222.F | HS2-00002CTC1 | #N/A | #N/A | #N/A
238.02 | HS2-00002N7UU | IDR 238.02 | HS2-00002N7UU | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-00002CTBX - CSO-03-1400T | UFDR 222.E - A4421 Buckingham Rd - Temporary Diversions | UFDR 222.E | HS2-00002CTBX | #N/A | #N/A | #N/A
237.02 | HS2-00002CTJT | IDR 237.02 | HS2-00002CTJT | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-00002CTBZ - CSO-03-1401T | UFDR 222.D - A421 London Rd + Featherbed Lane - Temporary Diversions | UFDR 222.D | HS2-00002CTBZ | #N/A | #N/A | #N/A
237.02 | HS2-00002EL0S | IDR 237.02 | HS2-00002EL0S | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-000020CGZ - CSO-03-3107 | UFDR 222.C - A421 London Rd - Permanent Diversions | UFDR 222.C | HS2-000020CGZ | #N/A | #N/A | #N/A
208.2 | HS2-00002CW19 | IDR 208.2 | HS2-00002CW19 | 2023-12-15 | 10 - Complete | 2023-12-18 |  | HS2-000020CGT - CSO-03-1401P | UFDR 222.B - A421 London Rd + Featherbed Lane OBs - Permanent Diversions | UFDR 222.B | HS2-000020CGT | #N/A | #N/A | #N/A
237.02 | HS2-000020P0J | IDR 237.02 | HS2-000020P0J | 2023-12-18 | 10 - Complete | 2024-01-05 |  | HS2-000020CGU - CSO-03-3104 | UFDR 222.B - A421 London Rd + Featherbed Lane OBs - Permanent Diversions | UFDR 222.B | HS2-000020CGU | #N/A | #N/A | #N/A
237.02 | HS2-00002CTJU | IDR 237.02 | HS2-00002CTJU | 2023-12-18 | 10 - Complete | 2024-01-05 |  | HS2-000020CGX - CSO-03-3105P | UFDR 222.B - A421 London Rd + Featherbed Lane OBs - Permanent Diversions | UFDR 222.B | HS2-000020CGX | #N/A | #N/A | #N/A
215.02-2 | HS2-000020NK2 | IDR 215.02-2 | HS2-000020NK2 | 2025-01-29 | 10 - Complete | 2025-02-10 |  | HS2-000020CGY - CSO-03-6201AP | UFDR 222.B - A421 London Rd + Featherbed Lane OBs - Permanent Diversions | UFDR 222.B | HS2-000020CGY | #N/A | #N/A | #N/A
215.02-2 | HS2-00002BJU3 | IDR 215.02-2 | HS2-00002BJU3 | 2025-01-29 | 10 - Complete | 2025-02-10 |  | HS2-0000245Z8 - CSO-03-6201P | UFDR 222.B - A421 London Rd + Featherbed Lane OBs - Permanent Diversions | UFDR 222.B | HS2-0000245Z8 | 2024-05-22 | 10 - Complete | 2024-05-30
215.02-2 | HS2-00002CT8R | IDR 215.02-2 | HS2-00002CT8R | 2024-01-23 | 10 - Complete | 2024-01-24 |  | HS2-00002BVPN - C23-089-0001 | UFDR 222.B - A421 London Rd + Featherbed Lane OBs - Permanent Diversions | UFDR 222.B | HS2-00002BVPN | #N/A | #N/A | #N/A
215.02-2 | HS2-00002CT8Y | IDR 215.02-2 | HS2-00002CT8Y | 2025-01-29 | 10 - Complete | 2025-02-12 |  | HS2-000020CGN - CSO-03-3103 | UFDR 222.A - A4421 Buckingham Rd OB - Permanent Diversions | UFDR 222.A | HS2-000020CGN | #N/A | #N/A | #N/A
215.02-2 | HS2-00002NNHZ | IDR 215.02-2 | HS2-00002NNHZ | 2023-12-20 | 10 - Complete | 2024-01-09 |  | HS2-000020CGP - CSO-03-3300 | UFDR 222.A - A4421 Buckingham Rd OB - Permanent Diversions | UFDR 222.A | HS2-000020CGP | #N/A | #N/A | #N/A
230.01-2 | HS2-00002CTFP | IDR 230.01-2 | HS2-00002CTFP | 2023-12-21 | 10 - Complete | 2023-12-22 |  | HS2-000020CGQ - CSO-03-6200 | UFDR 222.A - A4421 Buckingham Rd OB - Permanent Diversions | UFDR 222.A | HS2-000020CGQ | #N/A | #N/A | #N/A
230.01-2 | HS2-00002CTFR | IDR 230.01-2 | HS2-00002CTFR | 2023-12-21 | 10 - Complete | 2024-01-05 |  | HS2-00002G16X - C23-088-0002 | UFDR 222.A - A4421 Buckingham Rd OB - Permanent Diversions | UFDR 222.A | HS2-00002G16X | #N/A | #N/A | #N/A
228 | HS2-000033GP5 | IDR 228 | HS2-000033GP5 | 2023-12-22 | 10 - Complete | 2024-01-05 |  | HS2-000020CGR - CSO-03-1400P | UFDR 222.A - A4421 Buckingham Rd OB - Permanent Diversions | UFDR 222.A | HS2-000020CGR | #N/A | #N/A | #N/A
238.01 | HS2-000001462 | IDR 238.01 | HS2-000001462 | 2024-01-02 | 10 - Complete | 2024-01-18 |  | HS2-000020CGK - CSO-03-1305 | UFDR 221.D - CHW/18 Accommodation OB ‐ NGED Permanent Diversions | UFDR 221.D | HS2-000020CGK | 2024-03-22 | 10 - Complete | 2024-03-26
238.01 | HS2-00003DL20 | IDR 238.01 | HS2-00003DL20 | 2024-02-02 | 10 - Complete | 2024-02-07 |  | HS2-000020CGL - CSO-03-1306P | UFDR 221.D - CHW/18 Accommodation OB ‐ NGED Permanent Diversions | UFDR 221.D | HS2-000020CGL | 2024-03-22 | 10 - Complete | 2024-03-26
238.01 | HS2-00003DL21 | IDR 238.01 | HS2-00003DL21 | 2024-02-02 | 10 - Complete | 2024-02-07 |  | HS2-000020CGH - CSO-03-3102 | UFDR 221.C - Manthorne Farm, CHW/18 Accommodation OB - Permanent Diversions | UFDR 221.C | HS2-000020CGH | #N/A | #N/A | #N/A
238.01 | HS2-00003DL22 | IDR 238.01 | HS2-00003DL22 | 2024-02-02 | 10 - Complete | 2024-02-07 |  | HS2-000020CGJ - CSO-03-6102 | UFDR 221.C - Manthorne Farm, CHW/18 Accommodation OB - Permanent Diversions | UFDR 221.C | HS2-000020CGJ | #N/A | #N/A | #N/A
226.3 | HS2-00002N7X1 | IDR 226.3 | HS2-00002N7X1 | 2024-01-08 | 10 - Complete | 2024-01-11 |  | HS2-00002G16V - C23-085-0002 | UFDR 221.C - Manthorne Farm, CHW/18 Accommodation OB - Permanent Diversions | UFDR 221.C | HS2-00002G16V | #N/A | #N/A | #N/A
222.2 | HS2-00002N7WH | IDR 222.2 | HS2-00002N7WH | 2024-01-08 | 10 - Complete | 2024-01-10 |  | HS2-00002BVPK - C23-086-0001P | UFDR 221.B - School End OB - Permanent Diversions | UFDR 221.B | HS2-00002BVPK | #N/A | #N/A | #N/A
222.2 | HS2-00002N7WJ | IDR 222.2 | HS2-00002N7WJ | 2024-01-08 | 10 - Complete | 2024-01-11 |  | HS2-000020CGM - CSO-03-3106P | UFDR 221.B - School End OB - Permanent Diversions | UFDR 221.B | HS2-000020CGM | #N/A | #N/A | #N/A
UFDR 203.F | HS2-00002TMEM | UFDR 203.F | HS2-00002TMEM | 2024-01-09 | 10 - Complete | 2024-01-18 |  | HS2-00002CTB5 - CSO-03-1306T | UFDR 221.A - Manthorne Farm - Temporary Diversions | UFDR 221.A | HS2-00002CTB5 | #N/A | #N/A | #N/A
UFDR 203.F | HS2-00002TMET | UFDR 203.F | HS2-00002TMET | 2024-01-09 | 10 - Complete | 2024-01-18 |  | HS2-000020CGG - CSO-03-7102 | UFDR 218.A - Twyford Outfall Completion (Stage 1) | UFDR 218.A | HS2-000020CGG | #N/A | #N/A | #N/A
222.8 | HS2-00002BJUV | IDR 222.8 | HS2-00002BJUV | 2024-01-09 | 10 - Complete | 2024-01-11 |  | HS2-00002C3X7 - CSO-03-6103 | UFDR 217.B - Addison Road Completion (Stage 1) | UFDR 217.B | HS2-00002C3X7 | 2024-11-05 | 10 - Complete | 2024-12-04
222.4 | HS2-00002N7WQ | IDR 222.4 | HS2-00002N7WQ | 2024-01-09 | 10 - Complete | 2024-01-11 |  | HS2-0000245ZF - CSO-04-3125 | UFDR 217.B - Addison Road Completion (Stage 1) | UFDR 217.B | HS2-0000245ZF | 2024-08-19 | 10 - Complete | 2024-08-21
222.2 | HS2-00002N7WG | IDR 222.2 | HS2-00002N7WG | 2024-01-09 | 10 - Complete | 2024-01-11 |  | HS2-00002TTR2 - CSO-03-2210P | UFDR 216.I - West St IP Gas Permanent Diversion | UFDR 216.I | HS2-00002TTR2 | 2024-11-20 | 10 - Complete | 2024-12-02
238.01 | HS2-00002YNH7 | IDR 238.01 | HS2-00002YNH7 | 2024-01-10 | 10 - Complete | 2024-01-19 |  | HS2-00003GEEP - Portway Farm Slurry Pipe | UFDR 216.I - West St IP Gas Permanent Diversion | UFDR 216.I | HS2-00003GEEP | 2024-10-31 | 10 - Complete | 2024-12-03
237.02 | HS2-00002U6LP | IDR 237.02 | HS2-00002U6LP | 2024-01-10 | 10 - Complete | 2024-01-12 |  | HS2-00002TTR3 - Charndon Lodge UB PS Electric | UFDR 216.G - Charndon Lodge | UFDR 216.G | HS2-00002TTR3 | #N/A | #N/A | #N/A
226.2 | HS2-000001334 | IDR 226.2 | HS2-000001334 | 2025-01-28 | 10 - Complete | 2025-02-12 |  | HS2-00002YGQQ - LV DNO cabinet at Charndon Lodge PS | UFDR 216.G - Charndon Lodge | UFDR 216.G | HS2-00002YGQQ | #N/A | #N/A | #N/A
222.8 | HS2-000001325 | IDR 222.8 | HS2-000001325 | 2024-01-10 | 10 - Complete | 2024-01-19 |  | HS2-000020CGF - CSO-03-1304P | UFDR 216.F - West Street Completion (Stage 2) - NGED | UFDR 216.F | HS2-000020CGF | #N/A | #N/A | #N/A
208.2 | HS2-00002CT5P | IDR 208.2 | HS2-00002CT5P | 2024-10-29 | 10 - Complete | 2024-11-12 |  | HS2-00002CT9E - CSO-03-1304T | UFDR 216.E - West Street Completion (Stage 1) - NGED | UFDR 216.E | HS2-00002CT9E | #N/A | #N/A | #N/A
207.2 | HS2-00002CW1B | IDR 207.2 | HS2-00002CW1B | 2024-07-25 | 10 - Complete | 2024-08-09 |  | HS2-00002TUPL - Portway Farm ATS Telecoms | UFDR 216.D - West Street Completion (Stage 2) | UFDR 216.D | HS2-00002TUPL | 2024-04-16 | 10 - Complete | 2024-04-19
205.3 | HS2-00002CW1F | IDR 205.3 | HS2-00002CW1F | 2024-07-25 | 10 - Complete | 2024-08-13 |  | HS2-00002TUPM - IMD Potable Water | UFDR 216.D - West Street Completion (Stage 2) | UFDR 216.D | HS2-00002TUPM | 2024-04-16 | 10 - Complete | 2024-04-22
209.2-3 | HS2-00003GL99 | IDR 209.2-3 | HS2-00003GL99 | 2024-01-11 | 10 - Complete | 2024-01-11 |  | HS2-00002TUPN - IMD Foul Water | UFDR 216.D - West Street Completion (Stage 2) | UFDR 216.D | HS2-00002TUPN | 2024-04-16 | 10 - Complete | 2024-04-19
204.3-1 | HS2-00002CW1A | IDR 204.3-1 | HS2-00002CW1A | 2024-01-11 | 10 - Complete | 2024-01-12 |  | HS2-00002TUPP - IMD Electric | UFDR 216.D - West Street Completion (Stage 2) | UFDR 216.D | HS2-00002TUPP | 2024-04-16 | 10 - Complete | 2024-04-22
226.2 | HS2-00002GUVX | IDR 226.2 | HS2-00002GUVX | 2024-01-25 | 10 - Complete | 2024-01-30 |  | HS2-00002TUPQ - IMD Telecoms | UFDR 216.D - West Street Completion (Stage 2) | UFDR 216.D | HS2-00002TUPQ | 2024-04-16 | 10 - Complete | 2024-04-19
235.01-2 | HS2-000001091 | IDR 235.01-2 | HS2-000001091 | 2024-04-03 | 10 - Complete | 2024-04-07 |  | HS2-00002NHZA - C23-081-0001P | UFDR 216.D - West Street Completion (Stage 2) | UFDR 216.D | HS2-00002NHZA | 2024-04-16 | 10 - Complete | 2024-04-19
235.01-2 | HS2-00002BVMB | IDR 235.01-2 | HS2-00002BVMB | 2024-01-15 | 10 - Complete | 2024-02-07 |  | HS2-00002TTR0 - CSO-03-3110P | UFDR 216.D - West Street Completion (Stage 2) | UFDR 216.D | HS2-00002TTR0 | 2024-04-16 | 10 - Complete | 2024-04-22
213.01-1 | HS2-000020NF2 | IDR 213.01-1 | HS2-000020NF2 | 2024-06-10 | 99 - Cancelled | 0 |  | HS2-000020CGD - CSO-03-3101P | UFDR 216.D - West Street Completion (Stage 2) | UFDR 216.D | HS2-000020CGD | 2024-04-16 | 10 - Complete | 2024-04-19
213.01-1 | HS2-00002BJTK | IDR 213.01-1 | HS2-00002BJTK | 2024-01-15 | 10 - Complete | 2024-01-18 |  | HS2-000020CGE - CSO-03-6101P | UFDR 216.D - West Street Completion (Stage 2) | UFDR 216.D | HS2-000020CGE | 2024-04-16 | 10 - Complete | 2024-04-22
230.01-2 | HS2-00002CTF4 | IDR 230.01-2 | HS2-00002CTF4 | 2024-01-17 | 10 - Complete | 2024-01-19 |  | HS2-00002TTR1 - CSO-03-6110P | UFDR 216.D - West Street Completion (Stage 2) | UFDR 216.D | HS2-00002TTR1 | 2024-04-16 | 10 - Complete | 2024-04-22
201.3-3 | HS2-00002CW0U | IDR 201.3-3 | HS2-00002CW0U | 2024-01-17 | 10 - Complete | 2024-01-19 |  | HS2-00002YGQH - IMD Foul Pumping Station | UFDR 216.D - West Street Completion (Stage 2) | UFDR 216.D | HS2-00002YGQH | 2024-04-16 | 10 - Complete | 2024-04-24
205.3 | HS2-00002CW1L | IDR 205.3 | HS2-00002CW1L | 2024-08-09 | 10 - Complete | 2024-08-23 |  | HS2-00002C3X9 - CSO-03-2204P | UFDR 216.C - Perry Hill Completion (Stage 2) Post EI-530 | UFDR 216.C | HS2-00002C3X9 | #N/A | #N/A | #N/A
218.01-2 | HS2-00002Y0EY | IDR 218.01-2 | HS2-00002Y0EY | 2024-01-18 | 10 - Complete | 2024-01-19 |  | HS2-00002CT9J - CSO-03-2204T | UFDR 216.C - Perry Hill Completion (Stage 2) Post EI-530 | UFDR 216.C | HS2-00002CT9J | #N/A | #N/A | #N/A
228 | HS2-000020NUC | IDR 228 | HS2-000020NUC | 2024-01-18 | 10 - Complete | 2024-01-24 |  | HS2-00002CT99 - CSO-03-6101T | UFDR 216.B - West Street Completion (Stage 1) - AW BT & Giga | UFDR 216.B | HS2-00002CT99 | #N/A | #N/A | #N/A
228 | HS2-00002VXUJ | IDR 228 | HS2-00002VXUJ | 2024-01-18 | 10 - Complete | 2024-01-25 |  | HS2-00002CT9F - CSO-03-3101T | UFDR 216.B - West Street Completion (Stage 1) - AW BT & Giga | UFDR 216.B | HS2-00002CT9F | #N/A | #N/A | #N/A
230.01-2 | HS2-00003D82U | IDR 230.01-2 | HS2-00003D82U | 2024-01-19 | 10 - Complete | 2024-02-06 |  | HS2-00002FG42 - C23-081-0001T | UFDR 216.B - West Street Completion (Stage 1) - AW BT & Giga | UFDR 216.B | HS2-00002FG42 | #N/A | #N/A | #N/A
230.01-2 | HS2-00003D82V | IDR 230.01-2 | HS2-00003D82V | 2024-01-19 | 10 - Complete | 2024-02-06 |  | HS2-000020CG1 - CSO-03-1302P | UFDR 215.A - School Hill Completion (Stage 2) | UFDR 215.A | HS2-000020CG1 | #N/A | #N/A | #N/A
238.02 | HS2-00003AQDJ | IDR 238.02 | HS2-00003AQDJ | 2024-01-19 | 10 - Complete | 2024-01-22 |  | HS2-0000245ZH - CSO-04-3127P | UFDR 215.A - School Hill Completion (Stage 2) | UFDR 215.A | HS2-0000245ZH | #N/A | #N/A | #N/A
228 | HS2-00002BVK3 | IDR 228 | HS2-00002BVK3 | 2024-01-19 | 10 - Complete | 2024-02-01 |  | HS2-000020CG3 - CSO-03-1303P | UFDR 215.A - School Hill Completion (Stage 2) | UFDR 215.A | HS2-000020CG3 | #N/A | #N/A | #N/A
228 | HS2-00002CTEF | IDR 228 | HS2-00002CTEF | 2024-01-19 | 10 - Complete | 2024-02-01 |  | HS2-000020CG4 - CSO-03-3100P | UFDR 215.A - School Hill Completion (Stage 2) | UFDR 215.A | HS2-000020CG4 | #N/A | #N/A | #N/A
228 | HS2-00002CTEG | IDR 228 | HS2-00002CTEG | 2024-01-19 | 10 - Complete | 2024-01-30 |  | HS2-00002TUPF - FCC Sidings Electric | UFDR 214.A - FCC Sidings | UFDR 214.A | HS2-00002TUPF | 2024-10-25 | 10 - Complete | 2024-10-30
228 | HS2-00002CTEK | IDR 228 | HS2-00002CTEK | 2024-01-19 | 10 - Complete | 2024-02-08 |  | HS2-00002TUPG - FCC Sidings Substation | UFDR 214.A - FCC Sidings | UFDR 214.A | HS2-00002TUPG | 2024-10-25 | 10 - Complete | 2024-10-30
228 | HS2-00002CX3H | IDR 228 | HS2-00002CX3H | 2024-01-19 | 10 - Complete | 2024-01-30 |  | HS2-00002TUPH - FCC Sidings Water | UFDR 214.A - FCC Sidings | UFDR 214.A | HS2-00002TUPH | 2024-10-31 | 10 - Complete | 2024-11-04
228 | HS2-000032TBV | IDR 228 | HS2-000032TBV | 2024-01-19 | 10 - Complete | 2024-01-30 |  | HS2-00002TUPJ - FCC Sidings Telecoms | UFDR 214.A - FCC Sidings | UFDR 214.A | HS2-00002TUPJ | 2024-10-25 | 10 - Complete | 2024-10-31
214.1 | HS2-00002CW17 | IDR 214.1 | HS2-00002CW17 | 2025-05-22 | 10 - Complete | 2025-05-28 |  | HS2-00002YCLK - DNO Cabinet to FCC Sidings | UFDR 214.A - FCC Sidings | UFDR 214.A | HS2-00002YCLK | 2024-10-25 | 10 - Complete | 2024-10-31
215.02-2 | HS2-00002CT8R | IDR 215.02-2 | HS2-00002CT8R | 2024-01-23 | 10 - Complete | 2024-01-24 |  | HS2-00003E24S - BBOWT Water Supply | UFDR 214.A - FCC Sidings | UFDR 214.A | HS2-00003E24S | 2024-10-25 | 10 - Complete | 2024-10-30
238.02 | HS2-00002N7UV | IDR 238.02 | HS2-00002N7UV | 2024-01-23 | 10 - Complete | 2024-01-24 |  | HS2-00003KFPT - FCC Sidings UKPN 11kV Switch Site | UFDR 214.A - FCC Sidings | UFDR 214.A | HS2-00003KFPT | 2024-10-25 | 10 - Complete | 2024-10-30
208.2 | HS2-000020RKT | IDR 208.2 | HS2-000020RKT | 2024-01-23 | 10 - Complete | 2024-02-07 |  | HS2-000020CFQ - CSO-02-6213P | UFDR 213.B - Station Road and Doddershall Completion (Stage 2) | UFDR 213.B | HS2-000020CFQ | #N/A | #N/A | #N/A
208.2 | HS2-000020RKU | IDR 208.2 | HS2-000020RKU | 2024-01-23 | 10 - Complete | 2024-02-07 |  | HS2-000020CFR - CSO-02-7203 | UFDR 213.B - Station Road and Doddershall Completion (Stage 2) | UFDR 213.B | HS2-000020CFR | #N/A | #N/A | #N/A
208.2 | HS2-00003B5FT | IDR 208.2 | HS2-00003B5FT | 2024-01-23 | 10 - Complete | 2024-02-07 |  | HS2-00002FE9J - CSO-02-1217P | UFDR 213.B - Station Road and Doddershall Completion (Stage 2) | UFDR 213.B | HS2-00002FE9J | #N/A | #N/A | #N/A
217.04-2 | HS2-000020NK6 | IDR 217.04-2 | HS2-000020NK6 | 2024-01-24 | 10 - Complete | 2024-02-19 |  | HS2-000020CFS - CSO-02-3119P | UFDR 213.B - Station Road and Doddershall Completion (Stage 2) | UFDR 213.B | HS2-000020CFS | #N/A | #N/A | #N/A
226.2 | HS2-000020NTD | IDR 226.2 | HS2-000020NTD | 2024-01-24 | 10 - Complete | 2024-01-29 |  | HS2-00002TUPE - Quainton ATFS Telecoms | UFDR 213.B - Station Road and Doddershall Completion (Stage 2) | UFDR 213.B | HS2-00002TUPE | #N/A | #N/A | #N/A
226.2 | HS2-00002VXUH | IDR 226.2 | HS2-00002VXUH | 2024-01-24 | 10 - Complete | 2024-01-29 |  | HS2-00002TUPS - CSO-02-3120P | UFDR 213.B - Station Road and Doddershall Completion (Stage 2) | UFDR 213.B | HS2-00002TUPS | #N/A | #N/A | #N/A
221.2 | HS2-000001322 | IDR 221.2 | HS2-000001322 | 2024-01-24 | 10 - Complete | 2024-05-01 |  | HS2-000037832 - Railway Cottage Sub Station | UFDR 213.B - Station Road and Doddershall Completion (Stage 2) | UFDR 213.B | HS2-000037832 | #N/A | #N/A | #N/A
237.01-2 | HS2-00002YNH5 | IDR 237.01-2 | HS2-00002YNH5 | 2025-02-18 | 30 - Sent back to team | 0 |  | HS2-000020CFL - CSO-02-3116 | UFDR 213.A - Station Road and Doddershall Temporary Diversions | UFDR 213.A | HS2-000020CFL | #N/A | #N/A | #N/A
235.01 | HS2-00003GJJH | IDR 235.01 | HS2-00003GJJH | 2024-01-25 | 10 - Complete | 2024-04-02 |  | HS2-000020CFM - CSO-02-1217T | UFDR 213.A - Station Road and Doddershall Temporary Diversions | UFDR 213.A | HS2-000020CFM | #N/A | #N/A | #N/A
226.2 | HS2-00002GUVX | IDR 226.2 | HS2-00002GUVX | 2024-01-25 | 10 - Complete | 2024-01-30 |  | HS2-000020CFP - CSO-02-3118 | UFDR 213.A - Station Road and Doddershall Temporary Diversions | UFDR 213.A | HS2-000020CFP | #N/A | #N/A | #N/A
228 | HS2-000001338 | IDR 228 | HS2-000001338 | 2024-06-18 | 10 - Complete | 2024-08-01 |  | HS2-00002PQMX - Station Road UKPN Sub Station | UFDR 213.A - Station Road and Doddershall Temporary Diversions | UFDR 213.A | HS2-00002PQMX | #N/A | #N/A | #N/A
228 | HS2-00002BVK9 | IDR 228 | HS2-00002BVK9 | 2024-01-26 | 10 - Complete | 2024-01-29 |  | HS2-00002PQMY - Upper South Farm UKPN Sub Station | UFDR 213.A - Station Road and Doddershall Temporary Diversions | UFDR 213.A | HS2-00002PQMY | #N/A | #N/A | #N/A
205.3 | HS2-00002CW1F | IDR 205.3 | HS2-00002CW1F | 2024-07-25 | 10 - Complete | 2024-08-13 |  | HS2-00002PQMZ - Station Road Compact UKPN Sub Station | UFDR 213.A - Station Road and Doddershall Temporary Diversions | UFDR 213.A | HS2-00002PQMZ | #N/A | #N/A | #N/A
237.05 | HS2-000001099 | IDR 237.05 | HS2-000001099 | 2024-05-14 | 10 - Complete | 2024-05-15 |  | HS2-00002PRWZ - Station Road DNO Cabinet | UFDR 213.A - Station Road and Doddershall Temporary Diversions | UFDR 213.A | HS2-00002PRWZ | #N/A | #N/A | #N/A
221 | HS2-00002NNHV | IDR 221 | HS2-00002NNHV | 2024-01-29 | 10 - Complete | 2024-03-07 |  | HS2-00002CT74 - CSO-02-3119T | UFDR 213.A - Station Road and Doddershall Temporary Diversions | UFDR 213.A | HS2-00002CT74 | #N/A | #N/A | #N/A
205.3 | HS2-00002CW1L | IDR 205.3 | HS2-00002CW1L | 2024-08-09 | 10 - Complete | 2024-08-23 |  | HS2-000020CFU - CSO-02-1220 | UFDR 213.A - Station Road and Doddershall Temporary Diversions | UFDR 213.A | HS2-000020CFU | #N/A | #N/A | #N/A
UFDR 203.E | HS2-00002CT3W | UFDR 203.E | HS2-00002CT3W | 2024-01-30 | 10 - Complete | 2024-02-01 |  | HS2-000020CFV - CSO-02-1218 | UFDR 213.A - Station Road and Doddershall Temporary Diversions | UFDR 213.A | HS2-000020CFV | #N/A | #N/A | #N/A
UFDR 203.E | HS2-00002CT46 | UFDR 203.E | HS2-00002CT46 | 2024-02-16 | 10 - Complete | 2024-02-19 |  | HS2-00002NHZ9 - CSO-02-6213T | UFDR 213.A - Station Road and Doddershall Temporary Diversions | UFDR 213.A | HS2-00002NHZ9 | #N/A | #N/A | #N/A
UFDR 203.E | HS2-00002FG43 | UFDR 203.E | HS2-00002FG43 | 2024-01-30 | 10 - Complete | 2024-02-01 |  | HS2-00002TMEK - Waddesdon Underpass Drainage Pumping Station Electric | UFDR 211.C - Waddesdon WAD/3 Underpass Drainage Pumping Station | UFDR 211.C | HS2-00002TMEK | #N/A | #N/A | #N/A
218.01-2 | HS2-00002CT9X | IDR 218.01-2 | HS2-00002CT9X | 2024-01-30 | 10 - Complete | 2024-02-02 |  | HS2-000020CFC - CSO-02-1221P | UFDR 211.B - Waddesdon Embankment (UKPN) | UFDR 211.B | HS2-000020CFC | 2024-12-20 | 10 - Complete | 2025-01-10
218.01-2 | HS2-00002NNHP | IDR 218.01-2 | HS2-00002NNHP | 2024-01-30 | 10 - Complete | 2024-02-07 |  | HS2-000020CFD - CSO-02-1215 | UFDR 211.B - Waddesdon Embankment (UKPN) | UFDR 211.B | HS2-000020CFD | 2024-12-20 | 10 - Complete | 2025-01-10
229.03 | HS2-000001438 | IDR 229.03 | HS2-000001438 | 2024-01-30 | 10 - Complete | 2024-02-01 |  | HS2-00002VZUA - CSO-02-1216T | UFDR 211.B - Waddesdon Embankment (UKPN) | UFDR 211.B | HS2-00002VZUA | #N/A | #N/A | #N/A
220.3 | HS2-00002BVH8 | IDR 220.3 | HS2-00002BVH8 | 2024-01-31 | 10 - Complete | 2024-02-02 |  | HS2-000020CFE - CSO-02-1216 | UFDR 211.A - Waddesdon (Thames Water Sewerage/BT Openreach/UKPN) | UFDR 211.A | HS2-000020CFE | 2024-12-12 | 10 - Complete | 2024-12-13
220.3 | HS2-00002CW0Q | IDR 220.3 | HS2-00002CW0Q | 2024-01-31 | 10 - Complete | 2024-02-02 |  | HS2-000020CFF - CSO-02-3115 | UFDR 211.A - Waddesdon (Thames Water Sewerage/BT Openreach/UKPN) | UFDR 211.A | HS2-000020CFF | 2024-04-15 | 10 - Complete | 2024-04-17
208.2 | HS2-000001029 | IDR 208.2 | HS2-000001029 | 2024-01-31 | 10 - Complete | 2024-02-07 |  | HS2-000020CFG - CSO-02-7202 | UFDR 211.A - Waddesdon (Thames Water Sewerage/BT Openreach/UKPN) | UFDR 211.A | HS2-000020CFG | 2024-04-15 | 10 - Complete | 2024-04-19
208.2 | HS2-000001297 | IDR 208.2 | HS2-000001297 | 2024-01-31 | 10 - Complete | 2024-02-07 |  | HS2-000031J4L - Waddesdon Embankment Substation | UFDR 211.A - Waddesdon (Thames Water Sewerage/BT Openreach/UKPN) | UFDR 211.A | HS2-000031J4L | 2024-12-12 | 10 - Complete | 2024-12-16
208.2 | HS2-00002BVFF | IDR 208.2 | HS2-00002BVFF | 2024-01-31 | 10 - Complete | 2024-02-07 |  | HS2-00003KFPK - Waddesdon Sewage Treatment Water Supply | UFDR 211.A - Waddesdon (Thames Water Sewerage/BT Openreach/UKPN) | UFDR 211.A | HS2-00003KFPK | 2024-12-03 | 10 - Complete | 2024-12-12
208.2 | HS2-00002SZLX | IDR 208.2 | HS2-00002SZLX | 2024-10-29 | 30 - Sent back to team | 0 |  | HS2-00003KUMA - WAD-3 Sub-station Access Road | UFDR 211.A - Waddesdon (Thames Water Sewerage/BT Openreach/UKPN) | UFDR 211.A | HS2-00003KUMA | 2024-12-12 | 10 - Complete | 2024-12-13
UFDR 229.A | HS2-00002CTFG | UFDR 229.A | HS2-00002CTFG | 2024-02-01 | 10 - Complete | 2024-02-02 |  | HS2-000020CF6 - CSO-02-1214 | UFDR 210.C - Thame Valley (UKPN 1214) | UFDR 210.C | HS2-000020CF6 | #N/A | #N/A | #N/A
237.02 | HS2-00003GSK0 | IDR 237.02 | HS2-00003GSK0 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-000020CF7 - CSO-02-2204 | UFDR 210.B - A41 Bicester Road (Thames Water Openreach SGN Vodafone) | UFDR 210.B | HS2-000020CF7 | 2024-05-03 | 10 - Complete | 2024-05-14
237.02 | HS2-00003GSK1 | IDR 237.02 | HS2-00003GSK1 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-000020CF8 - CSO-02-3301 | UFDR 210.B - A41 Bicester Road (Thames Water Openreach SGN Vodafone) | UFDR 210.B | HS2-000020CF8 | 2024-02-16 | 10 - Complete | 2024-02-20
237.02 | HS2-00003GSK2 | IDR 237.02 | HS2-00003GSK2 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-00002TMEJ - Putlowes ATS Telecoms | UFDR 210.B - A41 Bicester Road (Thames Water Openreach SGN Vodafone) | UFDR 210.B | HS2-00002TMEJ | 2024-02-15 | 10 - Complete | 2024-02-19
237.02 | HS2-00003GSK3 | IDR 237.02 | HS2-00003GSK3 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-000020CF9 - CSO-02-3113 | UFDR 210.B - A41 Bicester Road (Thames Water Openreach SGN Vodafone) | UFDR 210.B | HS2-000020CF9 | 2025-01-27 | 10 - Complete | 2025-01-29
237.02 | HS2-00003GSK4 | IDR 237.02 | HS2-00003GSK4 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-000020CFA - CSO-02-3114P | UFDR 210.B - A41 Bicester Road (Thames Water Openreach SGN Vodafone) | UFDR 210.B | HS2-000020CFA | 2025-01-27 | 10 - Complete | 2025-01-29
237.02 | HS2-00003GSK5 | IDR 237.02 | HS2-00003GSK5 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-000020CFB - CSO-02-6212P | UFDR 210.B - A41 Bicester Road (Thames Water Openreach SGN Vodafone) | UFDR 210.B | HS2-000020CFB | 2024-05-23 | 10 - Complete | 2024-05-28
228 | HS2-00002NNHX | IDR 228 | HS2-00002NNHX | 2024-02-01 | 10 - Complete | 2024-02-16 |  | HS2-00002TU6N - C23-069-0002 | UFDR 210.B - A41 Bicester Road (Thames Water Openreach SGN Vodafone) | UFDR 210.B | HS2-00002TU6N | 2025-01-17 | 10 - Complete | 2025-01-20
228 | HS2-00003B2GL | IDR 228 | HS2-00003B2GL | 2024-02-01 | 10 - Complete | 2024-02-12 |  | HS2-00002V04E - C23-068-001 | UFDR 210.B - A41 Bicester Road (Thames Water Openreach SGN Vodafone) | UFDR 210.B | HS2-00002V04E | 2025-01-23 | 10 - Complete | 2025-01-28
228 | HS2-00003B2GM | IDR 228 | HS2-00003B2GM | 2024-02-01 | 10 - Complete | 2024-02-09 |  | HS2-00002ZH4F - C23-069-003 | UFDR 210.B - A41 Bicester Road (Thames Water Openreach SGN Vodafone) | UFDR 210.B | HS2-00002ZH4F | 2025-02-03 | 10 - Complete | 2025-02-17
228 | HS2-00003B2GN | IDR 228 | HS2-00003B2GN | 2024-02-01 | 10 - Complete | 2024-02-09 |  | HS2-000020CF5 - CSO-02-6211 | UFDR 210.A - Thame Valley (Thames Water Main 6211) | UFDR 210.A | HS2-000020CF5 | #N/A | #N/A | #N/A
228 | HS2-00003B2GP | IDR 228 | HS2-00003B2GP | 2024-02-01 | 10 - Complete | 2024-02-09 |  | HS2-000020CF3 - CSO-02-1212 | UFDR 209.C - Thame Valley (UKPN 1212) | UFDR 209.C | HS2-000020CF3 | #N/A | #N/A | #N/A
228 | HS2-00003B2GQ | IDR 228 | HS2-00003B2GQ | 2024-02-01 | 10 - Complete | 2024-02-09 |  | HS2-000020CF4 - CSO-02-1213HV | UFDR 209.B - Thame Valley (UKPN 1213) with Substation | UFDR 209.B | HS2-000020CF4 | #N/A | #N/A | #N/A
228 | HS2-00003B2GR | IDR 228 | HS2-00003B2GR | 2024-02-01 | 10 - Complete | 2024-02-13 |  | HS2-00002CT63 - CSO-02-1213LV | UFDR 209.B - Thame Valley (UKPN 1213) with Substation | UFDR 209.B | HS2-00002CT63 | #N/A | #N/A | #N/A
228 | HS2-00003B2GS | IDR 228 | HS2-00003B2GS | 2024-02-01 | 10 - Complete | 2024-02-09 |  | HS2-00002SZLU - Thame Valley UKPN Substation | UFDR 209.B - Thame Valley (UKPN 1213) with Substation | UFDR 209.B | HS2-00002SZLU | #N/A | #N/A | #N/A
228 | HS2-00003B2GT | IDR 228 | HS2-00003B2GT | 2024-02-01 | 10 - Complete | 2024-02-09 |  | HS2-000020CF0 - CSO-02-6209b | UFDR 209.A - Thame Valley Oxford Road (Thames Water Main 6209/6210) | UFDR 209.A | HS2-000020CF0 | 2024-11-19 | 10 - Complete | 2024-12-02
228 | HS2-00003B2GU | IDR 228 | HS2-00003B2GU | 2024-02-01 | 10 - Complete | 2024-02-09 |  | HS2-00002SZLY - CSO-02-6209a | UFDR 209.A - Thame Valley Oxford Road (Thames Water Main 6209/6210) | UFDR 209.A | HS2-00002SZLY | 2025-03-26 | 10 - Complete | 2025-03-27
228 | HS2-00003B2GV | IDR 228 | HS2-00003B2GV | 2024-02-01 | 10 - Complete | 2024-02-09 |  | HS2-000020CF1 - CSO-02-6210 | UFDR 209.A - Thame Valley Oxford Road (Thames Water Main 6209/6210) | UFDR 209.A | HS2-000020CF1 | 2025-03-25 | 10 - Complete | 2025-03-27
228 | HS2-00003B2GW | IDR 228 | HS2-00003B2GW | 2024-02-01 | 10 - Complete | 2024-02-09 |  | HS2-00002TMEH - Sedrup EFATS Telecoms | UFDR 208.C - Sedrup EFATS | UFDR 208.C | HS2-00002TMEH | #N/A | #N/A | #N/A
228 | HS2-00003B2GX | IDR 228 | HS2-00003B2GX | 2024-02-01 | 10 - Complete | 2024-02-09 |  | HS2-000020BTC - Sedrup EFATS | UFDR 208.C - Sedrup EFATS | UFDR 208.C | HS2-000020BTC | #N/A | #N/A | #N/A
228 | HS2-00003B2GY | IDR 228 | HS2-00003B2GY | 2024-02-01 | 10 - Complete | 2024-02-09 |  | HS2-00002FE9F - C23-062-0002 | UFDR 208.B - Access Track/A418 (UKPN 0001, BT Openreach 3112/0002, SGN 2203) | UFDR 208.B | HS2-00002FE9F | #N/A | #N/A | #N/A
228 | HS2-00003B2GZ | IDR 228 | HS2-00003B2GZ | 2024-02-01 | 10 - Complete | 2024-02-09 |  | HS2-00002BVP9 - C23-062-0001 | UFDR 208.B - Access Track/A418 (UKPN 0001, BT Openreach 3112/0002, SGN 2203) | UFDR 208.B | HS2-00002BVP9 | #N/A | #N/A | #N/A
228 | HS2-00003B2H0 | IDR 228 | HS2-00003B2H0 | 2024-02-01 | 10 - Complete | 2024-02-09 |  | HS2-000020CEY - CSO-02-2203 | UFDR 208.B - Access Track/A418 (UKPN 0001, BT Openreach 3112/0002, SGN 2203) | UFDR 208.B | HS2-000020CEY | 2024-04-16 | 10 - Complete | 2024-04-23
228 | HS2-00003B2H1 | IDR 228 | HS2-00003B2H1 | 2024-02-01 | 10 - Complete | 2024-02-13 |  | HS2-000020CEZ - CSO-02-3112 | UFDR 208.B - Access Track/A418 (UKPN 0001, BT Openreach 3112/0002, SGN 2203) | UFDR 208.B | HS2-000020CEZ | #N/A | #N/A | #N/A
208.2 | HS2-00003GNA7 | IDR 208.2 | HS2-00003GNA7 | 2024-02-01 | 10 - Complete | 2024-02-06 |  | HS2-000020CEX - CSO-02-1211LVP | UFDR 208.A - Access Track/A418 (UKPN 1211) with Substation | UFDR 208.A | HS2-000020CEX | 2024-07-16 | 10 - Complete | 2024-07-26
208.2 | HS2-00003GNA8 | IDR 208.2 | HS2-00003GNA8 | 2024-02-01 | 10 - Complete | 2024-02-06 |  | HS2-0000245Z0 - CSO-02-1211HVP | UFDR 208.A - Access Track/A418 (UKPN 1211) with Substation | UFDR 208.A | HS2-0000245Z0 | 2024-07-16 | 10 - Complete | 2024-07-26
UFDR 224.H | HS2-000020CHA | UFDR 224.H | HS2-000020CHA | 2024-02-02 | 10 - Complete | 2024-02-07 |  | HS2-00002SZLS - Hartwell Cottages UKPN Substation | UFDR 208.A - Access Track/A418 (UKPN 1211) with Substation | UFDR 208.A | HS2-00002SZLS | 2024-07-16 | 10 - Complete | 2024-07-30
238.01 | HS2-00003DL20 | IDR 238.01 | HS2-00003DL20 | 2024-02-02 | 10 - Complete | 2024-02-07 |  | HS2-000020CEQ - CSO-02-1208 | UFDR 205.B - Aylesbury (UKPN 1208/1209/1210) with Substation | UFDR 205.B | HS2-000020CEQ | 2024-09-06 | 99 - Cancelled | 0
238.01 | HS2-00003DL21 | IDR 238.01 | HS2-00003DL21 | 2024-02-02 | 10 - Complete | 2024-02-07 |  | HS2-00002SXNK - Aylesbury South UKPN Substation | UFDR 205.B - Aylesbury (UKPN 1208/1209/1210) with Substation | UFDR 205.B | HS2-00002SXNK | 2024-09-06 | 99 - Cancelled | 0
238.01 | HS2-00003DL22 | IDR 238.01 | HS2-00003DL22 | 2024-02-02 | 10 - Complete | 2024-02-07 |  | HS2-000020CET - CSO-02-1209 | UFDR 205.B - Aylesbury (UKPN 1208/1209/1210) with Substation | UFDR 205.B | HS2-000020CET | 2024-09-06 | 99 - Cancelled | 0
218.01-2 | HS2-000033GN1 | IDR 218.01-2 | HS2-000033GN1 | 2024-02-05 | 10 - Complete | 2024-02-08 |  | HS2-000020CEU - CSO-02-1210 | UFDR 205.B - Aylesbury (UKPN 1208/1209/1210) with Substation | UFDR 205.B | HS2-000020CEU | 2024-09-06 | 99 - Cancelled | 0
204.4-1 | HS2-00002CT2R | IDR 204.4-1 | HS2-00002CT2R | 2024-02-05 | 10 - Complete | 2024-02-13 |  | HS2-000020CEN - CSO-02-6207 | UFDR 205.A - Aylesbury (Thames Water Main 6207/6208/6214) | UFDR 205.A | HS2-000020CEN | #N/A | #N/A | #N/A
204.4-1 | HS2-00002CT2W | IDR 204.4-1 | HS2-00002CT2W | 2024-02-05 | 10 - Complete | 2024-02-14 |  | HS2-000020CER - CSO-02-6214 | UFDR 205.A - Aylesbury (Thames Water Main 6207/6208/6214) | UFDR 205.A | HS2-000020CER | #N/A | #N/A | #N/A
204.4-1 | HS2-00002CT30 | IDR 204.4-1 | HS2-00002CT30 | 2024-02-05 | 10 - Complete | 2023-02-13 |  | HS2-000020CES - CSO-02-6208 | UFDR 205.A - Aylesbury (Thames Water Main 6207/6208/6214) | UFDR 205.A | HS2-000020CES | #N/A | #N/A | #N/A
235.01 | HS2-00002CX3F | IDR 235.01 | HS2-00002CX3F | 2024-02-05 | 10 - Complete | 2024-02-13 |  | HS2-000020CEE - CSO-02-2201 | UFDR 204.E - Stoke Mandeville (BT Openreach 3109/3110, Vodafone 3300, SGN 2201) | UFDR 204.E | HS2-000020CEE | 2024-03-08 | 10 - Complete | 2024-03-13
229.03 | HS2-00002N7UB | IDR 229.03 | HS2-00002N7UB | 2024-05-14 | 10 - Complete | 2024-05-17 |  | HS2-000020CEF - CSO-02-3300 | UFDR 204.E - Stoke Mandeville (BT Openreach 3109/3110, Vodafone 3300, SGN 2201) | UFDR 204.E | HS2-000020CEF | 2024-03-08 | 10 - Complete | 2024-03-13
UFDR 232.B | HS2-000020CJG | UFDR 232.B | HS2-000020CJG | 2024-02-13 | 10 - Complete | 2024-02-16 |  | HS2-000020CEG - CSO-02-3109 | UFDR 204.E - Stoke Mandeville (BT Openreach 3109/3110, Vodafone 3300, SGN 2201) | UFDR 204.E | HS2-000020CEG | 2024-03-08 | 10 - Complete | 2024-03-13
224.4 | HS2-000033GP4 | IDR 224.4 | HS2-000033GP4 | 2024-02-06 | 10 - Complete | 2024-02-08 |  | HS2-000020CEH - CSO-02-3110 | UFDR 204.E - Stoke Mandeville (BT Openreach 3109/3110, Vodafone 3300, SGN 2201) | UFDR 204.E | HS2-000020CEH | 2024-03-08 | 10 - Complete | 2024-03-13
237.05 | HS2-00003D82S | IDR 237.05 | HS2-00003D82S | 2024-07-25 | 10 - Complete | 2024-08-02 |  | HS2-000020CEM - CSO-02-3111 | UFDR 204.C - Marsh Lane (BT Openreach 3111) | UFDR 204.C | HS2-000020CEM | #N/A | #N/A | #N/A
235.01 | HS2-000020NZW | IDR 235.01 | HS2-000020NZW | 2024-02-07 | 10 - Complete | 2024-02-13 |  | HS2-000020CEJ - CSO-02-6205 | UFDR 204.B - Stoke Mandeville (Thames Water Main 6205/6206/6215, Sewerage 7201) | UFDR 204.B | HS2-000020CEJ | 2024-08-22 | 10 - Complete | 2024-09-04
237.05-2 | HS2-000001460 | IDR 237.05-2 | HS2-000001460 | 2024-02-08 | 10 - Complete | 2024-02-23 |  | HS2-000020CEK - CSO-02-6206 | UFDR 204.B - Stoke Mandeville (Thames Water Main 6205/6206/6215, Sewerage 7201) | UFDR 204.B | HS2-000020CEK | 2024-08-22 | 10 - Complete | 2024-09-04
238.01 | HS2-00002CTK7 | IDR 238.01 | HS2-00002CTK7 | 2024-09-06 | 10 - Complete | 2024-09-25 |  | HS2-000020CEL - CSO-02-7201 | UFDR 204.B - Stoke Mandeville (Thames Water Main 6205/6206/6215, Sewerage 7201) | UFDR 204.B | HS2-000020CEL | 2024-08-01 | 10 - Complete | 2024-09-03
238.01 | HS2-00002CTK8 | IDR 238.01 | HS2-00002CTK8 | 2024-09-06 | 10 - Complete | 2024-09-30 |  | HS2-000020CEB - CSO-02-3108P | UFDR 204.A - Nash Lee Road Overbridge (UKPN 1206 t&P, 1224, 1207, Thames Water 6204, BT Openreach 3108P) | UFDR 204.A | HS2-000020CEB | 2024-03-05 | 10 - Complete | 2024-03-07
238.01 | HS2-00002TG2Q | IDR 238.01 | HS2-00002TG2Q | 2024-02-08 | 10 - Complete | 2024-02-20 |  | HS2-000020CEC - CSO-02-1207 | UFDR 204.A - Nash Lee Road Overbridge (UKPN 1206 t&P, 1224, 1207, Thames Water 6204, BT Openreach 3108P) | UFDR 204.A | HS2-000020CEC | 2024-03-19 | 10 - Complete | 2024-03-21
213.06 | HS2-00002CW0Z | IDR 213.06 | HS2-00002CW0Z | 2024-02-08 | 10 - Complete | 2024-02-14 |  | HS2-000020CED - CSO-02-6204 | UFDR 204.A - Nash Lee Road Overbridge (UKPN 1206 t&P, 1224, 1207, Thames Water 6204, BT Openreach 3108P) | UFDR 204.A | HS2-000020CED | 2024-02-28 | 10 - Complete | 2024-02-29
204.3 | HS2-000001288 | IDR 204.3 | HS2-000001288 | 2024-02-08 | 10 - Complete | 2024-02-22 |  | HS2-00002TMEM - Wendover ATS Telecoms | UFDR 203.F - Permanent Connections | UFDR 203.F | HS2-00002TMEM | 2024-01-09 | 10 - Complete | 2024-01-18
204.3 | HS2-00002SZLW | IDR 204.3 | HS2-00002SZLW | 2024-02-08 | 10 - Complete | 2024-02-25 |  | HS2-00002TMET - Stoke Grove ATS Telecoms | UFDR 203.F - Permanent Connections | UFDR 203.F | HS2-00002TMET | 2024-01-09 | 10 - Complete | 2024-01-18
UFDR 228.F | HS2-00003CFCL | UFDR 228.F | HS2-00003CFCL | 2024-04-08 | 10 - Complete | 2024-04-09 |  | HS2-00002CT3W - CSO-02-6202T | UFDR 203.E - Bacombe Lane / Ellesborough Road [Utilities Bridge](Thames (M) 6202T/6203T, Thames (S) 7200T, 3106T) | UFDR 203.E | HS2-00002CT3W | 2024-01-30 | 10 - Complete | 2024-02-01
237.02 | HS2-00002WUS2 | IDR 237.02 | HS2-00002WUS2 | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002CT46 - CSO-02-7200T | UFDR 203.E - Bacombe Lane / Ellesborough Road [Utilities Bridge](Thames (M) 6202T/6203T, Thames (S) 7200T, 3106T) | UFDR 203.E | HS2-00002CT46 | 2024-02-16 | 10 - Complete | 2024-02-19
237.02 | HS2-00002WUS3 | IDR 237.02 | HS2-00002WUS3 | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002FG43 - CSO-02-6203T | UFDR 203.E - Bacombe Lane / Ellesborough Road [Utilities Bridge](Thames (M) 6202T/6203T, Thames (S) 7200T, 3106T) | UFDR 203.E | HS2-00002FG43 | 2024-01-30 | 10 - Complete | 2024-02-01
237.02 | HS2-00002WUS4 | IDR 237.02 | HS2-00002WUS4 | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002CT44 - C23-054-0001T | UFDR 203.D - Bacombe Lane / Ellesborough Road [Road Bridge] inc. CE-4 UK Power Networks - Substation & transformer design works. (UKPN 1107T/1204T/1205T/1223T/0001, BT 3107T, Virgin 0001T, SGN 2200T) | UFDR 203.D | HS2-00002CT44 | #N/A | #N/A | #N/A
237.02 | HS2-00002WUS5 | IDR 237.02 | HS2-00002WUS5 | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002CT43 - CSO-02-3107T | UFDR 203.D - Bacombe Lane / Ellesborough Road [Road Bridge] inc. CE-4 UK Power Networks - Substation & transformer design works. (UKPN 1107T/1204T/1205T/1223T/0001, BT 3107T, Virgin 0001T, SGN 2200T) | UFDR 203.D | HS2-00002CT43 | #N/A | #N/A | #N/A
237.02 | HS2-00002WUS6 | IDR 237.02 | HS2-00002WUS6 | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002CT45 - CSO-02-2200T | UFDR 203.D - Bacombe Lane / Ellesborough Road [Road Bridge] inc. CE-4 UK Power Networks - Substation & transformer design works. (UKPN 1107T/1204T/1205T/1223T/0001, BT 3107T, Virgin 0001T, SGN 2200T) | UFDR 203.D | HS2-00002CT45 | #N/A | #N/A | #N/A
237.02 | HS2-00002WUS7 | IDR 237.02 | HS2-00002WUS7 | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002CT3X - CSO-02-1204HVT | UFDR 203.D - Bacombe Lane / Ellesborough Road [Road Bridge] inc. CE-4 UK Power Networks - Substation & transformer design works. (UKPN 1107T/1204T/1205T/1223T/0001, BT 3107T, Virgin 0001T, SGN 2200T) | UFDR 203.D | HS2-00002CT3X | #N/A | #N/A | #N/A
237.02 | HS2-00002WURR | IDR 237.02 | HS2-00002WURR | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002CT3Y - CSO-02-1204LVT | UFDR 203.D - Bacombe Lane / Ellesborough Road [Road Bridge] inc. CE-4 UK Power Networks - Substation & transformer design works. (UKPN 1107T/1204T/1205T/1223T/0001, BT 3107T, Virgin 0001T, SGN 2200T) | UFDR 203.D | HS2-00002CT3Y | #N/A | #N/A | #N/A
237.02 | HS2-00002WURS | IDR 237.02 | HS2-00002WURS | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002SZLQ - Ellesborough Road 1 UKPN Substation | UFDR 203.D - Bacombe Lane / Ellesborough Road [Road Bridge] inc. CE-4 UK Power Networks - Substation & transformer design works. (UKPN 1107T/1204T/1205T/1223T/0001, BT 3107T, Virgin 0001T, SGN 2200T) | UFDR 203.D | HS2-00002SZLQ | #N/A | #N/A | #N/A
237.02 | HS2-00002WURT | IDR 237.02 | HS2-00002WURT | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002SZLR - Ellesborough Road 2 Pad UKPN Substation | UFDR 203.D - Bacombe Lane / Ellesborough Road [Road Bridge] inc. CE-4 UK Power Networks - Substation & transformer design works. (UKPN 1107T/1204T/1205T/1223T/0001, BT 3107T, Virgin 0001T, SGN 2200T) | UFDR 203.D | HS2-00002SZLR | #N/A | #N/A | #N/A
237.02 | HS2-00002WURU | IDR 237.02 | HS2-00002WURU | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002TTL2 - C23-054-0002 | UFDR 203.D - Bacombe Lane / Ellesborough Road [Road Bridge] inc. CE-4 UK Power Networks - Substation & transformer design works. (UKPN 1107T/1204T/1205T/1223T/0001, BT 3107T, Virgin 0001T, SGN 2200T) | UFDR 203.D | HS2-00002TTL2 | #N/A | #N/A | #N/A
237.02 | HS2-00002WURV | IDR 237.02 | HS2-00002WURV | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-000020CE6 - CSO-02-1205P | UFDR 203.D - Bacombe Lane / Ellesborough Road [Road Bridge] inc. CE-4 UK Power Networks - Substation & transformer design works. (UKPN 1107T/1204T/1205T/1223T/0001, BT 3107T, Virgin 0001T, SGN 2200T) | UFDR 203.D | HS2-000020CE6 | #N/A | #N/A | #N/A
237.02 | HS2-00002WURW | IDR 237.02 | HS2-00002WURW | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002CT41 - CSO-02-1107T | UFDR 203.D - Bacombe Lane / Ellesborough Road [Road Bridge] inc. CE-4 UK Power Networks - Substation & transformer design works. (UKPN 1107T/1204T/1205T/1223T/0001, BT 3107T, Virgin 0001T, SGN 2200T) | UFDR 203.D | HS2-00002CT41 | #N/A | #N/A | #N/A
237.02 | HS2-00002WURX | IDR 237.02 | HS2-00002WURX | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-000020CE0 - CSO-02-6202P | UFDR 203.C - Ellesborough Road (BT Openreach 3107P, UKPN 1107P/1204LVP/1205P/1204HVP, SGN 2200P, VM 0001P, Thames Water Main 6202P/6203P & Thames Water Sewerage 7200P) | UFDR 203.C | HS2-000020CE0 | #N/A | #N/A | #N/A
237.02 | HS2-00002WURY | IDR 237.02 | HS2-00002WURY | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002NHZ8 - C23-053-0001P | UFDR 203.C - Ellesborough Road (BT Openreach 3107P, UKPN 1107P/1204LVP/1205P/1204HVP, SGN 2200P, VM 0001P, Thames Water Main 6202P/6203P & Thames Water Sewerage 7200P) | UFDR 203.C | HS2-00002NHZ8 | #N/A | #N/A | #N/A
237.02 | HS2-00002WURZ | IDR 237.02 | HS2-00002WURZ | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002BVP1 - C23-054-0001P | UFDR 203.C - Ellesborough Road (BT Openreach 3107P, UKPN 1107P/1204LVP/1205P/1204HVP, SGN 2200P, VM 0001P, Thames Water Main 6202P/6203P & Thames Water Sewerage 7200P) | UFDR 203.C | HS2-00002BVP1 | #N/A | #N/A | #N/A
237.02 | HS2-00002WUS0 | IDR 237.02 | HS2-00002WUS0 | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-000020CE1 - CSO-02-2200P | UFDR 203.C - Ellesborough Road (BT Openreach 3107P, UKPN 1107P/1204LVP/1205P/1204HVP, SGN 2200P, VM 0001P, Thames Water Main 6202P/6203P & Thames Water Sewerage 7200P) | UFDR 203.C | HS2-000020CE1 | #N/A | #N/A | #N/A
237.02 | HS2-00002WUS1 | IDR 237.02 | HS2-00002WUS1 | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-000020CE2 - CSO-02-3107P | UFDR 203.C - Ellesborough Road (BT Openreach 3107P, UKPN 1107P/1204LVP/1205P/1204HVP, SGN 2200P, VM 0001P, Thames Water Main 6202P/6203P & Thames Water Sewerage 7200P) | UFDR 203.C | HS2-000020CE2 | #N/A | #N/A | #N/A
237.02 | HS2-00002WUS8 | IDR 237.02 | HS2-00002WUS8 | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-000020CE3 - CSO-02-6203P | UFDR 203.C - Ellesborough Road (BT Openreach 3107P, UKPN 1107P/1204LVP/1205P/1204HVP, SGN 2200P, VM 0001P, Thames Water Main 6202P/6203P & Thames Water Sewerage 7200P) | UFDR 203.C | HS2-000020CE3 | #N/A | #N/A | #N/A
237.02 | HS2-00002WUS9 | IDR 237.02 | HS2-00002WUS9 | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-000020CE4 - CSO-02-7200P | UFDR 203.C - Ellesborough Road (BT Openreach 3107P, UKPN 1107P/1204LVP/1205P/1204HVP, SGN 2200P, VM 0001P, Thames Water Main 6202P/6203P & Thames Water Sewerage 7200P) | UFDR 203.C | HS2-000020CE4 | #N/A | #N/A | #N/A
237.02 | HS2-00002WUSA | IDR 237.02 | HS2-00002WUSA | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-000020CE5 - CSO-02-1204HVP | UFDR 203.C - Ellesborough Road (BT Openreach 3107P, UKPN 1107P/1204LVP/1205P/1204HVP, SGN 2200P, VM 0001P, Thames Water Main 6202P/6203P & Thames Water Sewerage 7200P) | UFDR 203.C | HS2-000020CE5 | #N/A | #N/A | #N/A
237.02 | HS2-00002WUSB | IDR 237.02 | HS2-00002WUSB | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002CT3Z - CSO-02-1204LVP | UFDR 203.C - Ellesborough Road (BT Openreach 3107P, UKPN 1107P/1204LVP/1205P/1204HVP, SGN 2200P, VM 0001P, Thames Water Main 6202P/6203P & Thames Water Sewerage 7200P) | UFDR 203.C | HS2-00002CT3Z | #N/A | #N/A | #N/A
237.02 | HS2-00002WUSC | IDR 237.02 | HS2-00002WUSC | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-000020CE7 - CSO-02-1107P | UFDR 203.C - Ellesborough Road (BT Openreach 3107P, UKPN 1107P/1204LVP/1205P/1204HVP, SGN 2200P, VM 0001P, Thames Water Main 6202P/6203P & Thames Water Sewerage 7200P) | UFDR 203.C | HS2-000020CE7 | #N/A | #N/A | #N/A
237.02 | HS2-00002WUSD | IDR 237.02 | HS2-00002WUSD | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002NHZ7 - CSO-02-1223LVP | UFDR 203.B - Bacombe Lane / Ellesborough Road 1223LVP, 3106P) | UFDR 203.B | HS2-00002NHZ7 | #N/A | #N/A | #N/A
237.02 | HS2-00002WUSE | IDR 237.02 | HS2-00002WUSE | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-000020CDZ - CSO-02-3106P | UFDR 203.B - Bacombe Lane / Ellesborough Road 1223LVP, 3106P) | UFDR 203.B | HS2-000020CDZ | #N/A | #N/A | #N/A
237.02 | HS2-00002WUSF | IDR 237.02 | HS2-00002WUSF | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-000020CDR - CSO-02-3102 | UFDR 202.E - Small Dean Viaduct Remaining (BT Openreach 3102, BT Openreach 3104P, TWUL 6201P) | UFDR 202.E | HS2-000020CDR | 2024-06-07 | 10 - Complete | 2024-07-04
237.02 | HS2-00002WUSG | IDR 237.02 | HS2-00002WUSG | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002NHZ4 - CSO-02-6201P | UFDR 202.E - Small Dean Viaduct Remaining (BT Openreach 3102, BT Openreach 3104P, TWUL 6201P) | UFDR 202.E | HS2-00002NHZ4 | 2024-06-07 | 10 - Complete | 2024-06-21
237.02 | HS2-00002WUSH | IDR 237.02 | HS2-00002WUSH | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-00002NHZ6 - CSO-02-3104P | UFDR 202.E - Small Dean Viaduct Remaining (BT Openreach 3102, BT Openreach 3104P, TWUL 6201P) | UFDR 202.E | HS2-00002NHZ6 | 2024-06-07 | 10 - Complete | 2024-07-04
237.02 | HS2-00002WUSJ | IDR 237.02 | HS2-00002WUSJ | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-000020CEA - CSO-02-1206P | UFDR 202.E - Small Dean Viaduct Remaining (BT Openreach 3102, BT Openreach 3104P, TWUL 6201P) | UFDR 202.E | HS2-000020CEA | 2024-08-06 | 10 - Complete | 2024-08-13
237.02 | HS2-00002WUSK | IDR 237.02 | HS2-00002WUSK | 2024-02-09 | 10 - Complete | 2024-02-13 |  | HS2-000020CDS - CSO-02-3103 | UFDR 202.D - Small Dean Viaduct Remaining (BT Openreach 3103, Virgin Media 3200, TWUL 6201 15") | UFDR 202.D | HS2-000020CDS | #N/A | #N/A | #N/A
205.3 | HS2-00002BJS2 | IDR 205.3 | HS2-00002BJS2 | 2024-02-09 | 10 - Complete | 2024-02-19 |  | HS2-000020CDT - CSO-02-3200 | UFDR 202.D - Small Dean Viaduct Remaining (BT Openreach 3103, Virgin Media 3200, TWUL 6201 15") | UFDR 202.D | HS2-000020CDT | #N/A | #N/A | #N/A
UFDR 202.B | HS2-000020CDN | UFDR 202.B | HS2-000020CDN | 2025-01-22 | 10 - Complete | 2025-01-24 |  | HS2-000020CDU - CSO-02-6201 15 inch | UFDR 202.D - Small Dean Viaduct Remaining (BT Openreach 3103, Virgin Media 3200, TWUL 6201 15") | UFDR 202.D | HS2-000020CDU | #N/A | #N/A | #N/A
UFDR 202.B | HS2-000020CDP | UFDR 202.B | HS2-000020CDP | 2024-02-12 | 10 - Complete | 2024-02-16 |  | HS2-00002NHZ5 - CSO-02-6201T | UFDR 202.C - Small Dean Viaduct (UKPN 1223, BT Openreach 3104/3105, Thames Water Mains 6201/3" Water Main) | UFDR 202.C | HS2-00002NHZ5 | #N/A | #N/A | #N/A
UFDR 202.B | HS2-000020CDQ | UFDR 202.B | HS2-000020CDQ | 2025-01-22 | 10 - Complete | 2025-01-24 |  | HS2-000020CDV - CSO-02-3104T | UFDR 202.C - Small Dean Viaduct (UKPN 1223, BT Openreach 3104/3105, Thames Water Mains 6201/3" Water Main) | UFDR 202.C | HS2-000020CDV | #N/A | #N/A | #N/A
UFDR 202.B | HS2-00002CT3A | UFDR 202.B | HS2-00002CT3A | 2025-01-22 | 10 - Complete | 2025-01-24 |  | HS2-000020CDW - CSO-02-1223HV | UFDR 202.C - Small Dean Viaduct (UKPN 1223, BT Openreach 3104/3105, Thames Water Mains 6201/3" Water Main) | UFDR 202.C | HS2-000020CDW | #N/A | #N/A | #N/A
UFDR 202.B | HS2-00002TG2R | UFDR 202.B | HS2-00002TG2R | 2025-01-22 | 10 - Complete | 2025-01-24 |  | HS2-000020CDY - CSO-02-3105 | UFDR 202.C - Small Dean Viaduct (UKPN 1223, BT Openreach 3104/3105, Thames Water Mains 6201/3" Water Main) | UFDR 202.C | HS2-000020CDY | #N/A | #N/A | #N/A
235.01 | HS2-00002TMFD | IDR 235.01 | HS2-00002TMFD | 2024-02-28 | 10 - Complete | 2024-02-29 |  | HS2-00002CTC0 - CSO-03-3105T | UFDR 202.C - Small Dean Viaduct (UKPN 1223, BT Openreach 3104/3105, Thames Water Mains 6201/3" Water Main) | UFDR 202.C | HS2-00002CTC0 | #N/A | #N/A | #N/A
220.3 | HS2-000001320 | IDR 220.3 | HS2-000001320 | 2024-03-26 | 10 - Complete | 2024-04-12 |  | HS2-000020CDN - CSO-02-1203HV | UFDR 202.B - Rocky Lane (UKPN 1203, Thames Water Main 6200, BT Openreach 3101) | UFDR 202.B | HS2-000020CDN | 2025-01-22 | 10 - Complete | 2025-01-24
207.2 | HS2-000032LLR | IDR 207.2 | HS2-000032LLR | 2024-02-12 | 10 - Complete | 2024-02-20 |  | HS2-00002CT3A - CSO-02-1203LV | UFDR 202.B - Rocky Lane (UKPN 1203, Thames Water Main 6200, BT Openreach 3101) | UFDR 202.B | HS2-00002CT3A | 2025-01-22 | 10 - Complete | 2025-01-24
UFDR 232.B | HS2-000020CJG | UFDR 232.B | HS2-000020CJG | 2024-02-13 | 10 - Complete | 2024-02-16 |  | HS2-00002TG2R - Rocky Lane Substation | UFDR 202.B - Rocky Lane (UKPN 1203, Thames Water Main 6200, BT Openreach 3101) | UFDR 202.B | HS2-00002TG2R | 2025-01-22 | 10 - Complete | 2025-01-24
237.02 | HS2-000001096 | IDR 237.02 | HS2-000001096 | 2024-02-13 | 10 - Complete | 2024-02-16 |  | HS2-000020CDP - CSO-02-3101 | UFDR 202.B - Rocky Lane (UKPN 1203, Thames Water Main 6200, BT Openreach 3101) | UFDR 202.B | HS2-000020CDP | 2024-02-12 | 10 - Complete | 2024-02-16
237.02 | HS2-00002BVMV | IDR 237.02 | HS2-00002BVMV | 2024-02-13 | 10 - Complete | 2024-02-16 |  | HS2-000020CDQ - CSO-02-6200 | UFDR 202.B - Rocky Lane (UKPN 1203, Thames Water Main 6200, BT Openreach 3101) | UFDR 202.B | HS2-000020CDQ | 2025-01-22 | 10 - Complete | 2025-01-24
218.02 | HS2-00002D2S2 | IDR 218.02 | HS2-00002D2S2 | 2024-03-28 | 10 - Complete | 2024-04-02 |  | HS2-000020CDL - CSO-02-1202 | UFDR 202.A - Wendover Dean Viaduct (UKPN 1202, BT Openreach 3100) | UFDR 202.A | HS2-000020CDL | #N/A | #N/A | #N/A
235.01-2 | HS2-000001091 | IDR 235.01-2 | HS2-000001091 | 2024-04-03 | 10 - Complete | 2024-04-07 |  | HS2-00002T426 - CSO-02-1200 | UFDR 201.B - South Heath Cutting (UKPN 1200) | UFDR 201.B | HS2-00002T426 | #N/A | #N/A | #N/A
228 | HS2-000001437 | IDR 228 | HS2-000001437 | 2024-02-14 | 10 - Complete | 2024-02-25 |  | HS2-000020CDF - CSO-02-1201 | UFDR 201.A - South Heath Cutting (UKPN 1201/1222) | UFDR 201.A | HS2-000020CDF | #N/A | #N/A | #N/A
228 | HS2-00002CTEC | IDR 228 | HS2-00002CTEC | 2024-02-14 | 10 - Complete | 2024-02-19 |  | HS2-000020CDG - CSO-02-1222HV | UFDR 201.A - South Heath Cutting (UKPN 1201/1222) | UFDR 201.A | HS2-000020CDG | #N/A | #N/A | #N/A
228 | HS2-00002CTEE | IDR 228 | HS2-00002CTEE | 2024-02-14 | 10 - Complete | 2024-02-16 |  | HS2-000020CDK - CSO-02-6300T | UFDR 201.A - South Heath Cutting (UKPN 1201/1222) | UFDR 201.A | HS2-000020CDK | #N/A | #N/A | #N/A
228 | HS2-00002CTEM | IDR 228 | HS2-00002CTEM | 2024-02-14 | 10 - Complete | 2024-02-19 |  | HS2-00002T215 - Lorry Route A41 Bicester Road out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T215 | #N/A | #N/A | #N/A
228 | HS2-00002CTEP | IDR 228 | HS2-00002CTEP | 2024-02-14 | 10 - Complete | 2024-02-15 |  | HS2-00002T217 - Lorry Route FCC Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T217 | #N/A | #N/A | #N/A
205.3 | HS2-000020NBF | IDR 205.3 | HS2-000020NBF | 2024-03-07 10:55 | 10 - Complete | 2024-03-07 12:46 |  | HS2-00002T219 - Lorry Route West Street-Edgcott Route 1 From South to Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T219 | #N/A | #N/A | #N/A
UFDR 210.B | HS2-00002TMEJ | UFDR 210.B | HS2-00002TMEJ | 2024-02-15 | 10 - Complete | 2024-02-19 |  | HS2-00002T21B - Lorry Route West Street-Edgcott Route 2 From North to Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21B | #N/A | #N/A | #N/A
220.3 | HS2-000020NL8 | IDR 220.3 | HS2-000020NL8 | 2024-02-15 | 10 - Complete | 2024-02-21 |  | HS2-00002T21D - Lorry Route West Street-Gawcott Route 1 From South to Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21D | #N/A | #N/A | #N/A
208.2 | HS2-00002CT5P | IDR 208.2 | HS2-00002CT5P | 2024-10-29 | 10 - Complete | 2024-11-12 |  | HS2-00002T21F - Lorry Route West Street-Gawcott Route 2 From North to Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21F | #N/A | #N/A | #N/A
UFDR 210.B | HS2-000020CF8 | UFDR 210.B | HS2-000020CF8 | 2024-02-16 | 10 - Complete | 2024-02-20 |  | HS2-00002T21H - Lorry Route School Hill, Calvert Route 1 From South to Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21H | #N/A | #N/A | #N/A
UFDR 210.B | HS2-000020CF9 | UFDR 210.B | HS2-000020CF9 | 2025-01-27 | 10 - Complete | 2025-01-29 |  | HS2-00002T21K - Lorry Route School Hill, Calvert Route 2 From North to Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21K | #N/A | #N/A | #N/A
UFDR 203.E | HS2-00002CT46 | UFDR 203.E | HS2-00002CT46 | 2024-02-16 | 10 - Complete | 2024-02-19 |  | HS2-00002T214 - Lorry Route A41 Bicester Road in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T214 | #N/A | #N/A | #N/A
237.05 | HS2-00002CX39 | IDR 237.05 | HS2-00002CX39 | 2024-02-16 | 10 - Complete | 2024-02-22 |  | HS2-00002T216 - Lorry Route FCC Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T216 | #N/A | #N/A | #N/A
228 | HS2-00002DVEJ | IDR 228 | HS2-00002DVEJ | 2024-02-16 | 10 - Complete | 2024-02-23 |  | HS2-00002T218 - Lorry Route West Street-Edgcott Route 1 From South to Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T218 | #N/A | #N/A | #N/A
201.4 | HS2-00002CT27 | IDR 201.4 | HS2-00002CT27 | 2024-02-16 | 10 - Complete | 2024-02-22 |  | HS2-00002T21C - Lorry Route West Street-Gawcott Route 1 From South to Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21C | #N/A | #N/A | #N/A
201.4 | HS2-00002CT28 | IDR 201.4 | HS2-00002CT28 | 2024-02-16 | 10 - Complete | 2024-02-22 |  | HS2-00002T21G - Lorry Route School Hill, Calvert Route 1 From South to Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21G | #N/A | #N/A | #N/A
204.3-1 | HS2-00002N7VA | IDR 204.3-1 | HS2-00002N7VA | 2024-02-19 | 10 - Complete | 2024-03-01 |  | HS2-00002T21L - Lorry Route A4421 Buckingham Road From South to Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21L | #N/A | #N/A | #N/A
220.3 | HS2-000020RMA | IDR 220.3 | HS2-000020RMA | 2024-02-19 | 10 - Complete | 2024-02-22 |  | HS2-00002T21Q - Lorry Route A421 London Road From South to Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21Q | #N/A | #N/A | #N/A
220.3 | HS2-00002BJUJ | IDR 220.3 | HS2-00002BJUJ | 2024-02-19 | 10 - Complete | 2024-02-22 |  | HS2-00002T21M - Lorry Route A4421 Buckingham Road From South to Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21M | #N/A | #N/A | #N/A
220.3 | HS2-00002J4YN | IDR 220.3 | HS2-00002J4YN | 2024-02-19 | 10 - Complete | 2024-02-23 |  | HS2-00002T21P - Lorry Route A4421 Buckingham Road From North to Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21P | #N/A | #N/A | #N/A
220.3 | HS2-00002VXUA | IDR 220.3 | HS2-00002VXUA | 2024-02-19 | 10 - Complete | 2024-02-23 |  | HS2-00002T21R - Lorry Route A421 London Road From South to Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21R | #N/A | #N/A | #N/A
220.3 | HS2-00002VXUB | IDR 220.3 | HS2-00002VXUB | 2024-02-19 | 10 - Complete | 2024-02-25 |  | HS2-00002T21T - Lorry Route A421 London Road From North to Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21T | #N/A | #N/A | #N/A
205.3 | HS2-00002N7VN | IDR 205.3 | HS2-00002N7VN | 2024-02-19 | 10 - Complete | 2024-02-20 |  | HS2-00002T21N - Lorry Route A4421 Buckingham Road From North to Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21N | #N/A | #N/A | #N/A
230.01-2 | HS2-00002CTFU | IDR 230.01-2 | HS2-00002CTFU | 2024-02-20 | 10 - Complete | 2024-02-22 |  | HS2-00002T21S - Lorry Route A421 London Road From North to Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21S | #N/A | #N/A | #N/A
201.0-1 | HS2-000001016 | IDR 201.0-1 | HS2-000001016 | 2024-11-15 | 10 - Complete | 2024-11-29 |  | HS2-00002T21A - Lorry Route West Street-Edgcott Route 2 From North to Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21A | #N/A | #N/A | #N/A
205.3 | HS2-000001292 | IDR 205.3 | HS2-000001292 | 2024-02-20 | 10 - Complete | 2024-02-21 |  | HS2-00002T21E - Lorry Route West Street-Gawcott Route 2 From North to Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21E | #N/A | #N/A | #N/A
205.3 | HS2-00002BJSA | IDR 205.3 | HS2-00002BJSA | 2024-02-20 | 10 - Complete | 2024-02-22 |  | HS2-00002T21J - Lorry Route School Hill, Calvert Route 2 From North to Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21J | #N/A | #N/A | #N/A
237.05-3 | HS2-000001461 | IDR 237.05-3 | HS2-000001461 | 2024-02-21 | 10 - Complete | 2024-02-23 |  | HS2-00002T21W - Lorry Route Greatworth Green Tunnel Route 2 From West to Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21W | #N/A | #N/A | #N/A
238.01 | HS2-000001100 | IDR 238.01 | HS2-000001100 | 2024-02-21 | 10 - Complete | 2024-02-27 |  | HS2-00002T21V - Lorry Route Greatworth Green Tunnel Route 1 From East to Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21V | #N/A | #N/A | #N/A
238.01 | HS2-00002BVNA | IDR 238.01 | HS2-00002BVNA | 2024-02-21 | 10 - Complete | 2024-02-28 |  | HS2-00002T21Z - Lorry Route Greatworth Green Tunnel Route 2 From West to Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21Z | #N/A | #N/A | #N/A
228 | HS2-000001069 | IDR 228 | HS2-000001069 | 2024-02-21 | 10 - Complete | 2024-02-23 |  | HS2-00002T21U - Lorry Route Greatworth Green Tunnel Route 1 From East to Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21U | #N/A | #N/A | #N/A
205.3 | HS2-00002N7VF | IDR 205.3 | HS2-00002N7VF | 2024-02-21 | 10 - Complete | 2024-02-22 |  | HS2-00002T21X - Lorry Route Chipping Warden Compound in | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21X | #N/A | #N/A | #N/A
UFDR 226.A | HS2-000020CHF | UFDR 226.A | HS2-000020CHF | 2024-02-23 | 10 - Complete | 2024-02-27 |  | HS2-00002T21Y - Lorry Route Chipping Warden Compound out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002T21Y | #N/A | #N/A | #N/A
215.02-02 | HS2-00002BJU3 | IDR 215.02-02 | HS2-00002BJU3 | 2025-01-29 | 10 - Complete | 2025-02-10 |  | HS2-00002YNGE - Lorry Route A418 Oxford Road Overbridge Compound From A418 Oxford Road In | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGE | #N/A | #N/A | #N/A
215.02-02 | HS2-00002CT8Y | IDR 215.02-02 | HS2-00002CT8Y | 2025-01-29 | 10 - Complete | 2025-02-12 |  | HS2-00002YNGF - Lorry Route A418 Oxford Road Overbridge Compound From A418 Oxford Road Out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGF | #N/A | #N/A | #N/A
216.01 | HS2-00002CT8T | IDR 216.01 | HS2-00002CT8T | 2025-05-30 | 10 - Complete | 2025-06-04 |  | HS2-00002YNGG - Lorry Route Stoneton Lane Green Overbridge From Stoneton Lane Wormleighton In | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGG | #N/A | #N/A | #N/A
205.03 | HS2-000001289 | IDR 205.03 | HS2-000001289 | 2024-03-01 | 10 - Complete | 2024-03-04 |  | HS2-00002YNGH - Lorry Route Stoneton Lane Green Overbridge From Stoneton Lane Wormleighton Out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGH | #N/A | #N/A | #N/A
229.03 | HS2-00003B2GH | IDR 229.03 | HS2-00003B2GH | 2024-02-26 | 10 - Complete | 2024-02-28 |  | HS2-00002YNGJ - Lorry Route A423 Banbury Road Overbridge Compound From A423 Banbury Road Southam In | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGJ | #N/A | #N/A | #N/A
207.2 | HS2-00003BPJG | IDR 207.2 | HS2-00003BPJG | 2024-02-26 | 10 - Complete | 2024-02-28 |  | HS2-00002YNGK - Lorry Route A423 Banbury Road Overbridge Compound From A423 Banbury Road Southam Out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGK | #N/A | #N/A | #N/A
UFDR 204.A | HS2-000020CED | UFDR 204.A | HS2-000020CED | 2024-02-28 | 10 - Complete | 2024-02-29 |  | HS2-00002YNGL - Lorry Route Wendover Green Tunnel (North portal) Compound From Wendover Green Tunnel North Portal In | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGL | #N/A | #N/A | #N/A
210.2-2 | HS2-000001299 | IDR 210.2-2 | HS2-000001299 | 2024-03-21 | 10 - Complete | 2024-04-09 |  | HS2-00002YNGM - Lorry Route Wendover Green Tunnel (North portal) Compound From Wendover Green Tunnel North Portal Out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGM | #N/A | #N/A | #N/A
204.3-1 | HS2-00002BJS0 | IDR 204.3-1 | HS2-00002BJS0 | 2024-02-28 | 10 - Complete | 2024-03-05 |  | HS2-00002YNGN - Lorry Route Station Road Overbridge Compound From Station Road Quainton In | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGN | #N/A | #N/A | #N/A
237.05 | HS2-00002BVN5 | IDR 237.05 | HS2-00002BVN5 | 2024-02-28 | 10 - Complete | 2024-03-01 |  | HS2-00002YNGP - Lorry Route Station Road Overbridge Compound From Station Road Quainton Out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGP | #N/A | #N/A | #N/A
235.01 | HS2-00002TMFD | IDR 235.01 | HS2-00002TMFD | 2024-02-28 | 10 - Complete | 2024-02-29 |  | HS2-00002YNGQ - Lorry Route A422 Brackley Road Overbridge North Compound From Brackley Road South Compound Turweston In | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGQ | #N/A | #N/A | #N/A
234.02 | HS2-00002CTHS | IDR 234.02 | HS2-00002CTHS | 2024-02-28 | 10 - Complete | 2024-02-28 |  | HS2-00002YNGR - Lorry Route A422 Brackley Road Overbridge North Compound From Brackley Road South Compound Turweston Out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGR | #N/A | #N/A | #N/A
228.1 | HS2-00003BPM6 | IDR 228.1 | HS2-00003BPM6 | 2024-02-28 | 10 - Complete | 2024-03-18 |  | HS2-00002YNGS - Lorry Route Small Dean Viaduct Accommodation Compound From Small Dean Compound In | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGS | #N/A | #N/A | #N/A
207.2 | HS2-00002CT4W | IDR 207.2 | HS2-00002CT4W | 2024-07-25 | 10 - Complete | 2024-08-27 |  | HS2-00002YNGT - Lorry Route Small Dean Viaduct Accommodation Compound From Small Dean Compound Out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGT | #N/A | #N/A | #N/A
204.3-1 | HS2-00002N7V9 | IDR 204.3-1 | HS2-00002N7V9 | 2024-02-29 | 10 - Complete | 2024-02-29 |  | HS2-00002YNGU - Lorry Route Small Dean Viaduct Launch-Worksite From Small Dean Viaduct Launch In | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGU | #N/A | #N/A | #N/A
204.3-1 | HS2-00002ZM6N | IDR 204.3-1 | HS2-00002ZM6N | 2024-02-29 | 10 - Complete | 2024-03-01 |  | HS2-00002YNGV - Lorry Route Small Dean Viaduct Launch-Worksite From Small Dean Viaduct Launch Out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGV | #N/A | #N/A | #N/A
235.01 | HS2-00002CUCM | IDR 235.01 | HS2-00002CUCM | 2024-02-29 | 10 - Complete | 2024-03-01 |  | HS2-00002YNGW - Lorry Route Chiltern Tunnel North Portal Compound From Chiltern Tunnel North Compound In | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGW | #N/A | #N/A | #N/A
237.05 | HS2-000020P0U | IDR 237.05 | HS2-000020P0U | 2024-03-01 | 10 - Complete | 2024-03-05 |  | HS2-00002YNGX - Lorry Route Chiltern Tunnel North Portal Compound From Chiltern Tunnel North Compound Out | TW 0020 - Lorry Routes | TW 0020 | HS2-00002YNGX | #N/A | #N/A | #N/A
237.05 | HS2-000020P0W | IDR 237.05 | HS2-000020P0W | 2025-01-09 | 10 - Complete | 2025-01-16 |  | HS2-00002ZPKZ - Transport Route NDE_EKF_00000074_to_NDE_EKF_00000075 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPKZ | #N/A | #N/A | #N/A
237.05 | HS2-00002TMWF | IDR 237.05 | HS2-00002TMWF | 2024-03-01 | 10 - Complete | 2024-03-04 |  | HS2-00002ZPL0 - Transport Route osgb4000000019034849_to_NDE_EKF_00000074 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPL0 | #N/A | #N/A | #N/A
237.05 | HS2-00003G3SJ | IDR 237.05 | HS2-00003G3SJ | 2024-03-01 | 10 - Complete | 2024-03-04 |  | HS2-00002ZPL1 - Transport Route NDE_EKF_00000074_to_osgb4000000019034851 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPL1 | #N/A | #N/A | #N/A
207.2 | HS2-000020RKL | IDR 207.2 | HS2-000020RKL | 2024-03-01 | 10 - Complete | 2024-03-06 |  | HS2-00002ZPL2 - Transport Route NDE_EKF_00000071_to_osgb4000000019034858 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPL2 | #N/A | #N/A | #N/A
205.03 | HS2-000001289 | IDR 205.03 | HS2-000001289 | 2024-03-01 | 10 - Complete | 2024-03-04 |  | HS2-00002ZPL3 - Transport Route NDE_EDP_00000188_to_NDE_EKF_00000071 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPL3 | #N/A | #N/A | #N/A
238.02_2 | HS2-00002YNH8 | IDR 238.02_2 | HS2-00002YNH8 | 2024-11-26 | 10 - Complete | 0 |  | HS2-00002ZPL4 - Transport Route NDE_EKF_00000071_to_NDE_EKF_00000073 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPL4 | #N/A | #N/A | #N/A
229.01-1 | HS2-00003B5FS | IDR 229.01-1 | HS2-00003B5FS | 2025-02-20 | 10 - Complete | 2025-02-21 |  | HS2-00002ZPL5 - Transport Route NDE_EKF_00000071_to_NDE_EKF_00000072 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPL5 | #N/A | #N/A | #N/A
235.01 | HS2-00003GEF1 | IDR 235.01 | HS2-00003GEF1 | 2024-03-04 | 10 - Complete | 2024-03-06 |  | HS2-00002ZPL6 - Transport Route osgb4000000019740331_to_NDE_EKF_00000069 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPL6 | #N/A | #N/A | #N/A
235.01 | HS2-00003GEEY | IDR 235.01 | HS2-00003GEEY | 2024-03-04 | 10 - Complete | 2024-03-06 |  | HS2-00002ZPL7 - Transport Route NDE_EKF_00000069_to_osgb4000000019740330 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPL7 | #N/A | #N/A | #N/A
235.01 | HS2-00003GEEZ | IDR 235.01 | HS2-00003GEEZ | 2024-03-04 | 10 - Complete | 2024-03-06 |  | HS2-00002ZPL8 - Transport Route NDE_EKF_00000069_to_NDE_EKF_00000070 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPL8 | #N/A | #N/A | #N/A
235.01 | HS2-00003GEF0 | IDR 235.01 | HS2-00003GEF0 | 2024-03-04 | 10 - Complete | 2024-03-06 |  | HS2-00002ZPL9 - Transport Route osgb4000000019567484_to_NDE_EKF_00000068 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPL9 | #N/A | #N/A | #N/A
235.01 | HS2-00003H077 | IDR 235.01 | HS2-00003H077 | 2024-03-04 | 10 - Complete | 2024-03-06 |  | HS2-00002ZPLA - Transport Route NDE_EKF_00000066_to_osgb4000000019035807 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLA | #N/A | #N/A | #N/A
UFDR 204.A | HS2-000020CEB | UFDR 204.A | HS2-000020CEB | 2024-03-05 | 10 - Complete | 2024-03-07 |  | HS2-00002ZPLB - Transport Route osgb4000000019035802_to_NDE_EKF_00000066 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLB | #N/A | #N/A | #N/A
235.01 | HS2-00003GJJR | IDR 235.01 | HS2-00003GJJR | 2024-03-05 | 10 - Complete | 2024-03-13 |  | HS2-00002ZPLC - Transport Route NDE_EKF_00000066_to_NDE_EKF_00000067 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLC | #N/A | #N/A | #N/A
235.01 | HS2-00003GJJS | IDR 235.01 | HS2-00003GJJS | 2024-03-05 | 10 - Complete | 2024-03-13 |  | HS2-00002ZPLD - Transport Route NDE_EKF_00000062_to_osgb4000000019659774 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLD | #N/A | #N/A | #N/A
235.01 | HS2-00003GJJT | IDR 235.01 | HS2-00003GJJT | 2024-03-05 | 10 - Complete | 2024-03-13 |  | HS2-00002ZPLE - Transport Route NDE_EKF_00000062_to_NDE_EKF_00000064 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLE | #N/A | #N/A | #N/A
228.2 | HS2-000001436 | IDR 228.2 | HS2-000001436 | 2024-03-05 | 10 - Complete | 2024-03-07 |  | HS2-00002ZPLF - Transport Route NDE_EKF_00000063_to_NDE_EKF_00000062 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLF | #N/A | #N/A | #N/A
212.3 | HS2-00002YD78 | IDR 212.3 | HS2-00002YD78 | 2024-03-05 | 10 - Complete | 2024-03-08 |  | HS2-00002ZPLG - Transport Route osgb4000000019035366_to_NDE_EKF_00000063 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLG | #N/A | #N/A | #N/A
212.3 | HS2-00002YYN2 | IDR 212.3 | HS2-00002YYN2 | 2024-03-05 | 10 - Complete | 2024-03-08 |  | HS2-00002ZPLH - Transport Route NDE_EKF_00000063_to_NDE_EKF_00000065 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLH | #N/A | #N/A | #N/A
212.3 | HS2-00002YZKU | IDR 212.3 | HS2-00002YZKU | 2024-03-05 | 10 - Complete | 2024-03-07 |  | HS2-00002ZPLJ - Transport Route NDE_EKF_00000053_to_NDE_EKF_00000048 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLJ | #N/A | #N/A | #N/A
212.3 | HS2-00002ZM2B | IDR 212.3 | HS2-00002ZM2B | 2024-03-05 | 10 - Complete | 2024-03-08 |  | HS2-00002ZPLK - Transport Route NDE_EKF_00000052_to_NDE_EKF_00000053 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLK | #N/A | #N/A | #N/A
207.2 | HS2-000001293 | IDR 207.2 | HS2-000001293 | 2024-03-05 | 10 - Complete | 2024-03-07 |  | HS2-00002ZPLL - Transport Route NDE_EKF_00000053_to_NDE_EKF_00000054 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLL | #N/A | #N/A | #N/A
207.2 | HS2-00002CT4Z | IDR 207.2 | HS2-00002CT4Z | 2024-03-05 | 10 - Complete | 2024-03-07 |  | HS2-00002ZPLM - Transport Route NDE_EKF_00000052_to_NDE_EKF_00000054 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLM | #N/A | #N/A | #N/A
207.2 | HS2-00002N7VP | IDR 207.2 | HS2-00002N7VP | 2024-03-05 | 10 - Complete | 2024-03-07 |  | HS2-00002ZPLN - Transport Route osgb4000000019036874_to_NDE_EKF_00000049 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLN | #N/A | #N/A | #N/A
207.2 | HS2-00002N7VQ | IDR 207.2 | HS2-00002N7VQ | 2024-03-05 | 10 - Complete | 2024-03-07 |  | HS2-00002ZPLP - Transport Route NDE_EKF_00000049_to_NDE_EKF_00000051 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLP | #N/A | #N/A | #N/A
205.3 | HS2-000020NBF | IDR 205.3 | HS2-000020NBF | 2024-03-07 10:55 | 10 - Complete | 2024-03-07 12:46 |  | HS2-00002ZPLQ - Transport Route NDE_EKF_00000049_to_NDE_EKF_00000050 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLQ | #N/A | #N/A | #N/A
229.03 | HS2-00003B2GJ | IDR 229.03 | HS2-00003B2GJ | 2024-03-06 | 10 - Complete | 2024-03-12 |  | HS2-00002ZPLR - Transport Route NDE_EKF_00000050_to_NDE_EKF_00000051 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLR | #N/A | #N/A | #N/A
219.3 | HS2-00002CTA0 | IDR 219.3 | HS2-00002CTA0 | 2024-03-21 | 10 - Complete | 2024-03-27 |  | HS2-00002ZPLS - Transport Route NDE_EKF_00000051_to_NDE_EKF_00000052 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLS | #N/A | #N/A | #N/A
219.3 | HS2-00002CTA4 | IDR 219.3 | HS2-00002CTA4 | 2024-04-02 | 10 - Complete | 2024-04-03 |  | HS2-00002ZPLT - Transport Route NDE_EKF_00000054_to_NDE_EKF_00000059 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLT | #N/A | #N/A | #N/A
219.3 | HS2-00002CTA6 | IDR 219.3 | HS2-00002CTA6 | 2024-04-04 | 10 - Complete | 2024-04-08 |  | HS2-00002ZPLU - Transport Route NDE_EKF_00000059_to_NDE_EKF_00000061 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLU | #N/A | #N/A | #N/A
219.3 | HS2-00002CT9Y | IDR 219.3 | HS2-00002CT9Y | 2024-03-21 | 10 - Complete | 2024-03-27 |  | HS2-00002ZPLV - Transport Route NDE_EKF_00000061_to_NDE_EKF_00000060 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLV | #N/A | #N/A | #N/A
219.3 | HS2-000033GP3 | IDR 219.3 | HS2-000033GP3 | 2024-04-05 | 10 - Complete | 2024-04-15 |  | HS2-00002ZPLW - Transport Route NDE_EKF_00000059_to_NDE_EKF_00000060 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLW | #N/A | #N/A | #N/A
UFDR 222.B | HS2-0000245Z8 | UFDR 222.B | HS2-0000245Z8 | 2024-05-22 | 10 - Complete | 2024-05-30 |  | HS2-00002ZPLX - Transport Route NDE_EKF_00000055_to_NDE_EKF_00000050 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLX | #N/A | #N/A | #N/A
224.F | HS2-000020CH8 | IDR 224.F | HS2-000020CH8 | 2024-03-07 | 10 - Complete | 2024-03-08 |  | HS2-00002ZPLY - Transport Route NDE_EKF_00000056_to_NDE_EKF_00000055 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLY | #N/A | #N/A | #N/A
205.3 | HS2-000020NBF | IDR 205.3 | HS2-000020NBF | 2024-03-07 10:55 | 10 - Complete | 2024-03-07 12:46 |  | HS2-00002ZPLZ - Transport Route NDE_EKF_00000060_to_NDE_EKF_00000056 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPLZ | #N/A | #N/A | #N/A
UFDR 232.C | HS2-000020CJE | UFDR 232.C | HS2-000020CJE | 2024-03-08 | 10 - Complete | 2024-03-11 |  | HS2-00002ZPM0 - Transport Route NDE_EKF_00000056_to_NDE_EKF_00000057 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPM0 | #N/A | #N/A | #N/A
UFDR 232.C | HS2-000020CJF | UFDR 232.C | HS2-000020CJF | 2024-03-08 | 10 - Complete | 2024-03-11 |  | HS2-00002ZPM1 - Transport Route NDE_EKF_00000057_to_NDE_EKF_00000055 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPM1 | #N/A | #N/A | #N/A
UFDR 232.C | HS2-00002FEA3 | UFDR 232.C | HS2-00002FEA3 | 2024-03-08 | 10 - Complete | 2024-03-11 |  | HS2-00002ZPM2 - Transport Route NDE_EKF_00000057_to_NDE_EKF_00000058 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPM2 | #N/A | #N/A | #N/A
UFDR 204.E | HS2-000020CEE | UFDR 204.E | HS2-000020CEE | 2024-03-08 | 10 - Complete | 2024-03-13 |  | HS2-00002ZPM3 - Transport Route NDE_EKF_00000046_to_osgb4000000019036973 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPM3 | #N/A | #N/A | #N/A
UFDR 204.E | HS2-000020CEF | UFDR 204.E | HS2-000020CEF | 2024-03-08 | 10 - Complete | 2024-03-13 |  | HS2-00002ZPM4 - Transport Route NDE_EDP_00000137_to_NDE_EKF_00000046 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPM4 | #N/A | #N/A | #N/A
UFDR 204.E | HS2-000020CEG | UFDR 204.E | HS2-000020CEG | 2024-03-08 | 10 - Complete | 2024-03-13 |  | HS2-00002ZPM5 - Transport Route NDE_EKF_00000046_to_NDE_EKF_00000047 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPM5 | #N/A | #N/A | #N/A
UFDR 204.E | HS2-000020CEH | UFDR 204.E | HS2-000020CEH | 2024-03-08 | 10 - Complete | 2024-03-13 |  | HS2-00002ZPM6 - Transport Route NDE_EKF_00000043_to_NDE_EKF_00000044 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPM6 | #N/A | #N/A | #N/A
235.01-2 | HS2-00003GEES | IDR 235.01-2 | HS2-00003GEES | 2024-03-11 | 10 - Complete | 2024-03-13 |  | HS2-00002ZPM7 - Transport Route NDE_EKF_00000043_to_NDE_EKF_00000045 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPM7 | #N/A | #N/A | #N/A
235.01-2 | HS2-00003GEET | IDR 235.01-2 | HS2-00003GEET | 2024-03-11 | 10 - Complete | 2024-03-13 |  | HS2-00002ZPM8 - Transport Route NDE_EKF_00000043_to_osgb4000000019751674 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPM8 | #N/A | #N/A | #N/A
235.01-2 | HS2-00003GEEU | IDR 235.01-2 | HS2-00003GEEU | 2024-03-11 | 10 - Complete | 2024-03-13 |  | HS2-00002ZPM9 - Transport Route osgb4000000019042726_to_NDE_EKF_00000043 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPM9 | #N/A | #N/A | #N/A
204.2-1 | HS2-000001025 | IDR 204.2-1 | HS2-000001025 | 2024-03-15 | 10 - Complete | 2024-03-19 |  | HS2-00002ZPMA - Transport Route NDE_EKF_00000033_to_NDE_EDP_00000261 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMA | #N/A | #N/A | #N/A
204.2-1 | HS2-00002F0X2 | IDR 204.2-1 | HS2-00002F0X2 | 2024-03-15 | 10 - Complete | 2024-03-18 |  | HS2-00002ZPMB - Transport Route NDE_EKF_00000033_to_NDE_EKF_00000035 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMB | #N/A | #N/A | #N/A
235.01 | HS2-00002CTJD | IDR 235.01 | HS2-00002CTJD | 2024-04-10 | 10 - Complete | 2024-04-16 |  | HS2-00002ZPMC - Transport Route osgb4000000019040742_to_NDE_EKF_00000033 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMC | #N/A | #N/A | #N/A
235.01 | HS2-00002CTJE | IDR 235.01 | HS2-00002CTJE | 2024-04-10 | 10 - Complete | 2024-04-17 |  | HS2-00002ZPMD - Transport Route osgb4000000019040742_to_NDE_EKF_00000034 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMD | #N/A | #N/A | #N/A
221.2 | HS2-000020357 | IDR 221.2 | HS2-000020357 | 2024-03-11 | 10 - Complete | 2024-03-12 |  | HS2-00002ZPME - Transport Route NDE_EKF_00000034_to_NDE_EKF_00000036 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPME | #N/A | #N/A | #N/A
221.2 | HS2-000020NLY | IDR 221.2 | HS2-000020NLY | 2024-03-11 | 10 - Complete | 2024-03-13 |  | HS2-00002ZPMF - Transport Route NDE_EKF_00000034_to_NDE_EDP_00000445 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMF | #N/A | #N/A | #N/A
221.2 | HS2-000020NLZ | IDR 221.2 | HS2-000020NLZ | 2024-04-03 | 10 - Complete | 2024-04-05 |  | HS2-00002ZPMG - Transport Route osgb4000000019040749_to_NDE_EKF_00000032 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMG | #N/A | #N/A | #N/A
221.2 | HS2-00002QH92 | IDR 221.2 | HS2-00002QH92 | 2024-03-11 | 10 - Complete | 2024-03-12 |  | HS2-00002ZPMH - Transport Route NDE_EKF_00000040_to_NDE_EDP_00000235 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMH | #N/A | #N/A | #N/A
220.3 | HS2-00002N7W7 | IDR 220.3 | HS2-00002N7W7 | 2024-03-11 | 10 - Complete | 2024-03-18 |  | HS2-00002ZPMJ - Transport Route NDE_EKF_00000039_to_NDE_EKF_00000040 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMJ | #N/A | #N/A | #N/A
220.3 | HS2-000032217 | IDR 220.3 | HS2-000032217 | 2024-03-11 | 10 - Complete | 2024-03-18 |  | HS2-00002ZPMK - Transport Route NDE_EKF_00000040_to_NDE_EKF_00000042 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMK | #N/A | #N/A | #N/A
UFDR 230.B | HS2-000020CJA | UFDR 230.B | HS2-000020CJA | 2024-03-12 | 10 - Complete | 2024-03-14 |  | HS2-00002ZPML - Transport Route NDE_EKF_00000039_to_NDE_EKF_00000041 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPML | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPMM - Transport Route NDE_EKF_00000037_to_NDE_EKF_00000038 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMM | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPMN - Transport Route NDE_EKF_00000037_to_NDE_EKF_00000039 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMN | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPMP - Transport Route osgb4000000019042375_to_NDE_EKF_00000037 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMP | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPMQ - Transport Route osgb4000000019042480_to_NDE_EKF_00000028 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMQ | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPMR - Transport Route osgb4000000019042478_to_NDE_EKF_00000028 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMR | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPMS - Transport Route NDE_EKF_00000028_to_NDE_EKF_00000029 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMS | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPMT - Transport Route NDE_EKF_00000029_to_NDE_EKF_00000030 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMT | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPMU - Transport Route NDE_EKF_00000029_to_NDE_EKF_00000031 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMU | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPMV - Transport Route NDE_EKF_00000030_to_NDE_EKF_00000031 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMV | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPMW - Transport Route NDE_EKF_00000031_to_NDE_EKF_00000076 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMW | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPMX - Transport Route osgb5000005135943471_to_NDE_EKF_00000025 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMX | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPMY - Transport Route NDE_EKF_00000025_to_NDE_EDP_00000509 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMY | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPMZ - Transport Route NDE_EKF_00000025_to_NDE_EKF_00000026 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPMZ | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPN0 - Transport Route NDE_EKF_00000025_to_NDE_EKF_00000027 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPN0 | #N/A | #N/A | #N/A
229.01-1 | HS2-000025B2C | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28 |  | HS2-00002ZPN1 - Transport Route osgb4000000019041666_to_NDE_EKF_00000024 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPN1 | #N/A | #N/A | #N/A
238.01 | HS2-00002CTK9 | IDR 238.01 | HS2-00002CTK9 | 2024-05-09 | 10 - Complete | 2024-05-14 |  | HS2-00002ZPN2 - Transport Route osgb4000000019041662_to_NDE_EKF_00000023 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPN2 | #N/A | #N/A | #N/A
213.02 | HS2-000001040 | IDR 213.02 | HS2-000001040 | 2024-08-26 | 10 - Complete | 2024-09-05 |  | HS2-00002ZPN3 - Transport Route NDE_EKF_00000021_to_NDE_EDP_00000632 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPN3 | #N/A | #N/A | #N/A
213.02 | HS2-00002BVGE | IDR 213.02 | HS2-00002BVGE | 2024-03-12 | 10 - Complete | 2024-03-15 |  | HS2-00002ZPN4 - Transport Route NDE_EKF_00000021_to_NDE_EKF_00000022 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPN4 | #N/A | #N/A | #N/A
235.01-2 | HS2-00003H075 | IDR 235.01-2 | HS2-00003H075 | 2024-03-13 | 10 - Complete | 2024-03-19 |  | HS2-00002ZPN5 - Transport Route NDE_EKF_00000019_to_NDE_EKF_00000021 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPN5 | #N/A | #N/A | #N/A
235.01-2 | HS2-00003H076 | IDR 235.01-2 | HS2-00003H076 | 2024-03-13 | 10 - Complete | 2024-03-19 |  | HS2-00002ZPN6 - Transport Route NDE_EKF_00000019_to_NDE_EKF_00000020 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPN6 | #N/A | #N/A | #N/A
238.01 | HS2-00002BVN8 | IDR 238.01 | HS2-00002BVN8 | 2025-03-03 | 10 - Complete | 2025-03-07 |  | HS2-00002ZPN7 - Transport Route osgb4000000019106015_to_NDE_EKF_00000019 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPN7 | #N/A | #N/A | #N/A
237.05 | HS2-00002CTK3 | IDR 237.05 | HS2-00002CTK3 | 2024-03-13 | 10 - Complete | 2024-03-22 |  | HS2-00002ZPN8 - Transport Route osgb4000000019105952_to_NDE_EKF_00000017 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPN8 | #N/A | #N/A | #N/A
221.2 | HS2-00002CW0X | IDR 221.2 | HS2-00002CW0X | 2024-03-14 | 10 - Complete | 2024-03-18 |  | HS2-00002ZPN9 - Transport Route NDE_EKF_00000017_to_NDE_EKF_00000018 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPN9 | #N/A | #N/A | #N/A
219.3 | HS2-0000386U9 | IDR 219.3 | HS2-0000386U9 | 2024-03-14 | 10 - Complete | 2024-03-27 |  | HS2-00002ZPNA - Transport Route NDE_EKF_00000017_to_osgb4000000019105955 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNA | #N/A | #N/A | #N/A
219.3 | HS2-0000386UA | IDR 219.3 | HS2-0000386UA | 2024-04-17 | 10 - Complete | 2024-04-22 |  | HS2-00002ZPNB - Transport Route NDE_EKF_00000015_to_osgb4000000019105954 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNB | #N/A | #N/A | #N/A
213.02 | HS2-00002BVGC | IDR 213.02 | HS2-00002BVGC | 2024-03-14 | 10 - Complete | 2024-03-18 |  | HS2-00002ZPNC - Transport Route NDE_EDP_00000294_to_NDE_EKF_00000015 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNC | #N/A | #N/A | #N/A
204.2-1 | HS2-000001025 | IDR 204.2-1 | HS2-000001025 | 2024-03-15 | 10 - Complete | 2024-03-19 |  | HS2-00002ZPND - Transport Route NDE_EKF_00000015_to_NDE_EKF_00000016 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPND | #N/A | #N/A | #N/A
204.2-1 | HS2-00002F0X2 | IDR 204.2-1 | HS2-00002F0X2 | 2024-03-15 | 10 - Complete | 2024-03-18 |  | HS2-00002ZPNE - Transport Route NDE_EDP_00000215_to_NDE_EKF_00000013 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNE | #N/A | #N/A | #N/A
237.05 | HS2-00002CTK4 | IDR 237.05 | HS2-00002CTK4 | 2024-12-12 | 30 - Sent back to team | 0 |  | HS2-00002ZPNF - Transport Route NDE_EKF_00000013_to_NDE_EKF_00000014 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNF | #N/A | #N/A | #N/A
213.02 | HS2-00002CT76 | IDR 213.02 | HS2-00002CT76 | 2024-10-04 | 99 - Cancelled | 0 |  | HS2-00002ZPNG - Transport Route NDE_EKF_00000013_to_osgb4000000019106132 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNG | #N/A | #N/A | #N/A
UFDR 232.C | HS2-000020CJH | UFDR 232.C | HS2-000020CJH | 2024-03-18 | 10 - Complete | 2024-03-19 |  | HS2-00002ZPNH - Transport Route NDE_EKF_00000011_to_osgb4000000019106151 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNH | #N/A | #N/A | #N/A
229.01-1 | HS2-000020359 | IDR 229.01-1 | HS2-000020359 | 2025-02-19 | 10 - Complete | 2025-02-26 |  | HS2-00002ZPNJ - Transport Route NDE_EKF_00000011_to_NDE_EKF_00000012 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNJ | #N/A | #N/A | #N/A
229.01-1 | HS2-00002CTF7 | IDR 229.01-1 | HS2-00002CTF7 | 2024-04-22 | 10 - Complete | 2024-05-03 |  | HS2-00002ZPNK - Transport Route osgb4000000019106169_to_NDE_EKF_00000011 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNK | #N/A | #N/A | #N/A
229.01-1 | HS2-00002CTF8 | IDR 229.01-1 | HS2-00002CTF8 | 2024-04-22 | 10 - Complete | 2024-05-03 |  | HS2-00002ZPNL - Transport Route NDE_EKF_00000009_to_NDE_EDP_00000094 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNL | #N/A | #N/A | #N/A
UFDR 204.A | HS2-000020CEC | UFDR 204.A | HS2-000020CEC | 2024-03-19 | 10 - Complete | 2024-03-21 |  | HS2-00002ZPNM - Transport Route NDE_EKF_00000009_to_NDE_EKF_00000010 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNM | #N/A | #N/A | #N/A
238.02_2 | HS2-000037830 | IDR 238.02_2 | HS2-000037830 | 2024-03-19 | 10 - Complete | 2024-03-21 |  | HS2-00002ZPNN - Transport Route osgb4000000019077107_to_NDE_EKF_00000009 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNN | #N/A | #N/A | #N/A
204.2-1 | HS2-00002CT4N | IDR 204.2-1 | HS2-00002CT4N | 2024-03-19 | 10 - Complete | 2024-03-22 |  | HS2-00002ZPNP - Transport Route osgb4000000019077106_to_NDE_EKF_00000005 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNP | #N/A | #N/A | #N/A
204.2-1 | HS2-00002CT4P | IDR 204.2-1 | HS2-00002CT4P | 2024-04-18 | 10 - Complete | 2024-04-19 |  | HS2-00002ZPNQ - Transport Route NDE_EKF_00000005_to_NDE_EKF_00000008 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNQ | #N/A | #N/A | #N/A
204.2-1 | HS2-000030TD4 | IDR 204.2-1 | HS2-000030TD4 | 2024-03-19 | 10 - Complete | 2024-03-28 |  | HS2-00002ZPNR - Transport Route NDE_EKF_00000005_to_osgb4000000019079039 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNR | #N/A | #N/A | #N/A
204.2-1 | HS2-000030TD5 | IDR 204.2-1 | HS2-000030TD5 | 2024-03-19 | 10 - Complete | 2024-03-28 |  | HS2-00002ZPNS - Transport Route osgb4000000019079054_to_NDE_EKF_00000004 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNS | #N/A | #N/A | #N/A
237.05 | HS2-000032216 | IDR 237.05 | HS2-000032216 | 2024-11-26 | 10 - Complete | 2025-01-10 |  | HS2-00002ZPNT - Transport Route NDE_EKF_00000004_to_osgb4000000019603220 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNT | #N/A | #N/A | #N/A
229.03 | HS2-00002N7UD | IDR 229.03 | HS2-00002N7UD | 2024-03-19 | 10 - Complete | 2024-03-22 |  | HS2-00002ZPNU - Transport Route NDE_EKF_00000004_to_NDE_EKF_00000007 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNU | #N/A | #N/A | #N/A
212.3 | HS2-00002EK6X | IDR 212.3 | HS2-00002EK6X | 2024-03-19 | 10 - Complete | 2024-03-27 |  | HS2-00002ZPNV - Transport Route NDE_EKF_00000003_to_osgb4000000019079196 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNV | #N/A | #N/A | #N/A
212.3 | HS2-00002Y0AR | IDR 212.3 | HS2-00002Y0AR | 2024-03-19 | 10 - Complete | 2024-03-22 |  | HS2-00002ZPNW - Transport Route osgb4000000019079197_to_NDE_EKF_00000003 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNW | #N/A | #N/A | #N/A
229.03 | HS2-00002N7UC | IDR 229.03 | HS2-00002N7UC | 2024-03-20 | 10 - Complete | 2024-03-27 |  | HS2-00002ZPNX - Transport Route NDE_EKF_00000001_to_NDE_EKF_00000002 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNX | #N/A | #N/A | #N/A
229.01 | HS2-00002EK7K | IDR 229.01 | HS2-00002EK7K | 2024-03-20 | 10 - Complete | 2024-03-28 |  | HS2-00002ZPNY - Transport Route NDE_EDP_00000327_to_NDE_EKF_00000001 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNY | #N/A | #N/A | #N/A
216.01 | HS2-000020NL1 | IDR 216.01 | HS2-000020NL1 | 2025-04-16 | 10 - Complete | 2025-04-25 |  | HS2-00002ZPNZ - Transport Route NDE_EKF_00000001_to_osgb4000000019079320 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPNZ | #N/A | #N/A | #N/A
216.01 | HS2-000020RM2 | IDR 216.01 | HS2-000020RM2 | 2025-04-16 | 10 - Complete | 2025-04-25 |  | HS2-00002ZPP0 - Transport Route NDE_EKF_00000003_to_NDE_EKF_00000006 | TW 0020 - Lorry Routes | TW 0020 | HS2-00002ZPP0 | #N/A | #N/A | #N/A
216.01 | HS2-000020356 | IDR 216.01 | HS2-000020356 | 2025-04-16 | 10 - Complete | 2025-04-25 |  | HS2-00003124N - Lorry Route A43 Brackley South Cutting In | TW 0020 - Lorry Routes | TW 0020 | HS2-00003124N | #N/A | #N/A | #N/A
212.3 | HS2-00002EK71 | IDR 212.3 | HS2-00002EK71 | 2024-03-20 | 10 - Complete | 2024-03-22 |  | HS2-00003124P - Lorry Route A43 Brackley South Cutting out | TW 0020 - Lorry Routes | TW 0020 | HS2-00003124P | #N/A | #N/A | #N/A
212.3 | HS2-00002EK72 | IDR 212.3 | HS2-00002EK72 | 2024-03-20 | 10 - Complete | 2024-03-22 |  | HS2-00003124Q - Transport Route NDE_EKF_00000077_to_NDE_EKF_00000078 | TW 0020 - Lorry Routes | TW 0020 | HS2-00003124Q | #N/A | #N/A | #N/A
212.3 | HS2-00002EK73 | IDR 212.3 | HS2-00002EK73 | 2024-03-20 | 10 - Complete | 2024-03-25 |  | HS2-00003124R - Transport Route osgb4000000019036962_to_NDE_EKF_00000077 | TW 0020 - Lorry Routes | TW 0020 | HS2-00003124R | #N/A | #N/A | #N/A
238.02_2 | HS2-00003H6PG | IDR 238.02_2 | HS2-00003H6PG | 2024-11-26 | 10 - Complete | 0 |  | HS2-00003124S - Transport Route NDE_EKF_00000077_to_osgb4000000019750144 | TW 0020 - Lorry Routes | TW 0020 | HS2-00003124S | #N/A | #N/A | #N/A
210.2-2 | HS2-000001299 | IDR 210.2-2 | HS2-000001299 | 2024-03-21 | 10 - Complete | 2024-04-09 |  | HS2-00002SZM4 - G2S Drainage Area 6 (124.450 126.450) | TW 0019 - TW Drainage G2S 124450 to 126450 | TW 0019 | HS2-00002SZM4 | #N/A | #N/A | #N/A
237.05 | HS2-00002CTK5 | IDR 237.05 | HS2-00002CTK5 | 2024-05-14 | 10 - Complete | 2024-05-16 |  | HS2-00002SZM3 - G2S Drainage Area 4 (113.800 119.000) | TW 0018 - TW Drainage G2S 113800 to 119000 | TW 0018 | HS2-00002SZM3 | #N/A | #N/A | #N/A
237.05 | HS2-00002CTK6 | IDR 237.05 | HS2-00002CTK6 | 2024-03-21 | 10 - Complete | 2024-04-12 |  | HS2-00002SZM2 - G2S Drainage Area 5 (119.000 124.450) | TW 0017 - TW Drainage G2S 119000 to 124450 | TW 0017 | HS2-00002SZM2 | #N/A | #N/A | #N/A
227.1 | HS2-00002N7X2 | IDR 227.1 | HS2-00002N7X2 | 2024-04-19 | 10 - Complete | 2024-04-25 |  | HS2-00002SZM1 - G2S Drainage Area 3 (110.800 113.800) | TW 0016 - TW Drainage G2S 110800 to 113800 | TW 0016 | HS2-00002SZM1 | #N/A | #N/A | #N/A
219.3 | HS2-00002CT9Y | IDR 219.3 | HS2-00002CT9Y | 2024-03-21 | 10 - Complete | 2024-03-27 |  | HS2-00002SZM0 - G2S Drainage Area 2 (104.000 110.800) | TW 0015 - TW Drainage G2S 104000 to 110800 | TW 0015 | HS2-00002SZM0 | #N/A | #N/A | #N/A
219.3 | HS2-00002CTA0 | IDR 219.3 | HS2-00002CTA0 | 2024-03-21 | 10 - Complete | 2024-03-27 |  | HS2-00002SZLZ - G2S Drainage Area 1 (101.700 104.000) | TW 0014 - TW Drainage G2S 101700 to 104000 | TW 0014 | HS2-00002SZLZ | #N/A | #N/A | #N/A
212.4 | HS2-00002Y0AT | IDR 212.4 | HS2-00002Y0AT | 2024-03-21 | 10 - Complete | 2024-03-28 |  | HS2-00002SY1N - Site Access Road G2S Section 7 (116.800 119.450) | TW 0013 - Site Access Roads G2S North Chainage 117700 to 126540 | TW 0013 | HS2-00002SY1N | #N/A | #N/A | #N/A
212.4 | HS2-00002Y479 | IDR 212.4 | HS2-00002Y479 | 2024-03-21 | 10 - Complete | 2024-03-28 |  | HS2-00002SY1P - Site Access Road G2S Section 8 (119.450 121.450) | TW 0013 - Site Access Roads G2S North Chainage 117700 to 126540 | TW 0013 | HS2-00002SY1P | #N/A | #N/A | #N/A
UFDR 230.C | HS2-000020CJ6 | UFDR 230.C | HS2-000020CJ6 | 2024-03-22 | 10 - Complete | 2024-03-27 |  | HS2-00002SY1Q - Site Access Road G2S Section 9 (121.450 124.450) | TW 0013 - Site Access Roads G2S North Chainage 117700 to 126540 | TW 0013 | HS2-00002SY1Q | #N/A | #N/A | #N/A
UFDR 221.D | HS2-000020CGK | UFDR 221.D | HS2-000020CGK | 2024-03-22 | 10 - Complete | 2024-03-26 |  | HS2-00002SY1R - Site Access Road G2S Section 10 (124.450 126.450) | TW 0013 - Site Access Roads G2S North Chainage 117700 to 126540 | TW 0013 | HS2-00002SY1R | #N/A | #N/A | #N/A
UFDR 221.D | HS2-000020CGL | UFDR 221.D | HS2-000020CGL | 2024-03-22 | 10 - Complete | 2024-03-26 |  | HS2-00002XP3Q - Oxford Canal Site Access Road Temporary Bridge | TW 0013 - Site Access Roads G2S North Chainage 117700 to 126540 | TW 0013 | HS2-00002XP3Q | #N/A | #N/A | #N/A
221.2_1 | HS2-000001321 | IDR 221.2_1 | HS2-000001321 | 2024-04-24 | 10 - Complete | 2024-04-25 |  | HS2-00002SY1K - Site Access Road G2S Section 4 (108.900 111.800) | TW 0012 - Site Access Roads G2S Central Chainage 108950 to 117700 | TW 0012 | HS2-00002SY1K | #N/A | #N/A | #N/A
204.2-1 | HS2-00002EK6W | IDR 204.2-1 | HS2-00002EK6W | 2024-03-22 | 10 - Complete | 2024-03-28 |  | HS2-00002SY1L - Site Access Road G2S Section 5 (111.800 113.800) | TW 0012 - Site Access Roads G2S Central Chainage 108950 to 117700 | TW 0012 | HS2-00002SY1L | #N/A | #N/A | #N/A
UFDR 228.A | HS2-000020CHV | UFDR 228.A | HS2-000020CHV | 2024-03-25 | 10 - Complete | 2024-03-27 |  | HS2-00002SY1M - Site Access Road G2S Section 6 (113.800 116.800) | TW 0012 - Site Access Roads G2S Central Chainage 108950 to 117700 | TW 0012 | HS2-00002SY1M | #N/A | #N/A | #N/A
UFDR 228.A | HS2-00002FE9V | UFDR 228.A | HS2-00002FE9V | 2024-03-25 | 10 - Complete | 2024-03-27 |  | HS2-00002SY1G - Site Access Road G2S Section 1 (101.700 104.900) | TW 0011 - Site Access Roads G2S South Chainage 101950 to 108950 | TW 0011 | HS2-00002SY1G | #N/A | #N/A | #N/A
UFDR 228.A | HS2-00002TTH9 | UFDR 228.A | HS2-00002TTH9 | 2024-03-25 | 10 - Complete | 2024-03-28 |  | HS2-00002SY1H - Site Access Road G2S Section 2 (104.900 106.900) | TW 0011 - Site Access Roads G2S South Chainage 101950 to 108950 | TW 0011 | HS2-00002SY1H | #N/A | #N/A | #N/A
UFDR 228.A | HS2-000020CHT | UFDR 228.A | HS2-000020CHT | 2024-03-25 | 10 - Complete | 2024-03-27 |  | HS2-00002SY1J - Site Access Road G2S Section 3 (106.900 108.900) | TW 0011 - Site Access Roads G2S South Chainage 101950 to 108950 | TW 0011 | HS2-00002SY1J | #N/A | #N/A | #N/A
UFDR 228.A | HS2-000020CHU | UFDR 228.A | HS2-000020CHU | 2024-03-25 | 10 - Complete | 2024-03-27 |  | HS2-00002S2UC - Calvert North Site Access Road (Access Track) | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002S2UC | #N/A | #N/A | #N/A
237.05 | HS2-00002TKV0 | IDR 237.05 | HS2-00002TKV0 | 2024-03-26 | 10 - Complete | 2024-04-02 |  | HS2-00002N7QC - Site Access Road-Calvert Cutting-1 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QC | #N/A | #N/A | #N/A
237.05 | HS2-000032216 | IDR 237.05 | HS2-000032216 | 2024-11-26 | 10 - Complete | 2025-01-10 |  | HS2-00002N7QE - Site Access Road-Calvert Cutting-2 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QE | #N/A | #N/A | #N/A
235.01 | HS2-00002TKUY | IDR 235.01 | HS2-00002TKUY | 2024-06-19 | 10 - Complete | 2024-06-20 |  | HS2-00002QSRV - School Hill Batching Plant Compound | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002QSRV | #N/A | #N/A | #N/A
235.01 | HS2-00002TKUZ | IDR 235.01 | HS2-00002TKUZ | 2024-03-26 | 10 - Complete | 2024-04-02 |  | HS2-00002N7QF - Site Access Road-Calvert Cutting-3 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QF | #N/A | #N/A | #N/A
227.1 | HS2-000001336 | IDR 227.1 | HS2-000001336 | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002N7QG - Site Access Road-Calvert Cutting-4 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QG | #N/A | #N/A | #N/A
227.1 | HS2-00002CQQF | IDR 227.1 | HS2-00002CQQF | 2024-04-10 | 10 - Complete | 2024-04-15 |  | HS2-00002N7QW - Site Access Road-Calvert Infrastructure Maintenance Depot-3 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QW | #N/A | #N/A | #N/A
220.3 | HS2-000001320 | IDR 220.3 | HS2-000001320 | 2024-03-26 | 10 - Complete | 2024-04-12 |  | HS2-00002N7R0 - Site Access Road-Calvert Infrastructure Maintenance Depot-7 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7R0 | #N/A | #N/A | #N/A
212.4 | HS2-00002ZM2A | IDR 212.4 | HS2-00002ZM2A | 2024-03-26 | 10 - Complete | 2024-04-02 |  | HS2-00002N7QX - Site Access Road-Calvert Infrastructure Maintenance Depot-4 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QX | #N/A | #N/A | #N/A
237.05 | HS2-00002TMFE | IDR 237.05 | HS2-00002TMFE | 2024-03-27 | 10 - Complete | 2024-04-03 |  | HS2-00002N7QY - Site Access Road-Calvert Infrastructure Maintenance Depot-5 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QY | #N/A | #N/A | #N/A
216.01 | HS2-000020NKK | IDR 216.01 | HS2-000020NKK | 2024-12-02 | 10 - Complete | 2025-01-08 |  | HS2-00002N7QV - Site Access Road-Calvert Infrastructure Maintenance Depot-2 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QV | #N/A | #N/A | #N/A
216.01 | HS2-00002BJUF | IDR 216.01 | HS2-00002BJUF | 2025-06-27 | 10 - Complete | 2025-07-02 |  | HS2-00002QSRU - Calvert North Railhead Compound (Stockpile) | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002QSRU | #N/A | #N/A | #N/A
216.01 | HS2-00002CT90 | IDR 216.01 | HS2-00002CT90 | 2024-12-02 | 10 - Complete | 2025-01-09 |  | HS2-00002N7R1 - Site Access Road-Calvert Infrastructure Maintenance Depot-8 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7R1 | #N/A | #N/A | #N/A
212.4 | HS2-00002Y47A | IDR 212.4 | HS2-00002Y47A | 2024-11-11 | 10 - Complete | 2025-01-09 |  | HS2-00002QSRT - Calvert North IMD Compound (Stockpile) | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002QSRT | #N/A | #N/A | #N/A
UFDR 237.C | HS2-000020CK7 | UFDR 237.C | HS2-000020CK7 | 2024-03-28 | 10 - Complete | 2024-04-02 |  | HS2-00002N7R2 - Site Access Road-Calvert Infrastructure Maintenance Depot-9 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7R2 | #N/A | #N/A | #N/A
235.01-2 | HS2-00003GEEX | IDR 235.01-2 | HS2-00003GEEX | 2024-03-28 | 10 - Complete | 2024-04-03 |  | HS2-00002N7QU - Site Access Road-Calvert Infrastructure Maintenance Depot-1 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QU | #N/A | #N/A | #N/A
233.01-2 | HS2-00002EK85 | IDR 233.01-2 | HS2-00002EK85 | 2024-03-28 | 10 - Complete | 2024-04-03 |  | HS2-00002N7QD - Site Access Road-Calvert Cutting-5 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QD | #N/A | #N/A | #N/A
237.05 | HS2-00002CX3B | IDR 237.05 | HS2-00002CX3B | 2024-03-28 | 10 - Complete | 2024-04-02 |  | HS2-00002N7QZ - Site Access Road-Calvert Infrastructure Maintenance Depot-6 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QZ | #N/A | #N/A | #N/A
220.5 | HS2-00002CTAL | IDR 220.5 | HS2-00002CTAL | 2024-03-28 | 10 - Complete | 2024-04-04 |  | HS2-00002N7QH - Site Access Road-Calvert Cutting-6 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QH | #N/A | #N/A | #N/A
218.02 | HS2-00002D2S2 | IDR 218.02 | HS2-00002D2S2 | 2024-03-28 | 10 - Complete | 2024-04-02 |  | HS2-00002N7QJ - Site Access Road-Calvert Cutting-7 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QJ | #N/A | #N/A | #N/A
212.4 | HS2-0000386T9 | IDR 212.4 | HS2-0000386T9 | 2024-03-28 | 10 - Complete | 2024-04-02 |  | HS2-00002N7QN - Site Access Road-Calvert cutting-11 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QN | #N/A | #N/A | #N/A
212.4 | HS2-0000386TC | IDR 212.4 | HS2-0000386TC | 2024-03-28 | 10 - Complete | 2024-04-02 |  | HS2-00002N7QP - Site Access Road-Calvert Cutting-12 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QP | #N/A | #N/A | #N/A
212.3 | HS2-00002EK6Z | IDR 212.3 | HS2-00002EK6Z | 2024-03-28 | 10 - Complete | 2024-04-02 |  | HS2-00002N7QK - Site Access Road-Calvert Cutting-8 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QK | #N/A | #N/A | #N/A
219.3 | HS2-00002YCW4 | IDR 219.3 | HS2-00002YCW4 | 2024-04-12 | 10 - Complete | 2024-05-03 |  | HS2-00002N7QR - Site Access Road-Calvert Cutting-14 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QR | #N/A | #N/A | #N/A
219.3 | HS2-000031EEZ | IDR 219.3 | HS2-000031EEZ | 2024-05-28 | 10 - Complete | 2024-05-29 |  | HS2-00002N7QQ - Site Access Road-Calvert Cutting-13 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QQ | #N/A | #N/A | #N/A
219.3 | HS2-000031EF0 | IDR 219.3 | HS2-000031EF0 | 2024-04-12 | 10 - Complete | 2024-05-08 |  | HS2-00002QSRS - Gawcott Road Temporary Bridge | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002QSRS | #N/A | #N/A | #N/A
219.3 | HS2-000037YLE | IDR 219.3 | HS2-000037YLE | 2024-04-12 | 10 - Complete | 2024-04-30 |  | HS2-00002N7QL - Site Access Road-Calvert Cutting-9 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QL | #N/A | #N/A | #N/A
219.3 | HS2-000037YLG | IDR 219.3 | HS2-000037YLG | 2024-04-12 | 10 - Complete | 2024-04-30 |  | HS2-00002N7QM - Site Access Road-Calvert Cutting-10 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QM | #N/A | #N/A | #N/A
219.3 | HS2-00002CTA4 | IDR 219.3 | HS2-00002CTA4 | 2024-04-02 | 10 - Complete | 2024-04-03 |  | HS2-00002N7QS - Site Access Road-Calvert Cutting-15 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QS | #N/A | #N/A | #N/A
216.01 | HS2-00002BJUE | IDR 216.01 | HS2-00002BJUE | 2024-12-02 | 10 - Complete | 2025-01-09 |  | HS2-00002N7QT - Site Access Road-Twyford Embankment-1 | TW 0007 - Site Access Roads CA North Chainage 77400 to 81450 | TW 0007 | HS2-00002N7QT | #N/A | #N/A | #N/A
216.01 | HS2-00002BJUG | IDR 216.01 | HS2-00002BJUG | 2025-06-27 | 10 - Complete | 2025-07-02 |  | HS2-00002S2UD - Calvert South Site Access Road (Access Track) | TW 0006 - Site Access Roads CA South Chainage 71460 to 77400 | TW 0006 | HS2-00002S2UD | #N/A | #N/A | #N/A
212.4 | HS2-00003B93V | IDR 212.4 | HS2-00003B93V | 2024-11-20 | 10 - Complete | 2025-01-08 |  | HS2-00002QSRW - Greatmoor Compound | TW 0006 - Site Access Roads CA South Chainage 71460 to 77400 | TW 0006 | HS2-00002QSRW | #N/A | #N/A | #N/A
212.3 | HS2-00003GNAB | IDR 212.3 | HS2-00003GNAB | 2024-04-02 | 10 - Complete | 2024-04-09 |  | HS2-00002QVCZ - Site Access Road AA Section 6 | TW 0005 - Site Access Roads AA North Chainage 64334 to 71460 | TW 0005 | HS2-00002QVCZ | #N/A | #N/A | #N/A
235.01-2 | HS2-000001091 | IDR 235.01-2 | HS2-000001091 | 2024-04-03 | 10 - Complete | 2024-04-07 |  | HS2-00002QVD0 - Site Access Road AA Section 7 | TW 0005 - Site Access Roads AA North Chainage 64334 to 71460 | TW 0005 | HS2-00002QVD0 | #N/A | #N/A | #N/A
237.05 | HS2-000020P1F | IDR 237.05 | HS2-000020P1F | 2024-12-05 | 10 - Complete | 2024-01-14 |  | HS2-00002QVD1 - Site Access Road AA Section 8 | TW 0005 - Site Access Roads AA North Chainage 64334 to 71460 | TW 0005 | HS2-00002QVD1 | #N/A | #N/A | #N/A
233.01 | HS2-00002CX3A | IDR 233.01 | HS2-00002CX3A | 2025-01-08 | 10 - Complete | 2025-01-17 |  | HS2-00002QVD2 - Site Access Road AA Section 9 | TW 0005 - Site Access Roads AA North Chainage 64334 to 71460 | TW 0005 | HS2-00002QVD2 | #N/A | #N/A | #N/A
221.2 | HS2-000020NLZ | IDR 221.2 | HS2-000020NLZ | 2024-04-03 | 10 - Complete | 2024-04-05 |  | HS2-00002QVD3 - Site Access Road AA Section 10 | TW 0005 - Site Access Roads AA North Chainage 64334 to 71460 | TW 0005 | HS2-00002QVD3 | #N/A | #N/A | #N/A
221.2 | HS2-00002CTB0 | IDR 221.2 | HS2-00002CTB0 | 2024-04-03 | 10 - Complete | 2024-04-05 |  | HS2-00002QVCW - Site Access Road AA Section 3 | TW 0004 - Site Access Roads AA South Chainage 57850 to 64334 | TW 0004 | HS2-00002QVCW | #N/A | #N/A | #N/A
214.09 | HS2-00002TTH6 | IDR 214.09 | HS2-00002TTH6 | 2024-04-15 | 10 - Complete | 2024-04-17 |  | HS2-00002QVCU - Site Access Road AA Section 1 | TW 0004 - Site Access Roads AA South Chainage 57850 to 64334 | TW 0004 | HS2-00002QVCU | #N/A | #N/A | #N/A
214.09 | HS2-00003G3SK | IDR 214.09 | HS2-00003G3SK | 2024-04-15 | 10 - Complete | 2024-04-17 |  | HS2-00002QVCV - Site Access Road AA Section 2 | TW 0004 - Site Access Roads AA South Chainage 57850 to 64334 | TW 0004 | HS2-00002QVCV | #N/A | #N/A | #N/A
212.4 | HS2-0000386TB | IDR 212.4 | HS2-0000386TB | 2024-04-03 | 10 - Complete | 2024-04-07 |  | HS2-00002QVCX - Site Access Road AA Section 4 | TW 0004 - Site Access Roads AA South Chainage 57850 to 64334 | TW 0004 | HS2-00002QVCX | #N/A | #N/A | #N/A
233.01-2 | HS2-00002TMFA | IDR 233.01-2 | HS2-00002TMFA | 2024-12-12 | 10 - Complete | 2024-01-14 |  | HS2-00002QVCY - Site Access Road AA Section 5 | TW 0004 - Site Access Roads AA South Chainage 57850 to 64334 | TW 0004 | HS2-00002QVCY | #N/A | #N/A | #N/A
233.01-2 | HS2-00002TMFC | IDR 233.01-2 | HS2-00002TMFC | 2024-12-12 | 10 - Complete | 2024-01-14 |  | HS2-00002QT8R - Site Access Road NCA Section 2 | TW 0003 - Site Access Roads NCA North Chainage 52000 to 57850 | TW 0003 | HS2-00002QT8R | #N/A | #N/A | #N/A
237.05 | HS2-00003B93P | IDR 237.05 | HS2-00003B93P | 2024-04-04 | 10 - Complete | 2024-04-07 |  | HS2-00002QT8W - Site Access Road NCA Section 4b | TW 0003 - Site Access Roads NCA North Chainage 52000 to 57850 | TW 0003 | HS2-00002QT8W | #N/A | #N/A | #N/A
237.05 | HS2-00003B93Q | IDR 237.05 | HS2-00003B93Q | 2024-04-04 | 10 - Complete | 2024-04-07 |  | HS2-00002QT8X - Site Access Road NCA Section 5 | TW 0003 - Site Access Roads NCA North Chainage 52000 to 57850 | TW 0003 | HS2-00002QT8X | #N/A | #N/A | #N/A
237.05 | HS2-00003B93R | IDR 237.05 | HS2-00003B93R | 2024-04-04 | 10 - Complete | 2024-04-07 |  | HS2-00002QT8P - NCA Site Access Road Risborough Road Temporary Bridge | TW 0003 - Site Access Roads NCA North Chainage 52000 to 57850 | TW 0003 | HS2-00002QT8P | #N/A | #N/A | #N/A
228.2 | HS2-000001339 | IDR 228.2 | HS2-000001339 | 2024-08-22 | 10 - Complete | 2024-10-03 |  | HS2-00002QT8U - Site Access Road NCA Section 3c | TW 0003 - Site Access Roads NCA North Chainage 52000 to 57850 | TW 0003 | HS2-00002QT8U | #N/A | #N/A | #N/A
227.1 | HS2-00003B5FR | IDR 227.1 | HS2-00003B5FR | 2024-04-04 | 10 - Complete | 2024-04-07 |  | HS2-00002QT8Q - Site Access Road NCA Section 1 | TW 0002 - Site Access Roads NCA South Chainage 47200 to 52000 | TW 0002 | HS2-00002QT8Q | #N/A | #N/A | #N/A
219.3 | HS2-00002CTA6 | IDR 219.3 | HS2-00002CTA6 | 2024-04-04 | 10 - Complete | 2024-04-08 |  | HS2-00002QT8S - Site Access Road NCA Section 3a | TW 0002 - Site Access Roads NCA South Chainage 47200 to 52000 | TW 0002 | HS2-00002QT8S | #N/A | #N/A | #N/A
UFDR 235.C | HS2-000020CJU | UFDR 235.C | HS2-000020CJU | 2024-04-05 | 10 - Complete | 2024-04-08 |  | HS2-00002QT8V - Site Access Road NCA Section 4a | TW 0002 - Site Access Roads NCA South Chainage 47200 to 52000 | TW 0002 | HS2-00002QT8V | #N/A | #N/A | #N/A
UFDR 235.C | HS2-000020CJV | UFDR 235.C | HS2-000020CJV | 2024-04-05 | 10 - Complete | 2024-04-08 |  | HS2-00002QT8T - Site Access Road NCA Section 3b | TW 0002 - Site Access Roads NCA South Chainage 47200 to 52000 | TW 0002 | HS2-00002QT8T | #N/A | #N/A | #N/A
UFDR 229.B | HS2-000020CHZ | UFDR 229.B | HS2-000020CHZ | 2024-04-05 | 10 - Complete | 2024-04-08 |  | HS2-00002E7FH - Chiltern Tunnel North Portal Compound | TW 0001 - Compounds | TW 0001 | HS2-00002E7FH | #N/A | #N/A | #N/A
UFDR 229.B | HS2-000020CJ0 | UFDR 229.B | HS2-000020CJ0 | 2024-04-05 | 10 - Complete | 2024-04-09 |  | HS2-00002CT26 - Bowood Lane Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CT26 | #N/A | #N/A | #N/A
UFDR 229.B | HS2-000020CJ1 | UFDR 229.B | HS2-000020CJ1 | 2024-04-05 | 10 - Complete | 2024-04-09 |  | HS2-00002TG33 - NRT GSM-R Compound Point 20 5596 | TW 0001 - Compounds | TW 0001 | HS2-00002TG33 | #N/A | #N/A | #N/A
UFDR 229.B | HS2-000020CJ2 | UFDR 229.B | HS2-000020CJ2 | 2024-04-05 | 10 - Complete | 2024-04-09 |  | HS2-00002CUW1 - Wendover Dean Viaduct-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUW1 | #N/A | #N/A | #N/A
UFDR 229.B | HS2-00002FE9X | UFDR 229.B | HS2-00002FE9X | 2024-04-05 | 10 - Complete | 2024-04-09 |  | HS2-00002TG34 - NRT GSM-R Compound Point 21 5597 | TW 0001 - Compounds | TW 0001 | HS2-00002TG34 | #N/A | #N/A | #N/A
UFDR 229.B | HS2-00002FE9Z | UFDR 229.B | HS2-00002FE9Z | 2024-04-05 | 10 - Complete | 2024-04-09 |  | HS2-00002CUW2 - Rocky Lane Underbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUW2 | #N/A | #N/A | #N/A
233.01-2 | HS2-00002TMFB | IDR 233.01-2 | HS2-00002TMFB | 2024-12-12 | 10 - Complete | 2025-01-22 |  | HS2-00002CUW3 - Small Dean Viaduct Launch-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUW3 | #N/A | #N/A | #N/A
235.01 | HS2-00003JG3Z | IDR 235.01 | HS2-00003JG3Z | 2024-04-05 | 10 - Complete | 2024-04-08 |  | HS2-00002VBZY - A413 London Road-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002VBZY | #N/A | #N/A | #N/A
235.01 | HS2-00003JG3Y | IDR 235.01 | HS2-00003JG3Y | 2024-04-05 | 10 - Complete | 2024-04-09 |  | HS2-00002CT3B - Small Dean Viaduct Accommodation Compound | TW 0001 - Compounds | TW 0001 | HS2-00002CT3B | #N/A | #N/A | #N/A
219.3 | HS2-000033GP3 | IDR 219.3 | HS2-000033GP3 | 2024-04-05 | 10 - Complete | 2024-04-15 |  | HS2-00002CUW4 - Grove Farm Accomodation Underbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUW4 | #N/A | #N/A | #N/A
218.02 | HS2-00002VK41 | IDR 218.02 | HS2-00002VK41 | 2024-05-07 | 10 - Complete | 2024-05-10 |  | HS2-00002UYE9 - Nash Lee Lane Road Diversion Compound | TW 0001 - Compounds | TW 0001 | HS2-00002UYE9 | #N/A | #N/A | #N/A
212.4 | HS2-00003GNAD | IDR 212.4 | HS2-00003GNAD | 2024-04-05 | 10 - Complete | 2024-04-09 |  | HS2-00002CT48 - B4009 Nash Lee Road Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CT48 | #N/A | #N/A | #N/A
212.4 | HS2-00003B5FW | IDR 212.4 | HS2-00003B5FW | 2024-04-05 | 10 - Complete | 2024-04-12 |  | HS2-00002CUW7 - Mill House South Culvert-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUW7 | #N/A | #N/A | #N/A
UFDR 228.F | HS2-00003CFCL | UFDR 228.F | HS2-00003CFCL | 2024-04-08 | 10 - Complete | 2024-04-09 |  | HS2-00002CUW8 - Risborough Road-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUW8 | #N/A | #N/A | #N/A
229.01-1 | HS2-00002C3YS | IDR 229.01-1 | HS2-00002C3YS | 2025-02-17 | 10 - Complete | 2025-02-20 |  | HS2-00002CUW9 - Footpath SMA 9 Accommodation Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUW9 | #N/A | #N/A | #N/A
237.05 | HS2-000020P0N | IDR 237.05 | HS2-000020P0N | 2024-11-26 | 10 - Complete | 2025-01-10 |  | HS2-00002TG37 - NRT GSM-R Compound Point 26 5601 | TW 0001 - Compounds | TW 0001 | HS2-00002TG37 | #N/A | #N/A | #N/A
218.02 | HS2-000035UXF | IDR 218.02 | HS2-000035UXF | 2025-02-06 | 10 - Complete | 2025-03-27 |  | HS2-00002CUWA - A4010 Stoke Mandeville Bypass Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWA | #N/A | #N/A | #N/A
212.4 | HS2-00002CT67 | IDR 212.4 | HS2-00002CT67 | 2024-04-08 | 10 - Complete | 2024-04-26 |  | HS2-00002CUWB - Princes Risborough to Aylesbury Rail Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWB | #N/A | #N/A | #N/A
212.4 | HS2-00002CT6A | IDR 212.4 | HS2-00002CT6A | 2024-04-08 | 10 - Complete | 2024-04-29 |  | HS2-00002CUWC - Bridleway SBH 19 Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWC | #N/A | #N/A | #N/A
218.02 | HS2-00002YXB3 | IDR 218.02 | HS2-00002YXB3 | 2024-04-09 | 10 - Complete | 2024-04-30 |  | HS2-00002CT5E - Footpath SBH 32 Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CT5E | #N/A | #N/A | #N/A
218.02 | HS2-00002YXB4 | IDR 218.02 | HS2-00002YXB4 | 2024-04-09 | 10 - Complete | 2024-04-30 |  | HS2-00002CUWD - A418 Oxford Road Overbridge Compound | TW 0001 - Compounds | TW 0001 | HS2-00002CUWD | #N/A | #N/A | #N/A
218.02 | HS2-00003124G | IDR 218.02 | HS2-00003124G | 2024-04-09 | 10 - Complete | 2024-04-30 |  | HS2-00002CUWE - Bridleway SBH 2 Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWE | #N/A | #N/A | #N/A
218.02 | HS2-00003124H | IDR 218.02 | HS2-00003124H | 2024-04-09 | 10 - Complete | 2024-05-01 |  | HS2-00002CT65 - Thame Valley Viaduct-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CT65 | #N/A | #N/A | #N/A
218.02 | HS2-00003124J | IDR 218.02 | HS2-00003124J | 2024-04-09 | 10 - Complete | 2024-05-01 |  | HS2-00002TG38 - NRT GSM-R Compound Point 31 5605 | TW 0001 - Compounds | TW 0001 | HS2-00002TG38 | #N/A | #N/A | #N/A
218.02 | HS2-00003124K | IDR 218.02 | HS2-00003124K | 2024-04-09 | 10 - Complete | 2024-05-01 |  | HS2-00002CUWF - A41 Bicester Road Embankment Compound | TW 0001 - Compounds | TW 0001 | HS2-00002CUWF | #N/A | #N/A | #N/A
212.4 | HS2-00002Y47A | IDR 212.4 | HS2-00002Y47A | 2024-11-11 | 10 - Complete | 2025-01-09 |  | HS2-00002TG3V - A41 Bicester Road embankment (North) Batching Plant | TW 0001 - Compounds | TW 0001 | HS2-00002TG3V | #N/A | #N/A | #N/A
233.01-2 | HS2-00002NJ06 | IDR 233.01-2 | HS2-00002NJ06 | 2024-04-10 | 10 - Complete | 2024-05-02 |  | HS2-00002TG39 - NRT GSM-R Compound Point 32 5606C | TW 0001 - Compounds | TW 0001 | HS2-00002TG39 | #N/A | #N/A | #N/A
233.01-2 | HS2-00002NJ06 | IDR 233.01-2 | HS2-00002NJ06 | 2024-04-10 | 10 - Complete | 2024-05-02 |  | HS2-00002CUWH - A41 Bicester Road Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWH | #N/A | #N/A | #N/A
233.01-2 | HS2-00002NJ06 | IDR 233.01-2 | HS2-00002NJ06 | 2024-04-10 | 10 - Complete | 2024-05-02 |  | HS2-00002TG3A - NRT GSM-R Compound Point 33 5607 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3A | #N/A | #N/A | #N/A
229.01-1 | HS2-00002TMF1 | IDR 229.01-1 | HS2-00002TMF1 | 2024-12-23 | 10 - Complete | 2025-01-14 |  | HS2-00002CUWK - Waddesdon-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWK | #N/A | #N/A | #N/A
229.01-1 | HS2-00002TMF2 | IDR 229.01-1 | HS2-00002TMF2 | 2024-12-23 | 10 - Complete | 2025-01-15 |  | HS2-00002CUWL - Needles Farm Accommodation Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWL | #N/A | #N/A | #N/A
229.01-1 | HS2-00002TMF4 | IDR 229.01-1 | HS2-00002TMF4 | 2024-12-23 | 10 - Complete | 2025-01-17 |  | HS2-00002SW8R - Quainton Road Temporary Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002SW8R | #N/A | #N/A | #N/A
237.05 | HS2-000020P16 | IDR 237.05 | HS2-000020P16 | 2024-04-10 | 10 - Complete | 2024-04-17 |  | HS2-00002CUWM - Station Road Overbridge Compound | TW 0001 - Compounds | TW 0001 | HS2-00002CUWM | #N/A | #N/A | #N/A
235.01 | HS2-00002CTJD | IDR 235.01 | HS2-00002CTJD | 2024-04-10 | 10 - Complete | 2024-04-16 |  | HS2-00002CUWN - Bridleway QUA 28A Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWN | #N/A | #N/A | #N/A
235.01 | HS2-00002CTJE | IDR 235.01 | HS2-00002CTJE | 2024-04-10 | 10 - Complete | 2024-04-17 |  | HS2-00002CUWP - Woodlands Cutting-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWP | #N/A | #N/A | #N/A
229.03 | HS2-00003124E | IDR 229.03 | HS2-00003124E | 2024-07-30 | 10 - Complete | 2024-08-09 |  | HS2-00002HUS2 - Edgcott Road Compound | TW 0001 - Compounds | TW 0001 | HS2-00002HUS2 | #N/A | #N/A | #N/A
227.1 | HS2-00002CQQF | IDR 227.1 | HS2-00002CQQF | 2024-04-10 | 10 - Complete | 2024-04-15 |  | HS2-00002CUWQ - FCC Sidings-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWQ | #N/A | #N/A | #N/A
215.02-02 | HS2-00002CT8Y | IDR 215.02-02 | HS2-00002CT8Y | 2025-01-29 | 10 - Complete | 2025-02-12 |  | HS2-00002CUWR - Footpath SCL 13 Green Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWR | #N/A | #N/A | #N/A
227.B | HS2-000020CHM | IDR 227.B | HS2-000020CHM | 2024-04-12 | 10 - Complete | 2024-04-19 |  | HS2-00002GBX6 - Bicester Main Compound | TW 0001 - Compounds | TW 0001 | HS2-00002GBX6 | #N/A | #N/A | #N/A
227.B | HS2-0000245Z9 | IDR 227.B | HS2-0000245Z9 | 2024-04-12 | 10 - Complete | 2024-04-19 |  | HS2-00002T6DL - Bicester Site G Compound | TW 0001 - Compounds | TW 0001 | HS2-00002T6DL | #N/A | #N/A | #N/A
227.B | HS2-00002FE9M | IDR 227.B | HS2-00002FE9M | 2024-04-12 | 10 - Complete | 2024-04-15 |  | HS2-00002TFS3 - Logistics Consolidation Centre | TW 0001 - Compounds | TW 0001 | HS2-00002TFS3 | #N/A | #N/A | #N/A
227.B | HS2-00002FE9P | IDR 227.B | HS2-00002FE9P | 2024-04-12 | 10 - Complete | 2024-04-19 |  | HS2-00002SW48 - FCC Offloading Platform and Satellite Compound | TW 0001 - Compounds | TW 0001 | HS2-00002SW48 | #N/A | #N/A | #N/A
225 | HS2-00002CTE3 | IDR 225 | HS2-00002CTE3 | 2024-04-12 | 10 - Complete | 2024-04-22 |  | HS2-00002TG3B - NRT GSM-R Compound Point 37 5609 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3B | #N/A | #N/A | #N/A
219.3 | HS2-00002YCW4 | IDR 219.3 | HS2-00002YCW4 | 2024-04-12 | 10 - Complete | 2024-05-03 |  | HS2-00002CUWS - School Hill Green Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWS | #N/A | #N/A | #N/A
219.3 | HS2-000031EEZ | IDR 219.3 | HS2-000031EEZ | 2024-05-28 | 10 - Complete | 2024-05-29 |  | HS2-00002TG3W - Milton Keynes HQ | TW 0001 - Compounds | TW 0001 | HS2-00002TG3W | #N/A | #N/A | #N/A
219.3 | HS2-000031EF0 | IDR 219.3 | HS2-000031EF0 | 2024-04-12 | 10 - Complete | 2024-05-08 |  | HS2-00002CUWT - Aylesbury Link-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWT | #N/A | #N/A | #N/A
219.3 | HS2-000037YLE | IDR 219.3 | HS2-000037YLE | 2024-04-12 | 10 - Complete | 2024-04-30 |  | HS2-00002CUWU - Addison Road Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWU | #N/A | #N/A | #N/A
219.3 | HS2-000037YLG | IDR 219.3 | HS2-000037YLG | 2024-04-12 | 10 - Complete | 2024-04-30 |  | HS2-00002CUWV - Charndon Lodge Underbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWV | #N/A | #N/A | #N/A
UFDR 211.A | HS2-000020CFE | UFDR 211.A | HS2-000020CFE | 2024-12-12 | 10 - Complete | 2024-12-13 |  | HS2-00002TGMN - PRS Area Satellite Site Compound | TW 0001 - Compounds | TW 0001 | HS2-00002TGMN | #N/A | #N/A | #N/A
UFDR 211.A | HS2-000020CFF | UFDR 211.A | HS2-000020CFF | 2024-04-15 | 10 - Complete | 2024-04-17 |  | HS2-00002TG3C - NRT GSM-R Compound Point 39 5610 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3C | #N/A | #N/A | #N/A
UFDR 211.A | HS2-000020CFG | UFDR 211.A | HS2-000020CFG | 2024-04-15 | 10 - Complete | 2024-04-19 |  | HS2-00002CUWW - West Street Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWW | #N/A | #N/A | #N/A
UFDR 211.A | HS2-000031J4L | UFDR 211.A | HS2-000031J4L | 2024-12-12 | 10 - Complete | 2024-12-16 |  | HS2-00002CUWX - West Street Compound | TW 0001 - Compounds | TW 0001 | HS2-00002CUWX | #N/A | #N/A | #N/A
238.02-2 | HS2-000020P2P | IDR 238.02-2 | HS2-000020P2P | 2024-11-19 | 10 - Complete | 2024-11-25 |  | HS2-00002CUWY - Twyford Viaduct-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWY | #N/A | #N/A | #N/A
238.02-2 | HS2-00002CTKE | IDR 238.02-2 | HS2-00002CTKE | 2024-11-19 | 10 - Complete | 2024-11-22 |  | HS2-00002CUWZ - Restricted Byway PBI 5A Accommodation Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUWZ | #N/A | #N/A | #N/A
214.09 | HS2-00002TTH6 | IDR 214.09 | HS2-00002TTH6 | 2024-04-15 | 10 - Complete | 2024-04-17 |  | HS2-00002TG3D - NRT GSM-R Compound Point 40 5611 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3D | #N/A | #N/A | #N/A
238.01 | HS2-00002CTK9 | IDR 238.01 | HS2-00002CTK9 | 2024-05-09 | 10 - Complete | 2024-05-14 |  | HS2-00002CUX0 - Godington East West Viaduct-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUX0 | #N/A | #N/A | #N/A
227.1 | HS2-000001336 | IDR 227.1 | HS2-000001336 | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002U7K5 - Chetwode Manor Road Compound | TW 0001 - Compounds | TW 0001 | HS2-00002U7K5 | #N/A | #N/A | #N/A
219.3 | HS2-000033XXU | IDR 219.3 | HS2-000033XXU | 2024-04-15 | 10 - Complete | 2024-04-23 |  | HS2-00002CTAV - Chetwode Cutting-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CTAV | #N/A | #N/A | #N/A
219.3 | HS2-000033XXV | IDR 219.3 | HS2-000033XXV | 2024-04-15 | 10 - Complete | 2024-04-23 |  | HS2-00002TG3E - NRT GSM-R Compound Point 41 5612 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3E | #N/A | #N/A | #N/A
219.3 | HS2-000033XXW | IDR 219.3 | HS2-000033XXW | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002TKM9 - School End Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002TKM9 | #N/A | #N/A | #N/A
219.3 | HS2-000033XXX | IDR 219.3 | HS2-000033XXX | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002CUX1 - Footpath BHA 2 Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUX1 | #N/A | #N/A | #N/A
219.3 | HS2-000033XXY | IDR 219.3 | HS2-000033XXY | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002NJWN - A4421 South Temporary Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002NJWN | #N/A | #N/A | #N/A
219.3 | HS2-000033XXZ | IDR 219.3 | HS2-000033XXZ | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002CTBD - A4421 Buckingham Road Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CTBD | #N/A | #N/A | #N/A
219.3 | HS2-000033XY0 | IDR 219.3 | HS2-000033XY0 | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002CUX2 - Bridleway 213 7 Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUX2 | #N/A | #N/A | #N/A
219.3 | HS2-000033XY1 | IDR 219.3 | HS2-000033XY1 | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002TG3F - NRT GSM-R Compound Point 42 5613 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3F | #N/A | #N/A | #N/A
219.3 | HS2-000033XY2 | IDR 219.3 | HS2-000033XY2 | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002QVD4 - A421 London Road Overbridge South WorkSite | TW 0001 - Compounds | TW 0001 | HS2-00002QVD4 | #N/A | #N/A | #N/A
219.3 | HS2-000033XY3 | IDR 219.3 | HS2-000033XY3 | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002CTBE - A421 London Road Overbridge Compound | TW 0001 - Compounds | TW 0001 | HS2-00002CTBE | #N/A | #N/A | #N/A
219.3 | HS2-000033XY4 | IDR 219.3 | HS2-000033XY4 | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002CTBF - Featherbed Lane Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CTBF | #N/A | #N/A | #N/A
219.3 | HS2-000033XY5 | IDR 219.3 | HS2-000033XY5 | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002TG3G - NRT GSM-R Compound Point 43 5614 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3G | #N/A | #N/A | #N/A
219.3 | HS2-000033XXN | IDR 219.3 | HS2-000033XXN | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002CUX5 - Bridleway 303 4 Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUX5 | #N/A | #N/A | #N/A
219.3 | HS2-000033XXP | IDR 219.3 | HS2-000033XXP | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002CUX6 - Westbury Viaduct-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUX6 | #N/A | #N/A | #N/A
219.3 | HS2-000033XXQ | IDR 219.3 | HS2-000033XXQ | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002TG3H - NRT GSM-R Compound Point 44 5615 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3H | #N/A | #N/A | #N/A
219.3 | HS2-000033XXR | IDR 219.3 | HS2-000033XXR | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002CUX7 - A422 Brackley Road Overbridge North Compound | TW 0001 - Compounds | TW 0001 | HS2-00002CUX7 | #N/A | #N/A | #N/A
219.3 | HS2-000033XXS | IDR 219.3 | HS2-000033XXS | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002CUX8 - Turweston Green Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUX8 | #N/A | #N/A | #N/A
219.3 | HS2-000033XXT | IDR 219.3 | HS2-000033XXT | 2024-04-15 | 10 - Complete | 2024-04-24 |  | HS2-00002TG3J - NRT GSM-R Compound Point 46 5617 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3J | #N/A | #N/A | #N/A
214.09 | HS2-00003G3SK | IDR 214.09 | HS2-00003G3SK | 2024-04-15 | 10 - Complete | 2024-04-17 |  | HS2-00002CUC7 - Turweston Viaduct-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUC7 | #N/A | #N/A | #N/A
212.4 | HS2-00002WUMM | IDR 212.4 | HS2-00002WUMM | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002CUC8 - A43 Brackley South Cutting Compound | TW 0001 - Compounds | TW 0001 | HS2-00002CUC8 | #N/A | #N/A | #N/A
212.4 | HS2-00002WUMN | IDR 212.4 | HS2-00002WUMN | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002TG3K - NRT GSM-R Compound Point 47 5618 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3K | #N/A | #N/A | #N/A
212.4 | HS2-00002WUMP | IDR 212.4 | HS2-00002WUMP | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002VBZX - Radstone Road South-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002VBZX | #N/A | #N/A | #N/A
212.4 | HS2-00002WUMQ | IDR 212.4 | HS2-00002WUMQ | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002CQQN - Radstone Road Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CQQN | #N/A | #N/A | #N/A
212.4 | HS2-00002WUMR | IDR 212.4 | HS2-00002WUMR | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002CUC9 - Footpath AN22 Accommodation Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUC9 | #N/A | #N/A | #N/A
212.4 | HS2-00002WUMS | IDR 212.4 | HS2-00002WUMS | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002TG3L - NRT GSM-R Compound Point 48 5619 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3L | #N/A | #N/A | #N/A
212.4 | HS2-00002WUMT | IDR 212.4 | HS2-00002WUMT | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002WF5V - Radstone North WorkSite | TW 0001 - Compounds | TW 0001 | HS2-00002WF5V | #N/A | #N/A | #N/A
212.4 | HS2-00002WUMU | IDR 212.4 | HS2-00002WUMU | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002CUCA - Bridleway AN14 Accommodation Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCA | #N/A | #N/A | #N/A
212.4 | HS2-00002WUMV | IDR 212.4 | HS2-00002WUMV | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002CUCB - Greatworth Manor-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCB | #N/A | #N/A | #N/A
212.4 | HS2-00002WUMW | IDR 212.4 | HS2-00002WUMW | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002TG3M - NRT GSM-R Compound Point 49 5620T | TW 0001 - Compounds | TW 0001 | HS2-00002TG3M | #N/A | #N/A | #N/A
212.4 | HS2-00002WUMX | IDR 212.4 | HS2-00002WUMX | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002MR36 - Greatworth Green Tunnel South Portal Building Compound | TW 0001 - Compounds | TW 0001 | HS2-00002MR36 | #N/A | #N/A | #N/A
212.4 | HS2-00002WUMY | IDR 212.4 | HS2-00002WUMY | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002GBX7 - Greatworth Park Compound | TW 0001 - Compounds | TW 0001 | HS2-00002GBX7 | #N/A | #N/A | #N/A
212.4 | HS2-00002WUMZ | IDR 212.4 | HS2-00002WUMZ | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002TZW9 - Sulgrave Road Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002TZW9 | #N/A | #N/A | #N/A
212.4 | HS2-00002WUN0 | IDR 212.4 | HS2-00002WUN0 | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002MR37 - Greatworth Green Tunnel North Portal Building Compound | TW 0001 - Compounds | TW 0001 | HS2-00002MR37 | #N/A | #N/A | #N/A
212.4 | HS2-00002WUN1 | IDR 212.4 | HS2-00002WUN1 | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002CUCD - Greatworth Green Tunnel Compound | TW 0001 - Compounds | TW 0001 | HS2-00002CUCD | #N/A | #N/A | #N/A
212.4 | HS2-00002WUN2 | IDR 212.4 | HS2-00002WUN2 | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002SY1T - Greatworth Compound | TW 0001 - Compounds | TW 0001 | HS2-00002SY1T | #N/A | #N/A | #N/A
212.4 | HS2-00002WUN3 | IDR 212.4 | HS2-00002WUN3 | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002TG3N - NRT GSM-R Compound Point 51 5622T | TW 0001 - Compounds | TW 0001 | HS2-00002TG3N | #N/A | #N/A | #N/A
212.4 | HS2-00002WUN4 | IDR 212.4 | HS2-00002WUN4 | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002CUCE - Lower Thorpe Viaduct-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCE | #N/A | #N/A | #N/A
212.4 | HS2-00002WUN5 | IDR 212.4 | HS2-00002WUN5 | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002CUCF - Culworth Grounds (AG 9) Accommodation Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCF | #N/A | #N/A | #N/A
212.4 | HS2-00002WUN6 | IDR 212.4 | HS2-00002WUN6 | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002TG3P - NRT GSM-R Compound Point 52 5623 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3P | #N/A | #N/A | #N/A
212.4 | HS2-00002WUN7 | IDR 212.4 | HS2-00002WUN7 | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002CUCG - Edgcote Viaduct South-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCG | #N/A | #N/A | #N/A
212.4 | HS2-00002WUN8 | IDR 212.4 | HS2-00002WUN8 | 2024-04-15 | 10 - Complete | 2024-04-26 |  | HS2-00002CUCH - Edgcote Viaduct North-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCH | #N/A | #N/A | #N/A
212.4 | HS2-00002WUN9 | IDR 212.4 | HS2-00002WUN9 | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002MR38 - Chipping Warden Tunnel South Portal Building Compound | TW 0001 - Compounds | TW 0001 | HS2-00002MR38 | #N/A | #N/A | #N/A
212.4 | HS2-00002WUNA | IDR 212.4 | HS2-00002WUNA | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002TG3Q - NRT GSM-R Compound Point 53 5624T | TW 0001 - Compounds | TW 0001 | HS2-00002TG3Q | #N/A | #N/A | #N/A
212.4 | HS2-00002WUNB | IDR 212.4 | HS2-00002WUNB | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002CUCJ - Chipping Warden Green Tunnel Compound | TW 0001 - Compounds | TW 0001 | HS2-00002CUCJ | #N/A | #N/A | #N/A
212.4 | HS2-00002WUNC | IDR 212.4 | HS2-00002WUNC | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002MR39 - Chipping Warden Tunnel North Portal Building Compound | TW 0001 - Compounds | TW 0001 | HS2-00002MR39 | #N/A | #N/A | #N/A
212.4 | HS2-00002WUND | IDR 212.4 | HS2-00002WUND | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002TG3R - NRT GSM-R Compound Point 55 5626T | TW 0001 - Compounds | TW 0001 | HS2-00002TG3R | #N/A | #N/A | #N/A
212.4 | HS2-00002WUNE | IDR 212.4 | HS2-00002WUNE | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002CUCK - Highfurlong Brook Viaduct-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCK | #N/A | #N/A | #N/A
212.4 | HS2-00002WUNF | IDR 212.4 | HS2-00002WUNF | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002CTHX - Claydon Road Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CTHX | #N/A | #N/A | #N/A
212.4 | HS2-00002WUNG | IDR 212.4 | HS2-00002WUNG | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002TG3S - NRT GSM-R Compound Point 56 5627 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3S | #N/A | #N/A | #N/A
212.4 | HS2-00002WUNH | IDR 212.4 | HS2-00002WUNH | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002CUCL - Banbury Road Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCL | #N/A | #N/A | #N/A
212.4 | HS2-00002WUNJ | IDR 212.4 | HS2-00002WUNJ | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002UMHL - Banbury Road Overbridge Boddington-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002UMHL | #N/A | #N/A | #N/A
212.4 | HS2-000038V0R | IDR 212.4 | HS2-000038V0R | 2024-04-15 | 10 - Complete | 2024-04-30 |  | HS2-00002CUCN - Stoneton Lane Green Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCN | #N/A | #N/A | #N/A
UFDR 216.D | HS2-00002TUPL | UFDR 216.D | HS2-00002TUPL | 2024-04-16 | 10 - Complete | 2024-04-19 |  | HS2-00002TG3T - NRT GSM-R Compound Point 57 5628 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3T | #N/A | #N/A | #N/A
UFDR 216.D | HS2-00002NHZA | UFDR 216.D | HS2-00002NHZA | 2024-04-16 | 10 - Complete | 2024-04-19 |  | HS2-00002CUCP - Footpath SM116a Underpass-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCP | #N/A | #N/A | #N/A
UFDR 216.D | HS2-00002TUPP | UFDR 216.D | HS2-00002TUPP | 2024-04-16 | 10 - Complete | 2024-04-22 |  | HS2-00002CUCQ - Oxford Canal Viaduct-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCQ | #N/A | #N/A | #N/A
UFDR 216.D | HS2-00002TUPQ | UFDR 216.D | HS2-00002TUPQ | 2024-04-16 | 10 - Complete | 2024-04-19 |  | HS2-00002CUCR - Oxford Canal North Embankment-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCR | #N/A | #N/A | #N/A
UFDR 216.D | HS2-00002TUPM | UFDR 216.D | HS2-00002TUPM | 2024-04-16 | 10 - Complete | 2024-04-22 |  | HS2-000020902 - Lower Radbourne South Viaduct-Worksite | TW 0001 - Compounds | TW 0001 | HS2-000020902 | #N/A | #N/A | #N/A
UFDR 216.D | HS2-00002TTR1 | UFDR 216.D | HS2-00002TTR1 | 2024-04-16 | 10 - Complete | 2024-04-22 |  | HS2-00002U6KH - Lower Radbourne Farm Accommodation Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002U6KH | #N/A | #N/A | #N/A
UFDR 216.D | HS2-00002TTR0 | UFDR 216.D | HS2-00002TTR0 | 2024-04-16 | 10 - Complete | 2024-04-22 |  | HS2-00002CUCT - Lower Radbourne Farm Accommodation Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCT | #N/A | #N/A | #N/A
UFDR 216.D | HS2-000020CGE | UFDR 216.D | HS2-000020CGE | 2024-04-16 | 10 - Complete | 2024-04-22 |  | HS2-00002CUCV - Windmill Lane Green Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCV | #N/A | #N/A | #N/A
UFDR 216.D | HS2-000020CGD | UFDR 216.D | HS2-000020CGD | 2024-04-16 | 10 - Complete | 2024-04-19 |  | HS2-00002TG3U - NRT GSM-R Compound Point 59 5630 | TW 0001 - Compounds | TW 0001 | HS2-00002TG3U | #N/A | #N/A | #N/A
UFDR 216.D | HS2-00002YGQH | UFDR 216.D | HS2-00002YGQH | 2024-04-16 | 10 - Complete | 2024-04-24 |  | HS2-00002U6KF - Windmill Lane Green Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002U6KF | #N/A | #N/A | #N/A
UFDR 216.D | HS2-00002TUPN | UFDR 216.D | HS2-00002TUPN | 2024-04-16 | 10 - Complete | 2024-04-19 |  | HS2-00002CUCW - A423 Banbury Road Overbridge Compound | TW 0001 - Compounds | TW 0001 | HS2-00002CUCW | #N/A | #N/A | #N/A
UFDR 208.B | HS2-000020CEY | UFDR 208.B | HS2-000020CEY | 2024-04-16 | 10 - Complete | 2024-04-23 |  | HS2-00002SY1S - A423 Banbury Road Overbridge Compound | TW 0001 - Compounds | TW 0001 | HS2-00002SY1S | #N/A | #N/A | #N/A
223.8 | HS2-000037YLY | IDR 223.8 | HS2-000037YLY | 2024-06-12 | 10 - Complete | 2024-06-21 |  | HS2-00002U7K3 - A423 North-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002U7K3 | #N/A | #N/A | #N/A
223.8 | HS2-000037YLZ | IDR 223.8 | HS2-000037YLZ | 2024-06-12 | 10 - Complete | 2024-06-21 |  | HS2-00002CUCX - B4451 Kineton Road Overbridge-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCX | #N/A | #N/A | #N/A
223.8 | HS2-00002YCW9 | IDR 223.8 | HS2-00002YCW9 | 2024-06-12 | 10 - Complete | 2024-06-21 |  | HS2-00002U7K1 - A425 Compound (Southam) | TW 0001 - Compounds | TW 0001 | HS2-00002U7K1 | #N/A | #N/A | #N/A
221.2 | HS2-00002BJUR | IDR 221.2 | HS2-00002BJUR | 2024-04-16 | 10 - Complete | 2024-04-19 |  | HS2-00002CUCY - River Itchen Viaduct-Worksite | TW 0001 - Compounds | TW 0001 | HS2-00002CUCY | #N/A | #N/A | #N/A
221.2 | HS2-000020NM3 | IDR 221.2 | HS2-000020NM3 | 2024-04-16 | 10 - Complete | 2024-04-19 |  | HS2-00002NFPR - Halse Copse Farm | TW 0001 - Compounds | TW 0001 | HS2-00002NFPR | #N/A | #N/A | #N/A
221.2 | HS2-000020NM2 | IDR 221.2 | HS2-000020NM2 | 2024-04-16 | 10 - Complete | 2024-04-23 |  | HS2-00002XN6T - Chipping Warden Plant Servicing Compound | TW 0001 - Compounds | TW 0001 | HS2-00002XN6T | #N/A | #N/A | #N/A
221.2 | HS2-00002VXUC | IDR 221.2 | HS2-00002VXUC | 2024-04-16 | 10 - Complete | 2024-04-23 |  | HS2-000030RKN - A413 Pier Worksite | TW 0001 - Compounds | TW 0001 | HS2-000030RKN | #N/A | #N/A | #N/A
208.4 | HS2-00002CW0R | IDR 208.4 | HS2-00002CW0R | 2024-04-16 | 10 - Complete | 2024-04-30 |  | HS2-00002NAA6 - Culworth Road Compound | TW 0001 - Compounds | TW 0001 | HS2-00002NAA6 | #N/A | #N/A | #N/A
218.02-1 | HS2-00002NSXQ | IDR 218.02-1 | HS2-00002NSXQ | 2024-08-19 | 10 - Complete | 2024-08-29 |  | HS2-00003H0FN - CFA_16_68_Site_Restoration | SR_CFA_16_68 - Site Restoration - SR_CFA_16_68 | SR_CFA_16_68 | HS2-00003H0FN | #N/A | #N/A | #N/A
218.02-1 | HS2-00002NSXP | IDR 218.02-1 | HS2-00002NSXP | 2024-04-17 | 99 - Cancelled | 0 |  | HS2-00003H0FM - CFA_16_67_Site_Restoration | SR_CFA_16_67 - Site Restoration - SR_CFA_16_67 | SR_CFA_16_67 | HS2-00003H0FM | #N/A | #N/A | #N/A
204.1-1 | HS2-000001024 | IDR 204.1-1 | HS2-000001024 | 2024-04-17 | 10 - Complete | 2024-05-02 |  | HS2-00003H0FL - CFA_16_66_Site_Restoration | SR_CFA_16_66 - Site Restoration - SR_CFA_16_66 | SR_CFA_16_66 | HS2-00003H0FL | #N/A | #N/A | #N/A
204.1-1 | HS2-00002Y8VY | IDR 204.1-1 | HS2-00002Y8VY | 2024-04-17 | 10 - Complete | 2024-05-02 |  | HS2-00003H0FK - CFA_16_65_Site_Restoration | SR_CFA_16_65 - Site Restoration - SR_CFA_16_65 | SR_CFA_16_65 | HS2-00003H0FK | #N/A | #N/A | #N/A
219.3 | HS2-0000386UA | IDR 219.3 | HS2-0000386UA | 2024-04-17 | 10 - Complete | 2024-04-22 |  | HS2-00003H0FJ - CFA_16_64_Site_Restoration | SR_CFA_16_64 - Site Restoration - SR_CFA_16_64 | SR_CFA_16_64 | HS2-00003H0FJ | #N/A | #N/A | #N/A
218.02 | HS2-000020NKT | IDR 218.02 | HS2-000020NKT | 2024-04-17 | 10 - Complete | 2024-05-09 |  | HS2-00003H0FH - CFA_16_61_Site_Restoration | SR_CFA_16_61 - Site Restoration - SR_CFA_16_61 | SR_CFA_16_61 | HS2-00003H0FH | #N/A | #N/A | #N/A
218.02 | HS2-00003124B | IDR 218.02 | HS2-00003124B | 2024-04-17 | 10 - Complete | 2024-05-09 |  | HS2-00003H0FG - CFA_16_60_Site_Restoration | SR_CFA_16_60 - Site Restoration - SR_CFA_16_60 | SR_CFA_16_60 | HS2-00003H0FG | #N/A | #N/A | #N/A
218.02 | HS2-00003124C | IDR 218.02 | HS2-00003124C | 2024-05-14 | 10 - Complete | 2024-05-15 |  | HS2-00003H0FF - CFA_16_59_Site_Restoration | SR_CFA_16_59 - Site Restoration - SR_CFA_16_59 | SR_CFA_16_59 | HS2-00003H0FF | #N/A | #N/A | #N/A
218.02 | HS2-00003CCJX | IDR 218.02 | HS2-00003CCJX | 2024-04-17 | 10 - Complete | 2024-05-09 |  | HS2-00003H0FE - CFA_16_57_Site_Restoration | SR_CFA_16_57 - Site Restoration - SR_CFA_16_57 | SR_CFA_16_57 | HS2-00003H0FE | #N/A | #N/A | #N/A
204.2-1 | HS2-00002CT4P | IDR 204.2-1 | HS2-00002CT4P | 2024-04-18 | 10 - Complete | 2024-04-19 |  | HS2-00003H0FD - CFA_16_56_Site_Restoration | SR_CFA_16_56 - Site Restoration - SR_CFA_16_56 | SR_CFA_16_56 | HS2-00003H0FD | #N/A | #N/A | #N/A
201.0-6 | HS2-00002CT2H | IDR 201.0-6 | HS2-00002CT2H | 2024-05-01 | 10 - Complete | 2024-05-07 |  | HS2-00003H0FC - CFA_16_55_Site_Restoration | SR_CFA_16_55 - Site Restoration - SR_CFA_16_55 | SR_CFA_16_55 | HS2-00003H0FC | #N/A | #N/A | #N/A
227.1 | HS2-00002N7X2 | IDR 227.1 | HS2-00002N7X2 | 2024-04-19 | 10 - Complete | 2024-04-25 |  | HS2-00003H0FB - CFA_16_54_Site_Restoration | SR_CFA_16_54 - Site Restoration - SR_CFA_16_54 | SR_CFA_16_54 | HS2-00003H0FB | #N/A | #N/A | #N/A
212.4 | HS2-00002CT6E | IDR 212.4 | HS2-00002CT6E | 2024-04-19 | 10 - Complete | 2024-04-29 |  | HS2-00003H0FA - CFA_16_52_Site_Restoration | SR_CFA_16_52 - Site Restoration - SR_CFA_16_52 | SR_CFA_16_52 | HS2-00003H0FA | #N/A | #N/A | #N/A
212.4 | HS2-00002CT6D | IDR 212.4 | HS2-00002CT6D | 2024-04-19 | 10 - Complete | 2024-04-29 |  | HS2-00003H0F9 - CFA_16_51_Site_Restoration | SR_CFA_16_51 - Site Restoration - SR_CFA_16_51 | SR_CFA_16_51 | HS2-00003H0F9 | #N/A | #N/A | #N/A
212.4 | HS2-00002CT6B | IDR 212.4 | HS2-00002CT6B | 2024-04-19 | 10 - Complete | 2024-04-29 |  | HS2-00003H0F8 - CFA_16_16_Site_Restoration | SR_CFA_16_16 - Site Restoration - SR_CFA_16_16 | SR_CFA_16_16 | HS2-00003H0F8 | #N/A | #N/A | #N/A
212.4 | HS2-00002CT68 | IDR 212.4 | HS2-00002CT68 | 2024-04-19 | 10 - Complete | 2024-04-29 |  | HS2-00003H0F7 - CFA_16_15_Site_Restoration | SR_CFA_16_15 - Site Restoration - SR_CFA_16_15 | SR_CFA_16_15 | HS2-00003H0F7 | #N/A | #N/A | #N/A
212.4 | HS2-00002CT5Z | IDR 212.4 | HS2-00002CT5Z | 2024-04-19 | 10 - Complete | 2024-04-29 |  | HS2-00003H0F6 - CFA_16_14_Site_Restoration | SR_CFA_16_14 - Site Restoration - SR_CFA_16_14 | SR_CFA_16_14 | HS2-00003H0F6 | #N/A | #N/A | #N/A
212.4 | HS2-00002CT5X | IDR 212.4 | HS2-00002CT5X | 2024-04-19 | 10 - Complete | 2024-04-29 |  | HS2-00003H0F5 - CFA_16_13_Site_Restoration | SR_CFA_16_13 - Site Restoration - SR_CFA_16_13 | SR_CFA_16_13 | HS2-00003H0F5 | #N/A | #N/A | #N/A
212.4 | HS2-00002CT6K | IDR 212.4 | HS2-00002CT6K | 2024-04-19 | 10 - Complete | 2024-04-29 |  | HS2-00003H0F4 - CFA_16_12_Site_Restoration | SR_CFA_16_12 - Site Restoration - SR_CFA_16_12 | SR_CFA_16_12 | HS2-00003H0F4 | #N/A | #N/A | #N/A
212.4 | HS2-00002CT6H | IDR 212.4 | HS2-00002CT6H | 2024-04-19 | 10 - Complete | 2024-04-29 |  | HS2-00003H0F3 - CFA_16_11_Site_Restoration | SR_CFA_16_11 - Site Restoration - SR_CFA_16_11 | SR_CFA_16_11 | HS2-00003H0F3 | #N/A | #N/A | #N/A
233.01-2 | HS2-000020364 | IDR 233.01-2 | HS2-000020364 | 2025-02-06 | 10 - Complete | 2025-02-12 |  | HS2-00003H0F2 - CFA_16_10_Site_Restoration | SR_CFA_16_10 - Site Restoration - SR_CFA_16_10 | SR_CFA_16_10 | HS2-00003H0F2 | #N/A | #N/A | #N/A
229.01-1 | HS2-00002CTF8 | IDR 229.01-1 | HS2-00002CTF8 | 2024-04-22 | 10 - Complete | 2024-05-03 |  | HS2-00003H0F1 - CFA_16_09_Site_Restoration | SR_CFA_16_09 - Site Restoration - SR_CFA_16_09 | SR_CFA_16_09 | HS2-00003H0F1 | #N/A | #N/A | #N/A
229.01-1 | HS2-00002CTF7 | IDR 229.01-1 | HS2-00002CTF7 | 2024-04-22 | 10 - Complete | 2024-05-03 |  | HS2-00003H0F0 - CFA_16_08_Site_Restoration | SR_CFA_16_08 - Site Restoration - SR_CFA_16_08 | SR_CFA_16_08 | HS2-00003H0F0 | #N/A | #N/A | #N/A
237.05 | HS2-00002BVMZ | IDR 237.05 | HS2-00002BVMZ | 2024-04-22 | 10 - Complete | 2024-05-01 |  | HS2-00003H0EZ - CFA_16_07_Site_Restoration | SR_CFA_16_07 - Site Restoration - SR_CFA_16_07 | SR_CFA_16_07 | HS2-00003H0EZ | #N/A | #N/A | #N/A
218.02 | HS2-000031248 | IDR 218.02 | HS2-000031248 | 2024-07-05 | 10 - Complete | 2024-07-11 |  | HS2-00003H0EY - CFA_16_06_Site_Restoration | SR_CFA_16_06 - Site Restoration - SR_CFA_16_06 | SR_CFA_16_06 | HS2-00003H0EY | #N/A | #N/A | #N/A
238.02-2 | HS2-000025B3T | IDR 238.02-2 | HS2-000025B3T | 2024-11-21 | 10 - Complete | 2024-11-22 |  | HS2-00003H0EX - CFA_16_05_Site_Restoration | SR_CFA_16_05 - Site Restoration - SR_CFA_16_05 | SR_CFA_16_05 | HS2-00003H0EX | #N/A | #N/A | #N/A
204.2-1 | HS2-00002TKV4 | IDR 204.2-1 | HS2-00002TKV4 | 2024-04-23 | 10 - Complete | 2024-04-24 |  | HS2-00003H0EW - CFA_16_04_Site_Restoration | SR_CFA_16_04 - Site Restoration - SR_CFA_16_04 | SR_CFA_16_04 | HS2-00003H0EW | #N/A | #N/A | #N/A
201.0-6 | HS2-00002BJQX | IDR 201.0-6 | HS2-00002BJQX | 2024-05-01 | 10 - Complete | 2024-05-07 |  | HS2-00003H0EV - CFA_16_03_Site_Restoration | SR_CFA_16_03 - Site Restoration - SR_CFA_16_03 | SR_CFA_16_03 | HS2-00003H0EV | #N/A | #N/A | #N/A
237.05 | HS2-00002EK8B | IDR 237.05 | HS2-00002EK8B | 2024-04-23 | 10 - Complete | 2024-04-25 |  | HS2-00003H0EU - CFA_16_02a_Site_Restoration | SR_CFA_16_02a - Site Restoration - SR_CFA_16_02a | SR_CFA_16_02a | HS2-00003H0EU | #N/A | #N/A | #N/A
213.05 | HS2-00002CW0N | IDR 213.05 | HS2-00002CW0N | 2025-01-10 | 10 - Complete | 2025-01-17 |  | HS2-00003H0ET - CFA_16_02_Site_Restoration | SR_CFA_16_02 - Site Restoration - SR_CFA_16_02 | SR_CFA_16_02 | HS2-00003H0ET | #N/A | #N/A | #N/A
221.2_1 | HS2-000001321 | IDR 221.2_1 | HS2-000001321 | 2024-04-24 | 10 - Complete | 2024-04-25 |  | HS2-00003H0ES - CFA_16_01_Site_Restoration | SR_CFA_16_01 - Site Restoration - SR_CFA_16_01 | SR_CFA_16_01 | HS2-00003H0ES | #N/A | #N/A | #N/A
227.1 | HS2-000025B28 | IDR 227.1 | HS2-000025B28 | 2024-04-24 | 10 - Complete | 2024-04-29 |  | HS2-00003H0ER - CFA_15_68_Site_Restoration | SR_CFA_15_68 - Site Restoration - SR_CFA_15_68 | SR_CFA_15_68 | HS2-00003H0ER | #N/A | #N/A | #N/A
227.1 | HS2-000025B29 | IDR 227.1 | HS2-000025B29 | 2024-04-24 | 10 - Complete | 2024-04-29 |  | HS2-00003H0EQ - CFA_15_67_Site_Restoration | SR_CFA_15_67 - Site Restoration - SR_CFA_15_67 | SR_CFA_15_67 | HS2-00003H0EQ | #N/A | #N/A | #N/A
218.02 | HS2-00003CCJY | IDR 218.02 | HS2-00003CCJY | 2024-04-24 | 10 - Complete | 2024-05-07 |  | HS2-00003H0EP - CFA_15_66_Site_Restoration | SR_CFA_15_66 - Site Restoration - SR_CFA_15_66 | SR_CFA_15_66 | HS2-00003H0EP | #N/A | #N/A | #N/A
218.02 | HS2-00003124A | IDR 218.02 | HS2-00003124A | 2024-06-10 | 10 - Complete | 2024-06-12 |  | HS2-00003H0EN - CFA_15_65_Site_Restoration | SR_CFA_15_65 - Site Restoration - SR_CFA_15_65 | SR_CFA_15_65 | HS2-00003H0EN | #N/A | #N/A | #N/A
218.02 | HS2-00002TPZ5 | IDR 218.02 | HS2-00002TPZ5 | 2024-06-10 | 10 - Complete | 2024-06-12 |  | HS2-00003H0EM - CFA_15_64_Site_Restoration | SR_CFA_15_64 - Site Restoration - SR_CFA_15_64 | SR_CFA_15_64 | HS2-00003H0EM | #N/A | #N/A | #N/A
218.02 | HS2-00002CT9Q | IDR 218.02 | HS2-00002CT9Q | 2024-04-24 | 10 - Complete | 2024-05-03 |  | HS2-00003H0EL - CFA_15_63_Site_Restoration | SR_CFA_15_63 - Site Restoration - SR_CFA_15_63 | SR_CFA_15_63 | HS2-00003H0EL | #N/A | #N/A | #N/A
218.02 | HS2-00002CT9N | IDR 218.02 | HS2-00002CT9N | 2024-04-24 | 10 - Complete | 2024-05-03 |  | HS2-00003H0EK - CFA_15_62_Site_Restoration | SR_CFA_15_62 - Site Restoration - SR_CFA_15_62 | SR_CFA_15_62 | HS2-00003H0EK | #N/A | #N/A | #N/A
218.02 | HS2-00002CTDA | IDR 218.02 | HS2-00002CTDA | 2024-04-24 | 10 - Complete | 2024-05-03 |  | HS2-00003H0EJ - CFA_15_61_Site_Restoration | SR_CFA_15_61 - Site Restoration - SR_CFA_15_61 | SR_CFA_15_61 | HS2-00003H0EJ | #N/A | #N/A | #N/A
218.02 | HS2-00002CTD9 | IDR 218.02 | HS2-00002CTD9 | 2024-04-24 | 10 - Complete | 2024-05-03 |  | HS2-00003H0EH - CFA_15_60_Site_Restoration | SR_CFA_15_60 - Site Restoration - SR_CFA_15_60 | SR_CFA_15_60 | HS2-00003H0EH | #N/A | #N/A | #N/A
208.4 | HS2-00002N7VS | IDR 208.4 | HS2-00002N7VS | 2024-04-24 | 10 - Complete | 2024-05-03 |  | HS2-00003H0EG - CFA_15_59_Site_Restoration | SR_CFA_15_59 - Site Restoration - SR_CFA_15_59 | SR_CFA_15_59 | HS2-00003H0EG | #N/A | #N/A | #N/A
208.4 | HS2-00002N7VT | IDR 208.4 | HS2-00002N7VT | 2024-04-24 | 10 - Complete | 2024-05-03 |  | HS2-00003H0EF - CFA_15_58_Site_Restoration | SR_CFA_15_58 - Site Restoration - SR_CFA_15_58 | SR_CFA_15_58 | HS2-00003H0EF | #N/A | #N/A | #N/A
235.01-1 | HS2-000025B3A | IDR 235.01-1 | HS2-000025B3A | 2025-02-14 | 10 - Complete | 2025-02-18 |  | HS2-00003H0EE - CFA_15_57_Site_Restoration | SR_CFA_15_57 - Site Restoration - SR_CFA_15_57 | SR_CFA_15_57 | HS2-00003H0EE | #N/A | #N/A | #N/A
235.01-1 | HS2-00002J4YX | IDR 235.01-1 | HS2-00002J4YX | 2025-02-14 | 10 - Complete | 2025-02-18 |  | HS2-00003H0ED - CFA_15_56_Site_Restoration | SR_CFA_15_56 - Site Restoration - SR_CFA_15_56 | SR_CFA_15_56 | HS2-00003H0ED | #N/A | #N/A | #N/A
233.01 | HS2-00002EF97 | IDR 233.01 | HS2-00002EF97 | 2024-04-25 | 10 - Complete | 2024-05-09 |  | HS2-00003H0EC - CFA_15_55_Site_Restoration | SR_CFA_15_55 - Site Restoration - SR_CFA_15_55 | SR_CFA_15_55 | HS2-00003H0EC | #N/A | #N/A | #N/A
229.01-1 | HS2-00002TMF3 | IDR 229.01-1 | HS2-00002TMF3 | 2024-12-23 | 10 - Complete | 2025-01-17 |  | HS2-00003H0EB - CFA_15_54_Site_Restoration | SR_CFA_15_54 - Site Restoration - SR_CFA_15_54 | SR_CFA_15_54 | HS2-00003H0EB | #N/A | #N/A | #N/A
204.1-1 | HS2-000030KBA | IDR 204.1-1 | HS2-000030KBA | 2024-04-26 | 10 - Complete | 2024-05-08 |  | HS2-00003H0EA - CFA_15_53_Site_Restoration | SR_CFA_15_53 - Site Restoration - SR_CFA_15_53 | SR_CFA_15_53 | HS2-00003H0EA | #N/A | #N/A | #N/A
229.03 | HS2-00002N7U9 | IDR 229.03 | HS2-00002N7U9 | 2024-04-26 | 10 - Complete | 2024-05-08 |  | HS2-00003H0E9 - CFA_15_52_Site_Restoration | SR_CFA_15_52 - Site Restoration - SR_CFA_15_52 | SR_CFA_15_52 | HS2-00003H0E9 | #N/A | #N/A | #N/A
213.07 | HS2-00003HWH2 | IDR 213.07 | HS2-00003HWH2 | 2024-05-08 | 10 - Complete | 2024-05-20 |  | HS2-00003H0E8 - CFA_15_51_Site_Restoration | SR_CFA_15_51 - Site Restoration - SR_CFA_15_51 | SR_CFA_15_51 | HS2-00003H0E8 | #N/A | #N/A | #N/A
208.4 | HS2-00003GL98 | IDR 208.4 | HS2-00003GL98 | 2024-04-26 | 10 - Complete | 2024-05-10 |  | HS2-00003H0E7 - CFA_15_31_Site_Restoration | SR_CFA_15_31 - Site Restoration - SR_CFA_15_31 | SR_CFA_15_31 | HS2-00003H0E7 | #N/A | #N/A | #N/A
204.1-1 | HS2-00002BVF0 | IDR 204.1-1 | HS2-00002BVF0 | 2024-04-29 | 10 - Complete | 2024-05-07 |  | HS2-00003H0E6 - CFA_15_30_Site_Restoration | SR_CFA_15_30 - Site Restoration - SR_CFA_15_30 | SR_CFA_15_30 | HS2-00003H0E6 | #N/A | #N/A | #N/A
204.1-1 | HS2-00002YYN4 | IDR 204.1-1 | HS2-00002YYN4 | 2024-04-29 | 10 - Complete | 2024-05-07 |  | HS2-00003H0E5 - CFA_15_29_Site_Restoration | SR_CFA_15_29 - Site Restoration - SR_CFA_15_29 | SR_CFA_15_29 | HS2-00003H0E5 | #N/A | #N/A | #N/A
229.03 | HS2-00003B2GK | IDR 229.03 | HS2-00003B2GK | 2024-04-29 | 10 - Complete | 2024-05-07 |  | HS2-00003H0E4 - CFA_15_28_Site_Restoration | SR_CFA_15_28 - Site Restoration - SR_CFA_15_28 | SR_CFA_15_28 | HS2-00003H0E4 | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0E3 - CFA_15_25_Site_Restoration | SR_CFA_15_25 - Site Restoration - SR_CFA_15_25 | SR_CFA_15_25 | HS2-00003H0E3 | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0E2 - CFA_15_23a_Site_Restoration | SR_CFA_15_23a - Site Restoration - SR_CFA_15_23a | SR_CFA_15_23a | HS2-00003H0E2 | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0E1 - CFA_15_22_Site_Restoration | SR_CFA_15_22 - Site Restoration - SR_CFA_15_22 | SR_CFA_15_22 | HS2-00003H0E1 | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0E0 - CFA_15_21_Site_Restoration | SR_CFA_15_21 - Site Restoration - SR_CFA_15_21 | SR_CFA_15_21 | HS2-00003H0E0 | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0DZ - CFA_15_19_Site_Restoration | SR_CFA_15_19 - Site Restoration - SR_CFA_15_19 | SR_CFA_15_19 | HS2-00003H0DZ | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0DY - CFA_15_18_Site_Restoration | SR_CFA_15_18 - Site Restoration - SR_CFA_15_18 | SR_CFA_15_18 | HS2-00003H0DY | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0DX - CFA_15_17b_Site_Restoration | SR_CFA_15_17b - Site Restoration - SR_CFA_15_17b | SR_CFA_15_17b | HS2-00003H0DX | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0DW - CFA_15_17a_Site_Restoration | SR_CFA_15_17a - Site Restoration - SR_CFA_15_17a | SR_CFA_15_17a | HS2-00003H0DW | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0DV - CFA_15_16c_Site_Restoration | SR_CFA_15_16c - Site Restoration - SR_CFA_15_16c | SR_CFA_15_16c | HS2-00003H0DV | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0DU - CFA_15_16b_Site_Restoration | SR_CFA_15_16b - Site Restoration - SR_CFA_15_16b | SR_CFA_15_16b | HS2-00003H0DU | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0DT - CFA_15_16a_Site_Restoration | SR_CFA_15_16a - Site Restoration - SR_CFA_15_16a | SR_CFA_15_16a | HS2-00003H0DT | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0DS - CFA_15_15_Site_Restoration | SR_CFA_15_15 - Site Restoration - SR_CFA_15_15 | SR_CFA_15_15 | HS2-00003H0DS | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0DR - CFA_15_14_Site_Restoration | SR_CFA_15_14 - Site Restoration - SR_CFA_15_14 | SR_CFA_15_14 | HS2-00003H0DR | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0DQ - CFA_15_13_Site_Restoration | SR_CFA_15_13 - Site Restoration - SR_CFA_15_13 | SR_CFA_15_13 | HS2-00003H0DQ | #N/A | #N/A | #N/A
233.01-2 | HS2-00002CTHF | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07 |  | HS2-00003H0DP - CFA_15_12_Site_Restoration | SR_CFA_15_12 - Site Restoration - SR_CFA_15_12 | SR_CFA_15_12 | HS2-00003H0DP | #N/A | #N/A | #N/A
204.1-1 | HS2-00002EK6V | IDR 204.1-1 | HS2-00002EK6V | 2024-04-30 | 10 - Complete | 2024-05-07 |  | HS2-00003H0DN - CFA_15_10_Site_Restoration | SR_CFA_15_10 - Site Restoration - SR_CFA_15_10 | SR_CFA_15_10 | HS2-00003H0DN | #N/A | #N/A | #N/A
208.4 | HS2-000001295 | IDR 208.4 | HS2-000001295 | 2024-04-30 | 10 - Complete | 2024-05-10 |  | HS2-00003H0DM - CFA_15_09_Site_Restoration | SR_CFA_15_09 - Site Restoration - SR_CFA_15_09 | SR_CFA_15_09 | HS2-00003H0DM | #N/A | #N/A | #N/A
UFDR 226.A | HS2-00002TTH7 | UFDR 226.A | HS2-00002TTH7 | 2024-05-01 | 10 - Complete | 2024-05-07 |  | HS2-00003H0DL - CFA_15_07_Site_Restoration | SR_CFA_15_07 - Site Restoration - SR_CFA_15_07 | SR_CFA_15_07 | HS2-00003H0DL | #N/A | #N/A | #N/A
201.0-6 | HS2-00002BJQX | IDR 201.0-6 | HS2-00002BJQX | 2024-05-01 | 10 - Complete | 2024-05-07 |  | HS2-00003H0DK - CFA_15_06_Site_Restoration | SR_CFA_15_06 - Site Restoration - SR_CFA_15_06 | SR_CFA_15_06 | HS2-00003H0DK | #N/A | #N/A | #N/A
201.0-6 | HS2-00002CT2H | IDR 201.0-6 | HS2-00002CT2H | 2024-05-01 | 10 - Complete | 2024-05-07 |  | HS2-00003H0DJ - CFA_15_05_Site_Restoration | SR_CFA_15_05 - Site Restoration - SR_CFA_15_05 | SR_CFA_15_05 | HS2-00003H0DJ | #N/A | #N/A | #N/A
228.1 | HS2-00002CX3Q | IDR 228.1 | HS2-00002CX3Q | 2024-05-01 | 10 - Complete | 2024-05-16 |  | HS2-00003H0DH - CFA_15_02_Site_Restoration | SR_CFA_15_02 - Site Restoration - SR_CFA_15_02 | SR_CFA_15_02 | HS2-00003H0DH | #N/A | #N/A | #N/A
220.5 | HS2-00002Y4JH | IDR 220.5 | HS2-00002Y4JH | 2024-05-01 | 10 - Complete | 2024-05-10 |  | HS2-00003H0DG - CFA_15_01_Site_Restoration | SR_CFA_15_01 - Site Restoration - SR_CFA_15_01 | SR_CFA_15_01 | HS2-00003H0DG | #N/A | #N/A | #N/A
208.4 | HS2-000020NC4 | IDR 208.4 | HS2-000020NC4 | 2024-05-01 | 10 - Complete | 2024-05-07 |  | HS2-00003H0DF - CFA_14_78_Site_Restoration | SR_CFA_14_78 - Site Restoration - SR_CFA_14_78 | SR_CFA_14_78 | HS2-00003H0DF | #N/A | #N/A | #N/A
208.4 | HS2-00002BJSK | IDR 208.4 | HS2-00002BJSK | 2024-05-01 | 10 - Complete | 2024-05-09 |  | HS2-00003H0DE - CFA_14_77_Site_Restoration | SR_CFA_14_77 - Site Restoration - SR_CFA_14_77 | SR_CFA_14_77 | HS2-00003H0DE | #N/A | #N/A | #N/A
238.02-2 | HS2-000020P2G | IDR 238.02-2 | HS2-000020P2G | 2024-11-21 | 10 - Complete | 2024-11-22 |  | HS2-00003H0DD - CFA_14_76_Site_Restoration | SR_CFA_14_76 - Site Restoration - SR_CFA_14_76 | SR_CFA_14_76 | HS2-00003H0DD | #N/A | #N/A | #N/A
UFDR 210.B | HS2-000020CF7 | UFDR 210.B | HS2-000020CF7 | 2024-05-03 | 10 - Complete | 2024-05-14 |  | HS2-00003H0DC - CFA_14_75_Site_Restoration | SR_CFA_14_75 - Site Restoration - SR_CFA_14_75 | SR_CFA_14_75 | HS2-00003H0DC | #N/A | #N/A | #N/A
233.01-3 | HS2-00002EK7X | IDR 233.01-3 | HS2-00002EK7X | 2024-05-03 | 10 - Complete | 2024-05-10 |  | HS2-00003H0DB - CFA_14_74_Site_Restoration | SR_CFA_14_74 - Site Restoration - SR_CFA_14_74 | SR_CFA_14_74 | HS2-00003H0DB | #N/A | #N/A | #N/A
223.8 | HS2-00002CTC2 | IDR 223.8 | HS2-00002CTC2 | 2024-05-14 | 10 - Complete | 2024-05-15 |  | HS2-00003H0DA - CFA_14_73_Site_Restoration | SR_CFA_14_73 - Site Restoration - SR_CFA_14_73 | SR_CFA_14_73 | HS2-00003H0DA | #N/A | #N/A | #N/A
223.8 | HS2-00002CTC4 | IDR 223.8 | HS2-00002CTC4 | 2024-05-03 | 10 - Complete | 2024-05-15 |  | HS2-00003H0D9 - CFA_14_72_Site_Restoration | SR_CFA_14_72 - Site Restoration - SR_CFA_14_72 | SR_CFA_14_72 | HS2-00003H0D9 | #N/A | #N/A | #N/A
223.8 | HS2-00002CTC9 | IDR 223.8 | HS2-00002CTC9 | 2024-05-03 | 10 - Complete | 2024-05-15 |  | HS2-00003H0D8 - CFA_14_71_Site_Restoration | SR_CFA_14_71 - Site Restoration - SR_CFA_14_71 | SR_CFA_14_71 | HS2-00003H0D8 | #N/A | #N/A | #N/A
223.8 | HS2-00002CTCC | IDR 223.8 | HS2-00002CTCC | 2025-05-21 | 10 - Complete | 2025-05-27 |  | HS2-00003H0D7 - CFA_14_70_Site_Restoration | SR_CFA_14_70 - Site Restoration - SR_CFA_14_70 | SR_CFA_14_70 | HS2-00003H0D7 | #N/A | #N/A | #N/A
233.01-3 | HS2-00002TMF9 | IDR 233.01-3 | HS2-00002TMF9 | 2024-05-07 | 10 - Complete | 2024-06-12 |  | HS2-00003H0D6 - CFA_14_69_Site_Restoration | SR_CFA_14_69 - Site Restoration - SR_CFA_14_69 | SR_CFA_14_69 | HS2-00003H0D6 | #N/A | #N/A | #N/A
229.01-1 | HS2-00003B5FS | IDR 229.01-1 | HS2-00003B5FS | 2025-02-20 | 10 - Complete | 2025-02-21 |  | HS2-00003H0D5 - CFA_14_68_Site_Restoration | SR_CFA_14_68 - Site Restoration - SR_CFA_14_68 | SR_CFA_14_68 | HS2-00003H0D5 | #N/A | #N/A | #N/A
218.02 | HS2-00002CT9P | IDR 218.02 | HS2-00002CT9P | 2024-05-07 | 10 - Complete | 2024-05-13 |  | HS2-00003H0D4 - CFA_14_67_Site_Restoration | SR_CFA_14_67 - Site Restoration - SR_CFA_14_67 | SR_CFA_14_67 | HS2-00003H0D4 | #N/A | #N/A | #N/A
218.02 | HS2-00002VK41 | IDR 218.02 | HS2-00002VK41 | 2024-05-07 | 10 - Complete | 2024-05-10 |  | HS2-00003H0D3 - CFA_14_65_Site_Restoration | SR_CFA_14_65 - Site Restoration - SR_CFA_14_65 | SR_CFA_14_65 | HS2-00003H0D3 | #N/A | #N/A | #N/A
238.02-2 | HS2-00002CTKE | IDR 238.02-2 | HS2-00002CTKE | 2024-11-19 | 10 - Complete | 2024-11-22 |  | HS2-00003H0D2 - CFA_14_64_Site_Restoration | SR_CFA_14_64 - Site Restoration - SR_CFA_14_64 | SR_CFA_14_64 | HS2-00003H0D2 | #N/A | #N/A | #N/A
238.02-2 | HS2-000020P2P | IDR 238.02-2 | HS2-000020P2P | 2024-11-19 | 10 - Complete | 2024-11-25 |  | HS2-00003H0D1 - CFA_14_63_Site_Restoration | SR_CFA_14_63 - Site Restoration - SR_CFA_14_63 | SR_CFA_14_63 | HS2-00003H0D1 | #N/A | #N/A | #N/A
238.02-2 | HS2-000020P2N | IDR 238.02-2 | HS2-000020P2N | 2024-11-21 | 10 - Complete | 0 |  | HS2-00003H0D0 - CFA_14_62_Site_Restoration | SR_CFA_14_62 - Site Restoration - SR_CFA_14_62 | SR_CFA_14_62 | HS2-00003H0D0 | #N/A | #N/A | #N/A
234.05 | HS2-00002TGP5 | IDR 234.05 | HS2-00002TGP5 | 2024-05-08 | 10 - Complete | 2024-05-09 |  | HS2-00003H0CZ - CFA_14_61_Site_Restoration | SR_CFA_14_61 - Site Restoration - SR_CFA_14_61 | SR_CFA_14_61 | HS2-00003H0CZ | #N/A | #N/A | #N/A
234.05 | HS2-00003A346 | IDR 234.05 | HS2-00003A346 | 2024-05-08 | 10 - Complete | 2024-05-09 |  | HS2-00003H0CY - CFA_14_60_Site_Restoration | SR_CFA_14_60 - Site Restoration - SR_CFA_14_60 | SR_CFA_14_60 | HS2-00003H0CY | #N/A | #N/A | #N/A
234.05 | HS2-00003A347 | IDR 234.05 | HS2-00003A347 | 2024-05-08 | 10 - Complete | 2024-05-10 |  | HS2-00003H0CX - CFA_14_59_Site_Restoration | SR_CFA_14_59 - Site Restoration - SR_CFA_14_59 | SR_CFA_14_59 | HS2-00003H0CX | #N/A | #N/A | #N/A
234.05 | HS2-00003A34A | IDR 234.05 | HS2-00003A34A | 2024-05-08 | 10 - Complete | 2024-05-10 |  | HS2-00003H0CW - CFA_14_58_Site_Restoration | SR_CFA_14_58 - Site Restoration - SR_CFA_14_58 | SR_CFA_14_58 | HS2-00003H0CW | #N/A | #N/A | #N/A
234.05 | HS2-00003A34B | IDR 234.05 | HS2-00003A34B | 2024-05-08 | 10 - Complete | 2024-05-10 |  | HS2-00003H0CV - CFA_14_57_Site_Restoration | SR_CFA_14_57 - Site Restoration - SR_CFA_14_57 | SR_CFA_14_57 | HS2-00003H0CV | #N/A | #N/A | #N/A
234.05 | HS2-00003A349 | IDR 234.05 | HS2-00003A349 | 2024-05-08 | 10 - Complete | 2024-05-10 |  | HS2-00003H0CU - CFA_14_56_Site_Restoration | SR_CFA_14_56 - Site Restoration - SR_CFA_14_56 | SR_CFA_14_56 | HS2-00003H0CU | #N/A | #N/A | #N/A
234.05 | HS2-00003A348 | IDR 234.05 | HS2-00003A348 | 2024-05-08 | 10 - Complete | 2024-05-10 |  | HS2-00003H0CT - CFA_14_55_Site_Restoration | SR_CFA_14_55 - Site Restoration - SR_CFA_14_55 | SR_CFA_14_55 | HS2-00003H0CT | #N/A | #N/A | #N/A
213.07-1 | HS2-00003HWH2 | IDR 213.07-1 | HS2-00003HWH2 | 2024-05-08 | 10 - Complete | 2024-05-20 |  | HS2-00003H0CS - CFA_14_54_Site_Restoration | SR_CFA_14_54 - Site Restoration - SR_CFA_14_54 | SR_CFA_14_54 | HS2-00003H0CS | #N/A | #N/A | #N/A
208.4 | HS2-000020NC7 | IDR 208.4 | HS2-000020NC7 | 2024-05-08 | 10 - Complete | 2024-05-24 |  | HS2-00003H0CR - CFA_14_53_Site_Restoration | SR_CFA_14_53 - Site Restoration - SR_CFA_14_53 | SR_CFA_14_53 | HS2-00003H0CR | #N/A | #N/A | #N/A
238.01 | HS2-00002CTK9 | IDR 238.01 | HS2-00002CTK9 | 2024-05-09 | 10 - Complete | 2024-05-14 |  | HS2-00003H0CQ - CFA_14_52_Site_Restoration | SR_CFA_14_52 - Site Restoration - SR_CFA_14_52 | SR_CFA_14_52 | HS2-00003H0CQ | #N/A | #N/A | #N/A
208.4 | HS2-00003HWH7 | IDR 208.4 | HS2-00003HWH7 | 2024-05-10 | 10 - Complete | 2024-05-14 |  | HS2-00003H0CP - CFA_14_51_Site_Restoration | SR_CFA_14_51 - Site Restoration - SR_CFA_14_51 | SR_CFA_14_51 | HS2-00003H0CP | #N/A | #N/A | #N/A
UFDR 226.A | HS2-000020CHD | UFDR 226.A | HS2-000020CHD | 2024-05-14 | 10 - Complete | 2024-05-15 |  | HS2-00003H0CN - CFA_14_19_Site_Restoration | SR_CFA_14_19 - Site Restoration - SR_CFA_14_19 | SR_CFA_14_19 | HS2-00003H0CN | #N/A | #N/A | #N/A
238.02-2 | HS2-00002C3Z1 | IDR 238.02-2 | HS2-00002C3Z1 | 2024-11-19 | 10 - Complete | 2024-11-26 |  | HS2-00003H0CM - CFA_14_18_Site_Restoration | SR_CFA_14_18 - Site Restoration - SR_CFA_14_18 | SR_CFA_14_18 | HS2-00003H0CM | #N/A | #N/A | #N/A
213.07-1 | HS2-00003CCK1 | IDR 213.07-1 | HS2-00003CCK1 | 2024-06-05 | 10 - Complete | 2024-06-07 |  | HS2-00003H0CL - CFA_14_17_Site_Restoration | SR_CFA_14_17 - Site Restoration - SR_CFA_14_17 | SR_CFA_14_17 | HS2-00003H0CL | #N/A | #N/A | #N/A
213.07-1 | HS2-00003CCJZ | IDR 213.07-1 | HS2-00003CCJZ | 2024-05-14 | 10 - Complete | 2024-05-16 |  | HS2-00003H0CK - CFA_14_16_Site_Restoration | SR_CFA_14_16 - Site Restoration - SR_CFA_14_16 | SR_CFA_14_16 | HS2-00003H0CK | #N/A | #N/A | #N/A
213.07-1 | HS2-00003CCK0 | IDR 213.07-1 | HS2-00003CCK0 | 2024-10-15 | 10 - Complete | 2024-10-18 |  | HS2-00003H0CJ - CFA_14_15_Site_Restoration | SR_CFA_14_15 - Site Restoration - SR_CFA_14_15 | SR_CFA_14_15 | HS2-00003H0CJ | #N/A | #N/A | #N/A
213.07-1 | HS2-00002D88S | IDR 213.07-1 | HS2-00002D88S | 2024-05-14 | 10 - Complete | 2024-06-07 |  | HS2-00003H0CH - CFA_14_14_Site_Restoration | SR_CFA_14_14 - Site Restoration - SR_CFA_14_14 | SR_CFA_14_14 | HS2-00003H0CH | #N/A | #N/A | #N/A
237.05 | HS2-000001099 | IDR 237.05 | HS2-000001099 | 2024-05-14 | 10 - Complete | 2024-05-15 |  | HS2-00003H0CG - CFA_14_13_Site_Restoration | SR_CFA_14_13 - Site Restoration - SR_CFA_14_13 | SR_CFA_14_13 | HS2-00003H0CG | #N/A | #N/A | #N/A
237.05 | HS2-00002CTK5 | IDR 237.05 | HS2-00002CTK5 | 2024-05-14 | 10 - Complete | 2024-05-16 |  | HS2-00003H0CF - CFA_14_12_Site_Restoration | SR_CFA_14_12 - Site Restoration - SR_CFA_14_12 | SR_CFA_14_12 | HS2-00003H0CF | #N/A | #N/A | #N/A
229.03 | HS2-00002N7UB | IDR 229.03 | HS2-00002N7UB | 2024-05-14 | 10 - Complete | 2024-05-17 |  | HS2-00003H0CE - CFA_14_11_Site_Restoration | SR_CFA_14_11 - Site Restoration - SR_CFA_14_11 | SR_CFA_14_11 | HS2-00003H0CE | #N/A | #N/A | #N/A
223.8 | HS2-00002CTC2 | IDR 223.8 | HS2-00002CTC2 | 2024-05-14 | 10 - Complete | 2024-05-15 |  | HS2-00003H0CD - CFA_14_10_Site_Restoration | SR_CFA_14_10 - Site Restoration - SR_CFA_14_10 | SR_CFA_14_10 | HS2-00003H0CD | #N/A | #N/A | #N/A
223.8 | HS2-00002CTC7 | IDR 223.8 | HS2-00002CTC7 | 2024-05-14 | 10 - Complete | 2024-05-15 |  | HS2-00003H0CC - CFA_14_09_Site_Restoration | SR_CFA_14_09 - Site Restoration - SR_CFA_14_09 | SR_CFA_14_09 | HS2-00003H0CC | #N/A | #N/A | #N/A
223.8 | HS2-00002CTCA | IDR 223.8 | HS2-00002CTCA | 2025-05-21 | 10 - Complete | 2025-05-27 |  | HS2-00003H0CB - CFA_14_08_Site_Restoration | SR_CFA_14_08 - Site Restoration - SR_CFA_14_08 | SR_CFA_14_08 | HS2-00003H0CB | #N/A | #N/A | #N/A
218.02 | HS2-00003124C | IDR 218.02 | HS2-00003124C | 2024-05-14 | 10 - Complete | 2024-05-15 |  | HS2-00003H0CA - CFA_14_06_Site_Restoration | SR_CFA_14_06 - Site Restoration - SR_CFA_14_06 | SR_CFA_14_06 | HS2-00003H0CA | #N/A | #N/A | #N/A
227.2 | HS2-000001337 | IDR 227.2 | HS2-000001337 | 2024-05-17 | 10 - Complete | 2024-05-21 |  | HS2-00003H0C9 - CFA_14_05_Site_Restoration | SR_CFA_14_05 - Site Restoration - SR_CFA_14_05 | SR_CFA_14_05 | HS2-00003H0C9 | #N/A | #N/A | #N/A
233.01-3 | HS2-00002TMF8 | IDR 233.01-3 | HS2-00002TMF8 | 2024-05-20 | 10 - Complete | 2024-05-21 |  | HS2-00003H0C8 - CFA_14_04_Site_Restoration | SR_CFA_14_04 - Site Restoration - SR_CFA_14_04 | SR_CFA_14_04 | HS2-00003H0C8 | #N/A | #N/A | #N/A
229.01-2 | HS2-00002TMF6 | IDR 229.01-2 | HS2-00002TMF6 | 2024-08-13 | 10 - Complete | 2024-08-22 |  | HS2-00003H0C7 - CFA_14_03_Site_Restoration | SR_CFA_14_03 - Site Restoration - SR_CFA_14_03 | SR_CFA_14_03 | HS2-00003H0C7 | #N/A | #N/A | #N/A
233.01 | HS2-00002CX3A | IDR 233.01 | HS2-00002CX3A | 2025-01-08 | 10 - Complete | 2025-01-17 |  | HS2-00003H0C6 - CFA_14_02_Site_Restoration | SR_CFA_14_02 - Site Restoration - SR_CFA_14_02 | SR_CFA_14_02 | HS2-00003H0C6 | #N/A | #N/A | #N/A
UFDR 222.B | HS2-0000245Z8 | UFDR 222.B | HS2-0000245Z8 | 2024-05-22 | 10 - Complete | 2024-05-30 |  | HS2-00003H0C5 - CFA_14_01_Site_Restoration | SR_CFA_14_01 - Site Restoration - SR_CFA_14_01 | SR_CFA_14_01 | HS2-00003H0C5 | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUQQ | IDR 234.04-2 | HS2-00002WUQQ | 2024-05-22 | 10 - Complete | 2024-05-29 |  | HS2-00003H0C4 - CFA_13_73_Site_Restoration | SR_CFA_13_73 - Site Restoration - SR_CFA_13_73 | SR_CFA_13_73 | HS2-00003H0C4 | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUQR | IDR 234.04-2 | HS2-00002WUQR | 2024-05-22 | 10 - Complete | 2024-05-23 |  | HS2-00003H0C3 - CFA_13_72_Site_Restoration | SR_CFA_13_72 - Site Restoration - SR_CFA_13_72 | SR_CFA_13_72 | HS2-00003H0C3 | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUQS | IDR 234.04-2 | HS2-00002WUQS | 2024-05-22 | 10 - Complete | 2024-05-30 |  | HS2-00003H0C2 - CFA_13_71_Site_Restoration | SR_CFA_13_71 - Site Restoration - SR_CFA_13_71 | SR_CFA_13_71 | HS2-00003H0C2 | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUQT | IDR 234.04-2 | HS2-00002WUQT | 2024-05-22 | 10 - Complete | 2024-05-30 |  | HS2-00003H0C1 - CFA_13_70_Site_Restoration | SR_CFA_13_70 - Site Restoration - SR_CFA_13_70 | SR_CFA_13_70 | HS2-00003H0C1 | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUQU | IDR 234.04-2 | HS2-00002WUQU | 2024-05-22 | 10 - Complete | 2024-05-29 |  | HS2-00003H0C0 - CFA_13_69_Site_Restoration | SR_CFA_13_69 - Site Restoration - SR_CFA_13_69 | SR_CFA_13_69 | HS2-00003H0C0 | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUQV | IDR 234.04-2 | HS2-00002WUQV | 2024-05-22 | 10 - Complete | 2024-05-29 |  | HS2-00003H0BZ - CFA_13_68_Site_Restoration | SR_CFA_13_68 - Site Restoration - SR_CFA_13_68 | SR_CFA_13_68 | HS2-00003H0BZ | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUQW | IDR 234.04-2 | HS2-00002WUQW | 2024-05-22 | 10 - Complete | 2024-05-29 |  | HS2-00003H0BY - CFA_13_67_Site_Restoration | SR_CFA_13_67 - Site Restoration - SR_CFA_13_67 | SR_CFA_13_67 | HS2-00003H0BY | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUQX | IDR 234.04-2 | HS2-00002WUQX | 2024-05-22 | 10 - Complete | 2024-05-29 |  | HS2-00003H0BX - CFA_13_66_Site_Restoration | SR_CFA_13_66 - Site Restoration - SR_CFA_13_66 | SR_CFA_13_66 | HS2-00003H0BX | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUQY | IDR 234.04-2 | HS2-00002WUQY | 2024-05-22 | 10 - Complete | 2024-05-23 |  | HS2-00003H0BW - CFA_13_65_Site_Restoration | SR_CFA_13_65 - Site Restoration - SR_CFA_13_65 | SR_CFA_13_65 | HS2-00003H0BW | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUQZ | IDR 234.04-2 | HS2-00002WUQZ | 2024-05-22 | 10 - Complete | 2024-05-23 |  | HS2-00003H0BV - CFA_13_64_Site_Restoration | SR_CFA_13_64 - Site Restoration - SR_CFA_13_64 | SR_CFA_13_64 | HS2-00003H0BV | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUR1 | IDR 234.04-2 | HS2-00002WUR1 | 2024-05-22 | 10 - Complete | 2024-05-23 |  | HS2-00003H0BU - CFA_13_63_Site_Restoration | SR_CFA_13_63 - Site Restoration - SR_CFA_13_63 | SR_CFA_13_63 | HS2-00003H0BU | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUR2 | IDR 234.04-2 | HS2-00002WUR2 | 2024-05-22 | 10 - Complete | 2024-05-29 |  | HS2-00003H0BT - CFA_13_62_Site_Restoration | SR_CFA_13_62 - Site Restoration - SR_CFA_13_62 | SR_CFA_13_62 | HS2-00003H0BT | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUR3 | IDR 234.04-2 | HS2-00002WUR3 | 2024-05-22 | 10 - Complete | 2024-05-30 |  | HS2-00003H0BS - CFA_13_61_Site_Restoration | SR_CFA_13_61 - Site Restoration - SR_CFA_13_61 | SR_CFA_13_61 | HS2-00003H0BS | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUR4 | IDR 234.04-2 | HS2-00002WUR4 | 2024-05-22 | 10 - Complete | 2024-05-28 |  | HS2-00003H0BR - CFA_13_60_Site_Restoration | SR_CFA_13_60 - Site Restoration - SR_CFA_13_60 | SR_CFA_13_60 | HS2-00003H0BR | #N/A | #N/A | #N/A
234.04-2 | HS2-00002WUR5 | IDR 234.04-2 | HS2-00002WUR5 | 2024-05-22 | 10 - Complete | 2024-05-30 |  | HS2-00003H0BQ - CFA_13_59_Site_Restoration | SR_CFA_13_59 - Site Restoration - SR_CFA_13_59 | SR_CFA_13_59 | HS2-00003H0BQ | #N/A | #N/A | #N/A
230.01-3 | HS2-00002CTFQ | IDR 230.01-3 | HS2-00002CTFQ | 2024-05-22 | 10 - Complete | 2024-05-29 |  | HS2-00003H0BP - CFA_13_58_Site_Restoration | SR_CFA_13_58 - Site Restoration - SR_CFA_13_58 | SR_CFA_13_58 | HS2-00003H0BP | #N/A | #N/A | #N/A
230.03-2 | HS2-00002TGPD | IDR 230.03-2 | HS2-00002TGPD | 2024-05-22 | 10 - Complete | 2024-05-30 |  | HS2-00003H0BN - CFA_13_57_Site_Restoration | SR_CFA_13_57 - Site Restoration - SR_CFA_13_57 | SR_CFA_13_57 | HS2-00003H0BN | #N/A | #N/A | #N/A
223.8 | HS2-000039DSD | IDR 223.8 | HS2-000039DSD | 2024-05-22 | 10 - Complete | 2024-05-30 |  | HS2-00003H0BM - CFA_13_56_Site_Restoration | SR_CFA_13_56 - Site Restoration - SR_CFA_13_56 | SR_CFA_13_56 | HS2-00003H0BM | #N/A | #N/A | #N/A
212.5 | HS2-00002YD7F | IDR 212.5 | HS2-00002YD7F | 2024-07-09 | 10 - Complete | 2024-07-17 |  | HS2-00003H0BL - CFA_13_55_Site_Restoration | SR_CFA_13_55 - Site Restoration - SR_CFA_13_55 | SR_CFA_13_55 | HS2-00003H0BL | #N/A | #N/A | #N/A
UFDR 210.B | HS2-00002V04E | UFDR 210.B | HS2-00002V04E | 2025-01-23 | 10 - Complete | 2025-01-28 |  | HS2-00003H0BK - CFA_13_54_Site_Restoration | SR_CFA_13_54 - Site Restoration - SR_CFA_13_54 | SR_CFA_13_54 | HS2-00003H0BK | #N/A | #N/A | #N/A
UFDR 210.B | HS2-000020CFB | UFDR 210.B | HS2-000020CFB | 2024-05-23 | 10 - Complete | 2024-05-28 |  | HS2-00003H0BJ - CFA_13_53_Site_Restoration | SR_CFA_13_53 - Site Restoration - SR_CFA_13_53 | SR_CFA_13_53 | HS2-00003H0BJ | #N/A | #N/A | #N/A
UFDR 210.B | HS2-000020CFA | UFDR 210.B | HS2-000020CFA | 2025-01-27 | 10 - Complete | 2025-01-29 |  | HS2-00003H0BH - CFA_13_52_Site_Restoration | SR_CFA_13_52 - Site Restoration - SR_CFA_13_52 | SR_CFA_13_52 | HS2-00003H0BH | #N/A | #N/A | #N/A
UFDR 210.B | HS2-00002TU6N | UFDR 210.B | HS2-00002TU6N | 2025-01-17 | 10 - Complete | 2025-01-20 |  | HS2-00003H0BG - CFA_13_51_Site_Restoration | SR_CFA_13_51 - Site Restoration - SR_CFA_13_51 | SR_CFA_13_51 | HS2-00003H0BG | #N/A | #N/A | #N/A
UFDR 210.B | HS2-00002ZH4F | UFDR 210.B | HS2-00002ZH4F | 2025-02-03 | 10 - Complete | 2025-02-17 |  | HS2-00003H0BF - CFA_13_20_Site_Restoration | SR_CFA_13_20 - Site Restoration - SR_CFA_13_20 | SR_CFA_13_20 | HS2-00003H0BF | #N/A | #N/A | #N/A
210.2-2 | HS2-00003GNAE | IDR 210.2-2 | HS2-00003GNAE | 2024-05-23 | 10 - Complete | 2024-06-06 |  | HS2-00003H0BE - CFA_13_19_Site_Restoration | SR_CFA_13_19 - Site Restoration - SR_CFA_13_19 | SR_CFA_13_19 | HS2-00003H0BE | #N/A | #N/A | #N/A
230.03-2 | HS2-00002CTFX | IDR 230.03-2 | HS2-00002CTFX | 2024-08-29 | 10 - Complete | 2024-09-06 |  | HS2-00003H0BD - CFA_13_17_Site_Restoration | SR_CFA_13_17 - Site Restoration - SR_CFA_13_17 | SR_CFA_13_17 | HS2-00003H0BD | #N/A | #N/A | #N/A
226.1_2 | HS2-000001333 | IDR 226.1_2 | HS2-000001333 | 2024-05-24 | 10 - Complete | 2024-05-30 |  | HS2-00003H0BC - CFA_13_15_Site_Restoration | SR_CFA_13_15 - Site Restoration - SR_CFA_13_15 | SR_CFA_13_15 | HS2-00003H0BC | #N/A | #N/A | #N/A
218.02 | HS2-00003B931 | IDR 218.02 | HS2-00003B931 | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0BB - CFA_13_14_Site_Restoration | SR_CFA_13_14 - Site Restoration - SR_CFA_13_14 | SR_CFA_13_14 | HS2-00003H0BB | #N/A | #N/A | #N/A
218.02 | HS2-00003B932 | IDR 218.02 | HS2-00003B932 | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0BA - CFA_13_13_Site_Restoration | SR_CFA_13_13 - Site Restoration - SR_CFA_13_13 | SR_CFA_13_13 | HS2-00003H0BA | #N/A | #N/A | #N/A
218.02 | HS2-00003B933 | IDR 218.02 | HS2-00003B933 | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0B9 - CFA_13_12_Site_Restoration | SR_CFA_13_12 - Site Restoration - SR_CFA_13_12 | SR_CFA_13_12 | HS2-00003H0B9 | #N/A | #N/A | #N/A
218.02 | HS2-00003B92J | IDR 218.02 | HS2-00003B92J | 2024-06-04 | 10 - Complete | 2024-06-05 |  | HS2-00003H0B8 - CFA_13_11_Site_Restoration | SR_CFA_13_11 - Site Restoration - SR_CFA_13_11 | SR_CFA_13_11 | HS2-00003H0B8 | #N/A | #N/A | #N/A
218.02 | HS2-00003B92L | IDR 218.02 | HS2-00003B92L | 2024-06-04 | 10 - Complete | 2024-06-05 |  | HS2-00003H0B7 - CFA_13_10_Site_Restoration | SR_CFA_13_10 - Site Restoration - SR_CFA_13_10 | SR_CFA_13_10 | HS2-00003H0B7 | #N/A | #N/A | #N/A
218.02 | HS2-00003B92N | IDR 218.02 | HS2-00003B92N | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0B6 - CFA_13_09_Site_Restoration | SR_CFA_13_09 - Site Restoration - SR_CFA_13_09 | SR_CFA_13_09 | HS2-00003H0B6 | #N/A | #N/A | #N/A
218.02 | HS2-00003B92Q | IDR 218.02 | HS2-00003B92Q | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0B5 - CFA_13_08_Site_Restoration | SR_CFA_13_08 - Site Restoration - SR_CFA_13_08 | SR_CFA_13_08 | HS2-00003H0B5 | #N/A | #N/A | #N/A
218.02 | HS2-00003B92U | IDR 218.02 | HS2-00003B92U | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0B4 - CFA_13_07_Site_Restoration | SR_CFA_13_07 - Site Restoration - SR_CFA_13_07 | SR_CFA_13_07 | HS2-00003H0B4 | #N/A | #N/A | #N/A
218.02 | HS2-00003B92W | IDR 218.02 | HS2-00003B92W | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0B3 - CFA_13_06_Site_Restoration | SR_CFA_13_06 - Site Restoration - SR_CFA_13_06 | SR_CFA_13_06 | HS2-00003H0B3 | #N/A | #N/A | #N/A
218.02 | HS2-00003B92X | IDR 218.02 | HS2-00003B92X | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0B2 - CFA_13_05_Site_Restoration | SR_CFA_13_05 - Site Restoration - SR_CFA_13_05 | SR_CFA_13_05 | HS2-00003H0B2 | #N/A | #N/A | #N/A
218.02 | HS2-00003B935 | IDR 218.02 | HS2-00003B935 | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0B1 - CFA_13_04_Site_Restoration | SR_CFA_13_04 - Site Restoration - SR_CFA_13_04 | SR_CFA_13_04 | HS2-00003H0B1 | #N/A | #N/A | #N/A
218.02 | HS2-00003B938 | IDR 218.02 | HS2-00003B938 | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0B0 - CFA_13_03c_Site_Restoration | SR_CFA_13_03c - Site Restoration - SR_CFA_13_03c | SR_CFA_13_03c | HS2-00003H0B0 | #N/A | #N/A | #N/A
218.02 | HS2-00003B93A | IDR 218.02 | HS2-00003B93A | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0AZ - CFA_13_03b_Site_Restoration | SR_CFA_13_03b - Site Restoration - SR_CFA_13_03b | SR_CFA_13_03b | HS2-00003H0AZ | #N/A | #N/A | #N/A
218.02 | HS2-00003B93C | IDR 218.02 | HS2-00003B93C | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0AY - CFA_13_03a_Site_Restoration | SR_CFA_13_03a - Site Restoration - SR_CFA_13_03a | SR_CFA_13_03a | HS2-00003H0AY | #N/A | #N/A | #N/A
218.02 | HS2-00003B93G | IDR 218.02 | HS2-00003B93G | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0AX - CFA_13_02_Site_Restoration | SR_CFA_13_02 - Site Restoration - SR_CFA_13_02 | SR_CFA_13_02 | HS2-00003H0AX | #N/A | #N/A | #N/A
218.02 | HS2-00003B93J | IDR 218.02 | HS2-00003B93J | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H0AW - CFA_13_01_Site_Restoration | SR_CFA_13_01 - Site Restoration - SR_CFA_13_01 | SR_CFA_13_01 | HS2-00003H0AW | #N/A | #N/A | #N/A
218.02 | HS2-00003B93M | IDR 218.02 | HS2-00003B93M | 2025-03-27 | 10 - Complete | 2025-04-01 |  | HS2-00003H0AV - CFA_12_65_Site_Restoration | SR_CFA_12_65 - Site Restoration - SR_CFA_12_65 | SR_CFA_12_65 | HS2-00003H0AV | #N/A | #N/A | #N/A
218.02 | HS2-00003B92Z | IDR 218.02 | HS2-00003B92Z | 2024-05-24 | 10 - Complete | 2024-05-29 |  | HS2-00003H0AU - CFA_12_64_Site_Restoration | SR_CFA_12_64 - Site Restoration - SR_CFA_12_64 | SR_CFA_12_64 | HS2-00003H0AU | #N/A | #N/A | #N/A
218.02 | HS2-00003B930 | IDR 218.02 | HS2-00003B930 | 2024-05-24 | 10 - Complete | 2024-05-29 |  | HS2-00003H0AT - CFA_12_63_Site_Restoration | SR_CFA_12_63 - Site Restoration - SR_CFA_12_63 | SR_CFA_12_63 | HS2-00003H0AT | #N/A | #N/A | #N/A
218.02 | HS2-00003B934 | IDR 218.02 | HS2-00003B934 | 2024-05-24 | 10 - Complete | 2024-05-29 |  | HS2-00003H0AS - CFA_12_61_Site_Restoration | SR_CFA_12_61 - Site Restoration - SR_CFA_12_61 | SR_CFA_12_61 | HS2-00003H0AS | #N/A | #N/A | #N/A
218.02 | HS2-00003B92K | IDR 218.02 | HS2-00003B92K | 2024-05-24 | 10 - Complete | 2024-06-03 |  | HS2-00003H0AR - CFA_12_60_Site_Restoration | SR_CFA_12_60 - Site Restoration - SR_CFA_12_60 | SR_CFA_12_60 | HS2-00003H0AR | #N/A | #N/A | #N/A
218.02 | HS2-00003B92M | IDR 218.02 | HS2-00003B92M | 2024-05-24 | 10 - Complete | 2024-05-29 |  | HS2-00003H0AQ - CFA_12_58_Site_Restoration | SR_CFA_12_58 - Site Restoration - SR_CFA_12_58 | SR_CFA_12_58 | HS2-00003H0AQ | #N/A | #N/A | #N/A
218.02 | HS2-00003B92R | IDR 218.02 | HS2-00003B92R | 2024-05-24 | 10 - Complete | 2024-05-29 |  | HS2-00003H0AP - CFA_12_57_Site_Restoration | SR_CFA_12_57 - Site Restoration - SR_CFA_12_57 | SR_CFA_12_57 | HS2-00003H0AP | #N/A | #N/A | #N/A
218.02 | HS2-00003B92S | IDR 218.02 | HS2-00003B92S | 2024-05-24 | 10 - Complete | 2024-05-29 |  | HS2-00003H0AN - CFA_12_56_Site_Restoration | SR_CFA_12_56 - Site Restoration - SR_CFA_12_56 | SR_CFA_12_56 | HS2-00003H0AN | #N/A | #N/A | #N/A
218.02 | HS2-00003B92T | IDR 218.02 | HS2-00003B92T | 2024-05-24 | 10 - Complete | 2024-05-29 |  | HS2-00003H0AM - CFA_12_55_Site_Restoration | SR_CFA_12_55 - Site Restoration - SR_CFA_12_55 | SR_CFA_12_55 | HS2-00003H0AM | #N/A | #N/A | #N/A
218.02 | HS2-00003B92V | IDR 218.02 | HS2-00003B92V | 2024-05-24 | 10 - Complete | 2024-06-03 |  | HS2-00003H0AL - CFA_12_54_Site_Restoration | SR_CFA_12_54 - Site Restoration - SR_CFA_12_54 | SR_CFA_12_54 | HS2-00003H0AL | #N/A | #N/A | #N/A
218.02 | HS2-00003B936 | IDR 218.02 | HS2-00003B936 | 2024-05-24 | 10 - Complete | 2024-06-03 |  | HS2-00003H0AK - CFA_12_53_Site_Restoration | SR_CFA_12_53 - Site Restoration - SR_CFA_12_53 | SR_CFA_12_53 | HS2-00003H0AK | #N/A | #N/A | #N/A
218.02 | HS2-00003B937 | IDR 218.02 | HS2-00003B937 | 2024-05-24 | 10 - Complete | 2024-06-03 |  | HS2-00003H0AJ - CFA_12_52_Site_Restoration | SR_CFA_12_52 - Site Restoration - SR_CFA_12_52 | SR_CFA_12_52 | HS2-00003H0AJ | #N/A | #N/A | #N/A
218.02 | HS2-00003B939 | IDR 218.02 | HS2-00003B939 | 2024-05-24 | 10 - Complete | 2024-06-03 |  | HS2-00003H0AH - CFA_12_51_Site_Restoration | SR_CFA_12_51 - Site Restoration - SR_CFA_12_51 | SR_CFA_12_51 | HS2-00003H0AH | #N/A | #N/A | #N/A
218.02 | HS2-00003B93B | IDR 218.02 | HS2-00003B93B | 2024-05-24 | 10 - Complete | 2024-06-03 |  | HS2-00003H0AG - CFA_12_16_Site_Restoration | SR_CFA_12_16 - Site Restoration - SR_CFA_12_16 | SR_CFA_12_16 | HS2-00003H0AG | #N/A | #N/A | #N/A
218.02 | HS2-00003B93D | IDR 218.02 | HS2-00003B93D | 2024-05-24 | 10 - Complete | 2024-06-03 |  | HS2-00003H0AF - CFA_12_14_Site_Restoration | SR_CFA_12_14 - Site Restoration - SR_CFA_12_14 | SR_CFA_12_14 | HS2-00003H0AF | #N/A | #N/A | #N/A
218.02 | HS2-00003B93F | IDR 218.02 | HS2-00003B93F | 2024-05-24 | 10 - Complete | 2024-06-03 |  | HS2-00003H0AE - CFA_12_11_Site_Restoration | SR_CFA_12_11 - Site Restoration - SR_CFA_12_11 | SR_CFA_12_11 | HS2-00003H0AE | #N/A | #N/A | #N/A
218.02 | HS2-00003B93H | IDR 218.02 | HS2-00003B93H | 2024-05-24 | 10 - Complete | 2024-06-03 |  | HS2-00003H0AD - CFA_12_10_Site_Restoration | SR_CFA_12_10 - Site Restoration - SR_CFA_12_10 | SR_CFA_12_10 | HS2-00003H0AD | #N/A | #N/A | #N/A
218.02 | HS2-00003B93K | IDR 218.02 | HS2-00003B93K | 2024-05-24 | 10 - Complete | 2024-06-03 |  | HS2-00003H0AC - CFA_12_09a_Site_Restoration | SR_CFA_12_09a - Site Restoration - SR_CFA_12_09a | SR_CFA_12_09a | HS2-00003H0AC | #N/A | #N/A | #N/A
218.02 | HS2-00003B93L | IDR 218.02 | HS2-00003B93L | 2024-05-24 | 10 - Complete | 2024-06-03 |  | HS2-00003H0AB - CFA_12_09_Site_Restoration | SR_CFA_12_09 - Site Restoration - SR_CFA_12_09 | SR_CFA_12_09 | HS2-00003H0AB | #N/A | #N/A | #N/A
214.07 | HS2-00002Y8V9 | IDR 214.07 | HS2-00002Y8V9 | 2024-05-24 | 10 - Complete | 2024-05-30 |  | HS2-00003H0AA - CFA_12_08_Site_Restoration | SR_CFA_12_08 - Site Restoration - SR_CFA_12_08 | SR_CFA_12_08 | HS2-00003H0AA | #N/A | #N/A | #N/A
214.07 | HS2-00002Y8VA | IDR 214.07 | HS2-00002Y8VA | 2024-05-24 | 10 - Complete | 2024-05-30 |  | HS2-00003H0A9 - CFA_12_05_Site_Restoration | SR_CFA_12_05 - Site Restoration - SR_CFA_12_05 | SR_CFA_12_05 | HS2-00003H0A9 | #N/A | #N/A | #N/A
214.07 | HS2-00002Y8VB | IDR 214.07 | HS2-00002Y8VB | 2024-05-24 | 10 - Complete | 2024-06-12 |  | HS2-00003H0A8 - CFA_12_02_Site_Restoration | SR_CFA_12_02 - Site Restoration - SR_CFA_12_02 | SR_CFA_12_02 | HS2-00003H0A8 | #N/A | #N/A | #N/A
214.07 | HS2-00002Y8VC | IDR 214.07 | HS2-00002Y8VC | 2024-05-24 | 10 - Complete | 2024-05-30 |  | HS2-00003H0A7 - CFA_12_01_Site_Restoration | SR_CFA_12_01 - Site Restoration - SR_CFA_12_01 | SR_CFA_12_01 | HS2-00003H0A7 | #N/A | #N/A | #N/A
214.07 | HS2-00002Y8VD | IDR 214.07 | HS2-00002Y8VD | 2024-05-24 | 10 - Complete | 2024-05-30 |  | HS2-00003H0A6 - CFA_11_77_Site_Restoration | SR_CFA_11_77 - Site Restoration - SR_CFA_11_77 | SR_CFA_11_77 | HS2-00003H0A6 | #N/A | #N/A | #N/A
214.07 | HS2-00002Y8VE | IDR 214.07 | HS2-00002Y8VE | 2024-05-24 | 10 - Complete | 2024-05-30 |  | HS2-00003H0A5 - CFA_11_76_Site_Restoration | SR_CFA_11_76 - Site Restoration - SR_CFA_11_76 | SR_CFA_11_76 | HS2-00003H0A5 | #N/A | #N/A | #N/A
214.07 | HS2-00003B2G9 | IDR 214.07 | HS2-00003B2G9 | 2024-05-24 | 10 - Complete | 2024-05-30 |  | HS2-00003H0A4 - CFA_11_75_Site_Restoration | SR_CFA_11_75 - Site Restoration - SR_CFA_11_75 | SR_CFA_11_75 | HS2-00003H0A4 | #N/A | #N/A | #N/A
214.07 | HS2-00003B2GA | IDR 214.07 | HS2-00003B2GA | 2024-05-24 | 10 - Complete | 2024-05-30 |  | HS2-00003H0A3 - CFA_11_74_Site_Restoration | SR_CFA_11_74 - Site Restoration - SR_CFA_11_74 | SR_CFA_11_74 | HS2-00003H0A3 | #N/A | #N/A | #N/A
214.07 | HS2-00003B2GB | IDR 214.07 | HS2-00003B2GB | 2024-05-24 | 10 - Complete | 2024-05-30 |  | HS2-00003H0A2 - CFA_11_73_Site_Restoration | SR_CFA_11_73 - Site Restoration - SR_CFA_11_73 | SR_CFA_11_73 | HS2-00003H0A2 | #N/A | #N/A | #N/A
214.07 | HS2-00003B2GC | IDR 214.07 | HS2-00003B2GC | 2024-05-24 | 10 - Complete | 2024-05-30 |  | HS2-00003H0A1 - CFA_11_72_Site_Restoration | SR_CFA_11_72 - Site Restoration - SR_CFA_11_72 | SR_CFA_11_72 | HS2-00003H0A1 | #N/A | #N/A | #N/A
219.3 | HS2-000031EEZ | IDR 219.3 | HS2-000031EEZ | 2024-05-28 | 10 - Complete | 2024-05-29 |  | HS2-00003H0A0 - CFA_11_71_Site_Restoration | SR_CFA_11_71 - Site Restoration - SR_CFA_11_71 | SR_CFA_11_71 | HS2-00003H0A0 | #N/A | #N/A | #N/A
215.03 | HS2-00003GL96 | IDR 215.03 | HS2-00003GL96 | 2024-08-12 | 10 - Complete | 2024-08-23 |  | HS2-00003H09Z - CFA_11_69_Site_Restoration | SR_CFA_11_69 - Site Restoration - SR_CFA_11_69 | SR_CFA_11_69 | HS2-00003H09Z | #N/A | #N/A | #N/A
215.03 | HS2-00003GL97 | IDR 215.03 | HS2-00003GL97 | 2024-08-12 | 10 - Complete | 2024-08-28 |  | HS2-00003H09Y - CFA_11_68_Site_Restoration | SR_CFA_11_68 - Site Restoration - SR_CFA_11_68 | SR_CFA_11_68 | HS2-00003H09Y | #N/A | #N/A | #N/A
211.1-3, 211.1-4. Ambiguous in JSON request | HS2-00002F0X7 | IDR 211.1-3, 211.1-4. Ambiguous in JSON request | HS2-00002F0X7 | 2024-05-29 | 10 - Complete | 2024-06-06 |  | HS2-00003H09X - CFA_11_67_Site_Restoration | SR_CFA_11_67 - Site Restoration - SR_CFA_11_67 | SR_CFA_11_67 | HS2-00003H09X | #N/A | #N/A | #N/A
223.8 | HS2-0000386TG | IDR 223.8 | HS2-0000386TG | 2024-05-29 | 10 - Complete | 2024-06-07 |  | HS2-00003H09W - CFA_11_66_Site_Restoration | SR_CFA_11_66 - Site Restoration - SR_CFA_11_66 | SR_CFA_11_66 | HS2-00003H09W | #N/A | #N/A | #N/A
223.8 | HS2-0000386TH | IDR 223.8 | HS2-0000386TH | 2024-05-29 | 10 - Complete | 2024-06-07 |  | HS2-00003H09V - CFA_11_65_Site_Restoration | SR_CFA_11_65 - Site Restoration - SR_CFA_11_65 | SR_CFA_11_65 | HS2-00003H09V | #N/A | #N/A | #N/A
223.8 | HS2-0000386TK | IDR 223.8 | HS2-0000386TK | 2024-05-29 | 10 - Complete | 2024-06-07 |  | HS2-00003H09U - CFA_11_64_Site_Restoration | SR_CFA_11_64 - Site Restoration - SR_CFA_11_64 | SR_CFA_11_64 | HS2-00003H09U | #N/A | #N/A | #N/A
223.8 | HS2-0000386TL | IDR 223.8 | HS2-0000386TL | 2024-05-29 | 10 - Complete | 2024-06-07 |  | HS2-00003H09T - CFA_11_63_Site_Restoration | SR_CFA_11_63 - Site Restoration - SR_CFA_11_63 | SR_CFA_11_63 | HS2-00003H09T | #N/A | #N/A | #N/A
223.8 | HS2-0000386TN | IDR 223.8 | HS2-0000386TN | 2024-05-29 | 10 - Complete | 2024-06-07 |  | HS2-00003H09S - CFA_11_62_Site_Restoration | SR_CFA_11_62 - Site Restoration - SR_CFA_11_62 | SR_CFA_11_62 | HS2-00003H09S | #N/A | #N/A | #N/A
223.8 | HS2-0000386TP | IDR 223.8 | HS2-0000386TP | 2024-05-29 | 10 - Complete | 2024-06-07 |  | HS2-00003H09R - CFA_11_61_Site_Restoration | SR_CFA_11_61 - Site Restoration - SR_CFA_11_61 | SR_CFA_11_61 | HS2-00003H09R | #N/A | #N/A | #N/A
223.8 | HS2-0000386TR | IDR 223.8 | HS2-0000386TR | 2024-05-29 | 10 - Complete | 2024-06-07 |  | HS2-00003H09Q - CFA_11_60_Site_Restoration | SR_CFA_11_60 - Site Restoration - SR_CFA_11_60 | SR_CFA_11_60 | HS2-00003H09Q | #N/A | #N/A | #N/A
223.8 | HS2-0000386TS | IDR 223.8 | HS2-0000386TS | 2024-05-29 | 10 - Complete | 2024-06-06 |  | HS2-00003H09P - CFA_11_59_Site_Restoration | SR_CFA_11_59 - Site Restoration - SR_CFA_11_59 | SR_CFA_11_59 | HS2-00003H09P | #N/A | #N/A | #N/A
223.8 | HS2-0000386TU | IDR 223.8 | HS2-0000386TU | 2024-05-29 | 10 - Complete | 2024-06-06 |  | HS2-00003H09N - CFA_11_58_Site_Restoration | SR_CFA_11_58 - Site Restoration - SR_CFA_11_58 | SR_CFA_11_58 | HS2-00003H09N | #N/A | #N/A | #N/A
223.8 | HS2-0000386TV | IDR 223.8 | HS2-0000386TV | 2024-05-29 | 10 - Complete | 2024-06-06 |  | HS2-00003H09M - CFA_11_56_Site_Restoration | SR_CFA_11_56 - Site Restoration - SR_CFA_11_56 | SR_CFA_11_56 | HS2-00003H09M | #N/A | #N/A | #N/A
223.8 | HS2-0000386TX | IDR 223.8 | HS2-0000386TX | 2024-05-29 | 10 - Complete | 2024-06-07 |  | HS2-00003H09L - CFA_11_55_Site_Restoration | SR_CFA_11_55 - Site Restoration - SR_CFA_11_55 | SR_CFA_11_55 | HS2-00003H09L | #N/A | #N/A | #N/A
223.8 | HS2-0000386TY | IDR 223.8 | HS2-0000386TY | 2024-05-29 | 10 - Complete | 2024-06-07 |  | HS2-00003H09K - CFA_11_53_Site_Restoration | SR_CFA_11_53 - Site Restoration - SR_CFA_11_53 | SR_CFA_11_53 | HS2-00003H09K | #N/A | #N/A | #N/A
223.8 | HS2-0000386U0 | IDR 223.8 | HS2-0000386U0 | 2024-05-29 | 10 - Complete | 2024-06-10 |  | HS2-00003H09J - CFA_11_51_Site_Restoration | SR_CFA_11_51 - Site Restoration - SR_CFA_11_51 | SR_CFA_11_51 | HS2-00003H09J | #N/A | #N/A | #N/A
223.8 | HS2-0000386U1 | IDR 223.8 | HS2-0000386U1 | 2024-05-29 | 10 - Complete | 2024-06-10 |  | HS2-00003H09H - CFA_11_13_Site_Restoration | SR_CFA_11_13 - Site Restoration - SR_CFA_11_13 | SR_CFA_11_13 | HS2-00003H09H | #N/A | #N/A | #N/A
223.8 | HS2-0000386U3 | IDR 223.8 | HS2-0000386U3 | 2024-05-29 | 10 - Complete | 2024-06-10 |  | HS2-00003H09G - CFA_11_12_Site_Restoration | SR_CFA_11_12 - Site Restoration - SR_CFA_11_12 | SR_CFA_11_12 | HS2-00003H09G | #N/A | #N/A | #N/A
223.8 | HS2-0000386U4 | IDR 223.8 | HS2-0000386U4 | 2024-05-29 | 10 - Complete | 2024-06-10 |  | HS2-00003H09F - CFA_11_11_Site_Restoration | SR_CFA_11_11 - Site Restoration - SR_CFA_11_11 | SR_CFA_11_11 | HS2-00003H09F | #N/A | #N/A | #N/A
223.8 | HS2-0000386U6 | IDR 223.8 | HS2-0000386U6 | 2024-05-29 | 10 - Complete | 2024-06-10 |  | HS2-00003H09E - CFA_11_10_Site_Restoration | SR_CFA_11_10 - Site Restoration - SR_CFA_11_10 | SR_CFA_11_10 | HS2-00003H09E | #N/A | #N/A | #N/A
223.8 | HS2-0000386U7 | IDR 223.8 | HS2-0000386U7 | 2024-05-29 | 10 - Complete | 2024-06-10 |  | HS2-00003H09D - CFA_11_09_Site_Restoration | SR_CFA_11_09 - Site Restoration - SR_CFA_11_09 | SR_CFA_11_09 | HS2-00003H09D | #N/A | #N/A | #N/A
208.4 | HS2-00003JQJP | IDR 208.4 | HS2-00003JQJP | 2024-05-29 | 10 - Complete | 2024-05-31 |  | HS2-00003H09C - CFA_11_08_Site_Restoration | SR_CFA_11_08 - Site Restoration - SR_CFA_11_08 | SR_CFA_11_08 | HS2-00003H09C | #N/A | #N/A | #N/A
UFDR 210.B | HS2-00002V04E | UFDR 210.B | HS2-00002V04E | 2025-01-23 | 10 - Complete | 2025-01-28 |  | HS2-00003H09B - CFA_11_07_Site_Restoration | SR_CFA_11_07 - Site Restoration - SR_CFA_11_07 | SR_CFA_11_07 | HS2-00003H09B | #N/A | #N/A | #N/A
230.01-3 | HS2-00002TGPA | IDR 230.01-3 | HS2-00002TGPA | 2024-05-30 | 10 - Complete | 2024-06-05 |  | HS2-00003H09A - CFA_11_06_Site_Restoration | SR_CFA_11_06 - Site Restoration - SR_CFA_11_06 | SR_CFA_11_06 | HS2-00003H09A | #N/A | #N/A | #N/A
230.01-3 | HS2-00003AL3P | IDR 230.01-3 | HS2-00003AL3P | 2024-05-30 | 10 - Complete | 2024-06-05 |  | HS2-00003H099 - CFA_11_04_Site_Restoration | SR_CFA_11_04 - Site Restoration - SR_CFA_11_04 | SR_CFA_11_04 | HS2-00003H099 | #N/A | #N/A | #N/A
215.02-02 | HS2-00002CT8Y | IDR 215.02-02 | HS2-00002CT8Y | 2025-01-29 | 10 - Complete | 2025-02-12 |  | HS2-00003H098 - CFA_11_01_Site_Restoration | SR_CFA_11_01 - Site Restoration - SR_CFA_11_01 | SR_CFA_11_01 | HS2-00003H098 | #N/A | #N/A | #N/A
213.08 | HS2-00002YPE9 | IDR 213.08 | HS2-00002YPE9 | 2024-06-06 | 10 - Complete | 2024-06-18 |  | HS2-00003H097 - CFA_10_81_Site_Restoration | SR_CFA_10_81 - Site Restoration - SR_CFA_10_81 | SR_CFA_10_81 | HS2-00003H097 | #N/A | #N/A | #N/A
213.08 | HS2-000031B41 | IDR 213.08 | HS2-000031B41 | 2024-06-06 | 10 - Complete | 2024-06-18 |  | HS2-00003H096 - CFA_10_80_Site_Restoration | SR_CFA_10_80 - Site Restoration - SR_CFA_10_80 | SR_CFA_10_80 | HS2-00003H096 | #N/A | #N/A | #N/A
213.08 | HS2-00002YPE7 | IDR 213.08 | HS2-00002YPE7 | 2024-05-30 | 10 - Complete | 2024-05-31 |  | HS2-00003H095 - CFA_10_79_Site_Restoration | SR_CFA_10_79 - Site Restoration - SR_CFA_10_79 | SR_CFA_10_79 | HS2-00003H095 | #N/A | #N/A | #N/A
213.08 | HS2-00002YPE8 | IDR 213.08 | HS2-00002YPE8 | 2024-05-30 | 10 - Complete | 2024-06-03 |  | HS2-00003H094 - CFA_10_78_Site_Restoration | SR_CFA_10_78 - Site Restoration - SR_CFA_10_78 | SR_CFA_10_78 | HS2-00003H094 | #N/A | #N/A | #N/A
213.08 | HS2-00002YPEA | IDR 213.08 | HS2-00002YPEA | 2024-05-30 | 10 - Complete | 2024-06-04 |  | HS2-00003H093 - CFA_10_77_Site_Restoration | SR_CFA_10_77 - Site Restoration - SR_CFA_10_77 | SR_CFA_10_77 | HS2-00003H093 | #N/A | #N/A | #N/A
213.08 | HS2-000031B3W | IDR 213.08 | HS2-000031B3W | 2024-05-30 | 10 - Complete | 2024-06-04 |  | HS2-00003H092 - CFA_10_76_Site_Restoration | SR_CFA_10_76 - Site Restoration - SR_CFA_10_76 | SR_CFA_10_76 | HS2-00003H092 | #N/A | #N/A | #N/A
213.08 | HS2-000031B3V | IDR 213.08 | HS2-000031B3V | 2024-05-30 | 10 - Complete | 2024-06-04 |  | HS2-00003H091 - CFA_10_75_Site_Restoration | SR_CFA_10_75 - Site Restoration - SR_CFA_10_75 | SR_CFA_10_75 | HS2-00003H091 | #N/A | #N/A | #N/A
213.08 | HS2-000031B3X | IDR 213.08 | HS2-000031B3X | 2024-05-30 | 10 - Complete | 2024-06-04 |  | HS2-00003H090 - CFA_10_74_Site_Restoration | SR_CFA_10_74 - Site Restoration - SR_CFA_10_74 | SR_CFA_10_74 | HS2-00003H090 | #N/A | #N/A | #N/A
213.08 | HS2-000031B3Y | IDR 213.08 | HS2-000031B3Y | 2024-05-30 | 10 - Complete | 2024-06-04 |  | HS2-00003H08Z - CFA_10_73_Site_Restoration | SR_CFA_10_73 - Site Restoration - SR_CFA_10_73 | SR_CFA_10_73 | HS2-00003H08Z | #N/A | #N/A | #N/A
213.08 | HS2-000031B3Z | IDR 213.08 | HS2-000031B3Z | 2024-05-30 | 10 - Complete | 2024-06-04 |  | HS2-00003H08Y - CFA_10_72_Site_Restoration | SR_CFA_10_72 - Site Restoration - SR_CFA_10_72 | SR_CFA_10_72 | HS2-00003H08Y | #N/A | #N/A | #N/A
213.08 | HS2-000031B40 | IDR 213.08 | HS2-000031B40 | 2024-05-30 | 10 - Complete | 2024-06-04 |  | HS2-00003H08X - CFA_10_71_Site_Restoration | SR_CFA_10_71 - Site Restoration - SR_CFA_10_71 | SR_CFA_10_71 | HS2-00003H08X | #N/A | #N/A | #N/A
212.5 | HS2-000035Q93 | IDR 212.5 | HS2-000035Q93 | 2024-05-30 | 10 - Complete | 2024-06-20 |  | HS2-00003H08W - CFA_10_70_Site_Restoration | SR_CFA_10_70 - Site Restoration - SR_CFA_10_70 | SR_CFA_10_70 | HS2-00003H08W | #N/A | #N/A | #N/A
238.02 | HS2-000020P2G | IDR 238.02 | HS2-000020P2G | 2024-11-21 | 10 - Complete | 2024-11-22 |  | HS2-00003H08V - CFA_10_69_Site_Restoration | SR_CFA_10_69 - Site Restoration - SR_CFA_10_69 | SR_CFA_10_69 | HS2-00003H08V | #N/A | #N/A | #N/A
211.1-3,211.1-4. (Technical Debt Works) | HS2-00002F0X6 | IDR 211.1-3,211.1-4. (Technical Debt Works) | HS2-00002F0X6 | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08U - CFA_10_68_Site_Restoration | SR_CFA_10_68 - Site Restoration - SR_CFA_10_68 | SR_CFA_10_68 | HS2-00003H08U | #N/A | #N/A | #N/A
235.01 | HS2-00002WUR6 | IDR 235.01 | HS2-00002WUR6 | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08T - CFA_10_67_Site_Restoration | SR_CFA_10_67 - Site Restoration - SR_CFA_10_67 | SR_CFA_10_67 | HS2-00003H08T | #N/A | #N/A | #N/A
235.01 | HS2-00002WUR7 | IDR 235.01 | HS2-00002WUR7 | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08S - CFA_10_66_Site_Restoration | SR_CFA_10_66 - Site Restoration - SR_CFA_10_66 | SR_CFA_10_66 | HS2-00003H08S | #N/A | #N/A | #N/A
235.01 | HS2-00002WUR8 | IDR 235.01 | HS2-00002WUR8 | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08R - CFA_10_65_Site_Restoration | SR_CFA_10_65 - Site Restoration - SR_CFA_10_65 | SR_CFA_10_65 | HS2-00003H08R | #N/A | #N/A | #N/A
235.01 | HS2-00002WUR9 | IDR 235.01 | HS2-00002WUR9 | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08Q - CFA_10_64_Site_Restoration | SR_CFA_10_64 - Site Restoration - SR_CFA_10_64 | SR_CFA_10_64 | HS2-00003H08Q | #N/A | #N/A | #N/A
235.01 | HS2-00002WURA | IDR 235.01 | HS2-00002WURA | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08P - CFA_10_63_Site_Restoration | SR_CFA_10_63 - Site Restoration - SR_CFA_10_63 | SR_CFA_10_63 | HS2-00003H08P | #N/A | #N/A | #N/A
235.01 | HS2-00002WURB | IDR 235.01 | HS2-00002WURB | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08N - CFA_10_62_Site_Restoration | SR_CFA_10_62 - Site Restoration - SR_CFA_10_62 | SR_CFA_10_62 | HS2-00003H08N | #N/A | #N/A | #N/A
235.01 | HS2-00002WURC | IDR 235.01 | HS2-00002WURC | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08M - CFA_10_61_Site_Restoration | SR_CFA_10_61 - Site Restoration - SR_CFA_10_61 | SR_CFA_10_61 | HS2-00003H08M | #N/A | #N/A | #N/A
235.01 | HS2-00002WURD | IDR 235.01 | HS2-00002WURD | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08L - CFA_10_60_Site_Restoration | SR_CFA_10_60 - Site Restoration - SR_CFA_10_60 | SR_CFA_10_60 | HS2-00003H08L | #N/A | #N/A | #N/A
235.01 | HS2-00002WURE | IDR 235.01 | HS2-00002WURE | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08K - CFA_10_59_Site_Restoration | SR_CFA_10_59 - Site Restoration - SR_CFA_10_59 | SR_CFA_10_59 | HS2-00003H08K | #N/A | #N/A | #N/A
235.01 | HS2-00002WURF | IDR 235.01 | HS2-00002WURF | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08J - CFA_10_58_Site_Restoration | SR_CFA_10_58 - Site Restoration - SR_CFA_10_58 | SR_CFA_10_58 | HS2-00003H08J | #N/A | #N/A | #N/A
235.01 | HS2-00002WURG | IDR 235.01 | HS2-00002WURG | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08H - CFA_10_57_Site_Restoration | SR_CFA_10_57 - Site Restoration - SR_CFA_10_57 | SR_CFA_10_57 | HS2-00003H08H | #N/A | #N/A | #N/A
235.01 | HS2-00002WURH | IDR 235.01 | HS2-00002WURH | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08G - CFA_10_56_Site_Restoration | SR_CFA_10_56 - Site Restoration - SR_CFA_10_56 | SR_CFA_10_56 | HS2-00003H08G | #N/A | #N/A | #N/A
235.01 | HS2-00002WURJ | IDR 235.01 | HS2-00002WURJ | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08F - CFA_10_55_Site_Restoration | SR_CFA_10_55 - Site Restoration - SR_CFA_10_55 | SR_CFA_10_55 | HS2-00003H08F | #N/A | #N/A | #N/A
235.01 | HS2-00002WURK | IDR 235.01 | HS2-00002WURK | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08E - CFA_10_54_Site_Restoration | SR_CFA_10_54 - Site Restoration - SR_CFA_10_54 | SR_CFA_10_54 | HS2-00003H08E | #N/A | #N/A | #N/A
235.01 | HS2-00002WURL | IDR 235.01 | HS2-00002WURL | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08D - CFA_10_53_Site_Restoration | SR_CFA_10_53 - Site Restoration - SR_CFA_10_53 | SR_CFA_10_53 | HS2-00003H08D | #N/A | #N/A | #N/A
235.01 | HS2-00002WURM | IDR 235.01 | HS2-00002WURM | 2024-05-31 | 10 - Complete | 2024-06-10 |  | HS2-00003H08C - CFA_10_52_Site_Restoration | SR_CFA_10_52 - Site Restoration - SR_CFA_10_52 | SR_CFA_10_52 | HS2-00003H08C | #N/A | #N/A | #N/A
235.01 | HS2-00002WURN | IDR 235.01 | HS2-00002WURN | 2024-05-31 | 10 - Complete | 2024-06-11 |  | HS2-00003H08B - CFA_10_51_Site_Restoration | SR_CFA_10_51 - Site Restoration - SR_CFA_10_51 | SR_CFA_10_51 | HS2-00003H08B | #N/A | #N/A | #N/A
235.01 | HS2-00002WURP | IDR 235.01 | HS2-00002WURP | 2024-05-31 | 10 - Complete | 2024-06-11 |  | HS2-00003H08A - CFA_10_16_Site_Restoration | SR_CFA_10_16 - Site Restoration - SR_CFA_10_16 | SR_CFA_10_16 | HS2-00003H08A | #N/A | #N/A | #N/A
235.01 | HS2-00002WURQ | IDR 235.01 | HS2-00002WURQ | 2024-05-31 | 10 - Complete | 2024-06-11 |  | HS2-00003FV0T - CFA_10_12_Site_Restoration | SR_CFA_10_12 - Site Restoration - HB-006 | SR_CFA_10_12 | HS2-00003FV0T | #N/A | #N/A | #N/A
214.07 | HS2-00002CT81 | IDR 214.07 | HS2-00002CT81 | 2025-02-17 | 10 - Complete | 2025-02-19 |  | HS2-00003H088 - CFA_10_11_Site_Restoration | SR_CFA_10_11 - Site Restoration - SR_CFA_10_11 | SR_CFA_10_11 | HS2-00003H088 | #N/A | #N/A | #N/A
238.02_2 | HS2-000025B3V | IDR 238.02_2 | HS2-000025B3V | 2024-11-21 | 10 - Complete | 2024-11-26 |  | HS2-00003H087 - CFA_10_10_Site_Restoration | SR_CFA_10_10 - Site Restoration - SR_CFA_10_10 | SR_CFA_10_10 | HS2-00003H087 | #N/A | #N/A | #N/A
210.2-2 | HS2-00002BJT6 | IDR 210.2-2 | HS2-00002BJT6 | 2024-06-03 | 10 - Complete | 2024-06-18 |  | HS2-00003H086 - CFA_10_09b_Site_Restoration | SR_CFA_10_09b - Site Restoration - SR_CFA_10_09b | SR_CFA_10_09b | HS2-00003H086 | #N/A | #N/A | #N/A
210.2-2 | HS2-00002ZM2C | IDR 210.2-2 | HS2-00002ZM2C | 2024-06-03 | 10 - Complete | 2024-06-17 |  | HS2-00003H085 - CFA_10_08a_Site_Restoration | SR_CFA_10_08a - Site Restoration - SR_CFA_10_08a | SR_CFA_10_08a | HS2-00003H085 | #N/A | #N/A | #N/A
204.2-2 | HS2-00003JN86 | IDR 204.2-2 | HS2-00003JN86 | 2024-06-03 | 10 - Complete | 2024-06-17 |  | HS2-00003H084 - CFA_10_08_Site_Restoration | SR_CFA_10_08 - Site Restoration - SR_CFA_10_08 | SR_CFA_10_08 | HS2-00003H084 | #N/A | #N/A | #N/A
229.03 | HS2-000001072 | IDR 229.03 | HS2-000001072 | 2024-08-28 | 10 - Complete | 2024-09-18 |  | HS2-00003H083 - CFA_10_05_Site_Restoration | SR_CFA_10_05 - Site Restoration - SR_CFA_10_05 | SR_CFA_10_05 | HS2-00003H083 | #N/A | #N/A | #N/A
212.5 | HS2-00002YD7F | IDR 212.5 | HS2-00002YD7F | 2024-07-09 | 10 - Complete | 2024-07-17 |  | HS2-00003H082 - CFA_10_03_Site_Restoration | SR_CFA_10_03 - Site Restoration - SR_CFA_10_03 | SR_CFA_10_03 | HS2-00003H082 | #N/A | #N/A | #N/A
230.04-2 | HS2-00002CTG0 | IDR 230.04-2 | HS2-00002CTG0 | 2024-08-28 | 10 - Complete | 2024-09-25 |  | HS2-00003H081 - CFA_10_02a_Site_Restoration | SR_CFA_10_02a - Site Restoration - SR_CFA_10_02a | SR_CFA_10_02a | HS2-00003H081 | #N/A | #N/A | #N/A
229.01-1 | HS2-00002NJ05 | IDR 229.01-1 | HS2-00002NJ05 | 2024-06-04 | 10 - Complete | 2024-07-29 |  | HS2-00003H080 - CFA_10_02_Site_Restoration | SR_CFA_10_02 - Site Restoration - SR_CFA_10_02 | SR_CFA_10_02 | HS2-00003H080 | #N/A | #N/A | #N/A
229.01-1 | HS2-00002NJ05 | IDR 229.01-1 | HS2-00002NJ05 | 2024-06-04 | 10 - Complete | 2024-07-29 |  | HS2-00003H07Z - CFA_10_01_Site_Restoration | SR_CFA_10_01 - Site Restoration - SR_CFA_10_01 | SR_CFA_10_01 | HS2-00003H07Z | #N/A | #N/A | #N/A
229.01-1 | HS2-00002NJ05 | IDR 229.01-1 | HS2-00002NJ05 | 2024-06-04 | 10 - Complete | 2024-07-29 |  | HS2-00003H07Y - CFA_09_64_Site_Restoration | SR_CFA_09_64 - Site Restoration - SR_CFA_09_64 | SR_CFA_09_64 | HS2-00003H07Y | #N/A | #N/A | #N/A
220.5 | HS2-00002N7W9 | IDR 220.5 | HS2-00002N7W9 | 2024-06-04 | 10 - Complete | 2024-06-14 |  | HS2-00003H07X - CFA_09_63_Site_Restoration | SR_CFA_09_63 - Site Restoration - SR_CFA_09_63 | SR_CFA_09_63 | HS2-00003H07X | #N/A | #N/A | #N/A
218.02 | HS2-00003B931 | IDR 218.02 | HS2-00003B931 | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H07W - CFA_09_62_Site_Restoration | SR_CFA_09_62 - Site Restoration - SR_CFA_09_62 | SR_CFA_09_62 | HS2-00003H07W | #N/A | #N/A | #N/A
218.02 | HS2-00003B932 | IDR 218.02 | HS2-00003B932 | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H07V - CFA_09_61_Site_Restoration | SR_CFA_09_61 - Site Restoration - SR_CFA_09_61 | SR_CFA_09_61 | HS2-00003H07V | #N/A | #N/A | #N/A
218.02 | HS2-00003B933 | IDR 218.02 | HS2-00003B933 | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H07U - CFA_09_60_Site_Restoration | SR_CFA_09_60 - Site Restoration - SR_CFA_09_60 | SR_CFA_09_60 | HS2-00003H07U | #N/A | #N/A | #N/A
218.02 | HS2-00003B92J | IDR 218.02 | HS2-00003B92J | 2024-06-04 | 10 - Complete | 2024-06-05 |  | HS2-00003H07T - CFA_09_59_Site_Restoration | SR_CFA_09_59 - Site Restoration - SR_CFA_09_59 | SR_CFA_09_59 | HS2-00003H07T | #N/A | #N/A | #N/A
218.02 | HS2-00003B92L | IDR 218.02 | HS2-00003B92L | 2024-06-04 | 10 - Complete | 2024-06-05 |  | HS2-00003H07S - CFA_09_58_Site_Restoration | SR_CFA_09_58 - Site Restoration - SR_CFA_09_58 | SR_CFA_09_58 | HS2-00003H07S | #N/A | #N/A | #N/A
218.02 | HS2-00003B92N | IDR 218.02 | HS2-00003B92N | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H07R - CFA_09_57_Site_Restoration | SR_CFA_09_57 - Site Restoration - SR_CFA_09_57 | SR_CFA_09_57 | HS2-00003H07R | #N/A | #N/A | #N/A
218.02 | HS2-00003B92Q | IDR 218.02 | HS2-00003B92Q | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H07Q - CFA_09_56_Site_Restoration | SR_CFA_09_56 - Site Restoration - SR_CFA_09_56 | SR_CFA_09_56 | HS2-00003H07Q | #N/A | #N/A | #N/A
218.02 | HS2-00003B92U | IDR 218.02 | HS2-00003B92U | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H07P - CFA_09_55_Site_Restoration | SR_CFA_09_55 - Site Restoration - SR_CFA_09_55 | SR_CFA_09_55 | HS2-00003H07P | #N/A | #N/A | #N/A
218.02 | HS2-00003B92W | IDR 218.02 | HS2-00003B92W | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H07N - CFA_09_54_Site_Restoration | SR_CFA_09_54 - Site Restoration - SR_CFA_09_54 | SR_CFA_09_54 | HS2-00003H07N | #N/A | #N/A | #N/A
218.02 | HS2-00003B92X | IDR 218.02 | HS2-00003B92X | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H07M - CFA_09_53_Site_Restoration | SR_CFA_09_53 - Site Restoration - SR_CFA_09_53 | SR_CFA_09_53 | HS2-00003H07M | #N/A | #N/A | #N/A
218.02 | HS2-00003B935 | IDR 218.02 | HS2-00003B935 | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H07L - CFA_09_52_Site_Restoration | SR_CFA_09_52 - Site Restoration - SR_CFA_09_52 | SR_CFA_09_52 | HS2-00003H07L | #N/A | #N/A | #N/A
218.02 | HS2-00003B938 | IDR 218.02 | HS2-00003B938 | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H07K - CFA_09_51_Site_Restoration | SR_CFA_09_51 - Site Restoration - SR_CFA_09_51 | SR_CFA_09_51 | HS2-00003H07K | #N/A | #N/A | #N/A
218.02 | HS2-00003B93A | IDR 218.02 | HS2-00003B93A | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H07J - CFA_09_10_Site_Restoration | SR_CFA_09_10 - Site Restoration - SR_CFA_09_10 | SR_CFA_09_10 | HS2-00003H07J | #N/A | #N/A | #N/A
218.02 | HS2-00003B93C | IDR 218.02 | HS2-00003B93C | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H07H - CFA_09_07a_Site_Restoration | SR_CFA_09_07a - Site Restoration - SR_CFA_09_07a | SR_CFA_09_07a | HS2-00003H07H | #N/A | #N/A | #N/A
218.02 | HS2-00003B93G | IDR 218.02 | HS2-00003B93G | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-00003H089 - CFA_10_14_Site_Restoration | Site Restoration - SR_CFA_10_14 | Site Restoration | HS2-00003H089 | #N/A | #N/A | #N/A
218.02 | HS2-00003B93J | IDR 218.02 | HS2-00003B93J | 2024-06-04 | 10 - Complete | 2024-06-06 |  | HS2-000020NF6 - Flood Compensation Area-071B | SDI 0007 - C2 IDR 07 - Putlowes to Quainton | SDI 0007 | HS2-000020NF6 | #N/A | #N/A | #N/A
218.02 | HS2-00003B93M | IDR 218.02 | HS2-00003B93M | 2025-03-27 | 10 - Complete | 2025-04-01 |  | HS2-000020NFD - Flood Compensation Area-071C | SDI 0007 - C2 IDR 07 - Putlowes to Quainton | SDI 0007 | HS2-000020NFD | #N/A | #N/A | #N/A
213.07-1 | HS2-00003CCK1 | IDR 213.07-1 | HS2-00003CCK1 | 2024-06-05 | 10 - Complete | 2024-06-07 |  | HS2-000020NFF - Flood Compensation Area-071D | SDI 0007 - C2 IDR 07 - Putlowes to Quainton | SDI 0007 | HS2-000020NFF | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-000020NFM - Flood Compensation Area-071E | SDI 0007 - C2 IDR 07 - Putlowes to Quainton | SDI 0007 | HS2-000020NFM | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-000020C17 - Flood Compensation Area-071F | SDI 0007 - C2 IDR 07 - Putlowes to Quainton | SDI 0007 | HS2-000020C17 | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-000020NFV - Flood Compensation Area-071G | SDI 0007 - C2 IDR 07 - Putlowes to Quainton | SDI 0007 | HS2-000020NFV | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-00002MR7A - Ladbroke Grove Cutting Devegetation | SC IDR C3-E Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002MR7A | #N/A | #N/A | #N/A
213.08 | HS2-00002YPE9 | IDR 213.08 | HS2-00002YPE9 | 2024-06-06 | 10 - Complete | 2024-06-18 |  | HS2-00002MR7B - Ladbroke Grove Embankment Devegetation | SC IDR C3-E Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002MR7B | #N/A | #N/A | #N/A
213.08 | HS2-000031B41 | IDR 213.08 | HS2-000031B41 | 2024-06-06 | 10 - Complete | 2024-06-18 |  | HS2-00002MR7C - Ladbroke Cutting Devegetation | SC IDR C3-E Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002MR7C | #N/A | #N/A | #N/A
UFDR 239.A | HS2-000020CKZ | UFDR 239.A | HS2-000020CKZ | 2024-06-12 | 10 - Complete | 2024-06-18 |  | HS2-00002MR7D - Southam Embankment Devegetation | SC IDR C3-E Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002MR7D | #N/A | #N/A | #N/A
UFDR 239.A | HS2-000020CKS | UFDR 239.A | HS2-000020CKS | 2024-06-12 | 10 - Complete | 2024-06-18 |  | HS2-00002MR7E - Southam Cutting Devegetation | SC IDR C3-E Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002MR7E | #N/A | #N/A | #N/A
UFDR 239.A | HS2-00003B2H4 | UFDR 239.A | HS2-00003B2H4 | 2024-06-12 | 10 - Complete | 2024-06-18 |  | HS2-00002MR7F - Mill Pond Embankment Devegetation | SC IDR C3-E Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002MR7F | #N/A | #N/A | #N/A
UFDR 217.B | HS2-0000245ZF | UFDR 217.B | HS2-0000245ZF | 2024-08-19 | 10 - Complete | 2024-08-21 |  | HS2-00002MR7G - River Itchen Viaduct Devegetation | SC IDR C3-E Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002MR7G | #N/A | #N/A | #N/A
UFDR 202.E | HS2-00002NHZ4 | UFDR 202.E | HS2-00002NHZ4 | 2024-06-07 | 10 - Complete | 2024-06-21 |  | HS2-00002MR7H - Leamington Road Embankment Devegetation | SC IDR C3-E Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002MR7H | #N/A | #N/A | #N/A
UFDR 202.E | HS2-00002NHZ6 | UFDR 202.E | HS2-00002NHZ6 | 2024-06-07 | 10 - Complete | 2024-07-04 |  | HS2-00002MR6X - Aston le Walls Embankment Devegetation | SC IDR C3-D Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002MR6X | #N/A | #N/A | #N/A
UFDR 202.E | HS2-000020CDR | UFDR 202.E | HS2-000020CDR | 2024-06-07 | 10 - Complete | 2024-07-04 |  | HS2-00002MR6Y - Highfurlong Brook Viaduct Devegetation | SC IDR C3-D Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002MR6Y | #N/A | #N/A | #N/A
233.01 | HS2-00003B93N | IDR 233.01 | HS2-00003B93N | 2024-06-07 | 10 - Complete | 2024-06-12 |  | HS2-00002MR6Z - Highfurlong Brook Embankment Devegetation | SC IDR C3-D Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002MR6Z | #N/A | #N/A | #N/A
220.5 | HS2-00002J4YG | IDR 220.5 | HS2-00002J4YG | 2024-06-07 | 10 - Complete | 2024-06-14 |  | HS2-00002MR70 - Lower Boddington Cutting Devegetation | SC IDR C3-D Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002MR70 | #N/A | #N/A | #N/A
220.5 | HS2-00002BJUM | IDR 220.5 | HS2-00002BJUM | 2024-06-07 | 10 - Complete | 2024-06-14 |  | HS2-00002MR71 - Lower Boddington Embankment Devegetation | SC IDR C3-D Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002MR71 | #N/A | #N/A | #N/A
220.5 | HS2-00002BJUL | IDR 220.5 | HS2-00002BJUL | 2024-06-07 | 10 - Complete | 2024-06-14 |  | HS2-00002MR72 - Boddington Cutting Devegetation | SC IDR C3-D Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002MR72 | #N/A | #N/A | #N/A
220.5 | HS2-000020NLQ | IDR 220.5 | HS2-000020NLQ | 2024-06-07 | 10 - Complete | 2024-06-18 |  | HS2-00002MR73 - Oxford Canal South Embankment Devegetation | SC IDR C3-D Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002MR73 | #N/A | #N/A | #N/A
213.01-01 | HS2-000020NF2 | IDR 213.01-01 | HS2-000020NF2 | 2024-06-10 | 99 - Cancelled | 0 |  | HS2-00002MR74 - Oxford Canal Viaduct Devegetation | SC IDR C3-D Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002MR74 | #N/A | #N/A | #N/A
213.01-01 | HS2-00002BJTJ | IDR 213.01-01 | HS2-00002BJTJ | 2025-06-27 | 10 - Complete | 2025-07-01 |  | HS2-00002MR75 - Oxford Canal North Embankment Devegetation | SC IDR C3-D Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002MR75 | #N/A | #N/A | #N/A
235.01 | HS2-00003K85S | IDR 235.01 | HS2-00003K85S | 2024-06-10 | 10 - Complete | 2024-06-18 |  | HS2-00002MR76 - Lower Radbourne South Viaduct Devegetation | SC IDR C3-D Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002MR76 | #N/A | #N/A | #N/A
228.2 | HS2-00002CX3J | IDR 228.2 | HS2-00002CX3J | 2024-06-10 | 99 - Cancelled | 0 |  | HS2-00002MR77 - Upper Radbourne Embankment Devegetation | SC IDR C3-D Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002MR77 | #N/A | #N/A | #N/A
218.02 | HS2-00002TPZ5 | IDR 218.02 | HS2-00002TPZ5 | 2024-06-10 | 10 - Complete | 2024-06-12 |  | HS2-00002MR78 - Lower Radbourne North Viaduct Devegetation | SC IDR C3-D Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002MR78 | #N/A | #N/A | #N/A
218.02 | HS2-00003124A | IDR 218.02 | HS2-00003124A | 2024-06-10 | 10 - Complete | 2024-06-12 |  | HS2-00002MR79 - Lower Radbourne Embankment Devegetation | SC IDR C3-D Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002MR79 | #N/A | #N/A | #N/A
213.08 | HS2-00002CT7E | IDR 213.08 | HS2-00002CT7E | 2024-07-18 | 10 - Complete | 2024-08-08 |  | HS2-00002MR6J - Thorpe Mandeville Embankment Devegetation | SC IDR C3-C Thorpe Mandeville to Edgcote Cutting | #VALUE! | HS2-00002MR6J | #N/A | #N/A | #N/A
213.08 | HS2-00002CT7F | IDR 213.08 | HS2-00002CT7F | 2024-06-10 | 10 - Complete | 2024-06-18 |  | HS2-00002MR6K - Lower Thorpe Viaduct Devegetation | SC IDR C3-C Thorpe Mandeville to Edgcote Cutting | #VALUE! | HS2-00002MR6K | #N/A | #N/A | #N/A
213.05 | HS2-00002CT7D | IDR 213.05 | HS2-00002CT7D | 2025-03-14 | 10 - Complete | 2025-03-20 |  | HS2-00002MR6L - Lower Thorpe South Embankment Devegetation | SC IDR C3-C Thorpe Mandeville to Edgcote Cutting | #VALUE! | HS2-00002MR6L | #N/A | #N/A | #N/A
213.05 | HS2-000020NGC | IDR 213.05 | HS2-000020NGC | 2025-03-14 | 10 - Complete | 2025-03-21 |  | HS2-00002MR6M - Lower Thorpe South Cutting Devegetation | SC IDR C3-C Thorpe Mandeville to Edgcote Cutting | #VALUE! | HS2-00002MR6M | #N/A | #N/A | #N/A
222.6 | HS2-000001326 | IDR 222.6 | HS2-000001326 | 2024-06-11 | 10 - Complete | 2024-07-10 |  | HS2-00002MR6N - Lower Thorpe North Embankment Devegetation | SC IDR C3-C Thorpe Mandeville to Edgcote Cutting | #VALUE! | HS2-00002MR6N | #N/A | #N/A | #N/A
214.1 | HS2-00002CW17 | IDR 214.1 | HS2-00002CW17 | 2025-05-22 | 10 - Complete | 2025-05-28 |  | HS2-00002MR6P - Lower Thorpe North Cutting Devegetation | SC IDR C3-C Thorpe Mandeville to Edgcote Cutting | #VALUE! | HS2-00002MR6P | #N/A | #N/A | #N/A
UFDR 239.A | HS2-000020CKZ | UFDR 239.A | HS2-000020CKZ | 2024-06-12 | 10 - Complete | 2024-06-18 |  | HS2-00002MR6Q - Culworth Embankment Devegetation | SC IDR C3-C Thorpe Mandeville to Edgcote Cutting | #VALUE! | HS2-00002MR6Q | #N/A | #N/A | #N/A
UFDR 239.A | HS2-000020CKS | UFDR 239.A | HS2-000020CKS | 2024-06-12 | 10 - Complete | 2024-06-18 |  | HS2-00002MR6R - Culworth Cutting Devegetation | SC IDR C3-C Thorpe Mandeville to Edgcote Cutting | #VALUE! | HS2-00002MR6R | #N/A | #N/A | #N/A
UFDR 239.A | HS2-00003B2H4 | UFDR 239.A | HS2-00003B2H4 | 2024-06-12 | 10 - Complete | 2024-06-18 |  | HS2-00002MR6S - Edgcote South Embankment Devegetation | SC IDR C3-C Thorpe Mandeville to Edgcote Cutting | #VALUE! | HS2-00002MR6S | #N/A | #N/A | #N/A
UFDR 236.A | HS2-000020CJZ | UFDR 236.A | HS2-000020CJZ | 2024-06-12 | 10 - Complete | 2024-06-25 |  | HS2-00002MR6T - Edgcote Viaduct Devegetation | SC IDR C3-C Thorpe Mandeville to Edgcote Cutting | #VALUE! | HS2-00002MR6T | #N/A | #N/A | #N/A
204.2-2 | HS2-00002YNHA | IDR 204.2-2 | HS2-00002YNHA | 2024-06-12 | 10 - Complete | 2024-08-16 |  | HS2-00002MR6U - Edgcote North Embankment Devegetation | SC IDR C3-C Thorpe Mandeville to Edgcote Cutting | #VALUE! | HS2-00002MR6U | #N/A | #N/A | #N/A
204.2-2 | HS2-00002YNHB | IDR 204.2-2 | HS2-00002YNHB | 2024-06-12 | 10 - Complete | 2024-08-16 |  | HS2-00002MR6V - Edgcote Cutting Devegetation | SC IDR C3-C Thorpe Mandeville to Edgcote Cutting | #VALUE! | HS2-00002MR6V | #N/A | #N/A | #N/A
204.2-2 | HS2-00002YNHC | IDR 204.2-2 | HS2-00002YNHC | 2024-06-12 | 10 - Complete | 2024-08-20 |  | HS2-00002MR6H - Greatworth Green Tunnel Devegetation | SC IDR C3-B Greatworth Green Tunnel | #VALUE! | HS2-00002MR6H | #N/A | #N/A | #N/A
223.8 | HS2-000037YLY | IDR 223.8 | HS2-000037YLY | 2024-06-12 | 10 - Complete | 2024-06-21 |  | HS2-00002MR6W - Chipping Warden Green Tunnel Devegetation | SC IDR C3-A Chipping Warden Green Tunnel | #VALUE! | HS2-00002MR6W | #N/A | #N/A | #N/A
223.8 | HS2-000037YLZ | IDR 223.8 | HS2-000037YLZ | 2024-06-12 | 10 - Complete | 2024-06-21 |  | HS2-00002MR3M - Aylesbury South Cutting Devegetation | SC IDR C2-F Aylesbury South Cutting to Thame Valley Viaduct | #VALUE! | HS2-00002MR3M | #N/A | #N/A | #N/A
223.8 | HS2-00002YCW9 | IDR 223.8 | HS2-00002YCW9 | 2024-06-12 | 10 - Complete | 2024-06-21 |  | HS2-00002MR3N - Aylesbury Embankment Devegetation | SC IDR C2-F Aylesbury South Cutting to Thame Valley Viaduct | #VALUE! | HS2-00002MR3N | #N/A | #N/A | #N/A
222.6 | HS2-00002N7WN | IDR 222.6 | HS2-00002N7WN | 2024-06-12 | 10 - Complete | 2024-06-19 |  | HS2-00002MR3P - Aylesbury North Cutting Devegetation | SC IDR C2-F Aylesbury South Cutting to Thame Valley Viaduct | #VALUE! | HS2-00002MR3P | #N/A | #N/A | #N/A
220.5 | HS2-00002Y0RV | IDR 220.5 | HS2-00002Y0RV | 2024-06-12 | 10 - Complete | 2024-06-26 |  | HS2-00002MR3Q - Oxford Road Embankment Devegetation | SC IDR C2-F Aylesbury South Cutting to Thame Valley Viaduct | #VALUE! | HS2-00002MR3Q | #N/A | #N/A | #N/A
214.1 | HS2-000020NJ5 | IDR 214.1 | HS2-000020NJ5 | 2024-06-12 | 10 - Complete | 2024-07-29 |  | HS2-00002MR3R - Whaddon Hill Cutting Devegetation | SC IDR C2-F Aylesbury South Cutting to Thame Valley Viaduct | #VALUE! | HS2-00002MR3R | #N/A | #N/A | #N/A
214.1 | HS2-00002DRXL | IDR 214.1 | HS2-00002DRXL | 2025-04-29 | 10 - Complete | 2025-05-29 |  | HS2-00002MR3S - Thame Valley South Embankment Devegetation | SC IDR C2-F Aylesbury South Cutting to Thame Valley Viaduct | #VALUE! | HS2-00002MR3S | #N/A | #N/A | #N/A
214.1 | HS2-00002BJTZ | IDR 214.1 | HS2-00002BJTZ | 2024-06-12 | 10 - Complete | 2024-07-30 |  | HS2-00002MR3T - Thame Valley Viaduct Devegetation | SC IDR C2-F Aylesbury South Cutting to Thame Valley Viaduct | #VALUE! | HS2-00002MR3T | #N/A | #N/A | #N/A
214.1 | HS2-00002CT8K | IDR 214.1 | HS2-00002CT8K | 2024-06-12 | 10 - Complete | 2024-07-09 |  | HS2-00002MR3J - Wendover Green Tunnel Devegetation | SC IDR C2-E Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002MR3J | #N/A | #N/A | #N/A
204.0-2 | HS2-00002CT4A | IDR 204.0-2 | HS2-00002CT4A | 2024-06-13 | 10 - Complete | 2024-07-10 |  | HS2-00002MR3K - Wendover North Cutting Devegetation | SC IDR C2-E Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002MR3K | #N/A | #N/A | #N/A
229.01-1 | HS2-000020360 | IDR 229.01-1 | HS2-000020360 | 2025-02-19 | 10 - Complete | 2025-02-24 |  | HS2-00002MR3L - Stoke Mandeville South Embankment Devegetation | SC IDR C2-E Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002MR3L | #N/A | #N/A | #N/A
229.01-1 | HS2-000020NVL | IDR 229.01-1 | HS2-000020NVL | 2024-06-14 | 10 - Complete | 2024-06-24 |  | HS2-00002MR3U - Thame Valley North Embankment Devegetation | SC IDR C2-D Thame Valley North Embankment to Quainton South Embankment | #VALUE! | HS2-00002MR3U | #N/A | #N/A | #N/A
214.07 | HS2-00002YXB5 | IDR 214.07 | HS2-00002YXB5 | 2024-07-03 | 10 - Complete | 2024-07-05 |  | HS2-00002MR3V - Putlowes Cutting Devegetation | SC IDR C2-D Thame Valley North Embankment to Quainton South Embankment | #VALUE! | HS2-00002MR3V | #N/A | #N/A | #N/A
214.07 | HS2-00002YXB0 | IDR 214.07 | HS2-00002YXB0 | 2024-06-17 | 10 - Complete | 2024-07-04 |  | HS2-00002MR3W - Bicester Road Embankment Devegetation | SC IDR C2-D Thame Valley North Embankment to Quainton South Embankment | #VALUE! | HS2-00002MR3W | #N/A | #N/A | #N/A
214.07 | HS2-0000300BT | IDR 214.07 | HS2-0000300BT | 2024-06-17 | 10 - Complete | 2024-07-09 |  | HS2-00002MR3X - Waddesdon South Cutting Devegetation | SC IDR C2-D Thame Valley North Embankment to Quainton South Embankment | #VALUE! | HS2-00002MR3X | #N/A | #N/A | #N/A
214.07 | HS2-00003H07G | IDR 214.07 | HS2-00003H07G | 2024-06-17 | 10 - Complete | 2024-08-05 |  | HS2-00002MR3Y - Waddesdon Embankment Devegetation | SC IDR C2-D Thame Valley North Embankment to Quainton South Embankment | #VALUE! | HS2-00002MR3Y | #N/A | #N/A | #N/A
214.07 | HS2-00003H5JJ | IDR 214.07 | HS2-00003H5JJ | 2024-06-17 | 10 - Complete | 2024-07-05 |  | HS2-00002MR3Z - Waddesdon North Cutting Devegetation | SC IDR C2-D Thame Valley North Embankment to Quainton South Embankment | #VALUE! | HS2-00002MR3Z | #N/A | #N/A | #N/A
214.07 | HS2-00003HWH3 | IDR 214.07 | HS2-00003HWH3 | 2024-06-17 | 10 - Complete | 2024-07-05 |  | HS2-00002MR40 - Quainton South Embankment Devegetation | SC IDR C2-D Thame Valley North Embankment to Quainton South Embankment | #VALUE! | HS2-00002MR40 | #N/A | #N/A | #N/A
228 | HS2-000001338 | IDR 228 | HS2-000001338 | 2024-06-18 | 10 - Complete | 2024-08-01 |  | HS2-00002MR3A - South Heath Cutting Devegetation | SC IDR C2-C South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002MR3A | #N/A | #N/A | #N/A
222.6 | HS2-00002CW0J | IDR 222.6 | HS2-00002CW0J | 2024-06-18 | 10 - Complete | 2024-06-21 |  | HS2-00002MR3B - Wendover Dean South Embankment Devegetation | SC IDR C2-C South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002MR3B | #N/A | #N/A | #N/A
212.5 | HS2-00002YD79 | IDR 212.5 | HS2-00002YD79 | 2024-07-08 | 10 - Complete | 2024-07-09 |  | HS2-00002MR3C - Wendover Dean Viaduct Devegetation | SC IDR C2-C South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002MR3C | #N/A | #N/A | #N/A
235.01 | HS2-00002TKUY | IDR 235.01 | HS2-00002TKUY | 2024-06-19 | 10 - Complete | 2024-06-20 |  | HS2-00002MR3D - Wendover Dean North Embankment Devegetation | SC IDR C2-C South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002MR3D | #N/A | #N/A | #N/A
234.05 | HS2-00002N7UN | IDR 234.05 | HS2-00002N7UN | 2024-07-18 | 10 - Complete | 2024-08-02 |  | HS2-00002MR3E - Rocky Lane Cutting Devegetation | SC IDR C2-C South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002MR3E | #N/A | #N/A | #N/A
233.01 | HS2-00002YKZ9 | IDR 233.01 | HS2-00002YKZ9 | 2024-06-19 | 10 - Complete | 2024-07-02 |  | HS2-00002MR3F - Small Dean South Embankment Devegetation | SC IDR C2-C South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002MR3F | #N/A | #N/A | #N/A
228.1 | HS2-000001340 | IDR 228.1 | HS2-000001340 | 2024-08-22 | 10 - Complete | 2024-10-04 |  | HS2-00002MR3G - Small Dean Viaduct Devegetation | SC IDR C2-C South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002MR3G | #N/A | #N/A | #N/A
214.1 | HS2-00003CPYS | IDR 214.1 | HS2-00003CPYS | 2024-06-19 | 10 - Complete | 2024-08-22 |  | HS2-00002MR3H - Small Dean North Embankment Devegetation | SC IDR C2-C South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002MR3H | #N/A | #N/A | #N/A
214.1 | HS2-000031B3U | IDR 214.1 | HS2-000031B3U | 2024-07-11 | 10 - Complete | 2024-07-23 |  | HS2-00002MR41 - Quainton Cutting Devegetation | SC IDR C2-B Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002MR41 | #N/A | #N/A | #N/A
214.1 | HS2-00002NSXM | IDR 214.1 | HS2-00002NSXM | 2024-06-19 | 10 - Complete | 2024-07-29 |  | HS2-00002MR42 - Doddershall Embankment Devegetation | SC IDR C2-B Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002MR42 | #N/A | #N/A | #N/A
214.1 | HS2-00002NSXL | IDR 214.1 | HS2-00002NSXL | 2024-06-19 | 10 - Complete | 2024-07-29 |  | HS2-00002MR43 - Woodlands Cutting Devegetation | SC IDR C2-B Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002MR43 | #N/A | #N/A | #N/A
212.5 | HS2-000035Q92 | IDR 212.5 | HS2-000035Q92 | 2024-06-19 | 10 - Complete | 2024-06-25 |  | HS2-00002MR44 - Grendon Underwood Embankment Devegetation | SC IDR C2-B Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002MR44 | #N/A | #N/A | #N/A
229.01-2 | HS2-00002EK7T | IDR 229.01-2 | HS2-00002EK7T | 2024-11-29 | 10 - Complete | 2024-12-17 |  | HS2-00002MR45 - Calvert Cutting Devegetation | SC IDR C2-A Calvert Cutting & IMD to Cowley Embankment | #VALUE! | HS2-00002MR45 | #N/A | #N/A | #N/A
230.01-3 | HS2-00002CTFN | IDR 230.01-3 | HS2-00002CTFN | 2025-02-06 | 10 - Complete | 2025-02-20 |  | HS2-00002MR46 - Calvert Infrastructure Maintenance Depot Devegetation | SC IDR C2-A Calvert Cutting & IMD to Cowley Embankment | #VALUE! | HS2-00002MR46 | #N/A | #N/A | #N/A
235.01-1 | HS2-000025B3A | IDR 235.01-1 | HS2-000025B3A | 2025-02-14 | 10 - Complete | 2025-02-18 |  | HS2-00002MR47 - Twyford Embankment Devegetation | SC IDR C2-A Calvert Cutting & IMD to Cowley Embankment | #VALUE! | HS2-00002MR47 | #N/A | #N/A | #N/A
210.2-2 | HS2-00002CW1D | IDR 210.2-2 | HS2-00002CW1D | 2024-06-24 | 99 - Cancelled | 0 |  | HS2-00002MR48 - Twyford Viaduct Devegetation | SC IDR C2-A Calvert Cutting & IMD to Cowley Embankment | #VALUE! | HS2-00002MR48 | #N/A | #N/A | #N/A
UFDR 227.A | HS2-00002CQQM | UFDR 227.A | HS2-00002CQQM | 2024-07-05 | 10 - Complete | 2024-07-10 |  | HS2-00002MR49 - Cowley Embankment Devegetation | SC IDR C2-A Calvert Cutting & IMD to Cowley Embankment | #VALUE! | HS2-00002MR49 | #N/A | #N/A | #N/A
UFDR 227.A | HS2-000020CHN | UFDR 227.A | HS2-000020CHN | 2024-07-05 | 10 - Complete | 2024-07-10 |  | HS2-00002MR62 - Mixbury Cutting Devegetation | SC IDR C23-C Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002MR62 | #N/A | #N/A | #N/A
204.0-2 | HS2-000020NAP | IDR 204.0-2 | HS2-000020NAP | 2025-08-26 | 30 - Sent back to team | 0 |  | HS2-00002MR63 - Westbury Embankment Devegetation | SC IDR C23-C Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002MR63 | #N/A | #N/A | #N/A
204.0-2 | HS2-00002CT4B | IDR 204.0-2 | HS2-00002CT4B | 2025-08-26 | 30 - Sent back to team | 0 |  | HS2-00002MR64 - Westbury Viaduct Devegetation | SC IDR C23-C Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002MR64 | #N/A | #N/A | #N/A
215.03 | HS2-00002TUPK | IDR 215.03 | HS2-00002TUPK | 2024-06-25 | 10 - Complete | 2024-08-16 |  | HS2-00002MR65 - Grovehill Embankment Devegetation | SC IDR C23-C Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002MR65 | #N/A | #N/A | #N/A
212.5 | HS2-00002VK4C | IDR 212.5 | HS2-00002VK4C | 2024-06-25 | 10 - Complete | 2024-07-02 |  | HS2-00002MR66 - Turweston Cutting Devegetation | SC IDR C23-C Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002MR66 | #N/A | #N/A | #N/A
UFDR 238.G | HS2-000020CKJ | UFDR 238.G | HS2-000020CKJ | 2024-06-26 | 10 - Complete | 2024-07-04 |  | HS2-00002MR67 - Turweston Embankment Devegetation | SC IDR C23-C Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002MR67 | #N/A | #N/A | #N/A
UFDR 238.G | HS2-000020CKL | UFDR 238.G | HS2-000020CKL | 2024-06-26 | 10 - Complete | 2024-07-03 |  | HS2-00002MR68 - Turweston Viaduct Devegetation | SC IDR C23-C Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002MR68 | #N/A | #N/A | #N/A
UFDR 238.G | HS2-000020CKM | UFDR 238.G | HS2-000020CKM | 2024-06-26 | 10 - Complete | 2024-07-03 |  | HS2-00002MR69 - Helmdon Embankment Devegetation | SC IDR C23-C Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002MR69 | #N/A | #N/A | #N/A
213.01-01 | HS2-00002BJTJ | IDR 213.01-01 | HS2-00002BJTJ | 2025-06-27 | 10 - Complete | 2025-07-01 |  | HS2-00002MR6A - Brackley South Cutting Devegetation | SC IDR C23-B Turweston Embankment to Greatworth North Embankment | #VALUE! | HS2-00002MR6A | #N/A | #N/A | #N/A
213.01-01 | HS2-00002BJTK | IDR 213.01-01 | HS2-00002BJTK | 2025-06-27 | 10 - Complete | 2025-07-01 |  | HS2-00002MR6B - Brackley Embankment Devegetation | SC IDR C23-B Turweston Embankment to Greatworth North Embankment | #VALUE! | HS2-00002MR6B | #N/A | #N/A | #N/A
213.01-01 | HS2-00002CT6X | IDR 213.01-01 | HS2-00002CT6X | 2025-06-27 | 10 - Complete | 2025-07-02 |  | HS2-00002MR6C - Brackley North Cutting Devegetation | SC IDR C23-B Turweston Embankment to Greatworth North Embankment | #VALUE! | HS2-00002MR6C | #N/A | #N/A | #N/A
213.01-01 | HS2-00002CT6W | IDR 213.01-01 | HS2-00002CT6W | 2025-06-27 | 10 - Complete | 2025-07-01 |  | HS2-00002MR6D - Greatworth South Embankment Devegetation | SC IDR C23-B Turweston Embankment to Greatworth North Embankment | #VALUE! | HS2-00002MR6D | #N/A | #N/A | #N/A
213.01-01 | HS2-000020NFY | IDR 213.01-01 | HS2-000020NFY | 2025-06-27 | 10 - Complete | 0 |  | HS2-00002MR6E - Greatworth South Cutting Devegetation | SC IDR C23-B Turweston Embankment to Greatworth North Embankment | #VALUE! | HS2-00002MR6E | #N/A | #N/A | #N/A
204.2-2 | HS2-00003JQJQ | IDR 204.2-2 | HS2-00003JQJQ | 2024-08-12 | 10 - Complete | 2024-08-16 |  | HS2-00002MR6F - Greatworth North Embankment Devegetation | SC IDR C23-B Turweston Embankment to Greatworth North Embankment | #VALUE! | HS2-00002MR6F | #N/A | #N/A | #N/A
204.2-2 | HS2-00003JQJR | IDR 204.2-2 | HS2-00003JQJR | 2024-08-12 | 10 - Complete | 2024-08-16 |  | HS2-00002MR6G - Greatworth North Cutting Devegetation | SC IDR C23-B Turweston Embankment to Greatworth North Embankment | #VALUE! | HS2-00002MR6G | #N/A | #N/A | #N/A
204.2-2 | HS2-00003JQJS | IDR 204.2-2 | HS2-00003JQJS | 2024-08-12 | 10 - Complete | 2024-08-16 |  | HS2-00002MR5S - Twyford Cutting Devegetation | SC IDR C23-A Twyford Cutting to Barton to Mixbury Cutting | #VALUE! | HS2-00002MR5S | #N/A | #N/A | #N/A
204.2-2 | HS2-00002CT52 | IDR 204.2-2 | HS2-00002CT52 | 2024-06-27 | 10 - Complete | 2024-08-13 |  | HS2-00002MR5T - Godington East Embankment Devegetation | SC IDR C23-A Twyford Cutting to Barton to Mixbury Cutting | #VALUE! | HS2-00002MR5T | #N/A | #N/A | #N/A
204.2-2 | HS2-00002BJS4 | IDR 204.2-2 | HS2-00002BJS4 | 2024-06-27 | 10 - Complete | 2024-08-05 |  | HS2-00002MR5U - Godington East Viaduct Devegetation | SC IDR C23-A Twyford Cutting to Barton to Mixbury Cutting | #VALUE! | HS2-00002MR5U | #N/A | #N/A | #N/A
204.2-2 | HS2-00002CT4Q | IDR 204.2-2 | HS2-00002CT4Q | 2024-06-27 | 10 - Complete | 2024-08-06 |  | HS2-00002MR5V - Godington West Embankment Devegetation | SC IDR C23-A Twyford Cutting to Barton to Mixbury Cutting | #VALUE! | HS2-00002MR5V | #N/A | #N/A | #N/A
222.6 | HS2-00002BJUW | IDR 222.6 | HS2-00002BJUW | 2024-06-27 | 10 - Complete | 2024-07-11 |  | HS2-00002MR5W - Godington West Viaduct Devegetation | SC IDR C23-A Twyford Cutting to Barton to Mixbury Cutting | #VALUE! | HS2-00002MR5W | #N/A | #N/A | #N/A
222.6 | HS2-00002VXUD | IDR 222.6 | HS2-00002VXUD | 2024-06-27 | 10 - Complete | 2024-07-08 |  | HS2-00002MR5X - Chetwode Embankment Devegetation | SC IDR C23-A Twyford Cutting to Barton to Mixbury Cutting | #VALUE! | HS2-00002MR5X | #N/A | #N/A | #N/A
221.5 | HS2-00002Y4JJ | IDR 221.5 | HS2-00002Y4JJ | 2024-11-13 | 10 - Complete | 2024-11-14 |  | HS2-00002MR5Y - Chetwode Cutting Devegetation | SC IDR C23-A Twyford Cutting to Barton to Mixbury Cutting | #VALUE! | HS2-00002MR5Y | #N/A | #N/A | #N/A
212.5 | HS2-000030TD8 | IDR 212.5 | HS2-000030TD8 | 2024-08-29 | 10 - Complete | 0 |  | HS2-00002MR5Z - Barton Hartshorn Embankment Devegetation | SC IDR C23-A Twyford Cutting to Barton to Mixbury Cutting | #VALUE! | HS2-00002MR5Z | #N/A | #N/A | #N/A
212.5 | HS2-000030TD7 | IDR 212.5 | HS2-000030TD7 | 2024-08-29 | 10 - Complete | 2024-09-13 |  | HS2-00002MR60 - Barton to Mixbury Cutting Devegetation | SC IDR C23-A Twyford Cutting to Barton to Mixbury Cutting | #VALUE! | HS2-00002MR60 | #N/A | #N/A | #N/A
235.01-1 | HS2-000001456 | IDR 235.01-1 | HS2-000001456 | 2025-03-07 | 10 - Complete | 2025-03-19 |  | HS2-00002MR61 - Mixbury Embankment Devegetation | SC IDR C23-A Twyford Cutting to Barton to Mixbury Cutting | #VALUE! | HS2-00002MR61 | #N/A | #N/A | #N/A
214.1 | HS2-00003E24K | IDR 214.1 | HS2-00003E24K | 2025-06-06 | 10 - Complete | 2025-06-17 |  | HS2-00002PXKL - Lower Radbourne South Viaduct General Demolition Assets | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXKL | #N/A | #N/A | #N/A
214.1 | HS2-00003CPYK | IDR 214.1 | HS2-00003CPYK | 2025-06-06 | 10 - Complete | 2025-06-17 |  | HS2-00002PXKM - Upper Radbourne Embankment General Demolition Assets | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXKM | #N/A | #N/A | #N/A
230.05-2 | HS2-00002CTG8 | IDR 230.05-2 | HS2-00002CTG8 | 2024-10-28 | 10 - Complete | 2024-10-30 |  | HS2-00002PXKN - Lower Radbourne North Viaduct General Demolition Assets | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXKN | #N/A | #N/A | #N/A
202.0-3 | HS2-00002CT2S | IDR 202.0-3 | HS2-00002CT2S | 2024-07-02 | 10 - Complete | 2024-07-10 |  | HS2-00002PXKP - Lower Radbourne Embankment General Demolition Assets | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXKP | #N/A | #N/A | #N/A
202.0-3 | HS2-00002CT2X | IDR 202.0-3 | HS2-00002CT2X | 2024-07-02 | 10 - Complete | 2024-07-10 |  | HS2-00002PXKQ - Ladbroke Grove Cutting General Demolition Assets | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXKQ | #N/A | #N/A | #N/A
202.0-3 | HS2-00002CT2Q | IDR 202.0-3 | HS2-00002CT2Q | 2024-07-02 | 10 - Complete | 2024-07-10 |  | HS2-00002QSMJ - CFA_16_51_Holt Farm_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMJ | #N/A | #N/A | #N/A
202.0-3 | HS2-00002CT2V | IDR 202.0-3 | HS2-00002CT2V | 2024-07-02 | 10 - Complete | 2024-07-10 |  | HS2-00002QSMK - CFA_16_05_Paxhall Farm_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMK | #N/A | #N/A | #N/A
202.0-3 | HS2-00002CT2E | IDR 202.0-3 | HS2-00002CT2E | 2024-07-02 | 10 - Complete | 2024-07-16 |  | HS2-00002QSML - CFA_16_07_Ladbroke Grove Farm_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSML | #N/A | #N/A | #N/A
202.0-3 | HS2-00002BVEA | IDR 202.0-3 | HS2-00002BVEA | 2024-07-02 | 10 - Complete | 2024-07-16 |  | HS2-00002PXKS - Ladbroke Grove Embankment General Demolition Assets | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXKS | #N/A | #N/A | #N/A
224.6 | HS2-00003D9D1 | IDR 224.6 | HS2-00003D9D1 | 2024-07-02 | 10 - Complete | 2024-07-17 |  | HS2-00002PXM3 - Ladbroke Grove Cutting General Demolition Assets_Priority 1 | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXM3 | #N/A | #N/A | #N/A
224.6 | HS2-000031EF3 | IDR 224.6 | HS2-000031EF3 | 2024-07-02 | 10 - Complete | 2024-07-12 |  | HS2-00002QSMM - CFA_16_06_Hodnell Manor Farm Partnership_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMM | #N/A | #N/A | #N/A
224.6 | HS2-000031EF4 | IDR 224.6 | HS2-000031EF4 | 2024-07-02 | 10 - Complete | 2024-07-26 |  | HS2-00002PXKU - Ladbroke Cutting General Demolition Assets | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXKU | #N/A | #N/A | #N/A
238.02_2 | HS2-00002YNH8 | IDR 238.02_2 | HS2-00002YNH8 | 2024-11-26 | 10 - Complete | 0 |  | HS2-00002PXM4 - Ladbroke Cutting General Demolition Assets_Priority 1 | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXM4 | #N/A | #N/A | #N/A
230.01-3 | HS2-00002WUPJ | IDR 230.01-3 | HS2-00002WUPJ | 2024-07-03 | 10 - Complete | 2024-07-17 |  | HS2-00002QSMN - CFA_16_08_The Bungalow Ladbroke Hill Lane_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMN | #N/A | #N/A | #N/A
230.01-3 | HS2-00002WUPK | IDR 230.01-3 | HS2-00002WUPK | 2024-07-03 | 10 - Complete | 2024-07-17 |  | HS2-00002QSMP - CFA_16_09_Ladbroke Hill Farm_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMP | #N/A | #N/A | #N/A
230.01-3 | HS2-00002WUPL | IDR 230.01-3 | HS2-00002WUPL | 2024-07-03 | 10 - Complete | 2024-07-17 |  | HS2-00002QSMQ - CFA_16_11_Starbold Farm_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMQ | #N/A | #N/A | #N/A
230.01-3 | HS2-00002WUPM | IDR 230.01-3 | HS2-00002WUPM | 2024-07-03 | 10 - Complete | 2024-07-17 |  | HS2-00002QSMR - CFA_16_10_Grounds Farm_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMR | #N/A | #N/A | #N/A
230.01-3 | HS2-00002WUPN | IDR 230.01-3 | HS2-00002WUPN | 2024-07-03 | 10 - Complete | 2024-07-11 |  | HS2-00002QSMS - CFA_16_56_Archers Rest_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMS | #N/A | #N/A | #N/A
230.01-3 | HS2-00002WUPP | IDR 230.01-3 | HS2-00002WUPP | 2024-07-03 | 10 - Complete | 2024-07-11 |  | HS2-00002PXGV - Ladbroke Cutting_Banbury Road_Harp Farm Complex Demolition | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXGV | #N/A | #N/A | #N/A
230.01-3 | HS2-00002WUPQ | IDR 230.01-3 | HS2-00002WUPQ | 2024-07-03 | 10 - Complete | 2024-07-12 |  | HS2-00002QSMT - CFA_16_52_Jack and Edith trust_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMT | #N/A | #N/A | #N/A
230.01-3 | HS2-00002WUPR | IDR 230.01-3 | HS2-00002WUPR | 2024-07-03 | 10 - Complete | 2024-07-12 |  | HS2-00002QSMU - CFA_16_57_Harp Farm Barn_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMU | #N/A | #N/A | #N/A
230.01-3 | HS2-00002WUPS | IDR 230.01-3 | HS2-00002WUPS | 2024-07-03 | 10 - Complete | 2024-07-12 |  | HS2-00002QSMV - CFA_16_61_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMV | #N/A | #N/A | #N/A
230.01-3 | HS2-00002WUPT | IDR 230.01-3 | HS2-00002WUPT | 2024-07-03 | 10 - Complete | 2024-07-12 |  | HS2-00002PXGW - Ladbroke Cutting_Banbury Road_Southam Carwash Demolition | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXGW | #N/A | #N/A | #N/A
224.6 | HS2-0000386UG | IDR 224.6 | HS2-0000386UG | 2024-07-03 | 10 - Complete | 2024-07-11 |  | HS2-00002QSMW - CFA_16_68_Bloor Homes_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMW | #N/A | #N/A | #N/A
214.07 | HS2-00002YXB5 | IDR 214.07 | HS2-00002YXB5 | 2024-07-03 | 10 - Complete | 2024-07-05 |  | HS2-00002QSMX - CFA_16_55_Southam United Charities_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMX | #N/A | #N/A | #N/A
UFDR 227.A | HS2-000020CHN | UFDR 227.A | HS2-000020CHN | 2024-07-05 | 10 - Complete | 2024-07-10 |  | HS2-00002PXKW - Southam Embankment General Demolition Assets | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXKW | #N/A | #N/A | #N/A
UFDR 227.A | HS2-00002CQQM | UFDR 227.A | HS2-00002CQQM | 2024-07-05 | 10 - Complete | 2024-07-10 |  | HS2-00002QSMY - CFA_16_65_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMY | #N/A | #N/A | #N/A
235.01-1 | HS2-000020NZU | IDR 235.01-1 | HS2-000020NZU | 2025-02-14 | 10 - Complete | 2025-02-18 |  | HS2-00002QSMZ - CFA_16_13_Land to east of Kineton Road_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSMZ | #N/A | #N/A | #N/A
233.01-3 | HS2-000020NXM | IDR 233.01-3 | HS2-000020NXM | 2024-11-12 | 10 - Complete | 2024-12-02 |  | HS2-00002PXKX - Southam Cutting General Demolition Assets | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXKX | #N/A | #N/A | #N/A
233.01-3 | HS2-000035Q9C | IDR 233.01-3 | HS2-000035Q9C | 2024-11-21 | 10 - Complete | 2024-12-04 |  | HS2-00002PXM5 - Southam Cutting General Demolition Assets_Priority 1 | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXM5 | #N/A | #N/A | #N/A
237.02 | HS2-00002CTJZ | IDR 237.02 | HS2-00002CTJZ | 2024-07-05 | 10 - Complete | 2024-07-31 |  | HS2-00002QSN0 - CFA_16_67_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSN0 | #N/A | #N/A | #N/A
228.2 | HS2-00002CTEL | IDR 228.2 | HS2-00002CTEL | 2024-07-05 | 10 - Complete | 2024-07-16 |  | HS2-00002QSN1 - CFA_16_59_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSN1 | #N/A | #N/A | #N/A
228.2 | HS2-000020NUE | IDR 228.2 | HS2-000020NUE | 2024-07-05 | 10 - Complete | 2024-07-16 |  | HS2-00002QSN2 - CFA_16_60_Rugby Club_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSN2 | #N/A | #N/A | #N/A
218.02 | HS2-000031248 | IDR 218.02 | HS2-000031248 | 2024-07-05 | 10 - Complete | 2024-07-11 |  | HS2-00002QSN3 - CFA_16_54_Land west of Kineton Road_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSN3 | #N/A | #N/A | #N/A
234.03 | HS2-00003JN82 | IDR 234.03 | HS2-00003JN82 | 2024-07-08 | 10 - Complete | 2024-07-15 |  | HS2-00002QSN4 - CFA_16_64_Green Farm_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSN4 | #N/A | #N/A | #N/A
234.03 | HS2-00003JN83 | IDR 234.03 | HS2-00003JN83 | 2024-07-08 | 10 - Complete | 2024-07-15 |  | HS2-00002QSN5 - CFA_16_12_Field House_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSN5 | #N/A | #N/A | #N/A
222.6 | HS2-00002YGQF | IDR 222.6 | HS2-00002YGQF | 2025-02-03 | 10 - Complete | 2025-02-17 |  | HS2-00002QSN6 - CFA_16_14_Wood Farm_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSN6 | #N/A | #N/A | #N/A
216.01 | HS2-00002CT8T | IDR 216.01 | HS2-00002CT8T | 2025-05-30 | 10 - Complete | 2025-06-04 |  | HS2-00002QSN7 - CFA_16_66_Old Coach House_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSN7 | #N/A | #N/A | #N/A
212.5 | HS2-00002YD79 | IDR 212.5 | HS2-00002YD79 | 2024-07-08 | 10 - Complete | 2024-07-09 |  | HS2-00002QSN8 - CFA_16_15_Agricultural land (south of Leamington Road A425)_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSN8 | #N/A | #N/A | #N/A
238.02_2 | HS2-00003H6PG | IDR 238.02_2 | HS2-00003H6PG | 2024-11-26 | 10 - Complete | 0 |  | HS2-00002QSN9 - CFA_16_16_Lower Farm House_Topsoil Stripping Asset | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002QSN9 | #N/A | #N/A | #N/A
226.5 | HS2-000031EF6 | IDR 226.5 | HS2-000031EF6 | 2024-08-13 | 10 - Complete | 2024-08-22 |  | HS2-00002PXKY - Mill Pond Embankment General Demolition Assets | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXKY | #N/A | #N/A | #N/A
221.5 | HS2-00002YGQ8 | IDR 221.5 | HS2-00002YGQ8 | 2024-07-09 | 10 - Complete | 2024-08-19 |  | HS2-00002PXKZ - River Itchen Viaduct General Demolition Assets | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXKZ | #N/A | #N/A | #N/A
221.5 | HS2-000037YLH | IDR 221.5 | HS2-000037YLH | 2024-07-09 | 10 - Complete | 2024-08-19 |  | HS2-00002PXL1 - Leamington Road Embankment General Demolition Assets | SC DATS 237 to 239 Lower Radbourne South Viaduct to Leamington Road Embankment | #VALUE! | HS2-00002PXL1 | #N/A | #N/A | #N/A
221.5 | HS2-00002YGQC | IDR 221.5 | HS2-00002YGQC | 2024-07-09 | 10 - Complete | 2024-08-19 |  | HS2-00002PXKB - Aston le Walls Embankment General Demolition Assets | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXKB | #N/A | #N/A | #N/A
221.5 | HS2-000037YLK | IDR 221.5 | HS2-000037YLK | 2024-07-09 | 10 - Complete | 2024-08-23 |  | HS2-00002PXMM - Aston le Walls Embankment General Demolition Assets _Priority 2 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXMM | #N/A | #N/A | #N/A
221.5 | HS2-00002YGQA | IDR 221.5 | HS2-00002YGQA | 2024-07-09 | 10 - Complete | 2024-08-20 |  | HS2-00002QSDX - Aston le Walls Embankment General Demolition Assets_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSDX | #N/A | #N/A | #N/A
221.5 | HS2-000037YLM | IDR 221.5 | HS2-000037YLM | 2024-07-09 | 10 - Complete | 2024-08-20 |  | HS2-00002QSLZ - CFA_15_54_Washbrook Farm_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSLZ | #N/A | #N/A | #N/A
202.4-2 | HS2-00002CT2Y | IDR 202.4-2 | HS2-00002CT2Y | 2024-07-09 | 10 - Complete | 2024-07-26 |  | HS2-00002QSP8 - CFA_15_54_Washbrook Farm_Topsoil Strip Asset_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSP8 | #N/A | #N/A | #N/A
202.4-2 | HS2-00002CT3Q | IDR 202.4-2 | HS2-00002CT3Q | 2024-07-09 | 10 - Complete | 2024-07-26 |  | HS2-00002PXKC - Highfurlong Brook Viaduct General Demolition Assets | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXKC | #N/A | #N/A | #N/A
237.05 | HS2-00003KFPU | IDR 237.05 | HS2-00003KFPU | 2024-07-09 | 10 - Complete | 2024-07-11 |  | HS2-00002QSDY - Highfurlong Brook Viaduct General Demolition Assets_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSDY | #N/A | #N/A | #N/A
237.05 | HS2-00003KFPV | IDR 237.05 | HS2-00003KFPV | 2024-07-09 | 10 - Complete | 2024-07-11 |  | HS2-00002PXKD - Highfurlong Brook Embankment General Demolition Assets | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXKD | #N/A | #N/A | #N/A
237.05 | HS2-00003KFPW | IDR 237.05 | HS2-00003KFPW | 2024-07-09 | 10 - Complete | 2024-07-11 |  | HS2-00002QSDZ - Highfurlong Brook Embankment General Demolition Assets_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSDZ | #N/A | #N/A | #N/A
237.05 | HS2-00003KFPX | IDR 237.05 | HS2-00003KFPX | 2024-07-09 | 10 - Complete | 2024-07-11 |  | HS2-00002QSM0 - CFA_15_21_Cleveland Farm_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSM0 | #N/A | #N/A | #N/A
226.5 | HS2-000031EF5 | IDR 226.5 | HS2-000031EF5 | 2024-08-13 | 10 - Complete | 2024-08-22 |  | HS2-00002QSP9 - CFA_15_21_Cleveland Farm_Topsoil Strip Asset_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSP9 | #N/A | #N/A | #N/A
221.5 | HS2-000031EF1 | IDR 221.5 | HS2-000031EF1 | 2024-07-09 | 10 - Complete | 2024-08-23 |  | HS2-00002QSM1 - CFA_15_22_Old House Farm_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSM1 | #N/A | #N/A | #N/A
212.5 | HS2-00002YD7F | IDR 212.5 | HS2-00002YD7F | 2024-07-09 | 10 - Complete | 2024-07-17 |  | HS2-00002QSPA - CFA_15_22_Old House Farm_Topsoil Strip Asset_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSPA | #N/A | #N/A | #N/A
UFDR 239.E | HS2-000020CKR | UFDR 239.E | HS2-000020CKR | 2024-07-11 | 10 - Complete | 2024-07-16 |  | HS2-00002PXKE - Lower Boddington Cutting General Demolition Assets | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXKE | #N/A | #N/A | #N/A
UFDR 239.E | HS2-00002CTKR | UFDR 239.E | HS2-00002CTKR | 2024-07-11 | 10 - Complete | 2024-07-16 |  | HS2-00002QSE0 - Lower Boddington Cutting General Demolition Assets_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSE0 | #N/A | #N/A | #N/A
202.4-2 | HS2-00002CT32 | IDR 202.4-2 | HS2-00002CT32 | 2024-07-11 | 10 - Complete | 2024-08-01 |  | HS2-00002QSM2 - CFA_16_03_Stoneton Moat Farm_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSM2 | #N/A | #N/A | #N/A
202.4-2 | HS2-00002BVEK | IDR 202.4-2 | HS2-00002BVEK | 2024-07-11 | 10 - Complete | 2024-08-01 |  | HS2-00002QSM3 - CFA_15_23a_Cedars Farm _Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSM3 | #N/A | #N/A | #N/A
214.1 | HS2-00003CPYN | IDR 214.1 | HS2-00003CPYN | 2024-07-11 | 10 - Complete | 2024-07-25 |  | HS2-00002PXGN - Lower Boddington Cutting-Banbury Road_Livestock Shelter Demolition | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXGN | #N/A | #N/A | #N/A
214.1 | HS2-000031B3U | IDR 214.1 | HS2-000031B3U | 2024-07-11 | 10 - Complete | 2024-07-23 |  | HS2-00002PXKF - Lower Boddington Embankment General Demolition Assets | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXKF | #N/A | #N/A | #N/A
202.1-1 | HS2-000001022 | IDR 202.1-1 | HS2-000001022 | 2024-07-12 | 99 - Cancelled | 0 |  | HS2-00002PXM0 - Lower Boddington Embankment General Demolition Assets_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXM0 | #N/A | #N/A | #N/A
235.01 | HS2-00002N7UR | IDR 235.01 | HS2-00002N7UR | 2024-07-12 | 10 - Complete | 2024-07-15 |  | HS2-00002QSM4 - CFA_15_61_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSM4 | #N/A | #N/A | #N/A
224.6 | HS2-00002CTDR | IDR 224.6 | HS2-00002CTDR | 2024-07-12 | 10 - Complete | 2024-07-22 |  | HS2-00002PXGP - Lower Boddington Embankment_Unknown Road_Barns Demolition | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXGP | #N/A | #N/A | #N/A
224.6 | HS2-00002CTDT | IDR 224.6 | HS2-00002CTDT | 2024-07-12 | 10 - Complete | 2024-07-22 |  | HS2-00002QSM5 - CFA_15_63_Fir Tree Nurseries_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSM5 | #N/A | #N/A | #N/A
224.6 | HS2-00002CTDY | IDR 224.6 | HS2-00002CTDY | 2024-07-12 | 10 - Complete | 2024-07-22 |  | HS2-00002PXGQ - Lower Boddington Embankment_Unknown Road_Residence Demolition | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXGQ | #N/A | #N/A | #N/A
224.6 | HS2-00002CTE1 | IDR 224.6 | HS2-00002CTE1 | 2024-07-12 | 10 - Complete | 2024-07-22 |  | HS2-00002QSM6 - CFA_15_62_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSM6 | #N/A | #N/A | #N/A
224.6 | HS2-00002CTCM | IDR 224.6 | HS2-00002CTCM | 2025-05-16 | 10 - Complete | 2025-05-21 |  | HS2-00002QSM7 - CFA_15_25_Hill Farm Three Shires Farm_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSM7 | #N/A | #N/A | #N/A
224.6 | HS2-00002CTCP | IDR 224.6 | HS2-00002CTCP | 2025-05-16 | 10 - Complete | 2025-05-20 |  | HS2-00002QSPB - CFA_15_25_Hill Farm Three Shires Farm_Topsoil Strip Asset_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSPB | #N/A | #N/A | #N/A
224.6 | HS2-00002CTCG | IDR 224.6 | HS2-00002CTCG | 2025-05-16 | 10 - Complete | 2025-05-20 |  | HS2-00002QSM8 - CFA_15_28_Land South of Boddington Road _Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSM8 | #N/A | #N/A | #N/A
224.6 | HS2-00002CTCJ | IDR 224.6 | HS2-00002CTCJ | 2025-05-16 | 10 - Complete | 2025-05-21 |  | HS2-00002QSM9 - CFA_15_64_Land south side of Boddington Road_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSM9 | #N/A | #N/A | #N/A
214.1 | HS2-00003CPYQ | IDR 214.1 | HS2-00003CPYQ | 2025-09-26 | 30 - Sent back to team | 0 |  | HS2-00002QSMA - CFA_15_65_Spella Oexhard_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSMA | #N/A | #N/A | #N/A
214.1 | HS2-00002EK75 | IDR 214.1 | HS2-00002EK75 | 2025-10-01 | #N/A | #N/A |  | HS2-00002QSMB - CFA_15_30_Spella House_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSMB | #N/A | #N/A | #N/A
214.1 | HS2-00003CPYP | IDR 214.1 | HS2-00003CPYP | 2025-09-26 | 10 - Complete | 0 |  | HS2-00002QSPD - CFA_15_30_Spella House_Topsoil Strip Asset_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSPD | #N/A | #N/A | #N/A
214.1 | HS2-00002XQ2Q | IDR 214.1 | HS2-00002XQ2Q | 2025-05-01 | 10 - Complete | 0 |  | HS2-00002PXGR - Boddington Cutting_Unknown Road_Horse Stables Demolition | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXGR | #N/A | #N/A | #N/A
214.1 | HS2-00002XQ2R | IDR 214.1 | HS2-00002XQ2R | 2025-05-02 | 10 - Complete | 2025-05-02 |  | HS2-00002PXKG - Boddington Cutting General Demolition Assets | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXKG | #N/A | #N/A | #N/A
212.5 | HS2-00003BPJH | IDR 212.5 | HS2-00003BPJH | 2024-09-06 | 10 - Complete | 2024-09-17 |  | HS2-00002PXM1 - Boddington Cutting General Demolition Assets_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXM1 | #N/A | #N/A | #N/A
212.5 | HS2-00002ZJQH | IDR 212.5 | HS2-00002ZJQH | 2024-07-12 | 10 - Complete | 2024-07-25 |  | HS2-00002QSMC - CFA_15_29_Oddfellows Boddington_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSMC | #N/A | #N/A | #N/A
226.1 | HS2-00002CTDV | IDR 226.1 | HS2-00002CTDV | 2024-07-15 | 10 - Complete | 2024-07-24 |  | HS2-00002QSPC - CFA_15_29_Oddfellows Boddington_Topsoil Strip Asset_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSPC | #N/A | #N/A | #N/A
UFDR 208.A | HS2-000020CEX | UFDR 208.A | HS2-000020CEX | 2024-07-16 | 10 - Complete | 2024-07-26 |  | HS2-00002QSMD - CFA_15_31_Glyn Davis Wood_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSMD | #N/A | #N/A | #N/A
UFDR 208.A | HS2-0000245Z0 | UFDR 208.A | HS2-0000245Z0 | 2024-07-16 | 10 - Complete | 2024-07-26 |  | HS2-00002QSPE - CFA_15_31_Glyn Davis Wood_Topsoil Strip Asset_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSPE | #N/A | #N/A | #N/A
UFDR 208.A | HS2-00002SZLT | UFDR 208.A | HS2-00002SZLT | 2024-07-16 | 10 - Complete | 2024-07-30 |  | HS2-00002QSME - CFA_16_01_Althorp Estate Wormleighton_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSME | #N/A | #N/A | #N/A
UFDR 208.A | HS2-00002SZLS | UFDR 208.A | HS2-00002SZLS | 2024-07-16 | 10 - Complete | 2024-07-30 |  | HS2-00002QSPF - CFA_16_01_Althorp Estate Wormleighton_Topsoil Strip Asset_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSPF | #N/A | #N/A | #N/A
202.4-2 | HS2-00002EK6M | IDR 202.4-2 | HS2-00002EK6M | 2024-07-16 | 10 - Complete | 2024-07-25 |  | HS2-00002PXKH - Oxford Canal South Embankment General Demolition Assets | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXKH | #N/A | #N/A | #N/A
217.03 | HS2-000001314 | IDR 217.03 | HS2-000001314 | 2024-11-20 | 50 - HOLD | 0 |  | HS2-00002PXM2 - Oxford Canal South Embankment General Demolition Assets_Priority 1 | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXM2 | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLB | IDR 224.6 | HS2-00003BPLB | 2024-07-17 | 10 - Complete | 2024-07-22 |  | HS2-00002QSMF - CFA_16_02a_Wormleighton Grange Farm_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSMF | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLD | IDR 224.6 | HS2-00003BPLD | 2024-07-17 | 10 - Complete | 2024-07-25 |  | HS2-00002PXGS - Oxford Canal Viaduct_Field_Barn Demolition | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXGS | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLE | IDR 224.6 | HS2-00003BPLE | 2024-07-17 | 10 - Complete | 2024-07-31 |  | HS2-00002PXGT - Oxford Canal North Embankment_Canal Bridge Demolition | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXGT | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLG | IDR 224.6 | HS2-00003BPLG | 2024-07-17 | 10 - Complete | 2024-07-29 |  | HS2-00002PXKJ - Oxford Canal Viaduct General Demolition Assets | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXKJ | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLN | IDR 224.6 | HS2-00003BPLN | 2024-07-17 | 10 - Complete | 2024-07-23 |  | HS2-00002PXKK - Oxford Canal North EmbankmentGeneral Demolition Assets | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXKK | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLF | IDR 224.6 | HS2-00003BPLF | 2024-07-17 | 10 - Complete | 2024-07-31 |  | HS2-00002QSMG - CFA_16_02_Lower New House Farm_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSMG | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLC | IDR 224.6 | HS2-00003BPLC | 2024-07-17 | 10 - Complete | 2024-07-23 |  | HS2-00002PXGU - Oxford Canal North Embankment_Church Farm_Barn Demolition | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002PXGU | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLJ | IDR 224.6 | HS2-00003BPLJ | 2024-07-17 | 10 - Complete | 2024-07-26 |  | HS2-00002QSMH - CFA_16_04_Lower Radbourne Grounds Farm_Topsoil Stripping Asset | SC DATS 234 to 236 Aston Le Walls Embankment to Oxford Canal North Embankment | #VALUE! | HS2-00002QSMH | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLK | IDR 224.6 | HS2-00003BPLK | 2024-07-17 | 10 - Complete | 2024-07-23 |  | HS2-00002QSLP - CFA_15_66_Topsoil Stripping Asset | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002QSLP | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLL | IDR 224.6 | HS2-00003BPLL | 2024-07-17 | 10 - Complete | 2024-07-30 |  | HS2-00002QSLQ - CFA_15_67_Barn Owl Cottage_Topsoil Stripping Asset | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002QSLQ | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLP | IDR 224.6 | HS2-00003BPLP | 2024-07-17 | 10 - Complete | 2024-07-24 |  | HS2-00002QSLR - CFA_15_17a_Beeches Farm RIFT Airsoft The Bungalow Calves Close_Topsoil Stripping Asset | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002QSLR | #N/A | #N/A | #N/A
224.6 | HS2-0000386UL | IDR 224.6 | HS2-0000386UL | 2024-07-17 | 10 - Complete | 2024-07-31 |  | HS2-00002PXKA - Chipping Warden Green Tunnel General Demolition Assets | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002PXKA | #N/A | #N/A | #N/A
224.6 | HS2-0000386UM | IDR 224.6 | HS2-0000386UM | 2024-07-17 | 10 - Complete | 2024-08-01 |  | HS2-00002PXGL - Chipping Warden Green Tunnel_Culworth Road_The Bungalow Residences Demolition | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002PXGL | #N/A | #N/A | #N/A
224.6 | HS2-0000386UP | IDR 224.6 | HS2-0000386UP | 2024-07-17 | 10 - Complete | 2024-07-26 |  | HS2-00002QSLS - CFA_15_16a_Warden Farms (including Trafford Bridge Farm)_Topsoil Stripping Asset | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002QSLS | #N/A | #N/A | #N/A
224.6 | HS2-0000386UQ | IDR 224.6 | HS2-0000386UQ | 2024-07-17 | 10 - Complete | 2024-07-26 |  | HS2-00002QSLT - CFA_15_17b_Topsoil Stripping Asset | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002QSLT | #N/A | #N/A | #N/A
224.6 | HS2-00003BPL5 | IDR 224.6 | HS2-00003BPL5 | 2024-07-17 | 10 - Complete | 2024-07-26 |  | HS2-00002QSLU - CFA_15_55_Old Coach House_Topsoil Stripping Asset | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002QSLU | #N/A | #N/A | #N/A
224.6 | HS2-00003BPL6 | IDR 224.6 | HS2-00003BPL6 | 2024-07-17 | 10 - Complete | 2024-07-26 |  | HS2-00002QSLV - CFA_15_16c_Land east of Byfield Road_Topsoil Stripping Asset | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002QSLV | #N/A | #N/A | #N/A
224.6 | HS2-00003BPL8 | IDR 224.6 | HS2-00003BPL8 | 2024-07-17 | 10 - Complete | 2024-07-26 |  | HS2-00002PXGM - Chipping Warden Green Tunnel_A361_Residence Demolition | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002PXGM | #N/A | #N/A | #N/A
224.6 | HS2-00003BPL9 | IDR 224.6 | HS2-00003BPL9 | 2024-07-17 | 10 - Complete | 2024-07-31 |  | HS2-00002QSLW - CFA_15_52_RAMAK British Car Auction_Topsoil Stripping Asset | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002QSLW | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLA | IDR 224.6 | HS2-00003BPLA | 2024-07-17 | 10 - Complete | 2024-07-24 |  | HS2-00002QSLX - CFA_15_18_Appletree Farm_Topsoil Stripping Asset | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002QSLX | #N/A | #N/A | #N/A
224.6 | HS2-00003BPL7 | IDR 224.6 | HS2-00003BPL7 | 2024-07-17 | 10 - Complete | 2024-07-30 |  | HS2-00002QSP6 - CFA_15_18_Appletree Farm_Topsoil Strip Asset_Priority 1 | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002QSP6 | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLS | IDR 224.6 | HS2-00003BPLS | 2024-07-17 | 10 - Complete | 2024-07-31 |  | HS2-00002QSLY - CFA_15_19_Manor Farm_Topsoil Stripping Asset | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002QSLY | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLU | IDR 224.6 | HS2-00003BPLU | 2024-07-17 | 10 - Complete | 2024-07-24 |  | HS2-00002QSP7 - CFA_15_19_Manor Farm_Topsoil Strip Asset_Priority 1 | SC DATS 233 Chipping Warden Green Tunnel and Associated Assets | #VALUE! | HS2-00002QSP7 | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLT | IDR 224.6 | HS2-00003BPLT | 2024-07-17 | 10 - Complete | 2024-07-24 |  | HS2-00002PXJY - Thorpe Mandeville Embankment General Demolition Assets | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXJY | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLR | IDR 224.6 | HS2-00003BPLR | 2024-07-17 | 10 - Complete | 2024-07-30 |  | HS2-00002PXJZ - Lower Thorpe Viaduct General Demolition Assets | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXJZ | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLW | IDR 224.6 | HS2-00003BPLW | 2024-07-17 | 10 - Complete | 2024-07-30 |  | HS2-00002QSLF - CFA_15_10_Lower Thorpe Farm_Topsoil Stripping Asset | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002QSLF | #N/A | #N/A | #N/A
224.6 | HS2-00003BPM1 | IDR 224.6 | HS2-00003BPM1 | 2024-07-17 | 10 - Complete | 2024-07-31 |  | HS2-00002QSLG - CFA_15_68_Manor Brook House_Topsoil Stripping Asset | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002QSLG | #N/A | #N/A | #N/A
224.6 | HS2-00003BPLY | IDR 224.6 | HS2-00003BPLY | 2024-07-17 | 10 - Complete | 2024-07-31 |  | HS2-00002PXGH - Lower Thorpe South Embankment_Banbury Lane_Residences Demolition | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXGH | #N/A | #N/A | #N/A
224.6 | HS2-00003BPM2 | IDR 224.6 | HS2-00003BPM2 | 2024-07-17 | 10 - Complete | 2024-07-31 |  | HS2-00002PXK0 - Lower Thorpe South Embankment General Demolition Assets | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXK0 | #N/A | #N/A | #N/A
224.6 | HS2-00003BPM3 | IDR 224.6 | HS2-00003BPM3 | 2024-07-17 | 10 - Complete | 2024-07-24 |  | HS2-00002QSLH - CFA_15_60_Twin Oaks_Topsoil Stripping Asset | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002QSLH | #N/A | #N/A | #N/A
224.6 | HS2-00003BPM4 | IDR 224.6 | HS2-00003BPM4 | 2024-07-17 | 10 - Complete | 2024-07-24 |  | HS2-00002PXGJ - Lower Thorpe South Embankment_Banbury Lane_Livestock Shelter Demolition | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXGJ | #N/A | #N/A | #N/A
224.6 | HS2-00003BPM5 | IDR 224.6 | HS2-00003BPM5 | 2024-07-17 | 10 - Complete | 2024-07-30 |  | HS2-00002PXK1 - Lower Thorpe South Cutting General Demolition Assets | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXK1 | #N/A | #N/A | #N/A
224.6 | HS2-00003BPM0 | IDR 224.6 | HS2-00003BPM0 | 2024-07-17 | 10 - Complete | 2024-07-30 |  | HS2-00002PXK2 - Lower Thorpe North Embankment General Demolition Assets | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXK2 | #N/A | #N/A | #N/A
222.2 | HS2-00002UVZ0 | IDR 222.2 | HS2-00002UVZ0 | 2024-07-17 | 10 - Complete | 2024-08-01 |  | HS2-00002QSLJ - CFA_15_12_Park Farm_Topsoil Stripping Asset | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002QSLJ | #N/A | #N/A | #N/A
222.2 | HS2-00002UVYY | IDR 222.2 | HS2-00002UVYY | 2024-07-17 | 10 - Complete | 2024-08-01 |  | HS2-00002QSLK - CFA_15_13_Culworth Grounds Farm_Topsoil Stripping Asset | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002QSLK | #N/A | #N/A | #N/A
213.01-01 | HS2-00002BJTK | IDR 213.01-01 | HS2-00002BJTK | 2025-06-27 | 10 - Complete | 2025-07-01 |  | HS2-00002PXK3 - Lower Thorpe North Cutting General Demolition Assets | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXK3 | #N/A | #N/A | #N/A
213.01-01 | HS2-000020NF2 | IDR 213.01-01 | HS2-000020NF2 | 2025-06-27 | 10 - Complete | 2025-07-08 |  | HS2-00002QSLL - CFA_15_14_West Hill Farm_Topsoil Stripping Asset | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002QSLL | #N/A | #N/A | #N/A
238.01 | HS2-00003KFPM | IDR 238.01 | HS2-00003KFPM | 2024-07-18 | 10 - Complete | 2024-08-08 |  | HS2-00002PXK4 - Culworth Embankment General Demolition Assets | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXK4 | #N/A | #N/A | #N/A
234.05 | HS2-00002N7UN | IDR 234.05 | HS2-00002N7UN | 2024-07-18 | 10 - Complete | 2024-08-02 |  | HS2-00002PXLY - Culworth Embankment General Demolition Assets_Priority 1 | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXLY | #N/A | #N/A | #N/A
226.1 | HS2-00002EK7G | IDR 226.1 | HS2-00002EK7G | 2025-02-03 | 10 - Complete | 2025-02-17 |  | HS2-00002PXK5 - Culworth Cutting General Demolition Assets | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXK5 | #N/A | #N/A | #N/A
222.2 | HS2-00002UVYZ | IDR 222.2 | HS2-00002UVYZ | 2024-07-18 | 10 - Complete | 2024-08-01 |  | HS2-00002PXK6 - Edgcote South Embankment General Demolition Assets | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXK6 | #N/A | #N/A | #N/A
214.1 | HS2-00003HWH8 | IDR 214.1 | HS2-00003HWH8 | 2024-07-18 | 10 - Complete | 2024-08-02 |  | HS2-00002PXLZ - Edgcote South Embankment General Demolition Assets_Priority 1 | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXLZ | #N/A | #N/A | #N/A
213.08 | HS2-00002CT7E | IDR 213.08 | HS2-00002CT7E | 2024-07-18 | 10 - Complete | 2024-08-08 |  | HS2-00002PXK7 - Edgcote Viaduct General Demolition Assets | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXK7 | #N/A | #N/A | #N/A
238.01 | HS2-00003KFPL | IDR 238.01 | HS2-00003KFPL | 2024-07-22 | 10 - Complete | 2024-08-01 |  | HS2-00002QSLM - CFA_15_15_Edgcote Estate_Topsoil Stripping Asset | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002QSLM | #N/A | #N/A | #N/A
212.5 | HS2-000035Q95 | IDR 212.5 | HS2-000035Q95 | 2024-07-22 | 10 - Complete | 2024-08-02 |  | HS2-00002QSLN - CFA_15_16b_Culworth Mill_Topsoil Stripping Asset | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002QSLN | #N/A | #N/A | #N/A
UFDR 204.B | HS2-000020CEJ | UFDR 204.B | HS2-000020CEJ | 2024-08-22 | 10 - Complete | 2024-09-04 |  | HS2-00002PXK8 - Edgcote North Embankment General Demolition Assets | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXK8 | #N/A | #N/A | #N/A
UFDR 204.B | HS2-000020CEK | UFDR 204.B | HS2-000020CEK | 2024-08-22 | 10 - Complete | 2024-09-04 |  | HS2-00002PXK9 - Edgcote Cutting General Demolition Assets | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXK9 | #N/A | #N/A | #N/A
204.2-2 | HS2-00002WULF | IDR 204.2-2 | HS2-00002WULF | 2024-07-23 | 10 - Complete | 2024-08-01 |  | HS2-00002PXGK - Chipping Warden Green Tunnel_Culworth Road_Blackgrounds Barn Demolition | SC DATS 230 to 232 Thorpe Mandeville Embankment to Edgcote Cutting | #VALUE! | HS2-00002PXGK | #N/A | #N/A | #N/A
204.2-2 | HS2-00002WULG | IDR 204.2-2 | HS2-00002WULG | 2024-09-13 | 10 - Complete | 2024-09-16 |  | HS2-00002QSQN - CFA_15_05_Greatworth hall_Topsoil Strip Asset_Priority 2 | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSQN | #N/A | #N/A | #N/A
204.2-2 | HS2-00002WULH | IDR 204.2-2 | HS2-00002WULH | 2024-07-23 | 10 - Complete | 2024-08-01 |  | HS2-00002PXLX - Greatworth North Embankment General Demolition Assets_Priority 1 | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002PXLX | #N/A | #N/A | #N/A
204.2-2 | HS2-00002WULJ | IDR 204.2-2 | HS2-00002WULJ | 2024-07-23 | 99 - Cancelled | 0 |  | HS2-00002PXJW - Greatworth North Cutting General Demolition Assets | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002PXJW | #N/A | #N/A | #N/A
204.2-2 | HS2-00002WULK | IDR 204.2-2 | HS2-00002WULK | 2024-07-23 | 10 - Complete | 2024-08-02 |  | HS2-00002PXJX - Greatworth Green Tunnel General Demolition Assets | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002PXJX | #N/A | #N/A | #N/A
204.2-2 | HS2-00002WULL | IDR 204.2-2 | HS2-00002WULL | 2024-07-23 | 10 - Complete | 2024-08-02 |  | HS2-00002PXML - Greatworth Green Tunnel General Demolition Assets _Priority 2 | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002PXML | #N/A | #N/A | #N/A
204.2-2 | HS2-00002WULM | IDR 204.2-2 | HS2-00002WULM | 2024-07-23 | 10 - Complete | 2024-08-02 |  | HS2-00002QSL8 - CFA_15_51_Greatworth Park_Topsoil Stripping Asset | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSL8 | #N/A | #N/A | #N/A
204.2-2 | HS2-00002WULN | IDR 204.2-2 | HS2-00002WULN | 2024-07-23 | 10 - Complete | 2024-08-02 |  | HS2-00002QSQR - CFA_15_51_Greatworth Park_Topsoil Strip Asset_Priority 2 | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSQR | #N/A | #N/A | #N/A
202.4-2 | HS2-00002CT39 | IDR 202.4-2 | HS2-00002CT39 | 2024-07-23 | 10 - Complete | 2024-08-08 |  | HS2-00002QSL9 - CFA_15_57_Greatworth Park-RAF Station_Topsoil Stripping Asset | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSL9 | #N/A | #N/A | #N/A
202.4-2 | HS2-00002CT37 | IDR 202.4-2 | HS2-00002CT37 | 2024-07-23 | 10 - Complete | 2024-08-08 |  | HS2-00002QSQS - CFA_15_57_Greatworth Park-RAF Station_Topsoil Strip Asset_Priority 2 | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSQS | #N/A | #N/A | #N/A
202.0-3 | HS2-00002WUJM | IDR 202.0-3 | HS2-00002WUJM | 2024-07-23 | 10 - Complete | 2024-07-25 |  | HS2-00002QSLA - CFA_15_59_MP Motorsports_Topsoil Stripping Asset | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSLA | #N/A | #N/A | #N/A
202.0-3 | HS2-00002WUJN | IDR 202.0-3 | HS2-00002WUJN | 2024-07-23 | 10 - Complete | 2024-07-25 |  | HS2-00002QSQT - CFA_15_59_MP Motorsports_Topsoil Strip Asset_Priority 2 | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSQT | #N/A | #N/A | #N/A
202.0-3 | HS2-00002WUJP | IDR 202.0-3 | HS2-00002WUJP | 2024-07-23 | 10 - Complete | 2024-07-25 |  | HS2-00002PXGF - Greatworth Green Tunnel_B4525_Greatworth Park_Residences Demolition | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002PXGF | #N/A | #N/A | #N/A
202.0-3 | HS2-00002WUJQ | IDR 202.0-3 | HS2-00002WUJQ | 2024-07-23 | 10 - Complete | 2024-07-25 |  | HS2-00002QSLB - CFA_15_06_Whitmans Farm_Topsoil Stripping Asset | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSLB | #N/A | #N/A | #N/A
202.0-3 | HS2-00002WUJR | IDR 202.0-3 | HS2-00002WUJR | 2024-07-23 | 10 - Complete | 2024-07-30 |  | HS2-00002QSQP - CFA_15_06_Whitmans Farm_Topsoil Strip Asset_Priority 2 | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSQP | #N/A | #N/A | #N/A
202.0-3 | HS2-00002WUJS | IDR 202.0-3 | HS2-00002WUJS | 2024-07-23 | 10 - Complete | 2024-07-26 |  | HS2-00002QSLC - CFA_15_07_Marston St Lawrence Estate _Topsoil Stripping Asset | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSLC | #N/A | #N/A | #N/A
202.0-3 | HS2-00002WUJT | IDR 202.0-3 | HS2-00002WUJT | 2024-07-23 | 99 - Cancelled | 0 |  | HS2-00002QSQQ - CFA_15_07_Marston St Lawrence Estate _Topsoil Strip Asset_Priority 2 | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSQQ | #N/A | #N/A | #N/A
202.0-3 | HS2-00002WUJU | IDR 202.0-3 | HS2-00002WUJU | 2024-07-23 | 10 - Complete | 2024-07-26 |  | HS2-00002PXGG - Greatworth Green Tunnel_B4525_Dean Barn_Barn Demolition | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002PXGG | #N/A | #N/A | #N/A
202.0-3 | HS2-00002WUJV | IDR 202.0-3 | HS2-00002WUJV | 2024-07-23 | 10 - Complete | 2024-07-29 |  | HS2-00002QSLD - CFA_15_56_Fern Hill Farms_Topsoil Stripping Asset | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSLD | #N/A | #N/A | #N/A
202.0-3 | HS2-00002WUJW | IDR 202.0-3 | HS2-00002WUJW | 2024-07-23 | 10 - Complete | 2024-07-29 |  | HS2-00002QSQV - CFA_15_56_Fern Hill Farms_Topsoil Strip Asset_Priority 2 | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSQV | #N/A | #N/A | #N/A
202.0-3 | HS2-00002WUJX | IDR 202.0-3 | HS2-00002WUJX | 2024-07-23 | 10 - Complete | 2024-07-29 |  | HS2-00002QSLE - CFA_15_09_Magpie Farm-Manor Farm_Topsoil Stripping Asset | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSLE | #N/A | #N/A | #N/A
226.1 | HS2-000025B21 | IDR 226.1 | HS2-000025B21 | 2024-07-23 | 10 - Complete | 2024-07-25 |  | HS2-00002QSQU - CFA_15_09_Magpie Farm-Manor Farm_Topsoil Strip Asset_Priority 2 | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSQU | #N/A | #N/A | #N/A
226.1 | HS2-000025B20 | IDR 226.1 | HS2-000025B20 | 2024-07-23 | 10 - Complete | 2024-07-25 |  | HS2-00002QSQW - CFA_15_10_Lower Thorpe Farm_Topsoil Strip Asset_Priority 2 | SC DATS 229 Greatworth North Embankment to Thorpe Mandeville Cutting | #VALUE! | HS2-00002QSQW | #N/A | #N/A | #N/A
226.1 | HS2-000025B1Z | IDR 226.1 | HS2-000025B1Z | 2024-07-23 | 10 - Complete | 2024-07-24 |  | HS2-00002PXLV - Turweston Cutting General Demolition Assets _Priority 1 | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXLV | #N/A | #N/A | #N/A
226.1 | HS2-00002Y89A | IDR 226.1 | HS2-00002Y89A | 2024-07-23 | 10 - Complete | 2024-07-26 |  | HS2-00002QSKN - CFA_14_15_Parkside_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSKN | #N/A | #N/A | #N/A
226.1 | HS2-00002C3YF | IDR 226.1 | HS2-00002C3YF | 2024-07-23 | 10 - Complete | 2024-07-25 |  | HS2-00002PXG9 - Turweston Embankment_Turweston Village_Residence Demolition | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXG9 | #N/A | #N/A | #N/A
226.1 | HS2-00002BVJR | IDR 226.1 | HS2-00002BVJR | 2024-07-23 | 10 - Complete | 2024-07-26 |  | HS2-00002PXGA - Turweston Embankment_Ballabeg Stables_Residence Demolition | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXGA | #N/A | #N/A | #N/A
226.1 | HS2-00002N7WZ | IDR 226.1 | HS2-00002N7WZ | 2024-07-23 | 10 - Complete | 2024-07-26 |  | HS2-00002QSKP - CFA_14_64_Turweston Parish Council Playing Fields_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSKP | #N/A | #N/A | #N/A
226.1 | HS2-00002N7X0 | IDR 226.1 | HS2-00002N7X0 | 2024-07-23 | 10 - Complete | 2024-07-26 |  | HS2-00002PXGB - Turweston Embankment_Turweston Village_Barn Demolition | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXGB | #N/A | #N/A | #N/A
212.5 | HS2-00003H07A | IDR 212.5 | HS2-00003H07A | 2024-09-06 | 10 - Complete | 2024-09-17 |  | HS2-00002QSKS - CFA_14_61_Turweston Mill_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSKS | #N/A | #N/A | #N/A
212.5 | HS2-000035Q98 | IDR 212.5 | HS2-000035Q98 | 2024-10-16 | 10 - Complete | 2024-10-18 |  | HS2-00002PXJL - Turweston Embankment General Demolition Assets | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXJL | #N/A | #N/A | #N/A
233.01-3 | HS2-00003FV0K | IDR 233.01-3 | HS2-00003FV0K | 2024-07-25 | 10 - Complete | 2024-08-08 |  | HS2-00002QSKT - CFA_14_54_Foot Versions Cottages_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSKT | #N/A | #N/A | #N/A
233.01-3 | HS2-00003B93W | IDR 233.01-3 | HS2-00003B93W | 2024-07-25 | 10 - Complete | 2024-08-09 |  | HS2-00002PXJM - Turweston Viaduct General Demolition Assets | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXJM | #N/A | #N/A | #N/A
237.05 | HS2-00003D82S | IDR 237.05 | HS2-00003D82S | 2024-07-25 | 10 - Complete | 2024-08-02 |  | HS2-00002PXJN - Helmdon Embankment General Demolition Assets | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXJN | #N/A | #N/A | #N/A
227 | HS2-00002NNHW | IDR 227 | HS2-00002NNHW | 2024-11-15 | 10 - Complete | 2024-12-04 |  | HS2-00002QSKU - CFA_14_16_Manor Farm (Whitfield)_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSKU | #N/A | #N/A | #N/A
207.2 | HS2-00002CT4W | IDR 207.2 | HS2-00002CT4W | 2024-07-25 | 10 - Complete | 2024-08-27 |  | HS2-00002QSP0 - CFA_14_16_Manor Farm (Whitfield)_Topsoil Strip Asset_Priority 1 | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSP0 | #N/A | #N/A | #N/A
207.2 | HS2-00002CW1B | IDR 207.2 | HS2-00002CW1B | 2024-07-25 | 10 - Complete | 2024-08-09 |  | HS2-00002QSKV - CFA_14_04_The Bungalow_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSKV | #N/A | #N/A | #N/A
205.3 | HS2-00002CW1F | IDR 205.3 | HS2-00002CW1F | 2024-07-25 | 10 - Complete | 2024-08-13 |  | HS2-00002PXJP - Brackley South Cutting General Demolition Assets | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXJP | #N/A | #N/A | #N/A
234.02-2 | HS2-00002WUQF | IDR 234.02-2 | HS2-00002WUQF | 2024-07-26 | 10 - Complete | 2024-08-02 |  | HS2-00002PXLW - Brackley South Cutting General Demolition Assets_Priority 1 | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXLW | #N/A | #N/A | #N/A
234.02-2 | HS2-00002WUQG | IDR 234.02-2 | HS2-00002WUQG | 2024-07-26 | 10 - Complete | 2024-08-02 |  | HS2-00002QSKW - CFA_14_52_BP OIL_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSKW | #N/A | #N/A | #N/A
234.02-2 | HS2-00002WUQH | IDR 234.02-2 | HS2-00002WUQH | 2024-07-26 | 10 - Complete | 2024-08-08 |  | HS2-00002QSKX - CFA_14_17_Illets Farm _Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSKX | #N/A | #N/A | #N/A
234.02-2 | HS2-00002WUQJ | IDR 234.02-2 | HS2-00002WUQJ | 2024-07-26 | 10 - Complete | 2024-08-08 |  | HS2-00002QSKY - CFA_14_76_Sundale_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSKY | #N/A | #N/A | #N/A
234.02-2 | HS2-00002WUQK | IDR 234.02-2 | HS2-00002WUQK | 2024-07-26 | 10 - Complete | 2024-08-02 |  | HS2-00002QSP1 - CFA_14_17_Illets Farm _Topsoil Strip Asset_Priority 1 | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSP1 | #N/A | #N/A | #N/A
234.02-2 | HS2-00002WUQL | IDR 234.02-2 | HS2-00002WUQL | 2024-07-26 | 10 - Complete | 2024-08-02 |  | HS2-00002QSP3 - CFA_14_76_Sundale_Topsoil Strip Asset_Priority 1 | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSP3 | #N/A | #N/A | #N/A
234.02-2 | HS2-00002WUQM | IDR 234.02-2 | HS2-00002WUQM | 2024-07-26 | 10 - Complete | 2024-08-08 |  | HS2-00002PXGC - Brackley South Cutting_A43_Iletts Farm Residence Demolition | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXGC | #N/A | #N/A | #N/A
234.02-2 | HS2-00002WUQN | IDR 234.02-2 | HS2-00002WUQN | 2024-07-26 | 10 - Complete | 2024-08-02 |  | HS2-00002PXGD - Brackley South Cutting_A43_Iletts Farm Barns Demolition | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXGD | #N/A | #N/A | #N/A
234.02-2 | HS2-00002WUQP | IDR 234.02-2 | HS2-00002WUQP | 2024-07-26 | 10 - Complete | 2024-08-02 |  | HS2-00002QSKZ - CFA_14_18_Radstone Manor_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSKZ | #N/A | #N/A | #N/A
229.01-1 | HS2-00002HQ9E | IDR 229.01-1 | HS2-00002HQ9E | 2024-07-26 | 10 - Complete | 2024-08-13 |  | HS2-00002QSP2 - CFA_14_18_Radstone Manor_Topsoil Strip Asset_Priority 1 | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSP2 | #N/A | #N/A | #N/A
229.01-1 | HS2-000037YM1 | IDR 229.01-1 | HS2-000037YM1 | 2024-07-26 | 10 - Complete | 2024-08-16 |  | HS2-00002QSL0 - CFA_14_12_Hall Farm_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSL0 | #N/A | #N/A | #N/A
204.2-2 | HS2-00002CT4R | IDR 204.2-2 | HS2-00002CT4R | 2024-07-26 | 10 - Complete | 2024-08-13 |  | HS2-00002PXGE - Brackley South Cutting_Footbridge Demolition | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXGE | #N/A | #N/A | #N/A
204.2-2 | HS2-00002CT4H | IDR 204.2-2 | HS2-00002CT4H | 2024-07-26 | 10 - Complete | 2024-08-27 |  | HS2-00002QSL1 - CFA_14_62_1 Radstone Cottage Paxhall Farm_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSL1 | #N/A | #N/A | #N/A
204.2-2 | HS2-00002CT4D | IDR 204.2-2 | HS2-00002CT4D | 2024-09-23 | 10 - Complete | 2024-09-24 |  | HS2-00002PXJQ - Brackley Embankment General Demolition Assets | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXJQ | #N/A | #N/A | #N/A
212.5 | HS2-00002VK4B | IDR 212.5 | HS2-00002VK4B | 2024-09-06 | 10 - Complete | 2024-09-17 |  | HS2-00002PXJR - Brackley North Cutting General Demolition Assets | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXJR | #N/A | #N/A | #N/A
212.5 | HS2-00002VK4A | IDR 212.5 | HS2-00002VK4A | 2024-07-26 | 10 - Complete | 2024-08-08 |  | HS2-00002PXJS - Greatworth South Embankment General Demolition Assets | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXJS | #N/A | #N/A | #N/A
229.01-1 | HS2-00002HCE5 | IDR 229.01-1 | HS2-00002HCE5 | 2024-07-29 | 10 - Complete | 2024-08-14 |  | HS2-00002PXJT - Greatworth South Cutting General Demolition Assets | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXJT | #N/A | #N/A | #N/A
214.07 | HS2-00002CT81 | IDR 214.07 | HS2-00002CT81 | 2025-02-17 | 10 - Complete | 2025-02-19 |  | HS2-00002QSL2 - CFA_15_01_Halse Grange Farm_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSL2 | #N/A | #N/A | #N/A
233.01-3 | HS2-00002CX3P | IDR 233.01-3 | HS2-00002CX3P | 2024-07-30 | 10 - Complete | 2024-08-13 |  | HS2-00002QSL3 - CFA_15_02_Falcutt Hall_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSL3 | #N/A | #N/A | #N/A
214.02-2 | HS2-000020NH1 | IDR 214.02-2 | HS2-000020NH1 | 2024-07-30 | 10 - Complete | 2024-08-09 |  | HS2-00002QSL4 - CFA_15_05_Greatworth hall_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSL4 | #N/A | #N/A | #N/A
229.03 | HS2-00003124E | IDR 229.03 | HS2-00003124E | 2024-07-30 | 10 - Complete | 2024-08-09 |  | HS2-00002QSL5 - CFA_14_77_Versions Farm_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSL5 | #N/A | #N/A | #N/A
213.08 | HS2-00003CPWX | IDR 213.08 | HS2-00003CPWX | 2024-07-30 | 10 - Complete | 2024-08-09 |  | HS2-00002QSL6 - CFA_14_13_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSL6 | #N/A | #N/A | #N/A
213.08 | HS2-00003CPWY | IDR 213.08 | HS2-00003CPWY | 2024-07-30 | 10 - Complete | 2024-08-09 |  | HS2-00002QSL7 - CFA_15_58_Sewage Water Treatment_Topsoil Stripping Asset | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSL7 | #N/A | #N/A | #N/A
213.08 | HS2-00003CPWZ | IDR 213.08 | HS2-00003CPWZ | 2024-07-30 | 10 - Complete | 2024-08-09 |  | HS2-00002QSP4 - CFA_14_77_Versions Farm_Topsoil Strip Asset_Priority 1 | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002QSP4 | #N/A | #N/A | #N/A
213.08 | HS2-00003CPX1 | IDR 213.08 | HS2-00003CPX1 | 2024-07-30 | 10 - Complete | 2024-08-09 |  | HS2-00002PXJV - Greatworth North Embankment General Demolition Assets | SC DATS 225 to 228 Turweston Embankment to Greatworth South Cutting | #VALUE! | HS2-00002PXJV | #N/A | #N/A | #N/A
213.08 | HS2-00003CPX2 | IDR 213.08 | HS2-00003CPX2 | 2024-07-30 | 10 - Complete | 2024-08-09 |  | HS2-00002QSQD - CFA_14_05_Tibbetts Farm and Mill Farm_Topsoil Strip Asset_Priority 2 | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSQD | #N/A | #N/A | #N/A
213.08 | HS2-00003CPX3 | IDR 213.08 | HS2-00003CPX3 | 2024-07-30 | 10 - Complete | 2024-08-09 |  | HS2-00002PXJE - Mixbury Embankment General Demolition Assets | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002PXJE | #N/A | #N/A | #N/A
213.08 | HS2-00003CPX4 | IDR 213.08 | HS2-00003CPX4 | 2024-07-30 | 10 - Complete | 2024-08-09 |  | HS2-00002PXJF - Mixbury Cutting General Demolition Assets | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002PXJF | #N/A | #N/A | #N/A
213.08 | HS2-00003CPX6 | IDR 213.08 | HS2-00003CPX6 | 2024-07-30 | 10 - Complete | 2024-08-12 |  | HS2-00002PXJG - Westbury Embankment General Demolition Assets | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002PXJG | #N/A | #N/A | #N/A
213.08 | HS2-00003CPX7 | IDR 213.08 | HS2-00003CPX7 | 2024-07-30 | 10 - Complete | 2024-08-09 |  | HS2-00002PXJH - Westbury Viaduct General Demolition Assets | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002PXJH | #N/A | #N/A | #N/A
213.06 | HS2-00002Z6NM | IDR 213.06 | HS2-00002Z6NM | 2024-07-30 | 10 - Complete | 2024-08-20 |  | HS2-00002QSKA - CFA_14_06_Mill Farm_Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKA | #N/A | #N/A | #N/A
212.5 | HS2-000035Q94 | IDR 212.5 | HS2-000035Q94 | 2024-07-30 | 10 - Complete | 2024-08-13 |  | HS2-00002QSKB - CFA_14_65_ Westbury Parish Council_Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKB | #N/A | #N/A | #N/A
212.5 | HS2-00003KFPN | IDR 212.5 | HS2-00003KFPN | 2024-09-06 | 10 - Complete | 2024-09-18 |  | HS2-00002QSKC - CFA_14_63_Greenfinches_Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKC | #N/A | #N/A | #N/A
212.5 | HS2-00003JKXT | IDR 212.5 | HS2-00003JKXT | 2024-07-31 | 10 - Complete | 2024-08-14 |  | HS2-00002PXJJ - Grovehill Embankment General Demolition Assets | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002PXJJ | #N/A | #N/A | #N/A
UFDR 204.B | HS2-000020CEL | UFDR 204.B | HS2-000020CEL | 2024-08-01 | 10 - Complete | 2024-09-03 |  | HS2-00002PXMJ - Grovehill Embankment General Demolition Assets _Priority 2 | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002PXMJ | #N/A | #N/A | #N/A
230.01-3 | HS2-00002EKZV | IDR 230.01-3 | HS2-00002EKZV | 2024-08-01 | 10 - Complete | 2024-08-05 |  | HS2-00002PXJK - Turweston Cutting General Demolition Assets | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002PXJK | #N/A | #N/A | #N/A
214.07 | HS2-000031GXR | IDR 214.07 | HS2-000031GXR | 2024-08-01 | 10 - Complete | 2024-08-22 |  | HS2-00002PXMK - Turweston Cutting General Demolition Assets _Priority 2 | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002PXMK | #N/A | #N/A | #N/A
214.07 | HS2-00002Z3NJ | IDR 214.07 | HS2-00002Z3NJ | 2024-08-01 | 10 - Complete | 2024-08-23 |  | HS2-00002QSKD - CFA_14_55_Gibson and Duffy (Grovehill Barn-NEXT TO 14-8)_Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKD | #N/A | #N/A | #N/A
214.07 | HS2-00002VK3Y | IDR 214.07 | HS2-00002VK3Y | 2024-08-01 | 10 - Complete | 2024-08-21 |  | HS2-00002QSQH - CFA_14_55_Gibson and Duffy (Grovehill Barn-NEXT TO 14-8)_Topsoil Strip Asset_Priority 2 | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSQH | #N/A | #N/A | #N/A
212.5 | HS2-00003H079 | IDR 212.5 | HS2-00003H079 | 2024-09-06 | 10 - Complete | 2024-09-17 |  | HS2-00002QSKE - CFA_14_59_Land on the A422_Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKE | #N/A | #N/A | #N/A
UFDR 238.H | HS2-000020CKP | UFDR 238.H | HS2-000020CKP | 2024-08-06 | 10 - Complete | 2024-08-09 |  | HS2-00002QSKF - CFA_14_08_Grovehill Farm_Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKF | #N/A | #N/A | #N/A
UFDR 204.A | HS2-000020CEA | UFDR 204.A | HS2-000020CEA | 2024-08-06 | 10 - Complete | 2024-08-13 |  | HS2-00002QSQE - CFA_14_08_Grovehill Farm_Topsoil Strip Asset_Priority 2 | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSQE | #N/A | #N/A | #N/A
UFDR 202.E | HS2-00002NHZ4 | UFDR 202.E | HS2-00002NHZ4 | 2024-08-06 | 10 - Complete | 2024-08-09 |  | HS2-00002QSKG - CFA_14_09_Oatleys Farm _Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKG | #N/A | #N/A | #N/A
233.01-3 | HS2-0000386TE | IDR 233.01-3 | HS2-0000386TE | 2024-08-06 | 10 - Complete | 2024-08-20 |  | HS2-00002QSKH - CFA_14_19_Old Rectory_Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKH | #N/A | #N/A | #N/A
202.4-2 | HS2-00002WUK2 | IDR 202.4-2 | HS2-00002WUK2 | 2024-08-06 | 10 - Complete | 2024-08-08 |  | HS2-00002QSQF - CFA_14_09_Oatleys Farm _Topsoil Strip Asset_Priority 2 | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSQF | #N/A | #N/A | #N/A
202.4-2 | HS2-00002WUK3 | IDR 202.4-2 | HS2-00002WUK3 | 2024-08-06 | 10 - Complete | 2024-08-08 |  | HS2-00002QSKJ - CFA_14_10_Glebe Farm (Turweston)_Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKJ | #N/A | #N/A | #N/A
202.4-2 | HS2-00002WUK4 | IDR 202.4-2 | HS2-00002WUK4 | 2024-08-06 | 10 - Complete | 2024-08-08 |  | HS2-00002QSQG - CFA_14_10_Glebe Farm (Turweston)_Topsoil Strip Asset_Priority 2 | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSQG | #N/A | #N/A | #N/A
202.4-2 | HS2-00002WUK5 | IDR 202.4-2 | HS2-00002WUK5 | 2024-08-06 | 10 - Complete | 2024-08-08 |  | HS2-00002QSKK - CFA_14_03_Oatleys Hall_Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKK | #N/A | #N/A | #N/A
202.4-2 | HS2-00002WUK6 | IDR 202.4-2 | HS2-00002WUK6 | 2024-08-06 | 10 - Complete | 2024-08-09 |  | HS2-00002QSQJ - CFA_14_03_Oatleys Hall_Topsoil Strip Asset_Priority 2 | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSQJ | #N/A | #N/A | #N/A
202.4-2 | HS2-00002WUK7 | IDR 202.4-2 | HS2-00002WUK7 | 2024-08-06 | 10 - Complete | 2024-08-09 |  | HS2-00002QSKL - CFA_14_68_Ballabeg Stables_Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKL | #N/A | #N/A | #N/A
202.4-2 | HS2-00002WUK8 | IDR 202.4-2 | HS2-00002WUK8 | 2024-08-06 | 10 - Complete | 2024-08-09 |  | HS2-00002QSQM - CFA_14_68_Ballabeg Stables_Topsoil Strip Asset_Priority 2 | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSQM | #N/A | #N/A | #N/A
202.4-2 | HS2-00002WUK9 | IDR 202.4-2 | HS2-00002WUK9 | 2024-08-06 | 10 - Complete | 2024-08-08 |  | HS2-00002QSKM - CFA_14_11_Turweston Glebe_Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKM | #N/A | #N/A | #N/A
202.4-2 | HS2-00002WUKA | IDR 202.4-2 | HS2-00002WUKA | 2024-08-06 | 10 - Complete | 2024-08-08 |  | HS2-00002QSQK - CFA_14_11_Turweston Glebe_Topsoil Strip Asset_Priority 2 | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSQK | #N/A | #N/A | #N/A
234.05 | HS2-000001375 | IDR 234.05 | HS2-000001375 | 2024-08-07 | 10 - Complete | 2024-08-21 |  | HS2-00002QSQL - CFA_14_15_Parkside_Topsoil Strip Asset_Priority 2 | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSQL | #N/A | #N/A | #N/A
204.2-2 | HS2-00002CT4M | IDR 204.2-2 | HS2-00002CT4M | 2024-09-02 | 10 - Complete | 2024-09-16 |  | HS2-00002QSKQ - CFA_14_14_Turweston Fields_Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKQ | #N/A | #N/A | #N/A
204.2-2 | HS2-00002EKX6 | IDR 204.2-2 | HS2-00002EKX6 | 2024-08-07 | 10 - Complete | 2024-08-22 |  | HS2-00002QSKR - CFA_14_78_Turweston Manor_Topsoil Stripping Asset | SC DATS 223 to 224 Mixbury Embankment to Turweston Cutting | #VALUE! | HS2-00002QSKR | #N/A | #N/A | #N/A
204.2-2 | HS2-00002EKX5 | IDR 204.2-2 | HS2-00002EKX5 | 2024-08-07 | 10 - Complete | 2024-08-22 |  | HS2-00002PXLH - Twyford Embankment General Demolition Assets _Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXLH | #N/A | #N/A | #N/A
204.2-2 | HS2-00002ZPP6 | IDR 204.2-2 | HS2-00002ZPP6 | 2024-08-07 | 10 - Complete | 2024-08-22 |  | HS2-00002PXLJ - Twyford Viaduct General Demolition Assets _Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXLJ | #N/A | #N/A | #N/A
204.2-2 | HS2-00003E24P | IDR 204.2-2 | HS2-00003E24P | 2024-08-07 | 10 - Complete | 2024-08-22 |  | HS2-00002PXFL - Twyford Cutting_Disused Railway Bridge 1 Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFL | #N/A | #N/A | #N/A
204.2-2 | HS2-00003E24R | IDR 204.2-2 | HS2-00003E24R | 2024-08-07 | 10 - Complete | 2024-08-22 |  | HS2-00002PXLK - Cowley Embankment General Demolition Assets _Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXLK | #N/A | #N/A | #N/A
214.1 | HS2-00003CPYM | IDR 214.1 | HS2-00003CPYM | 2024-08-08 | 10 - Complete | 2024-08-28 |  | HS2-00002QSJ9 - CFA_13_06_Clewley Lodge Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJ9 | #N/A | #N/A | #N/A
213.08 | HS2-00002VK43 | IDR 213.08 | HS2-00002VK43 | 2024-08-08 | 10 - Complete | 2024-08-21 |  | HS2-00002QSQA - CFA_13_06_Clewley Lodge Farm_Topsoil Strip Asset_Priority 2 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSQA | #N/A | #N/A | #N/A
213.08 | HS2-00002VK42 | IDR 213.08 | HS2-00002VK42 | 2024-08-08 | 10 - Complete | 2024-08-23 |  | HS2-00002QSJA - CFA_13_08_Cowley Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJA | #N/A | #N/A | #N/A
213.08 | HS2-00003H6PF | IDR 213.08 | HS2-00003H6PF | 2024-08-08 | 10 - Complete | 2024-08-21 |  | HS2-00002QSQC - CFA_13_08_Cowley Farm_Topsoil Strip Asset_Priority 2 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSQC | #N/A | #N/A | #N/A
213.08 | HS2-000031247 | IDR 213.08 | HS2-000031247 | 2024-08-08 | 10 - Complete | 2024-08-21 |  | HS2-00002PXFM - Twyford Cutting_Disused Railway Overbridge 1_Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFM | #N/A | #N/A | #N/A
213.08 | HS2-00002VK3X | IDR 213.08 | HS2-00002VK3X | 2024-08-08 | 10 - Complete | 2024-08-21 |  | HS2-00002PXJ2 - Twyford Cutting General Demolition Assets | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXJ2 | #N/A | #N/A | #N/A
213.08 | HS2-00002Z6NL | IDR 213.08 | HS2-00002Z6NL | 2024-08-08 | 10 - Complete | 2024-08-21 |  | HS2-00002PXLL - Twyford Cutting General Demolition Assets _Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXLL | #N/A | #N/A | #N/A
212.6 | HS2-00002CT54 | IDR 212.6 | HS2-00002CT54 | 2024-08-08 | 10 - Complete | 2024-09-05 |  | HS2-00002QSJB - CFA_13_07_Charndon Grounds Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJB | #N/A | #N/A | #N/A
212.6 | HS2-00002CT5B | IDR 212.6 | HS2-00002CT5B | 2024-08-08 | 10 - Complete | 2024-09-09 |  | HS2-00002QSQB - CFA_13_07_Charndon Grounds Farm_Topsoil Strip Asset_Priority 2 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSQB | #N/A | #N/A | #N/A
212.6 | HS2-00002CT5J | IDR 212.6 | HS2-00002CT5J | 2024-08-08 | 10 - Complete | 2024-08-29 |  | HS2-00002PXFN - Twyford Cutting_Disused Railway Overbridge 2_Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFN | #N/A | #N/A | #N/A
212.6 | HS2-00002CT5R | IDR 212.6 | HS2-00002CT5R | 2024-08-08 | 10 - Complete | 2024-09-02 |  | HS2-00002QSJC - CFA_13_09_Casemore Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJC | #N/A | #N/A | #N/A
212.6 | HS2-00002CT5V | IDR 212.6 | HS2-00002CT5V | 2024-08-08 | 10 - Complete | 2024-09-09 |  | HS2-00002QSJD - CFA_13_10_Grange Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJD | #N/A | #N/A | #N/A
212.6 | HS2-00002CT5Y | IDR 212.6 | HS2-00002CT5Y | 2024-08-08 | 10 - Complete | 2024-08-29 |  | HS2-00002PXJ3 - Godington East Embankment General Demolition Assets | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXJ3 | #N/A | #N/A | #N/A
233.01-3 | HS2-00003B93X | IDR 233.01-3 | HS2-00003B93X | 2024-08-09 | 10 - Complete | 2024-08-15 |  | HS2-00002PXLM - Godington East Embankment General Demolition Assets_Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXLM | #N/A | #N/A | #N/A
234.03 | HS2-00002TG2Z | IDR 234.03 | HS2-00002TG2Z | 2024-08-09 | 10 - Complete | 2024-08-20 |  | HS2-00002PXJ5 - Godington East Viaduct General Demolition Assets | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXJ5 | #N/A | #N/A | #N/A
205.3 | HS2-00002CW1L | IDR 205.3 | HS2-00002CW1L | 2024-08-09 | 10 - Complete | 2024-08-23 |  | HS2-00002PXLN - Godington East Viaduct General Demolition Assets_Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXLN | #N/A | #N/A | #N/A
204.2-2 | HS2-00003JQJQ | IDR 204.2-2 | HS2-00003JQJQ | 2024-08-12 | 10 - Complete | 2024-08-16 |  | HS2-00002PXFP - Twyford Cutting_Disused Railway Bridge 2_Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFP | #N/A | #N/A | #N/A
204.2-2 | HS2-00003JQJR | IDR 204.2-2 | HS2-00003JQJR | 2024-08-12 | 10 - Complete | 2024-08-16 |  | HS2-00002PXJ6 - Godington West Embankment General Demolition Assets | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXJ6 | #N/A | #N/A | #N/A
204.2-2 | HS2-00003JQJS | IDR 204.2-2 | HS2-00003JQJS | 2024-08-12 | 10 - Complete | 2024-08-16 |  | HS2-00002PXLP - Godington West Embankment General Demolition Assets_Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXLP | #N/A | #N/A | #N/A
204.2-2 | HS2-00003K2XQ | IDR 204.2-2 | HS2-00003K2XQ | 2024-08-12 | 10 - Complete | 2024-08-16 |  | HS2-00002QSJE - CFA_13_11_Moat farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJE | #N/A | #N/A | #N/A
215.03 | HS2-00003GL96 | IDR 215.03 | HS2-00003GL96 | 2024-08-12 | 10 - Complete | 2024-08-23 |  | HS2-00002PXFQ - Twyford Cutting_Disused Railway Bridge 3_Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFQ | #N/A | #N/A | #N/A
215.03 | HS2-00003GL97 | IDR 215.03 | HS2-00003GL97 | 2024-08-12 | 10 - Complete | 2024-08-28 |  | HS2-00002PXJ7 - Godington West Viaduct General Demolition Assets | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXJ7 | #N/A | #N/A | #N/A
215.03 | HS2-00002Y8VT | IDR 215.03 | HS2-00002Y8VT | 2024-08-12 | 10 - Complete | 2024-08-23 |  | HS2-00002PXLQ - Godington West Viaduct General Demolition Assets_Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXLQ | #N/A | #N/A | #N/A
215.03 | HS2-00002YXB6 | IDR 215.03 | HS2-00002YXB6 | 2024-08-12 | 10 - Complete | 2024-08-23 |  | HS2-00002PXJ8 - Chetwode Embankment General Demolition Assets | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXJ8 | #N/A | #N/A | #N/A
215.03 | HS2-00003D9CF | IDR 215.03 | HS2-00003D9CF | 2024-08-12 | 10 - Complete | 2024-08-23 |  | HS2-00002PXLR - Chetwode Embankment General Demolition Assets_Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXLR | #N/A | #N/A | #N/A
215.03 | HS2-00002YPE6 | IDR 215.03 | HS2-00002YPE6 | 2024-08-12 | 10 - Complete | 2024-08-27 |  | HS2-00002PXFR - Twyford Cutting_Disused Railway Bridge 4_Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFR | #N/A | #N/A | #N/A
215.03 | HS2-00002Y8VS | IDR 215.03 | HS2-00002Y8VS | 2024-08-12 | 10 - Complete | 2024-08-27 |  | HS2-00002PXFS - Twyford Cutting_Disused Railway Bridge 5_Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFS | #N/A | #N/A | #N/A
215.03 | HS2-00003GNA5 | IDR 215.03 | HS2-00003GNA5 | 2024-09-26 | 10 - Complete | 2024-09-27 |  | HS2-00002PXJA - Chetwode Cutting General Demolition Assets | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXJA | #N/A | #N/A | #N/A
212.5 | HS2-000035Q91 | IDR 212.5 | HS2-000035Q91 | 2024-08-12 | 10 - Complete | 2024-08-23 |  | HS2-00002PXLS - Chetwode Cutting General Demolition Assets_Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXLS | #N/A | #N/A | #N/A
229.01-2 | HS2-00002TMF6 | IDR 229.01-2 | HS2-00002TMF6 | 2024-08-13 | 10 - Complete | 2024-08-22 |  | HS2-00002QSJF - CFA_13_53_Rosehill Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJF | #N/A | #N/A | #N/A
229.01-2 | HS2-00002TMF5 | IDR 229.01-2 | HS2-00002TMF5 | 2024-08-13 | 10 - Complete | 2024-08-21 |  | HS2-00002PXFT - Godington East Embankment_RoseHill Farm_Residence Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFT | #N/A | #N/A | #N/A
204.2-2 | HS2-000031GXP | IDR 204.2-2 | HS2-000031GXP | 2024-08-13 | 10 - Complete | 0 |  | HS2-00002QSJG - CFA_13_58_Rosehill Cottage_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJG | #N/A | #N/A | #N/A
204.2-2 | HS2-000031GXK | IDR 204.2-2 | HS2-000031GXK | 2024-08-13 | 10 - Complete | 2024-08-20 |  | HS2-00002PXFU - Godington East Embankment_Sunflower Farm Cottage_Residence Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFU | #N/A | #N/A | #N/A
204.2-2 | HS2-000031GXL | IDR 204.2-2 | HS2-000031GXL | 2024-08-13 | 10 - Complete | 2024-09-11 |  | HS2-00002QSJH - CFA_13_72_Sunflower Farm Cottage_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJH | #N/A | #N/A | #N/A
204.2-2 | HS2-000031GXM | IDR 204.2-2 | HS2-000031GXM | 2024-08-13 | 10 - Complete | 2024-09-11 |  | HS2-00002PXFV - Godington East Embankment_The Green_Residence Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFV | #N/A | #N/A | #N/A
204.2-2 | HS2-000031GXN | IDR 204.2-2 | HS2-000031GXN | 2024-08-13 | 10 - Complete | 2024-08-20 |  | HS2-00002PXFW - Chetwode Cutting_Disused Railway Overbridge 1 Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFW | #N/A | #N/A | #N/A
204.2-2 | HS2-00003CPYY | IDR 204.2-2 | HS2-00003CPYY | 2024-08-13 | 10 - Complete | 2024-08-21 |  | HS2-00002QSJJ - CFA_13_12_Chetwode manor including Manthorne Farm and Boundary Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJJ | #N/A | #N/A | #N/A
204.2-2 | HS2-000031GXQ | IDR 204.2-2 | HS2-000031GXQ | 2024-08-13 | 10 - Complete | 2024-08-16 |  | HS2-00002QSJK - CFA_13_73_Sunflower Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJK | #N/A | #N/A | #N/A
204.2-2 | HS2-00003CPYX | IDR 204.2-2 | HS2-00003CPYX | 2024-08-13 | 10 - Complete | 2024-08-16 |  | HS2-00002PXFX - Chetwode Cutting_Manthorn Farm_Barns Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFX | #N/A | #N/A | #N/A
204.2-2 | HS2-0000325TJ | IDR 204.2-2 | HS2-0000325TJ | 2024-08-13 | 10 - Complete | 2024-08-16 |  | HS2-00002QSJL - CFA_13_70_The Hermitage_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJL | #N/A | #N/A | #N/A
204.2-2 | HS2-0000325TK | IDR 204.2-2 | HS2-0000325TK | 2024-08-13 | 10 - Complete | 2024-08-16 |  | HS2-00002PXFY - Chetwode Cutting_Disused Railway Overbridge 2 Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFY | #N/A | #N/A | #N/A
204.2-2 | HS2-00003CPYU | IDR 204.2-2 | HS2-00003CPYU | 2024-08-13 | 10 - Complete | 2024-08-16 |  | HS2-00002QSJM - CFA_13_13_Barton Hill Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJM | #N/A | #N/A | #N/A
226.5 | HS2-000031EF5 | IDR 226.5 | HS2-000031EF5 | 2024-08-13 | 10 - Complete | 2024-08-22 |  | HS2-00002PXJC - Barton Hartshorn Embankment General Demolition Assets | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXJC | #N/A | #N/A | #N/A
226.5 | HS2-000031EF6 | IDR 226.5 | HS2-000031EF6 | 2024-08-13 | 10 - Complete | 2024-08-22 |  | HS2-00002PXLT - Barton Hartshorn Embankment General Demolition Assets_Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXLT | #N/A | #N/A | #N/A
213.08 | HS2-00002Y0EX | IDR 213.08 | HS2-00002Y0EX | 2024-08-14 | 10 - Complete | 2024-08-21 |  | HS2-00002QSJN - CFA_13_20_New Manor Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJN | #N/A | #N/A | #N/A
213.08 | HS2-00002VK4D | IDR 213.08 | HS2-00002VK4D | 2024-08-14 | 10 - Complete | 2024-08-21 |  | HS2-00002PXFZ - Barton Hartshorn Embankment_Barn Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXFZ | #N/A | #N/A | #N/A
213.08 | HS2-00002VK3Q | IDR 213.08 | HS2-00002VK3Q | 2024-08-14 | 10 - Complete | 2024-08-21 |  | HS2-00002QSJP - CFA_13_15_Barton Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJP | #N/A | #N/A | #N/A
229.01-2 | HS2-00002CTF3 | IDR 229.01-2 | HS2-00002CTF3 | 2024-08-15 | 10 - Complete | 2024-09-12 |  | HS2-00002PXJD - Barton to Mixbury Cutting General Demolition Assets | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXJD | #N/A | #N/A | #N/A
215.03 | HS2-00003H07F | IDR 215.03 | HS2-00003H07F | 2024-08-15 | 10 - Complete | 2024-08-28 |  | HS2-00002PXLU - Barton to Mixbury Cutting General Demolition Assets_Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXLU | #N/A | #N/A | #N/A
215.03 | HS2-00002Y8VU | IDR 215.03 | HS2-00002Y8VU | 2024-08-15 | 10 - Complete | 2024-08-27 |  | HS2-00002PXMH - Barton to Mixbury Cutting General Demolition Assets _Priority 2 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXMH | #N/A | #N/A | #N/A
215.03 | HS2-00003D9CD | IDR 215.03 | HS2-00003D9CD | 2024-08-15 | 10 - Complete | 2024-08-27 |  | HS2-00002QSJQ - CFA_13_14_Barton Grounds Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJQ | #N/A | #N/A | #N/A
213.08 | HS2-00002BJTN | IDR 213.08 | HS2-00002BJTN | 2024-10-15 | 10 - Complete | 2024-10-23 |  | HS2-00002PXG0 - Barton to Mixbury Cutting_Disused Railway Bridge 1 Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXG0 | #N/A | #N/A | #N/A
UFDR 217.B | HS2-0000245ZF | UFDR 217.B | HS2-0000245ZF | 2024-08-19 | 10 - Complete | 2024-08-21 |  | HS2-00002QSJR - CFA_13_52_Twyford fields at CH 82000_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJR | #N/A | #N/A | #N/A
229.01-2 | HS2-00003FV0F | IDR 229.01-2 | HS2-00003FV0F | 2024-08-19 | 10 - Complete | 2024-08-29 |  | HS2-00002QSJS - CFA_14_57_Shelswell Inn_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJS | #N/A | #N/A | #N/A
229.01-2 | HS2-00003FV0G | IDR 229.01-2 | HS2-00003FV0G | 2024-08-19 | 10 - Complete | 2024-08-29 |  | HS2-00002QSJT - CFA_13_57_Barley Fields Farmhouse Newton Purcell MK18 _Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJT | #N/A | #N/A | #N/A
218.02-1 | HS2-00002NSXQ | IDR 218.02-1 | HS2-00002NSXQ | 2024-08-19 | 10 - Complete | 2024-08-29 |  | HS2-00002PXG1 - Barton to Mixbury Cutting_A4421_Residence Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXG1 | #N/A | #N/A | #N/A
217.03 | HS2-00002CT8S | IDR 217.03 | HS2-00002CT8S | 2025-05-01 | 10 - Complete | 2025-05-02 |  | HS2-00002PXG2 - Barton to Mixbury Cutting_A4421_Disused Railway Bridge 2 Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXG2 | #N/A | #N/A | #N/A
212.5 | HS2-00003JKXS | IDR 212.5 | HS2-00003JKXS | 2024-08-19 | 10 - Complete | 2024-08-29 |  | HS2-00002QSJU - CFA_14_01_Manor Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJU | #N/A | #N/A | #N/A
212.5 | HS2-00003H07B | IDR 212.5 | HS2-00003H07B | 2024-08-19 | 10 - Complete | 2024-08-30 |  | HS2-00002QSJV - CFA_14_73_Station House_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJV | #N/A | #N/A | #N/A
230.01-3 | HS2-00002CTFN | IDR 230.01-3 | HS2-00002CTFN | 2025-02-06 | 10 - Complete | 2025-02-20 |  | HS2-00002QSJW - CFA_14_69_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJW | #N/A | #N/A | #N/A
215.02-2 | HS2-00002CX35 | IDR 215.02-2 | HS2-00002CX35 | 2024-08-21 | 10 - Complete | 2024-09-05 |  | HS2-00002QSJX - CFA_14_60_Finmore Station Newton Purcell_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJX | #N/A | #N/A | #N/A
213.08 | HS2-00003HWH0 | IDR 213.08 | HS2-00003HWH0 | 2024-08-21 | 10 - Complete | 2024-08-28 |  | HS2-00002QSJY - CFA_13_54_Boundary Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJY | #N/A | #N/A | #N/A
UFDR 204.B | HS2-000020CEJ | UFDR 204.B | HS2-000020CEJ | 2024-08-22 | 10 - Complete | 2024-09-04 |  | HS2-00002QSJZ - CFA_14_02_Shelswell Estate_(Ten Widmore Farm)_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSJZ | #N/A | #N/A | #N/A
UFDR 204.B | HS2-000020CEK | UFDR 204.B | HS2-000020CEK | 2024-08-22 | 10 - Complete | 2024-09-04 |  | HS2-00002QSNW - CFA_14_02_Shelswell Estate (Ten Widmore Farm)_Topsoil Strip Asset_Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSNW | #N/A | #N/A | #N/A
215.02-2 | HS2-00002CX36 | IDR 215.02-2 | HS2-00002CX36 | 2025-01-10 | 10 - Complete | 2025-01-17 |  | HS2-00002QSK0 - CFA_14_53_Finmere Quarry_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSK0 | #N/A | #N/A | #N/A
215.02-2 | HS2-00002CT8V | IDR 215.02-2 | HS2-00002CT8V | 2024-08-22 | 10 - Complete | 2024-09-05 |  | HS2-00002QSNX - CFA_14_53_Finmere Quarry_Topsoil Strip Asset_Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSNX | #N/A | #N/A | #N/A
228.2 | HS2-000001339 | IDR 228.2 | HS2-000001339 | 2024-08-22 | 10 - Complete | 2024-10-03 |  | HS2-00002QSK1 - CFA_14_56_Hill Leys_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSK1 | #N/A | #N/A | #N/A
228.2 | HS2-000001436 | IDR 228.2 | HS2-000001436 | 2024-08-22 | 10 - Complete | 2024-09-25 |  | HS2-00002QSP5 - CFA_14_56_Hill Leys_Topsoil Strip Asset_Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSP5 | #N/A | #N/A | #N/A
228.1 | HS2-000001340 | IDR 228.1 | HS2-000001340 | 2024-08-22 | 10 - Complete | 2024-10-04 |  | HS2-00002PXG3 - Barton to Mixbury Cutting_Widmore Farm_Field Barn Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXG3 | #N/A | #N/A | #N/A
213.02-2 | HS2-000001040 | IDR 213.02-2 | HS2-000001040 | 2024-08-26 | 10 - Complete | 2024-09-05 |  | HS2-00002QSK2 - CFA_14_70_Warren Farmhouse_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSK2 | #N/A | #N/A | #N/A
234.01 | HS2-00002U4NE | IDR 234.01 | HS2-00002U4NE | 2025-01-09 | 10 - Complete | 2025-01-16 |  | HS2-00002QSNY - CFA_14_70_Warren Farmhouse_Topsoil Strip Asset_Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSNY | #N/A | #N/A | #N/A
229.03 | HS2-00002CTES | IDR 229.03 | HS2-00002CTES | 2024-08-26 | 10 - Complete | 2024-09-10 |  | HS2-00002QSK3 - CFA_14_72_Ashley Stables_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSK3 | #N/A | #N/A | #N/A
226.5 | HS2-0000386UJ | IDR 226.5 | HS2-0000386UJ | 2024-08-26 | 10 - Complete | 2024-09-03 |  | HS2-00002QSNZ - CFA_14_72_Ashley Stables_Topsoil Strip Asset_Priority 1 | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSNZ | #N/A | #N/A | #N/A
230.04-2 | HS2-00002CTG0 | IDR 230.04-2 | HS2-00002CTG0 | 2024-08-28 | 10 - Complete | 2024-09-25 |  | HS2-00002PXG4 - Barton to Mixbury Cutting_A421_Livestock Shelter Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXG4 | #N/A | #N/A | #N/A
229.03 | HS2-000001072 | IDR 229.03 | HS2-000001072 | 2024-08-28 | 10 - Complete | 2024-09-18 |  | HS2-00002QSK4 - CFA_14_71_Land at Warren Farmhouse_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSK4 | #N/A | #N/A | #N/A
229.03 | HS2-00002CTET | IDR 229.03 | HS2-00002CTET | 2024-09-30 | 10 - Complete | 2024-10-04 |  | HS2-00002QSK5 - CFA_14_58_Warren Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSK5 | #N/A | #N/A | #N/A
216.01 | HS2-000001318 | IDR 216.01 | HS2-000001318 | 2024-08-28 | 10 - Complete | 2024-10-14 |  | HS2-00002QSK6 - CFA_14_75_Orchard Barn Land and Stables_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSK6 | #N/A | #N/A | #N/A
215.03 | HS2-00002CT93 | IDR 215.03 | HS2-00002CT93 | 2024-08-28 | 10 - Complete | 2024-09-10 |  | HS2-00002QSK7 - CFA_14_74_4 Warren Farm Cottages_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSK7 | #N/A | #N/A | #N/A
213.07-1 | HS2-00003JN81 | IDR 213.07-1 | HS2-00003JN81 | 2024-08-28 | 10 - Complete | 2024-09-12 |  | HS2-00002PXG5 - Barton to Mixbury Cutting_A421_The Oaks Horse Stables Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXG5 | #N/A | #N/A | #N/A
213.07-1 | HS2-000032LLS | IDR 213.07-1 | HS2-000032LLS | 2024-08-28 | 10 - Complete | 2024-09-16 |  | HS2-00002PXG6 - Barton to Mixbury Cutting_A421_Warren Farm Horse Stables Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXG6 | #N/A | #N/A | #N/A
213.07-1 | HS2-000032LLT | IDR 213.07-1 | HS2-000032LLT | 2024-08-28 | 10 - Complete | 2024-09-19 |  | HS2-00002QSK8 - CFA_14_67_Oaks Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSK8 | #N/A | #N/A | #N/A
213.07-1 | HS2-000032LLU | IDR 213.07-1 | HS2-000032LLU | 2024-08-28 | 10 - Complete | 2024-09-19 |  | HS2-00002QSK9 - CFA_14_05_Tibbetts Farm and Mill Farm_Topsoil Stripping Asset | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002QSK9 | #N/A | #N/A | #N/A
213.07-1 | HS2-000032LLV | IDR 213.07-1 | HS2-000032LLV | 2024-08-28 | 10 - Complete | 2024-09-19 |  | HS2-00002PXG7 - Barton to Mixbury Cutting_Church Lane_Tibbets Farm Barns Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXG7 | #N/A | #N/A | #N/A
213.07-1 | HS2-000032LLW | IDR 213.07-1 | HS2-000032LLW | 2024-08-28 | 10 - Complete | 2024-09-19 |  | HS2-00002PXG8 - Barton to Mixbury Cutting_Highways Bridge Demolition | SC DATS 219 to 222 Twyford Viaduct to Barton To Mixbury Cutting | #VALUE! | HS2-00002PXG8 | #N/A | #N/A | #N/A
230.03-2 | HS2-00002CTFX | IDR 230.03-2 | HS2-00002CTFX | 2024-08-29 | 10 - Complete | 2024-09-06 |  | HS2-00002QSHL - CFA_13_60_FCC_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHL | #N/A | #N/A | #N/A
212.5 | HS2-000030TD8 | IDR 212.5 | HS2-000030TD8 | 2024-08-29 | 10 - Complete | 0 |  | HS2-00002PXHX - Calvert Cutting General Demolition Assets | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXHX | #N/A | #N/A | #N/A
212.5 | HS2-000030TD7 | IDR 212.5 | HS2-000030TD7 | 2024-08-29 | 10 - Complete | 2024-09-13 |  | HS2-00002PXLF - Calvert Cutting General Demolition Assets_Priority 1 | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXLF | #N/A | #N/A | #N/A
204.2-2 | HS2-00002CT4M | IDR 204.2-2 | HS2-00002CT4M | 2024-09-02 | 10 - Complete | 2024-09-16 |  | HS2-00002PXMG - Calvert Cutting General Demolition Assets_Priority 2 | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXMG | #N/A | #N/A | #N/A
215.03 | HS2-00002YPEG | IDR 215.03 | HS2-00002YPEG | 2024-09-02 | 10 - Complete | 2024-09-26 |  | HS2-00002PXF6 - Calvert Cutting_Calvert Railway Station_Workshop Unit Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXF6 | #N/A | #N/A | #N/A
215.03 | HS2-00002YPEH | IDR 215.03 | HS2-00002YPEH | 2024-09-02 | 10 - Complete | 2024-09-26 |  | HS2-00002QSHM - CFA_13_62_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHM | #N/A | #N/A | #N/A
215.03 | HS2-00002VK40 | IDR 215.03 | HS2-00002VK40 | 2024-09-02 | 10 - Complete | 2024-09-26 |  | HS2-00002PXF7 - Calvert Cutting_FCC Environment Property Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXF7 | #N/A | #N/A | #N/A
215.03 | HS2-00003GSJY | IDR 215.03 | HS2-00003GSJY | 2024-09-02 | 10 - Complete | 2024-09-26 |  | HS2-00002QSHN - CFA_13_66_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHN | #N/A | #N/A | #N/A
215.03 | HS2-00003GSJZ | IDR 215.03 | HS2-00003GSJZ | 2024-09-02 | 10 - Complete | 2024-09-26 |  | HS2-00002PXF8 - Calvert Cutting_Brackley Ln_Residences Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXF8 | #N/A | #N/A | #N/A
UFDR 214.A | HS2-00002TUPJ | UFDR 214.A | HS2-00002TUPJ | 2024-10-25 | 10 - Complete | 2024-10-31 |  | HS2-00002QSHP - CFA_13_64_13 Brackley Lane_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHP | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-00002QSHQ - CFA_13_71_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHQ | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-00002QSHR - CFA_13_65_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHR | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-00002PXF9 - Calvert Cutting_School Hill_Barn Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXF9 | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-00002QSHS - CFA_13_63_12B Beackley Lane_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHS | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-00002PXFA - Calvert Cutting_School Hill Road_Railway Overbridge Bridge Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXFA | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-00002PXFB - Calvert Cutting_Calvert Lakeside_Residences Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXFB | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-00002QSHT - CFA_13_02_Portway Greatmoor and Shepherds Furze_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHT | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-00002QSQ5 - CFA_13_02_Portway Greatmoor and Shepherds Furze_Topsoil Strip Asset_Priority 2 | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSQ5 | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-00002QSHU - CFA_13_61_Greatmoor Sailing Club_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHU | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-00002PXFC - Calvert Cutting_Addison Road_Railway Overbridge Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXFC | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2P | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0 |  | HS2-00002QSHV - CFA_13_17_Rose Hill Farm Steeple Claydon_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHV | #N/A | #N/A | #N/A
215.02-02 | HS2-00002BJU3 | IDR 215.02-02 | HS2-00002BJU3 | 2025-01-29 | 10 - Complete | 2025-02-10 |  | HS2-00002QSQY - CFA_13_17_Rose Hill Farm Steeple Claydon_Topsoil Strip Asset_Priority 2 | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSQY | #N/A | #N/A | #N/A
215.02-02 | HS2-00002CT8Y | IDR 215.02-02 | HS2-00002CT8Y | 2025-01-29 | 10 - Complete | 2025-02-12 |  | HS2-00002PXFD - Calvert Cutting_Shepherds Furze Farm Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXFD | #N/A | #N/A | #N/A
229.03 | HS2-00002CTEY | IDR 229.03 | HS2-00002CTEY | 2024-09-03 | 10 - Complete | 2024-09-11 |  | HS2-00002PXHY - Calvert Infrastructure Maintenance Depot General Demolition Assets | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXHY | #N/A | #N/A | #N/A
233.01-3 | HS2-00002NJ07 | IDR 233.01-3 | HS2-00002NJ07 | 2024-09-05 | 10 - Complete | 2024-11-08 |  | HS2-00002PXLG - Calvert Infrastructure Maintenance Depot General Demolition Assets _Priority 1 | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXLG | #N/A | #N/A | #N/A
233.01-3 | HS2-00002NJ07 | IDR 233.01-3 | HS2-00002NJ07 | 2024-09-05 | 10 - Complete | 2024-11-08 |  | HS2-00002QSHW - CFA_13_56_Poors Piece_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHW | #N/A | #N/A | #N/A
233.01-3 | HS2-00002NJ07 | IDR 233.01-3 | HS2-00002NJ07 | 2024-09-05 | 10 - Complete | 2024-11-08 |  | HS2-00002QSHX - CFA_13_67_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHX | #N/A | #N/A | #N/A
UFDR 238.E | HS2-000020CKG | UFDR 238.E | HS2-000020CKG | 2024-09-06 | 10 - Complete | 2024-09-11 |  | HS2-00002QSHY - CFA_13_68_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHY | #N/A | #N/A | #N/A
UFDR 205.B | HS2-000020CET | UFDR 205.B | HS2-000020CET | 2024-09-06 | 99 - Cancelled | 0 |  | HS2-00002QSHZ - CFA_13_69_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSHZ | #N/A | #N/A | #N/A
UFDR 205.B | HS2-000020CEU | UFDR 205.B | HS2-000020CEU | 2024-09-06 | 99 - Cancelled | 0 |  | HS2-00002QSQZ - CFA_13_56_Poors Piece_Topsoil Strip Asset_Priority 2 | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSQZ | #N/A | #N/A | #N/A
UFDR 205.B | HS2-00002SXNK | UFDR 205.B | HS2-00002SXNK | 2024-09-06 | 99 - Cancelled | 0 |  | HS2-00002QSR0 - CFA_13_69_Topsoil Strip Asset_Priority 2 | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSR0 | #N/A | #N/A | #N/A
UFDR 205.B | HS2-000020CEQ | UFDR 205.B | HS2-000020CEQ | 2024-09-06 | 99 - Cancelled | 0 |  | HS2-00002PXFE - Calvert Cutting_Substation Property Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXFE | #N/A | #N/A | #N/A
238.01 | HS2-00002BVN8 | IDR 238.01 | HS2-00002BVN8 | 2025-03-03 | 10 - Complete | 2025-03-07 |  | HS2-00002PXFF - Calvert Cutting_Calvert Jubilee Nature Reserve Road Bridge Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXFF | #N/A | #N/A | #N/A
238.01 | HS2-00002CTK8 | IDR 238.01 | HS2-00002CTK8 | 2024-09-06 | 10 - Complete | 2024-09-30 |  | HS2-00002QSJ0 - CFA_13_03b_ Stone Court Farm_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSJ0 | #N/A | #N/A | #N/A
238.01 | HS2-00002CTK7 | IDR 238.01 | HS2-00002CTK7 | 2024-09-06 | 10 - Complete | 2024-09-25 |  | HS2-00002QSJ1 - CFA_13_03a_Elm Farm_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSJ1 | #N/A | #N/A | #N/A
215.03 | HS2-00003GEER | IDR 215.03 | HS2-00003GEER | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-00002QSQX - CFA_13_03a_Elm Farm_Topsoil Strip Asset_Priority 2 | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSQX | #N/A | #N/A | #N/A
212.5 | HS2-00002VK4B | IDR 212.5 | HS2-00002VK4B | 2024-09-06 | 10 - Complete | 2024-09-17 |  | HS2-00002QSJ2 - CFA_13_04_Lake Farm_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSJ2 | #N/A | #N/A | #N/A
212.5 | HS2-00003BPJH | IDR 212.5 | HS2-00003BPJH | 2024-09-06 | 10 - Complete | 2024-09-17 |  | HS2-00002QSJ3 - CFA_13_51_Briarhill Farm Steeple Claydon MK18 2EP_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSJ3 | #N/A | #N/A | #N/A
212.5 | HS2-00003H079 | IDR 212.5 | HS2-00003H079 | 2024-09-06 | 10 - Complete | 2024-09-17 |  | HS2-00002PXFG - Calvert Cutting_Large Barn Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXFG | #N/A | #N/A | #N/A
212.5 | HS2-00003KFPN | IDR 212.5 | HS2-00003KFPN | 2024-09-06 | 10 - Complete | 2024-09-18 |  | HS2-00002QSJ4 - CFA_13_03c_The Green_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSJ4 | #N/A | #N/A | #N/A
212.5 | HS2-00003H07A | IDR 212.5 | HS2-00003H07A | 2024-09-06 | 10 - Complete | 2024-09-17 |  | HS2-00002PXFH - Calvert Cutting_Disused Railway Overbridge Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXFH | #N/A | #N/A | #N/A
212.5 | HS2-00003H078 | IDR 212.5 | HS2-00003H078 | 2024-10-16 | 10 - Complete | 2024-10-18 |  | HS2-00002QSJ5 - CFA_13_55_Meadow View_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSJ5 | #N/A | #N/A | #N/A
212.5 | HS2-00003H07C | IDR 212.5 | HS2-00003H07C | 2024-10-16 | 10 - Complete | 2024-10-18 |  | HS2-00002QSQ8 - CFA_13_55_Meadow View_Topsoil Strip Asset_Priority 2 | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSQ8 | #N/A | #N/A | #N/A
UFDR 238.E | HS2-00003L5EE | UFDR 238.E | HS2-00003L5EE | 2024-09-09 | 10 - Complete | 2024-09-11 |  | HS2-00002QSJ6 - CFA_13_59_7 Stars Cottage (north of Calvert)_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSJ6 | #N/A | #N/A | #N/A
233.01-2 | HS2-00003AQDH | IDR 233.01-2 | HS2-00003AQDH | 2024-09-09 | 10 - Complete | 2024-09-20 |  | HS2-00002QSQ9 - CFA_13_59_7 Stars Cottage (north of Calvert)_Topsoil Strip Asset_Priority 2 | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSQ9 | #N/A | #N/A | #N/A
218.02-1 | HS2-00002VK47 | IDR 218.02-1 | HS2-00002VK47 | 2024-09-10 | 10 - Complete | 2024-09-20 |  | HS2-00002PXHZ - Twyford Embankment General Demolition Assets | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXHZ | #N/A | #N/A | #N/A
234.04 | HS2-000001345 | IDR 234.04 | HS2-000001345 | 2024-09-11 | 10 - Complete | 2024-09-16 |  | HS2-00002QSJ7 - CFA_13_19_Three Bridge Mill_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSJ7 | #N/A | #N/A | #N/A
233.01-3 | HS2-00003124M | IDR 233.01-3 | HS2-00003124M | 2024-09-12 | 10 - Complete | 2024-11-25 |  | HS2-00002QSQ7 - CFA_13_19_Three Bridge Mill_Topsoil Strip Asset_Priority 2 | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSQ7 | #N/A | #N/A | #N/A
233.01-3 | HS2-000035Q9B | IDR 233.01-3 | HS2-000035Q9B | 2024-09-12 | 10 - Complete | 2024-11-15 |  | HS2-00002PXFJ - Calvert Cutting_Farm Building Recycling Enclosure Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXFJ | #N/A | #N/A | #N/A
204.2-2 | HS2-00002WULG | IDR 204.2-2 | HS2-00002WULG | 2024-09-13 | 10 - Complete | 2024-09-16 |  | HS2-00002PXFK - Twyford Embankment_Disused Railway Overbridge Demolition | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXFK | #N/A | #N/A | #N/A
229.03 | HS2-000020NVF | IDR 229.03 | HS2-000020NVF | 2024-09-13 | 10 - Complete | 2024-10-04 |  | HS2-00002QSJ8 - CFA_13_05_Home Farm_Topsoil Stripping Asset | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSJ8 | #N/A | #N/A | #N/A
226.5 | HS2-00002CTE4 | IDR 226.5 | HS2-00002CTE4 | 2024-09-13 | 10 - Complete | 2024-09-23 |  | HS2-00002QSQ6 - CFA_13_05_Home Farm_Topsoil Strip Asset_Priority 2 | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002QSQ6 | #N/A | #N/A | #N/A
226.5 | HS2-00002CTE9 | IDR 226.5 | HS2-00002CTE9 | 2024-09-13 | 10 - Complete | 2024-09-20 |  | HS2-00002PXJ0 - Twyford Viaduct General Demolition Assets | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXJ0 | #N/A | #N/A | #N/A
226.5 | HS2-00002CTEB | IDR 226.5 | HS2-00002CTEB | 2024-09-13 | 10 - Complete | 2024-09-24 |  | HS2-00002PXJ1 - Cowley Embankment General Demolition Assets | SC DATS 215 to 218 Calvert Cutting inc Twyford Embankment and IMD | #VALUE! | HS2-00002PXJ1 | #N/A | #N/A | #N/A
226.5 | HS2-00002BVK1 | IDR 226.5 | HS2-00002BVK1 | 2024-09-13 | 10 - Complete | 2024-09-19 |  | HS2-00002PXHS - Quainton South Embankment General Demolition Assets | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXHS | #N/A | #N/A | #N/A
226.5 | HS2-00002CQQK | IDR 226.5 | HS2-00002CQQK | 2024-09-13 | 10 - Complete | 2024-09-20 |  | HS2-00002QSH1 - CFA_12_57_Land at Station Road_Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSH1 | #N/A | #N/A | #N/A
226.5 | HS2-00002CTE6 | IDR 226.5 | HS2-00002CTE6 | 2024-09-13 | 10 - Complete | 2024-09-24 |  | HS2-00002QSH3 - CFA_12_64_Crossroads Farm_Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSH3 | #N/A | #N/A | #N/A
221.5 | HS2-00002BVHV | IDR 221.5 | HS2-00002BVHV | 2024-09-13 | 10 - Complete | 2024-09-20 |  | HS2-00002QSH5 - CFA_12_55_Land at Station Road_Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSH5 | #N/A | #N/A | #N/A
221.5 | HS2-00002CTAX | IDR 221.5 | HS2-00002CTAX | 2024-09-13 | 10 - Complete | 2024-09-20 |  | HS2-00002QSH7 - CFA_12_53_Cowle_Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSH7 | #N/A | #N/A | #N/A
221.5 | HS2-00002N7WF | IDR 221.5 | HS2-00002N7WF | 2024-09-13 | 10 - Complete | 2024-09-20 |  | HS2-00002QSH9 - CFA_12_52_Land at Station Road_Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSH9 | #N/A | #N/A | #N/A
221.5 | HS2-00002YUF9 | IDR 221.5 | HS2-00002YUF9 | 2024-09-13 | 10 - Complete | 2024-09-20 |  | HS2-00002QSHA - CFA_12_08_Fieldside Farm Quainton_Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSHA | #N/A | #N/A | #N/A
221.5 | HS2-00002EKXU | IDR 221.5 | HS2-00002EKXU | 2024-09-19 | 10 - Complete | 2024-10-11 |  | HS2-00002PXEW - Quainton Cutting_Livestock Shelter Demolition | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXEW | #N/A | #N/A | #N/A
221.5 | HS2-00003FV0J | IDR 221.5 | HS2-00003FV0J | 2024-09-13 | 10 - Complete | 2024-09-20 |  | HS2-00002PXHT - Quainton Cutting General Demolition Assets | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXHT | #N/A | #N/A | #N/A
221.5 | HS2-0000386UC | IDR 221.5 | HS2-0000386UC | 2024-09-13 | 10 - Complete | 2024-09-20 |  | HS2-00002PXLC - Quainton Cutting General Demolition Assets_Priority 1 | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXLC | #N/A | #N/A | #N/A
229.03 | HS2-00002CTEU | IDR 229.03 | HS2-00002CTEU | 2024-10-25 | 10 - Complete | 2024-10-30 |  | HS2-00002PXEX - Quainton Cutting_Railway Overbridge 1 Demolition | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXEX | #N/A | #N/A | #N/A
229.03 | HS2-00002CTEW | IDR 229.03 | HS2-00002CTEW | 2024-09-16 | 10 - Complete | 2024-10-23 |  | HS2-00002PXEY - Quainton Cutting_ The Lodge_Residence Demolition | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXEY | #N/A | #N/A | #N/A
229.03 | HS2-00002CTF0 | IDR 229.03 | HS2-00002CTF0 | 2024-09-16 | 10 - Complete | 2024-10-30 |  | HS2-00002PXHU - Doddershall Embankment General Demolition Assets | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXHU | #N/A | #N/A | #N/A
229.03 | HS2-00002CTF2 | IDR 229.03 | HS2-00002CTF2 | 2024-09-16 | 10 - Complete | 2024-10-23 |  | HS2-00002QSHC - CFA_12_10_Doddershall Estate_Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSHC | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXZ | IDR 226.5 | HS2-00003CPXZ | 2024-09-16 | 10 - Complete | 2024-09-16 |  | HS2-00002QSHD - CFA_12_11_Hill farm_Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSHD | #N/A | #N/A | #N/A
226.5 | HS2-00003CPY0 | IDR 226.5 | HS2-00003CPY0 | 2024-09-16 | 10 - Complete | 2024-09-17 |  | HS2-00002PXEZ - Quainton Cutting_Farm_Barn Demolition | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXEZ | #N/A | #N/A | #N/A
226.5 | HS2-00003CPY1 | IDR 226.5 | HS2-00003CPY1 | 2024-09-16 | 10 - Complete | 2024-09-17 |  | HS2-00002PXF0 - Quainton Cutting_Railway Underbridge 1 Demolition | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXF0 | #N/A | #N/A | #N/A
226.5 | HS2-00003CPY3 | IDR 226.5 | HS2-00003CPY3 | 2024-09-16 | 10 - Complete | 2024-09-17 |  | HS2-00002PXHV - Woodlands Cutting General Demolition Assets | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXHV | #N/A | #N/A | #N/A
226.5 | HS2-00003CPY4 | IDR 226.5 | HS2-00003CPY4 | 2024-09-16 | 10 - Complete | 2024-09-17 |  | HS2-00002QSHE - CFA_12_56_Dry Leys Farm_Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSHE | #N/A | #N/A | #N/A
226.5 | HS2-00003CPY5 | IDR 226.5 | HS2-00003CPY5 | 2024-09-16 | 10 - Complete | 2024-09-18 |  | HS2-00002PXF1 - Quainton Cutting_Railway Overbridge 2 Demolition | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXF1 | #N/A | #N/A | #N/A
226.5 | HS2-00003CPY6 | IDR 226.5 | HS2-00003CPY6 | 2024-09-16 | 10 - Complete | 2024-09-18 |  | HS2-00002QSHF - CFA_12_51_BBOWT _Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSHF | #N/A | #N/A | #N/A
226.5 | HS2-00003CPY8 | IDR 226.5 | HS2-00003CPY8 | 2024-09-16 | 10 - Complete | 2024-09-18 |  | HS2-00002QSHG - CFA_12_63_Woodlands Farm_Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSHG | #N/A | #N/A | #N/A
226.5 | HS2-00003CPY9 | IDR 226.5 | HS2-00003CPY9 | 2024-09-16 | 10 - Complete | 2024-09-18 |  | HS2-00002PXHW - Grendon Underwood Embankment General Demolition Assets | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXHW | #N/A | #N/A | #N/A
226.5 | HS2-00003CPYA | IDR 226.5 | HS2-00003CPYA | 2024-09-16 | 10 - Complete | 2024-09-18 |  | HS2-00002PXLD - Grendon Underwood Embankment General Demolition Assets _Priority 1 | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXLD | #N/A | #N/A | #N/A
226.5 | HS2-00003CPYC | IDR 226.5 | HS2-00003CPYC | 2024-09-16 | 10 - Complete | 2024-09-18 |  | HS2-00002PXF2 - Quainton Cutting_Railway Underbridge 2 Demolition | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXF2 | #N/A | #N/A | #N/A
226.5 | HS2-00003CPYD | IDR 226.5 | HS2-00003CPYD | 2024-09-16 | 10 - Complete | 2024-09-18 |  | HS2-00002QSHH - CFA_12_61_Woodland and pond at Edgecott Road Quainton Aylesbury HP22 4DE_Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSHH | #N/A | #N/A | #N/A
226.5 | HS2-00003CPYE | IDR 226.5 | HS2-00003CPYE | 2024-09-16 | 10 - Complete | 2024-09-18 |  | HS2-00002QSHJ - CFA_12_14_Oak Tree Farm_Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSHJ | #N/A | #N/A | #N/A
226.5 | HS2-00003CPYF | IDR 226.5 | HS2-00003CPYF | 2024-09-16 | 10 - Complete | 2024-09-18 |  | HS2-00002QSHK - CFA_13_01_Claydon Estate_Topsoil Stripping Asset | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002QSHK | #N/A | #N/A | #N/A
226.5 | HS2-00003CPYH | IDR 226.5 | HS2-00003CPYH | 2024-09-16 | 10 - Complete | 2024-09-18 |  | HS2-00002PXF3 - Quainton Cutting_Road OverbridgeDemolition | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXF3 | #N/A | #N/A | #N/A
226.5 | HS2-00003CPYJ | IDR 226.5 | HS2-00003CPYJ | 2024-09-16 | 10 - Complete | 2024-09-18 |  | HS2-00002PXF4 - Quainton Cutting_FCC Enviroment Pathway Bridge Demolition | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXF4 | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXS | IDR 226.5 | HS2-00003CPXS | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002PXF5 - Quainton Cutting_Railway Underbridge 3 Demolition | SC DATS 213 to 214 Quainton Cutting to Grendon Underwood Embankment | #VALUE! | HS2-00002PXF5 | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXT | IDR 226.5 | HS2-00003CPXT | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002PXHJ - Thame Valley South Embankment General Demolition Assets | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002PXHJ | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXV | IDR 226.5 | HS2-00003CPXV | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002PXHK - Thame Valley Viaduct General Demolition Assets | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002PXHK | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXW | IDR 226.5 | HS2-00003CPXW | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002QSGS - CFA_11_10_Putlowes Farm_Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSGS | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXX | IDR 226.5 | HS2-00003CPXX | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002PXHL - Thame Valley North Embankment General Demolition Assets | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002PXHL | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXC | IDR 226.5 | HS2-00003CPXC | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002PXHM - Putlowes Cutting General Demolition Assets | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002PXHM | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXD | IDR 226.5 | HS2-00003CPXD | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002PXME - Putlowes Cutting General Demolition Assets _Priority 2 | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002PXME | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXF | IDR 226.5 | HS2-00003CPXF | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002PXHN - Bicester Road Embankment General Demolition Assets | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002PXHN | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXG | IDR 226.5 | HS2-00003CPXG | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002PXMF - Bicester Road Embankment General Demolition Assets _Priority 2 | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002PXMF | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXH | IDR 226.5 | HS2-00003CPXH | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002QSGT - CFA_11_11_Fleet Marston Farm_Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSGT | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXJ | IDR 226.5 | HS2-00003CPXJ | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002QSGU - CFA_12_02_Waddesdon Estate Lower Blackgrove Farm_Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSGU | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXL | IDR 226.5 | HS2-00003CPXL | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002QSGV - CFA_12_01_Lower Cranwell Farm_Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSGV | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXM | IDR 226.5 | HS2-00003CPXM | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002PXHP - Waddesdon South Cutting General Demolition Assets | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002PXHP | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXN | IDR 226.5 | HS2-00003CPXN | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002QSGW - CFA_12_60_Bolchers Place _Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSGW | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXQ | IDR 226.5 | HS2-00003CPXQ | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002QSGX - CFA_12_65_Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSGX | #N/A | #N/A | #N/A
226.5 | HS2-00003CPXR | IDR 226.5 | HS2-00003CPXR | 2024-09-16 | 10 - Complete | 2024-09-19 |  | HS2-00002QSGY - CFA_12_04_Glebe Farm_Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSGY | #N/A | #N/A | #N/A
234.03 | HS2-00002TGPC | IDR 234.03 | HS2-00002TGPC | 2024-09-17 | 10 - Complete | 2024-09-20 |  | HS2-00002PXHQ - Waddesdon Embankment General Demolition Assets | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002PXHQ | #N/A | #N/A | #N/A
234.03 | HS2-00003E24L | IDR 234.03 | HS2-00003E24L | 2024-09-17 | 10 - Complete | 2024-09-20 |  | HS2-00002QSGZ - CFA_12_16_Littleton Middle Farm Manor_Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSGZ | #N/A | #N/A | #N/A
229.03 | HS2-000001071 | IDR 229.03 | HS2-000001071 | 2024-10-18 | 10 - Complete | 2024-10-23 |  | HS2-00002PXHR - Waddesdon North Cutting General Demolition Assets | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002PXHR | #N/A | #N/A | #N/A
202.5-2_2 | HS2-000001363 | IDR 202.5-2_2 | HS2-000001363 | 2024-09-18 | 10 - Complete | 2024-12-17 |  | HS2-00002QSH0 - CFA_12_05_Needles Farm_Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSH0 | #N/A | #N/A | #N/A
201.3-2 | HS2-000001285 | IDR 201.3-2 | HS2-000001285 | 2025-05-12 | 10 - Complete | 2025-05-22 |  | HS2-00002PXEU - Thame Valley North Embankment_Station Road_Railway Overbridge Demolition | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002PXEU | #N/A | #N/A | #N/A
229.03 | HS2-00002CTF5 | IDR 229.03 | HS2-00002CTF5 | 2024-09-18 | 10 - Complete | 2024-10-04 |  | HS2-00002PXEV - Thame Valley North Embankment_Railway Overbridge Demolition | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002PXEV | #N/A | #N/A | #N/A
233.01-3 | HS2-000025B2Q | IDR 233.01-3 | HS2-000025B2Q | 2024-09-19 | 10 - Complete | 2024-11-27 |  | HS2-00002QSH2 - CFA_12_66_Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSH2 | #N/A | #N/A | #N/A
233.01-3 | HS2-00003H5JH | IDR 233.01-3 | HS2-00003H5JH | 2024-10-25 | 10 - Complete | 2024-11-05 |  | HS2-00002QSH4 - CFA_12_58_Buckinghamshire Railway Centre_Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSH4 | #N/A | #N/A | #N/A
215.01-2 | HS2-00002CT80 | IDR 215.01-2 | HS2-00002CT80 | 2024-09-19 | 10 - Complete | 2024-10-08 |  | HS2-00002QSH6 - CFA_12_54_Faccenda Foods Limited_Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSH6 | #N/A | #N/A | #N/A
235.02 | HS2-000001455 | IDR 235.02 | HS2-000001455 | 2024-09-19 | 10 - Complete | 2024-09-25 |  | HS2-00002QSH8 - CFA_12_09_Upper South Farm_Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSH8 | #N/A | #N/A | #N/A
229.03 | HS2-000025B2D | IDR 229.03 | HS2-000025B2D | 2024-09-19 | 10 - Complete | 2024-10-03 |  | HS2-00002QSHB - CFA_12_09a_Topsoil Stripping Asset | SC DATS 209 to 212 Thame Valley Viaduct to Quainton South Embankment | #VALUE! | HS2-00002QSHB | #N/A | #N/A | #N/A
229.03 | HS2-00002CTEZ | IDR 229.03 | HS2-00002CTEZ | 2024-09-19 | 10 - Complete | 2024-10-03 |  | HS2-00002PXL8 - Stoke Mandeville South Embankment General Demolition Assets _Priority 1 | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXL8 | #N/A | #N/A | #N/A
221.5 | HS2-00002EKXU | IDR 221.5 | HS2-00002EKXU | 2024-09-19 | 10 - Complete | 2024-10-11 |  | HS2-00002QSFY - CFA_11_58_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSFY | #N/A | #N/A | #N/A
221.5 | HS2-00002EKXU | IDR 221.5 | HS2-00002EKXU | 2024-09-19 | 10 - Complete | 2024-10-11 |  | HS2-00002QSFZ - CFA_11_61_Mill House Farm_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSFZ | #N/A | #N/A | #N/A
204.2-2 | HS2-00002CT4D | IDR 204.2-2 | HS2-00002CT4D | 2024-09-23 | 10 - Complete | 2024-09-24 |  | HS2-00002QSG0 - CFA_11_12_Bucks Goat Centre_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSG0 | #N/A | #N/A | #N/A
222.9 | HS2-00003JYGS | IDR 222.9 | HS2-00003JYGS | 2024-09-24 | 10 - Complete | 2024-09-27 |  | HS2-00002PXEF - Wendover Green Tunnel_Old Risborough Road_Barn Demolition | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXEF | #N/A | #N/A | #N/A
222.9 | HS2-00003JYGT | IDR 222.9 | HS2-00003JYGT | 2024-09-24 | 10 - Complete | 2024-09-27 |  | HS2-00002QSG1 - CFA_10_68_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSG1 | #N/A | #N/A | #N/A
222.9 | HS2-00003JYGU | IDR 222.9 | HS2-00003JYGU | 2024-09-24 | 10 - Complete | 2024-09-27 |  | HS2-00002QSG2 - CFA_10_70_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSG2 | #N/A | #N/A | #N/A
222.9 | HS2-00003JYGV | IDR 222.9 | HS2-00003JYGV | 2024-09-24 | 10 - Complete | 2024-09-27 |  | HS2-00002QSG3 - CFA_10_53_The Paddock_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSG3 | #N/A | #N/A | #N/A
222.9 | HS2-00003JYGW | IDR 222.9 | HS2-00003JYGW | 2024-09-24 | 10 - Complete | 2024-09-27 |  | HS2-00002QSG4 - CFA_11_64_Whitethorn Farm_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSG4 | #N/A | #N/A | #N/A
222.9 | HS2-00003JYGX | IDR 222.9 | HS2-00003JYGX | 2024-09-24 | 10 - Complete | 2024-10-01 |  | HS2-00002QSG5 - CFA_11_62_Whitethorn Medi Clinic_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSG5 | #N/A | #N/A | #N/A
222.9 | HS2-000037YLR | IDR 222.9 | HS2-000037YLR | 2024-09-24 | 10 - Complete | 2024-10-08 |  | HS2-00002QSG6 - CFA_11_63_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSG6 | #N/A | #N/A | #N/A
222.9 | HS2-000037YLS | IDR 222.9 | HS2-000037YLS | 2024-09-24 | 10 - Complete | 2024-10-03 |  | HS2-00002QSG7 - CFA_11_67_Whitethorn Close Management_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSG7 | #N/A | #N/A | #N/A
222.9 | HS2-000031EF2 | IDR 222.9 | HS2-000031EF2 | 2024-09-24 | 10 - Complete | 2024-10-15 |  | HS2-00002QSG8 - CFA_11_68_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSG8 | #N/A | #N/A | #N/A
222.9 | HS2-000037YLP | IDR 222.9 | HS2-000037YLP | 2024-09-24 | 10 - Complete | 2024-10-04 |  | HS2-00002PXEG - Wendover Green Tunnel_Old Risborough Road_Whitethorn Farm Demolition | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXEG | #N/A | #N/A | #N/A
222.9 | HS2-000037YLT | IDR 222.9 | HS2-000037YLT | 2024-09-24 | 10 - Complete | 2024-10-03 |  | HS2-00002QSG9 - CFA_11_65_5 Whitethorn Close_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSG9 | #N/A | #N/A | #N/A
222.9 | HS2-00003JYGN | IDR 222.9 | HS2-00003JYGN | 2024-09-24 | 10 - Complete | 2024-10-03 |  | HS2-00002QSGA - CFA_11_60_4 Whitethorn Close_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGA | #N/A | #N/A | #N/A
222.9 | HS2-00003JYGP | IDR 222.9 | HS2-00003JYGP | 2024-09-24 | 10 - Complete | 2024-09-30 |  | HS2-00002PXEH - Wendover Green Tunnel_Old Risborough Road_Residence Demolition | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXEH | #N/A | #N/A | #N/A
222.9 | HS2-00003JYGQ | IDR 222.9 | HS2-00003JYGQ | 2024-09-24 | 10 - Complete | 2024-09-30 |  | HS2-00002QSGB - CFA_11_71_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGB | #N/A | #N/A | #N/A
222.9 | HS2-00003JYGR | IDR 222.9 | HS2-00003JYGR | 2024-09-24 | 10 - Complete | 2024-09-30 |  | HS2-00002PXH8 - Aylesbury South Cutting General Demolition Assets | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXH8 | #N/A | #N/A | #N/A
UFDR 223.A | HS2-000020CH2 | UFDR 223.A | HS2-000020CH2 | 2024-09-25 | 10 - Complete | 2024-10-08 |  | HS2-00002PXLA - Aylesbury South Cutting General Demolition Assets_Priority 1 | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXLA | #N/A | #N/A | #N/A
233.01-3 | HS2-00003CPYT | IDR 233.01-3 | HS2-00003CPYT | 2024-09-26 | 10 - Complete | 2024-09-30 |  | HS2-00002QSE2 - Aylesbury South Cutting General Demolition Assets_Priority 2 | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSE2 | #N/A | #N/A | #N/A
204.0-1 | HS2-000001287 | IDR 204.0-1 | HS2-000001287 | 2024-09-26 | 10 - Complete | 2024-09-27 |  | HS2-00002QSGC - CFA_11_51_Dodds Farm_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGC | #N/A | #N/A | #N/A
234.03 | HS2-00002TGP3 | IDR 234.03 | HS2-00002TGP3 | 2024-09-26 | 10 - Complete | 2024-10-07 |  | HS2-00002QSGD - CFA_11_04_Marsh Mill Hill Farm_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGD | #N/A | #N/A | #N/A
234.03 | HS2-00003LAXM | IDR 234.03 | HS2-00003LAXM | 2024-09-26 | 10 - Complete | 2024-10-03 |  | HS2-00002QSPZ - CFA_11_04_Marsh Mill Hill Farm_Topsoil Strip Asset_Priority 2 | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSPZ | #N/A | #N/A | #N/A
234.03 | HS2-00003LAXL | IDR 234.03 | HS2-00003LAXL | 2024-09-26 | 10 - Complete | 2024-09-27 |  | HS2-00002QSGE - CFA_11_56_Leslie Wells Patrick Sweeney_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGE | #N/A | #N/A | #N/A
215.03 | HS2-00003GNA5 | IDR 215.03 | HS2-00003GNA5 | 2024-09-26 | 10 - Complete | 2024-09-27 |  | HS2-00002QSGF - CFA_11_06_Moat farm_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGF | #N/A | #N/A | #N/A
229.03 | HS2-000020358 | IDR 229.03 | HS2-000020358 | 2024-09-30 | 10 - Complete | 2024-10-04 |  | HS2-00002QSQ0 - CFA_11_06_Moat farm_Topsoil Strip Asset_Priority 2 | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSQ0 | #N/A | #N/A | #N/A
229.03 | HS2-00002CTET | IDR 229.03 | HS2-00002CTET | 2024-09-30 | 10 - Complete | 2024-10-04 |  | HS2-00002QSGG - CFA_11_72_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGG | #N/A | #N/A | #N/A
213.02-2 | HS2-00002CT76 | IDR 213.02-2 | HS2-00002CT76 | 2024-10-04 | 99 - Cancelled | 0 |  | HS2-00002QSGH - CFA_11_73_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGH | #N/A | #N/A | #N/A
213.02-2 | HS2-00002CT79 | IDR 213.02-2 | HS2-00002CT79 | 2024-10-04 | 10 - Complete | 2024-10-18 |  | HS2-00002QSGJ - CFA_11_74_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGJ | #N/A | #N/A | #N/A
204.4-2 | HS2-00002CT38 | IDR 204.4-2 | HS2-00002CT38 | 2024-10-07 | 10 - Complete | 2024-10-10 |  | HS2-00002QSGK - CFA_11_07_Standalls Farm_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGK | #N/A | #N/A | #N/A
204.4-2 | HS2-00002CT4F | IDR 204.4-2 | HS2-00002CT4F | 2024-10-07 | 10 - Complete | 2024-10-10 |  | HS2-00002QSQ1 - CFA_11_07_Standalls Farm_Topsoil Strip Asset_Priority 2 | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSQ1 | #N/A | #N/A | #N/A
233.01-3 | HS2-00003FV0Q | IDR 233.01-3 | HS2-00003FV0Q | 2024-10-11 | 10 - Complete | 2024-10-14 |  | HS2-00002QSGL - CFA_11_75_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGL | #N/A | #N/A | #N/A
230.05-2 | HS2-00002TTH0 | IDR 230.05-2 | HS2-00002TTH0 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-00002QSQ3 - CFA_11_75_Topsoil Strip Asset_Priority 2 | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSQ3 | #N/A | #N/A | #N/A
229.03 | HS2-00002BVKC | IDR 229.03 | HS2-00002BVKC | 2024-10-11 | 10 - Complete | 2024-10-16 |  | HS2-00002QSGM - CFA_11_76_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGM | #N/A | #N/A | #N/A
215.03 | HS2-00003GEER | IDR 215.03 | HS2-00003GEER | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-00002QSQ4 - CFA_11_76_Topsoil Strip Asset_Priority 2 | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSQ4 | #N/A | #N/A | #N/A
218.02-1 | HS2-0000307ZQ | IDR 218.02-1 | HS2-0000307ZQ | 2024-10-14 | 10 - Complete | 2024-10-17 |  | HS2-00002PXHA - Aylesbury Embankment General Demolition Assets | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXHA | #N/A | #N/A | #N/A
215.02-2 | HS2-00002CX36 | IDR 215.02-2 | HS2-00002CX36 | 2025-01-10 | 10 - Complete | 2025-01-17 |  | HS2-00002QSE3 - Aylesbury Embankment General Demolition Assets_Priority 2 | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSE3 | #N/A | #N/A | #N/A
229.03 | S` | IDR 229.03 | S` | 2024-10-15 | 10 - Complete | 2024-10-29 |  | HS2-00002QSGN - CFA_11_08_Aylesbuty Golf Course _Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGN | #N/A | #N/A | #N/A
233.01-3 | HS2-00003LA5E | IDR 233.01-3 | HS2-00003LA5E | 2024-10-15 | 10 - Complete | 2024-10-17 |  | HS2-00002QSQ2 - CFA_11_08_Aylesbuty Golf Course _Topsoil Strip Asset_Priority 2 | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSQ2 | #N/A | #N/A | #N/A
213.07-1 | HS2-00003CCK0 | IDR 213.07-1 | HS2-00003CCK0 | 2024-10-15 | 10 - Complete | 2024-10-18 |  | HS2-00002PXEJ - Aylesbury South Cutting_Ellen Road_Housing Estate Residences Demolition | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXEJ | #N/A | #N/A | #N/A
214.06 | HS2-000001309 | IDR 214.06 | HS2-000001309 | 2025-04-08 | 10 - Complete | 2025-04-09 |  | HS2-00002PXHC - Aylesbury North Cutting General Demolition Assets | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXHC | #N/A | #N/A | #N/A
214.06 | HS2-000001309 | IDR 214.06 | HS2-000001309 | 2025-04-08 | 10 - Complete | 2025-04-09 |  | HS2-00002PXLB - Aylesbury North Cutting General Demolition Assets_Priority 1 | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXLB | #N/A | #N/A | #N/A
214.06 | HS2-000001309 | IDR 214.06 | HS2-000001309 | 2025-04-08 | 10 - Complete | 2025-04-09 |  | HS2-00002PXMD - Aylesbury North Cutting General Demolition Assets_Priority 2 | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXMD | #N/A | #N/A | #N/A
213.08 | HS2-00002BJTN | IDR 213.08 | HS2-00002BJTN | 2024-10-15 | 10 - Complete | 2024-10-23 |  | HS2-00002QSGP - CFA_11_66_Park House_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGP | #N/A | #N/A | #N/A
212.5 | HS2-00002EKX8 | IDR 212.5 | HS2-00002EKX8 | 2024-10-15 | 10 - Complete | 2024-10-21 |  | HS2-00002QSGQ - CFA_11_77_Hartwell Cottage_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGQ | #N/A | #N/A | #N/A
212.5 | HS2-00002EKXA | IDR 212.5 | HS2-00002EKXA | 2024-10-15 | 10 - Complete | 2024-10-18 |  | HS2-00002PXEK - Aylesbury South Cutting_Oxford Road_Residence 1 Demolition | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXEK | #N/A | #N/A | #N/A
212.5 | HS2-00002EKXB | IDR 212.5 | HS2-00002EKXB | 2024-10-15 | 10 - Complete | 2024-10-18 |  | HS2-00002PXEL - Aylesbury South Cutting_Oxford Road_Residence 2 Demolition | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXEL | #N/A | #N/A | #N/A
212.5 | HS2-000035Q98 | IDR 212.5 | HS2-000035Q98 | 2024-10-16 | 10 - Complete | 2024-10-18 |  | HS2-00002QSGR - CFA_11_69_Glebe House_Topsoil Stripping Asset | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002QSGR | #N/A | #N/A | #N/A
212.5 | HS2-00003H078 | IDR 212.5 | HS2-00003H078 | 2024-10-16 | 10 - Complete | 2024-10-18 |  | HS2-00002PXEM - Aylesbury South Cutting_Oxford Road_Glebe House Demolition | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXEM | #N/A | #N/A | #N/A
212.5 | HS2-00003H07C | IDR 212.5 | HS2-00003H07C | 2024-10-16 | 10 - Complete | 2024-10-18 |  | HS2-00002PXEN - Aylesbury South Cutting_Oxford Road_Residence 3 Demolition | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXEN | #N/A | #N/A | #N/A
222.9 | HS2-00003KX2T | IDR 222.9 | HS2-00003KX2T | 2024-10-17 | 10 - Complete | 2024-10-18 |  | HS2-00002PXHE - Oxford Road Embankment General Demolition Assets | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXHE | #N/A | #N/A | #N/A
222.9 | HS2-00003KX2U | IDR 222.9 | HS2-00003KX2U | 2024-10-17 | 10 - Complete | 2024-10-18 |  | HS2-00002PXEP - Aylesbury South Cutting_Andrews Way_Fairford Lays Football BuildingDemolition | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXEP | #N/A | #N/A | #N/A
218.02-1 | HS2-0000307ZR | IDR 218.02-1 | HS2-0000307ZR | 2024-10-17 | 10 - Complete | 2024-10-24 |  | HS2-00002PXEQ - Aylesbury South Cutting_Andrews Way_Recreation Building 1 Demolition | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXEQ | #N/A | #N/A | #N/A
221.5 | HS2-00002CTB3 | IDR 221.5 | HS2-00002CTB3 | 2024-10-17 | 10 - Complete | 2024-10-23 |  | HS2-00002PXER - Aylesbury South Cutting_Andrews Way_Recreation Building 2 Demolition | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXER | #N/A | #N/A | #N/A
221.5 | HS2-00002CTB1 | IDR 221.5 | HS2-00002CTB1 | 2024-10-17 | 10 - Complete | 2024-10-23 |  | HS2-00002PXHG - Whaddon Hill Cutting General Demolition Assets | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXHG | #N/A | #N/A | #N/A
221.5 | HS2-00002CTAT | IDR 221.5 | HS2-00002CTAT | 2024-10-17 | 10 - Complete | 2024-10-23 |  | HS2-00002PXES - Aylesbury South Cutting_Whaddon Hill Farm_Residence Demolition | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXES | #N/A | #N/A | #N/A
221.5 | HS2-00002CTAR | IDR 221.5 | HS2-00002CTAR | 2024-10-17 | 10 - Complete | 2024-10-23 |  | HS2-00002PXET - Aylesbury South Cutting_ Whaddon Hill Farm_Barn Demolition | SC DATS 205 to 209 Aylesbury South Cutting to Whaddon Hill Cutting | #VALUE! | HS2-00002PXET | #N/A | #N/A | #N/A
221.5 | HS2-00002CTAH | IDR 221.5 | HS2-00002CTAH | 2024-10-17 | 10 - Complete | 2024-10-24 |  | HS2-00002QSNC - CFA_10_52_Land at Bacombe Lane_Topsoil Strip Asset_Priority 1 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSNC | #N/A | #N/A | #N/A
221.5 | HS2-00002CTAF | IDR 221.5 | HS2-00002CTAF | 2024-10-17 | 10 - Complete | 2024-10-22 |  | HS2-00002PXH5 - Wendover Green Tunnel General Demolition Assets | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002PXH5 | #N/A | #N/A | #N/A
221.5 | HS2-00002CTAA | IDR 221.5 | HS2-00002CTAA | 2024-10-17 | 10 - Complete | 2024-10-23 |  | HS2-00002PXL6 - Wendover Green Tunnel General Demolition Assets_Priority 1 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002PXL6 | #N/A | #N/A | #N/A
221.5 | HS2-00002CTA8 | IDR 221.5 | HS2-00002CTA8 | 2024-10-17 | 10 - Complete | 2024-10-30 |  | HS2-00002PXEC - Wendover Green Tunnel_Ellesborough Road_Residences Demolition | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002PXEC | #N/A | #N/A | #N/A
221.5 | HS2-00002CTBB | IDR 221.5 | HS2-00002CTBB | 2024-10-17 | 10 - Complete | 2024-10-23 |  | HS2-00002PXED - Wendover Green Tunnel_Wendover Cricket Club Demolition | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002PXED | #N/A | #N/A | #N/A
221.5 | HS2-00002CTB9 | IDR 221.5 | HS2-00002CTB9 | 2024-10-17 | 10 - Complete | 2024-10-23 |  | HS2-00002PXH6 - Wendover North Cutting General Demolition Assets | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002PXH6 | #N/A | #N/A | #N/A
219.1 | HS2-00002CT9Z | IDR 219.1 | HS2-00002CT9Z | 2025-02-24 | 10 - Complete | 2025-02-25 |  | HS2-00002PXL7 - Wendover North Cutting General Demolition Assets_Priority 1 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002PXL7 | #N/A | #N/A | #N/A
213.07-1 | HS2-00003LH5P | IDR 213.07-1 | HS2-00003LH5P | 2024-10-18 | 10 - Complete | 2024-10-28 |  | HS2-00002QSFK - CFA_10_16_Springfield Farm LTD_Topsoil Stripping Asset | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSFK | #N/A | #N/A | #N/A
229.03 | HS2-000001071 | IDR 229.03 | HS2-000001071 | 2024-10-18 | 10 - Complete | 2024-10-23 |  | HS2-00002QSNR - CFA_10_16_Springfield Farm LTD_Topsoil Strip Asset_Priority 1 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSNR | #N/A | #N/A | #N/A
221.5 | HS2-00002CTAN | IDR 221.5 | HS2-00002CTAN | 2024-10-18 | 10 - Complete | 2024-10-23 |  | HS2-00002QSR2 - CFA_10_16_Springfield Farm LTD_Topsoil Strip Asset_Priority 2 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSR2 | #N/A | #N/A | #N/A
221.5 | HS2-00002Y0AU | IDR 221.5 | HS2-00002Y0AU | 2024-10-18 | 10 - Complete | 2024-10-24 |  | HS2-00002QSFL - CFA_10_09b_Bank Farm_Topsoil Stripping Asset | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSFL | #N/A | #N/A | #N/A
215.03 | HS2-00002CT94 | IDR 215.03 | HS2-00002CT94 | 2024-10-18 | 10 - Complete | 2024-10-24 |  | HS2-00002QSNA - CFA_10_09b_Bank Farm_Topsoil Strip Asset_Priority 1 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSNA | #N/A | #N/A | #N/A
215.03 | HS2-00002CT92 | IDR 215.03 | HS2-00002CT92 | 2024-10-18 | 10 - Complete | 2024-10-28 |  | HS2-00002QSFM - CFA_10_12_Wellwick Farm_Topsoil Stripping Asset | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSFM | #N/A | #N/A | #N/A
229.01-2 | HS2-00002NJ04 | IDR 229.01-2 | HS2-00002NJ04 | 2024-10-21 | 10 - Complete | 2025-01-08 |  | HS2-00002QSNB - CFA_10_12_Wellwick Farm_Topsoil Strip Asset_Priority 1 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSNB | #N/A | #N/A | #N/A
229.01-2 | HS2-00002NJ04 | IDR 229.01-2 | HS2-00002NJ04 | 2024-10-21 | 10 - Complete | 2025-01-08 |  | HS2-00002QSFN - CFA_10_79_Topsoil Stripping Asset | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSFN | #N/A | #N/A | #N/A
229.01-2 | HS2-00002NJ04 | IDR 229.01-2 | HS2-00002NJ04 | 2024-10-21 | 10 - Complete | 2025-01-08 |  | HS2-00002QSNP - CFA_10_79_Topsoil Strip Asset_Priority 1 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSNP | #N/A | #N/A | #N/A
214.03-1 | HS2-00002KRAP | IDR 214.03-1 | HS2-00002KRAP | 2024-10-21 | 10 - Complete | 2024-10-30 |  | HS2-00002QSFP - CFA_10_80_Topsoil Stripping Asset | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSFP | #N/A | #N/A | #N/A
213.02-1 | HS2-00002BVGH | IDR 213.02-1 | HS2-00002BVGH | 2024-10-21 | 10 - Complete | 2024-10-30 |  | HS2-00002QSNU - CFA_10_80_Topsoil Strip Asset_Priority 1 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSNU | #N/A | #N/A | #N/A
230.05-2 | HS2-00002TTH0 | IDR 230.05-2 | HS2-00002TTH0 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-00002QSR5 - CFA_10_80_Topsoil Strip Asset_Priority 2 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSR5 | #N/A | #N/A | #N/A
229.01-2 | HS2-00002CTF6 | IDR 229.01-2 | HS2-00002CTF6 | 2024-10-22 | 10 - Complete | 2024-10-25 |  | HS2-00002QSFQ - CFA_10_55_Land at Nash Lee Ln Aylesbury HP17 0TQ_Topsoil Stripping Asset | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSFQ | #N/A | #N/A | #N/A
216.01-2 | HS2-00002CW0B | IDR 216.01-2 | HS2-00002CW0B | 2024-10-22 | 10 - Complete | 2024-11-12 |  | HS2-00002QSNS - CFA_10_55_Land at Nash Lee Ln Aylesbury HP17 0TQ_Topsoil Strip Asset_Priority 1 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSNS | #N/A | #N/A | #N/A
237.02 | HS2-00003GSK0 | IDR 237.02 | HS2-00003GSK0 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-00002QSR3 - CFA_10_55_Land at Nash Lee Ln Aylesbury HP17 0TQ_Topsoil Strip Asset_Priority 2 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSR3 | #N/A | #N/A | #N/A
237.02 | HS2-00003GSK1 | IDR 237.02 | HS2-00003GSK1 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-00002QSFR - CFA_10_81_Topsoil Stripping Asset | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSFR | #N/A | #N/A | #N/A
237.02 | HS2-00003GSK2 | IDR 237.02 | HS2-00003GSK2 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-00002QSNV - CFA_10_81_Topsoil Strip Asset_Priority 1 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSNV | #N/A | #N/A | #N/A
237.02 | HS2-00003GSK3 | IDR 237.02 | HS2-00003GSK3 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-00002QSR6 - CFA_10_81_Topsoil Strip Asset_Priority 2 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSR6 | #N/A | #N/A | #N/A
237.02 | HS2-00003GSK4 | IDR 237.02 | HS2-00003GSK4 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-00002QSFS - CFA_10_59_Topsoil Stripping Asset | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSFS | #N/A | #N/A | #N/A
237.02 | HS2-00003GSK5 | IDR 237.02 | HS2-00003GSK5 | 2024-10-22 | 10 - Complete | 2024-10-24 |  | HS2-00002QSNT - CFA_10_59_Topsoil Strip Asset_Priority 1 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSNT | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJP | IDR 221.5 | HS2-00003BPJP | 2024-10-22 | 10 - Complete | 2024-10-29 |  | HS2-00002QSR4 - CFA_10_59_Topsoil Strip Asset_Priority 2 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSR4 | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJQ | IDR 221.5 | HS2-00003BPJQ | 2024-10-22 | 10 - Complete | 2024-10-29 |  | HS2-00002PXEE - Wendover Green Tunnel_Nash Lee Road_Residence Demolition | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002PXEE | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJM | IDR 221.5 | HS2-00003BPJM | 2024-10-22 | 10 - Complete | 2024-10-30 |  | HS2-00002PXH7 - Stoke Mandeville South Embankment General Demolition Assets | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002PXH7 | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJN | IDR 221.5 | HS2-00003BPJN | 2024-10-22 | 10 - Complete | 2024-10-30 |  | HS2-00002QSE1 - Stoke Mandeville South Embankment General Demolition Assets_Priority 2 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSE1 | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJK | IDR 221.5 | HS2-00003BPJK | 2024-10-22 | 10 - Complete | 2024-10-25 |  | HS2-00002QSFT - CFA_10_14_Nash Lees Farm _Topsoil Stripping Asset | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSFT | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJL | IDR 221.5 | HS2-00003BPJL | 2024-10-22 | 10 - Complete | 2024-10-30 |  | HS2-00002QSNQ - CFA_10_14_Nash Lees Farm _Topsoil Strip Asset_Priority 1 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSNQ | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJJ | IDR 221.5 | HS2-00003BPJJ | 2024-10-22 | 10 - Complete | 2024-10-25 |  | HS2-00002QSR1 - CFA_10_14_Nash Lees Farm _Topsoil Strip Asset_Priority 2 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSR1 | #N/A | #N/A | #N/A
221.5 | HS2-00003BPK2 | IDR 221.5 | HS2-00003BPK2 | 2024-10-22 | 10 - Complete | 2024-10-29 |  | HS2-00002QSFU - CFA_11_13_Red House Farm_Topsoil Stripping Asset | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSFU | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJY | IDR 221.5 | HS2-00003BPJY | 2024-10-22 | 10 - Complete | 2024-10-30 |  | HS2-00002QSR7 - CFA_11_13_Red House Farm_Topsoil Strip Asset_Priority 2 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSR7 | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJZ | IDR 221.5 | HS2-00003BPJZ | 2024-10-22 | 10 - Complete | 2024-10-30 |  | HS2-00002QSFV - CFA_11_01_Stoke House_Topsoil Stripping Asset | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSFV | #N/A | #N/A | #N/A
221.5 | HS2-00003BPK3 | IDR 221.5 | HS2-00003BPK3 | 2024-10-22 | 10 - Complete | 2024-10-30 |  | HS2-00002QSPY - CFA_11_01_Stoke House_Topsoil Strip Asset_Priority 2 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSPY | #N/A | #N/A | #N/A
221.5 | HS2-00003BPK0 | IDR 221.5 | HS2-00003BPK0 | 2024-10-22 | 10 - Complete | 2024-11-05 |  | HS2-00002QSFW - CFA_11_59_Topsoil Stripping Asset | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSFW | #N/A | #N/A | #N/A
221.5 | HS2-00003BPK5 | IDR 221.5 | HS2-00003BPK5 | 2024-10-22 | 10 - Complete | 2024-11-04 |  | HS2-00002QSRA - CFA_11_59_Topsoil Strip Asset_Priority 2 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSRA | #N/A | #N/A | #N/A
221.5 | HS2-00003BPK1 | IDR 221.5 | HS2-00003BPK1 | 2024-10-22 | 10 - Complete | 2024-11-04 |  | HS2-00002QSFX - CFA_11_53_St Marys Church_Topsoil Stripping Asset | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSFX | #N/A | #N/A | #N/A
221.5 | HS2-00003BPK8 | IDR 221.5 | HS2-00003BPK8 | 2024-10-22 | 10 - Complete | 2024-11-04 |  | HS2-00002QSR9 - CFA_11_53_St Marys Church_Topsoil Strip Asset_Priority 2 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSR9 | #N/A | #N/A | #N/A
221.5 | HS2-00003BPKB | IDR 221.5 | HS2-00003BPKB | 2024-10-22 | 10 - Complete | 2024-11-04 |  | HS2-00002QSRB - CFA_11_61_Mill House Farm_Topsoil Strip Asset_Priority 2 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSRB | #N/A | #N/A | #N/A
221.5 | HS2-00003BPKD | IDR 221.5 | HS2-00003BPKD | 2024-10-22 | 10 - Complete | 2024-11-04 |  | HS2-00002QSR8 - CFA_11_12_Bucks Goat Centre_Topsoil Strip Asset_Priority 2 | SC DATS 203 to 204 Wendover Green Tunnel to Stoke Mandeville South Embankment | #VALUE! | HS2-00002QSR8 | #N/A | #N/A | #N/A
221.5 | HS2-00003BPKE | IDR 221.5 | HS2-00003BPKE | 2024-10-22 | 10 - Complete | 2024-11-04 |  | HS2-00002PXGX - South Heath Cutting General Demolition Assets | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXGX | #N/A | #N/A | #N/A
221.5 | HS2-00003BPK6 | IDR 221.5 | HS2-00003BPK6 | 2024-10-22 | 10 - Complete | 2024-11-04 |  | HS2-00002PXL2 - South Heath Cutting General Demolition Assets _Priority 1 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXL2 | #N/A | #N/A | #N/A
221.5 | HS2-00003BPK4 | IDR 221.5 | HS2-00003BPK4 | 2024-10-22 | 10 - Complete | 2024-11-04 |  | HS2-00002PXM6 - South Heath Cutting General Demolition Assets _Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXM6 | #N/A | #N/A | #N/A
221.5 | HS2-00003BPK9 | IDR 221.5 | HS2-00003BPK9 | 2024-10-22 | 10 - Complete | 2024-11-05 |  | HS2-00002QSEE - CFA_09_10_Park Farm_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSEE | #N/A | #N/A | #N/A
221.5 | HS2-00003BPK7 | IDR 221.5 | HS2-00003BPK7 | 2024-10-22 | 10 - Complete | 2024-11-04 |  | HS2-00002QSPG - CFA_09_10_Park Farm_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPG | #N/A | #N/A | #N/A
221.5 | HS2-00003BPKA | IDR 221.5 | HS2-00003BPKA | 2024-10-22 | 10 - Complete | 2024-10-28 |  | HS2-00002PXE8 - South Heath Cutting_Potter Row_Mulberry Hall and Residences Demolition | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXE8 | #N/A | #N/A | #N/A
221.5 | HS2-00003BPKC | IDR 221.5 | HS2-00003BPKC | 2024-10-22 | 10 - Complete | 2024-10-29 |  | HS2-00002QSEN - CFA_10_01_Hunts Green Farm_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSEN | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJS | IDR 221.5 | HS2-00003BPJS | 2024-10-22 | 10 - Complete | 2024-10-29 |  | HS2-00002QSPH - CFA_10_01_Hunts Green Farm_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPH | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJT | IDR 221.5 | HS2-00003BPJT | 2024-10-22 | 10 - Complete | 2024-10-29 |  | HS2-00002QSEP - CFA_10_02_Strawberry Hill Farm_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSEP | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJR | IDR 221.5 | HS2-00003BPJR | 2024-10-22 | 10 - Complete | 2024-10-29 |  | HS2-00002QSPK - CFA_10_02_Strawberry Hill Farm_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPK | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJU | IDR 221.5 | HS2-00003BPJU | 2024-10-22 | 10 - Complete | 2024-11-05 |  | HS2-00002QSEQ - CFA_10_61_Tree Copse_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSEQ | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJV | IDR 221.5 | HS2-00003BPJV | 2024-10-22 | 10 - Complete | 2024-11-05 |  | HS2-00002QSER - CFA_10_03_Durham Farm_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSER | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJX | IDR 221.5 | HS2-00003BPJX | 2024-10-22 | 10 - Complete | 2024-11-05 |  | HS2-00002PXGY - Wendover Dean South Embankment General Demolition Assets | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXGY | #N/A | #N/A | #N/A
221.5 | HS2-00003BPJW | IDR 221.5 | HS2-00003BPJW | 2024-10-22 | 10 - Complete | 2024-11-05 |  | HS2-00002PXL3 - Wendover Dean South EmbankmentGeneral Demolition Assets_Priority 1 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXL3 | #N/A | #N/A | #N/A
221.5 | HS2-00003BPKG | IDR 221.5 | HS2-00003BPKG | 2024-10-22 | 10 - Complete | 2024-11-05 |  | HS2-00002PXM7 - Wendover Dean South Embankment General Demolition Assets_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXM7 | #N/A | #N/A | #N/A
221.5 | HS2-00003BPKJ | IDR 221.5 | HS2-00003BPKJ | 2024-10-22 | 10 - Complete | 2024-11-07 |  | HS2-00002PXGZ - Wendover Dean Viaduct General Demolition Assets | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXGZ | #N/A | #N/A | #N/A
221.5 | HS2-00003BPKH | IDR 221.5 | HS2-00003BPKH | 2024-10-22 | 10 - Complete | 2024-11-07 |  | HS2-00002PXL4 - Wendover Dean Viaduct General Demolition Assets_Priority 1 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXL4 | #N/A | #N/A | #N/A
221.5 | HS2-00003BPKF | IDR 221.5 | HS2-00003BPKF | 2024-10-22 | 10 - Complete | 2024-11-07 |  | HS2-00002PXM8 - Wendover Dean Viaduct General Demolition Assets_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXM8 | #N/A | #N/A | #N/A
235.01-1 | HS2-00003LGKV | IDR 235.01-1 | HS2-00003LGKV | 2024-10-23 | 10 - Complete | 2024-10-25 |  | HS2-00002PXE9 - South Heath Cutting_Bowood Lane_Durham Farm Demolition | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXE9 | #N/A | #N/A | #N/A
229.01-2 | HS2-00002CUCC | IDR 229.01-2 | HS2-00002CUCC | 2024-10-23 | 10 - Complete | 2024-11-04 |  | HS2-00002QSES - CFA_10_05_ Upper Wendover Dean Farm _Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSES | #N/A | #N/A | #N/A
229.01-1 | HS2-00002TMF3 | IDR 229.01-1 | HS2-00002TMF3 | 2024-12-23 | 10 - Complete | 2025-01-17 |  | HS2-00002PXH0 - Wendover Dean North Embankment General Demolition Assets | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXH0 | #N/A | #N/A | #N/A
201.3-2 | HS2-000020134 | IDR 201.3-2 | HS2-000020134 | 2024-10-23 | 10 - Complete | 2024-11-13 |  | HS2-00002PXL5 - Wendover Dean North EmbankmentGeneral Demolition Assets_Priority 1 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXL5 | #N/A | #N/A | #N/A
233.01-3 | HS2-000035Q9A | IDR 233.01-3 | HS2-000035Q9A | 2024-10-25 | 10 - Complete | 2024-11-05 |  | HS2-00002PXM9 - Wendover Dean North Embankment General Demolition Assets_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXM9 | #N/A | #N/A | #N/A
233.01-3 | HS2-00003H5JH | IDR 233.01-3 | HS2-00003H5JH | 2024-10-25 | 10 - Complete | 2024-11-05 |  | HS2-00002PXH1 - Rocky Lane Cutting General Demolition Assets | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXH1 | #N/A | #N/A | #N/A
UFDR 211.A | HS2-00003KUMA | UFDR 211.A | HS2-00003KUMA | 2024-12-12 | 10 - Complete | 2024-12-13 |  | HS2-00002QSET - CFA_10_08_Boswells Farm_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSET | #N/A | #N/A | #N/A
233.01-3 | HS2-00003FV0R | IDR 233.01-3 | HS2-00003FV0R | 2024-10-25 | 10 - Complete | 2024-11-05 |  | HS2-00002QSPL - CFA_10_08_Boswells Farm_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPL | #N/A | #N/A | #N/A
229.03 | HS2-00002CTEU | IDR 229.03 | HS2-00002CTEU | 2024-10-25 | 10 - Complete | 2024-10-30 |  | HS2-00002QSEU - CFA_10_63_Hartley Farm_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSEU | #N/A | #N/A | #N/A
214.06 | HS2-000001310 | IDR 214.06 | HS2-000001310 | 2024-10-25 | 10 - Complete | 2024-11-06 |  | HS2-00002PXH2 - Small Dean South Embankment General Demolition Assets | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXH2 | #N/A | #N/A | #N/A
UFDR 214.A | HS2-00002TUPJ | UFDR 214.A | HS2-00002TUPJ | 2024-10-25 | 10 - Complete | 2024-10-31 |  | HS2-00002PXMA - Small Dean South Embankment General Demolition Assets _Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXMA | #N/A | #N/A | #N/A
UFDR 214.A | HS2-00002TUPF | UFDR 214.A | HS2-00002TUPF | 2024-10-25 | 10 - Complete | 2024-10-30 |  | HS2-00002QSEV - CFA_10_62_TBC_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSEV | #N/A | #N/A | #N/A
UFDR 214.A | HS2-00003KFPT | UFDR 214.A | HS2-00003KFPT | 2024-10-25 | 10 - Complete | 2024-10-30 |  | HS2-00002QSPR - CFA_10_62_TBC_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPR | #N/A | #N/A | #N/A
UFDR 214.A | HS2-00003E24S | UFDR 214.A | HS2-00003E24S | 2024-10-25 | 10 - Complete | 2024-10-30 |  | HS2-00002QSEW - CFA_10_65_Rocketer_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSEW | #N/A | #N/A | #N/A
UFDR 214.A | HS2-00002YCLK | UFDR 214.A | HS2-00002YCLK | 2024-10-25 | 10 - Complete | 2024-10-31 |  | HS2-00002QSPS - CFA_10_65_Rocketer_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPS | #N/A | #N/A | #N/A
UFDR 214.A | HS2-00002TUPG | UFDR 214.A | HS2-00002TUPG | 2024-10-25 | 10 - Complete | 2024-10-30 |  | HS2-00002QSEY - CFA_10_64_The Laurels_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSEY | #N/A | #N/A | #N/A
UFDR 214.A | HS2-00002TUPH | UFDR 214.A | HS2-00002TUPH | 2024-10-31 | 10 - Complete | 2024-11-04 |  | HS2-00002QSEZ - CFA_10_51_Chiltern Milion London Road Wendover HP22 6PN_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSEZ | #N/A | #N/A | #N/A
226.2 | HS2-00002Y4JL | IDR 226.2 | HS2-00002Y4JL | 2025-01-24 | 10 - Complete | 2025-01-30 |  | HS2-00002QSPQ - CFA_10_51_Chiltern Milion London Road Wendover HP22 6PN_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPQ | #N/A | #N/A | #N/A
222.9 | HS2-00003D82W | IDR 222.9 | HS2-00003D82W | 2024-10-28 | 10 - Complete | 2024-11-07 |  | HS2-00002QSF0 - CFA_10_08a_Road Barn Farm_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSF0 | #N/A | #N/A | #N/A
222.9 | HS2-00003D82X | IDR 222.9 | HS2-00003D82X | 2024-10-28 | 10 - Complete | 2024-11-07 |  | HS2-00002QSPM - CFA_10_08a_Road Barn Farm_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPM | #N/A | #N/A | #N/A
222.9 | HS2-00003D82Y | IDR 222.9 | HS2-00003D82Y | 2024-10-28 | 10 - Complete | 2024-11-07 |  | HS2-00002QSF1 - CFA_10_67_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSF1 | #N/A | #N/A | #N/A
222.9 | HS2-00003D82Z | IDR 222.9 | HS2-00003D82Z | 2024-10-28 | 10 - Complete | 2024-11-07 |  | HS2-00002QSPU - CFA_10_67_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPU | #N/A | #N/A | #N/A
222.9 | HS2-00003D832 | IDR 222.9 | HS2-00003D832 | 2024-10-28 | 10 - Complete | 2024-11-11 |  | HS2-00002PXEA - South Heath Cutting_Road Barn Farm_Residence Demolition | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXEA | #N/A | #N/A | #N/A
222.9 | HS2-00003D833 | IDR 222.9 | HS2-00003D833 | 2024-10-28 | 10 - Complete | 2024-11-08 |  | HS2-00002PXH3 - Small Dean Viaduct General Demolition Assets | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXH3 | #N/A | #N/A | #N/A
222.9 | HS2-00003D834 | IDR 222.9 | HS2-00003D834 | 2024-10-28 | 10 - Complete | 2024-11-11 |  | HS2-00002PXMB - Small Dean Viaduct General Demolition Assets _Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXMB | #N/A | #N/A | #N/A
222.9 | HS2-00003D835 | IDR 222.9 | HS2-00003D835 | 2024-10-28 | 10 - Complete | 2024-11-11 |  | HS2-00002PXEB - South Heath Cutting_Railway Overbridge Demolition | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXEB | #N/A | #N/A | #N/A
222.9 | HS2-00003D836 | IDR 222.9 | HS2-00003D836 | 2024-10-28 | 10 - Complete | 2024-11-11 |  | HS2-00002QSF2 - CFA_10_66_Verges_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSF2 | #N/A | #N/A | #N/A
222.9 | HS2-00003D837 | IDR 222.9 | HS2-00003D837 | 2024-10-28 | 10 - Complete | 2024-11-11 |  | HS2-00002QSPT - CFA_10_66_Verges_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPT | #N/A | #N/A | #N/A
222.9 | HS2-00003D838 | IDR 222.9 | HS2-00003D838 | 2024-10-28 | 10 - Complete | 2024-11-11 |  | HS2-00002QSF3 - CFA_10_69_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSF3 | #N/A | #N/A | #N/A
222.9 | HS2-00003D839 | IDR 222.9 | HS2-00003D839 | 2024-10-28 | 10 - Complete | 2024-11-11 |  | HS2-00002QSPV - CFA_10_69_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPV | #N/A | #N/A | #N/A
222.9 | HS2-00003D83A | IDR 222.9 | HS2-00003D83A | 2024-10-28 | 10 - Complete | 2024-11-11 |  | HS2-00002PXH4 - Small Dean North Embankment General Demolition Assets | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXH4 | #N/A | #N/A | #N/A
222.9 | HS2-00003D83B | IDR 222.9 | HS2-00003D83B | 2024-10-28 | 10 - Complete | 2024-11-12 |  | HS2-00002PXMC - Small Dean North Embankment General Demolition Assets _Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002PXMC | #N/A | #N/A | #N/A
222.9 | HS2-00003D83C | IDR 222.9 | HS2-00003D83C | 2024-10-28 | 10 - Complete | 2024-11-12 |  | HS2-00002QSF4 - CFA_10_11_Smalldean Farm_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSF4 | #N/A | #N/A | #N/A
222.9 | HS2-00003D83D | IDR 222.9 | HS2-00003D83D | 2024-10-28 | 10 - Complete | 2024-11-12 |  | HS2-00002QSPP - CFA_10_11_Smalldean Farm_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPP | #N/A | #N/A | #N/A
222.9 | HS2-00003D83E | IDR 222.9 | HS2-00003D83E | 2024-10-28 | 10 - Complete | 2024-11-12 |  | HS2-00002QSF5 - CFA_10_71_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSF5 | #N/A | #N/A | #N/A
222.9 | HS2-00003D83F | IDR 222.9 | HS2-00003D83F | 2024-10-28 | 10 - Complete | 2024-11-13 |  | HS2-00002QSPX - CFA_10_71_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPX | #N/A | #N/A | #N/A
222.9 | HS2-00003D83G | IDR 222.9 | HS2-00003D83G | 2024-10-28 | 10 - Complete | 2024-11-13 |  | HS2-00002QSF6 - CFA_10_10_Grove Farm_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSF6 | #N/A | #N/A | #N/A
222.9 | HS2-00003D83J | IDR 222.9 | HS2-00003D83J | 2024-10-28 | 10 - Complete | 2024-11-13 |  | HS2-00002QSPN - CFA_10_10_Grove Farm_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPN | #N/A | #N/A | #N/A
222.9 | HS2-00003D83K | IDR 222.9 | HS2-00003D83K | 2024-10-28 | 10 - Complete | 2025-01-24 |  | HS2-00002QSF7 - CFA_10_52_Land at Bacombe Lane_Topsoil Stripping Asset | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSF7 | #N/A | #N/A | #N/A
222.9 | HS2-00003D83L | IDR 222.9 | HS2-00003D83L | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-00002QSPW - CFA_10_52_Land at Bacombe Lane_Topsoil Strip Asset_Priority 2 | SC DATS 201 to 202 South Heath Cutting to Small Dean North Embankment | #VALUE! | HS2-00002QSPW | #N/A | #N/A | #N/A
222.9 | HS2-00003D83M | IDR 222.9 | HS2-00003D83M | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-000037YM0 - Archaeological Recording at Aylesbury Park Golf Course | PXA - Routewide PXA (Post Excavation Assessment) | PXA | HS2-000037YM0 | #N/A | #N/A | #N/A
222.9 | HS2-00003D83N | IDR 222.9 | HS2-00003D83N | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-00002CT42 - CSO-02-3106T | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002CT42 | #N/A | #N/A | #N/A
222.9 | HS2-00003D83P | IDR 222.9 | HS2-00003D83P | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-00002BVP2 - C23-059-0006 | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002BVP2 | #N/A | #N/A | #N/A
222.9 | HS2-00003D83Q | IDR 222.9 | HS2-00003D83Q | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-000001406 - Lower Hartwell No. 3 Culvert | PE 0003 - Routewide Information Package | PE 0003 | HS2-000001406 | #N/A | #N/A | #N/A
222.9 | HS2-00003D83R | IDR 222.9 | HS2-00003D83R | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-00002TUPR - CSO-02-1230P | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002TUPR | #N/A | #N/A | #N/A
222.9 | HS2-00003D83S | IDR 222.9 | HS2-00003D83S | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-00002NNJ0 - FCC Sheephouse Wood Highway Access | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002NNJ0 | #N/A | #N/A | #N/A
222.9 | HS2-00003D83T | IDR 222.9 | HS2-00003D83T | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-00002TTR5 - CSO-03-3111P | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002TTR5 | #N/A | #N/A | #N/A
222.9 | HS2-00003D83U | IDR 222.9 | HS2-00003D83U | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-000020CFY - CSO-03-1300 | PE 0003 - Routewide Information Package | PE 0003 | HS2-000020CFY | #N/A | #N/A | #N/A
222.9 | HS2-00003D83V | IDR 222.9 | HS2-00003D83V | 2025-02-20 | 10 - Complete | 2025-02-24 |  | HS2-00002TTR4 - Charndon Lodge UB PS Substation | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002TTR4 | #N/A | #N/A | #N/A
222.9 | HS2-00003D84T | IDR 222.9 | HS2-00003D84T | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-00002FE9L - C23-097-0001 | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002FE9L | #N/A | #N/A | #N/A
222.9 | HS2-00003D84U | IDR 222.9 | HS2-00003D84U | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-00002PW6A - C23-097-0001T | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002PW6A | #N/A | #N/A | #N/A
222.9 | HS2-00003D84Z | IDR 222.9 | HS2-00003D84Z | 2024-10-28 | 10 - Complete | 2025-01-24 |  | HS2-00002VZUJ - C23-107-0001 | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002VZUJ | #N/A | #N/A | #N/A
222.9 | HS2-00003D850 | IDR 222.9 | HS2-00003D850 | 2024-10-28 | 10 - Complete | 2025-01-24 |  | HS2-0000245ZL - CSO-04-6112 | PE 0003 - Routewide Information Package | PE 0003 | HS2-0000245ZL | #N/A | #N/A | #N/A
222.9 | HS2-00003D854 | IDR 222.9 | HS2-00003D854 | 2024-10-28 | 10 - Complete | 2025-01-23 |  | HS2-000020CJB - CSO-04-3112 | PE 0003 - Routewide Information Package | PE 0003 | HS2-000020CJB | #N/A | #N/A | #N/A
222.9 | HS2-00003FV0S | IDR 222.9 | HS2-00003FV0S | 2024-10-28 | 10 - Complete | 2025-01-23 |  | HS2-000020CJC - CSO-04-6106 | PE 0003 - Routewide Information Package | PE 0003 | HS2-000020CJC | #N/A | #N/A | #N/A
222.9 | HS2-00003D855 | IDR 222.9 | HS2-00003D855 | 2024-10-28 | 10 - Complete | 2025-01-23 |  | HS2-00002FEA2 - C23-108-0001 | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002FEA2 | #N/A | #N/A | #N/A
222.9 | HS2-00003D857 | IDR 222.9 | HS2-00003D857 | 2024-10-28 | 10 - Complete | 2025-01-23 |  | HS2-00002VZUG - C23-108-0002 | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002VZUG | #N/A | #N/A | #N/A
222.9 | HS2-00003D858 | IDR 222.9 | HS2-00003D858 | 2024-10-28 | 10 - Complete | 2025-01-23 |  | HS2-00002VZUH - C23-108-0003 | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002VZUH | #N/A | #N/A | #N/A
222.9 | HS2-00003D85A | IDR 222.9 | HS2-00003D85A | 2024-10-28 | 10 - Complete | 2025-01-23 |  | HS2-0000245ZW - CSO-04-6122 | PE 0003 - Routewide Information Package | PE 0003 | HS2-0000245ZW | #N/A | #N/A | #N/A
222.9 | HS2-00003D85B | IDR 222.9 | HS2-00003D85B | 2024-10-28 | 10 - Complete | 2025-01-23 |  | HS2-0000245ZX - CSO-04-6123 | PE 0003 - Routewide Information Package | PE 0003 | HS2-0000245ZX | #N/A | #N/A | #N/A
222.9 | HS2-00003D85C | IDR 222.9 | HS2-00003D85C | 2024-10-28 | 10 - Complete | 2025-01-23 |  | HS2-00002UU9M - C23-126-0001 | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002UU9M | #N/A | #N/A | #N/A
222.9 | HS2-00003D85D | IDR 222.9 | HS2-00003D85D | 2024-10-28 | 10 - Complete | 2025-01-23 |  | HS2-00002UU9N - C23-126-0001A | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002UU9N | #N/A | #N/A | #N/A
222.9 | HS2-00003D85E | IDR 222.9 | HS2-00003D85E | 2024-10-28 | 10 - Complete | 2025-01-23 |  | HS2-00002XP3R - EWM32 SWM033 Canal-Boddington Canal Feeder | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP3R | #N/A | #N/A | #N/A
233.01-3 | HS2-00003LCQE | IDR 233.01-3 | HS2-00003LCQE | 2024-10-28 | 10 - Complete | 2024-11-25 |  | HS2-00002XP3S - EWM33 SWM032 Canal-Boddington Canal Feeder | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP3S | #N/A | #N/A | #N/A
233.01-3 | HS2-00003LCQD | IDR 233.01-3 | HS2-00003LCQD | 2024-10-28 | 10 - Complete | 2024-11-06 |  | HS2-00002XP3T - EWM34 SWM034 Canal-Oxford Canal | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP3T | #N/A | #N/A | #N/A
222.9 | HS2-00003KX2V | IDR 222.9 | HS2-00003KX2V | 2024-10-28 | 10 - Complete | 2024-12-23 |  | HS2-00002XP3U - EWM35 SWM035 Canal-Oxford Canal | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP3U | #N/A | #N/A | #N/A
222.9 | HS2-00003KX2W | IDR 222.9 | HS2-00003KX2W | 2024-10-28 | 10 - Complete | 2024-12-23 |  | HS2-00002XP3V - EWM318 SWM040 Pond-Cottisford Pond | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP3V | #N/A | #N/A | #N/A
222.9 | HS2-0000386UD | IDR 222.9 | HS2-0000386UD | 2024-10-28 | 10 - Complete | 2024-12-23 |  | HS2-00002XP3W - EWM321 SWM038 Pond-Shelswell South | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP3W | #N/A | #N/A | #N/A
230.05-2 | HS2-00002CTG8 | IDR 230.05-2 | HS2-00002CTG8 | 2024-10-28 | 10 - Complete | 2024-10-30 |  | HS2-00002XP3X - EWM1 SWM001 River-Nash Lee Orchard Watercourses | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP3X | #N/A | #N/A | #N/A
215.03 | HS2-00003GEER | IDR 215.03 | HS2-00003GEER | 2024-10-28 | 10 - Complete | 2024-11-14 |  | HS2-00002XP3Y - EWM2 SWM002 River-Nash Lee Orchard Watercourses | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP3Y | #N/A | #N/A | #N/A
208.2 | HS2-00002SZLX | IDR 208.2 | HS2-00002SZLX | 2024-10-29 | 30 - Sent back to team | 0 |  | HS2-00002XP3Z - EWM3 SWM003 River-Stoke Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP3Z | #N/A | #N/A | #N/A
206.1-2 | HS2-00002WUTU | IDR 206.1-2 | HS2-00002WUTU | 2024-10-29 | 10 - Complete | 2024-11-08 |  | HS2-00002XP40 - EWM4 SWM004 River-Stoke Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP40 | #N/A | #N/A | #N/A
206.1-2 | HS2-00002WUTV | IDR 206.1-2 | HS2-00002WUTV | 2024-10-29 | 10 - Complete | 2024-11-08 |  | HS2-00002XP41 - EWM5 SWM005 River-Stoke Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP41 | #N/A | #N/A | #N/A
206.1-2 | HS2-00002WUTW | IDR 206.1-2 | HS2-00002WUTW | 2024-10-29 | 10 - Complete | 2024-11-08 |  | HS2-00002XP42 - EWM6 SWM007 River-River Thame | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP42 | #N/A | #N/A | #N/A
206.1-2 | HS2-00002WUTX | IDR 206.1-2 | HS2-00002WUTX | 2024-10-29 | 10 - Complete | 2024-11-08 |  | HS2-00002XP43 - EWM7 SWM006 River-River Thame | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP43 | #N/A | #N/A | #N/A
206.1-2 | HS2-00002WUTY | IDR 206.1-2 | HS2-00002WUTY | 2024-10-29 | 10 - Complete | 2024-11-08 |  | HS2-00002XP44 - EWM8 SWM008 River-River Ray | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP44 | #N/A | #N/A | #N/A
206.1-2 | HS2-00002WUTZ | IDR 206.1-2 | HS2-00002WUTZ | 2024-10-29 | 10 - Complete | 2024-11-08 |  | HS2-00002XP45 - EWM9 SWM009 River-River Ray | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP45 | #N/A | #N/A | #N/A
208.2 | HS2-00002CT5P | IDR 208.2 | HS2-00002CT5P | 2024-10-29 | 10 - Complete | 2024-11-12 |  | HS2-00002XP46 - EWM11 SWM010 River-Muxwell Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP46 | #N/A | #N/A | #N/A
215.01-2 | HS2-000001044 | IDR 215.01-2 | HS2-000001044 | 2024-11-21 | 10 - Complete | 2025-01-07 |  | HS2-00002XP47 - EWM20 SWM021 River-Great Ouse | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP47 | #N/A | #N/A | #N/A
222.9 | HS2-00003JAYD | IDR 222.9 | HS2-00003JAYD | 2024-10-29 | 10 - Complete | 2024-11-14 |  | HS2-00002XP48 - EWM21 SWM020 River-Great Ouse | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP48 | #N/A | #N/A | #N/A
222.9 | HS2-00003JAYE | IDR 222.9 | HS2-00003JAYE | 2024-10-29 | 10 - Complete | 2024-11-13 |  | HS2-00002XP49 - EWM22 SWM024 River-Great Ouse | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP49 | #N/A | #N/A | #N/A
233.01-3 | HS2-00003LGKW | IDR 233.01-3 | HS2-00003LGKW | 2024-10-30 | 10 - Complete | 2024-11-11 |  | HS2-00002XP4A - EWM23 SWM023 River-Great Ouse | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4A | #N/A | #N/A | #N/A
233.01-3 | HS2-00003LGKX | IDR 233.01-3 | HS2-00003LGKX | 2024-10-30 | 10 - Complete | 2024-11-08 |  | HS2-00002XP4B - EWM24 SWM022 River-Great Ouse | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4B | #N/A | #N/A | #N/A
215.03 | HS2-00003GNA4 | IDR 215.03 | HS2-00003GNA4 | 2024-10-31 | 10 - Complete | 2024-11-07 |  | HS2-00002XP4C - EWM28 SWM028 River-Cherwell | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4C | #N/A | #N/A | #N/A
215.03 | HS2-00003GNA3 | IDR 215.03 | HS2-00003GNA3 | 2024-10-31 | 10 - Complete | 2024-11-06 |  | HS2-00002XP4D - EWM29 SWM029 River-Cherwell | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4D | #N/A | #N/A | #N/A
215.03 | HS2-00002TTH1 | IDR 215.03 | HS2-00002TTH1 | 2024-10-31 | 10 - Complete | 2024-11-06 |  | HS2-00002XP4E - EWM30 SWM031 River-Highfurlong Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4E | #N/A | #N/A | #N/A
229.03 | HS2-00003JYH5 | IDR 229.03 | HS2-00003JYH5 | 2024-10-31 | 10 - Complete | 2024-11-07 |  | HS2-00002XP4F - EWM31 SWM030 River-Highfurlong Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4F | #N/A | #N/A | #N/A
229.03 | HS2-00003JYH6 | IDR 229.03 | HS2-00003JYH6 | 2024-10-31 | 10 - Complete | 2024-11-07 |  | HS2-00002XP4G - EWM291 SWM042 River-River Great Ouse | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4G | #N/A | #N/A | #N/A
229.03 | HS2-00003JYH7 | IDR 229.03 | HS2-00003JYH7 | 2024-10-31 | 10 - Complete | 2024-11-07 |  | HS2-00002XP4H - EWM10 SWM011 Stream-Muxwell Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4H | #N/A | #N/A | #N/A
229.03 | HS2-00003JYH2 | IDR 229.03 | HS2-00003JYH2 | 2024-10-31 | 10 - Complete | 2024-11-07 |  | HS2-00002XP4J - EWM12 SWM012 Stream-Calvert | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4J | #N/A | #N/A | #N/A
229.03 | HS2-00003JYH3 | IDR 229.03 | HS2-00003JYH3 | 2024-10-31 | 10 - Complete | 2024-11-07 |  | HS2-00002XP4K - EWM13 SWM013 Stream-Calvert | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4K | #N/A | #N/A | #N/A
229.03 | HS2-00003JYH4 | IDR 229.03 | HS2-00003JYH4 | 2024-10-31 | 10 - Complete | 2024-11-07 |  | HS2-00002XP4L - EWM14 SWM015 Stream-Padbury Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4L | #N/A | #N/A | #N/A
212.5 | HS2-00003KFPP | IDR 212.5 | HS2-00003KFPP | 2024-10-31 | 10 - Complete | 2024-11-14 |  | HS2-00002XP4M - EWM15 SWM014 Stream-Padbury Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4M | #N/A | #N/A | #N/A
212.5 | HS2-00003KFPQ | IDR 212.5 | HS2-00003KFPQ | 2024-10-31 | 10 - Complete | 2024-11-19 |  | HS2-00002XP4N - EWM16 SWM017 Stream-Padbury Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4N | #N/A | #N/A | #N/A
212.5 | HS2-00003KFPR | IDR 212.5 | HS2-00003KFPR | 2024-10-31 | 10 - Complete | 2024-11-19 |  | HS2-00002XP4P - EWM17 SWM016 Stream-Padbury Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4P | #N/A | #N/A | #N/A
212.5 | HS2-00003KFPS | IDR 212.5 | HS2-00003KFPS | 2024-10-31 | 10 - Complete | 2024-11-19 |  | HS2-00002XP4Q - EWM18 SWM019 Stream-Padbury Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4Q | #N/A | #N/A | #N/A
UFDR 216.I | HS2-00003GEEP | UFDR 216.I | HS2-00003GEEP | 2024-10-31 | 10 - Complete | 2024-12-03 |  | HS2-00002XP4R - EWM19 SWM018 Stream-Padbury Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4R | #N/A | #N/A | #N/A
215.03 | HS2-00003LGKQ | IDR 215.03 | HS2-00003LGKQ | 2024-11-01 | 10 - Complete | 2024-11-11 |  | HS2-00002XP4S - EWM25 SWM025 Stream-Radstone Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4S | #N/A | #N/A | #N/A
201.0-1 | HS2-00002CT2G | IDR 201.0-1 | HS2-00002CT2G | 2024-11-04 | 10 - Complete | 2024-11-29 |  | HS2-00002XP4T - EWM26 SWM026 Stream-Radstone Brook | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4T | #N/A | #N/A | #N/A
212.5 | HS2-00003KR5H | IDR 212.5 | HS2-00003KR5H | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-00002XP4U - EWM27 SWM027 Stream-Cherwell | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4U | #N/A | #N/A | #N/A
212.5 | HS2-00003KR5J | IDR 212.5 | HS2-00003KR5J | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-00002XP4V - EWM36 SWM037 Stream-Itchen | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4V | #N/A | #N/A | #N/A
212.5 | HS2-00003LCQ9 | IDR 212.5 | HS2-00003LCQ9 | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-00002XP4W - EWM37 SWM036 Stream-Itchen | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4W | #N/A | #N/A | #N/A
212.5 | HS2-00003LCQA | IDR 212.5 | HS2-00003LCQA | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-00002XP4X - EWM292 SWM043 Stream-Mixbury stream | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4X | #N/A | #N/A | #N/A
212.5 | HS2-00003LGKN | IDR 212.5 | HS2-00003LGKN | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-00002XP4Y - EWM308 SWM041 Stream-Cottisford Stream | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4Y | #N/A | #N/A | #N/A
212.5 | HS2-00003LGKP | IDR 212.5 | HS2-00003LGKP | 2024-11-20 | 10 - Complete | 2024-11-22 |  | HS2-00002XP4Z - EWM310 SWM039 Stream-Shelswell North | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XP4Z | #N/A | #N/A | #N/A
235.01 | HS2-00003LA5C | IDR 235.01 | HS2-00003LA5C | 2024-11-05 | 10 - Complete | 2024-11-12 |  | HS2-00002XRJX - Turweston Causeway Temporary Bridges | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XRJX | #N/A | #N/A | #N/A
235.01 | HS2-00003LA5D | IDR 235.01 | HS2-00003LA5D | 2024-11-05 | 10 - Complete | 2024-11-12 |  | HS2-00002XRJY - Twyford Temporary Bridge | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XRJY | #N/A | #N/A | #N/A
201.0-1 | HS2-00002CT2D | IDR 201.0-1 | HS2-00002CT2D | 2024-11-05 | 10 - Complete | 2024-11-29 |  | HS2-00002XRJZ - Westbury Temporary Bridge | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XRJZ | #N/A | #N/A | #N/A
212.5 | HS2-00002WULZ | IDR 212.5 | HS2-00002WULZ | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-00002XRK0 - A421 Temporary Bridge | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XRK0 | #N/A | #N/A | #N/A
212.5 | HS2-00002WUM0 | IDR 212.5 | HS2-00002WUM0 | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-00002XRK1 - A422 Temporary Bridge | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002XRK1 | #N/A | #N/A | #N/A
212.5 | HS2-00002WUM1 | IDR 212.5 | HS2-00002WUM1 | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-00002Y0RQ - Steeple Claydon to Twyford (West Street) Temporary Highway Diversion | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002Y0RQ | #N/A | #N/A | #N/A
212.5 | HS2-00002WUM2 | IDR 212.5 | HS2-00002WUM2 | 2024-11-05 | 10 - Complete | 2024-11-21 |  | HS2-00002YA8D - Addison Temporary Highway Diversion | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002YA8D | #N/A | #N/A | #N/A
212.5 | HS2-00002WUM3 | IDR 212.5 | HS2-00002WUM3 | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-00002ZGD0 - CNO-125-013 | PE 0003 - Routewide Information Package | PE 0003 | HS2-00002ZGD0 | #N/A | #N/A | #N/A
212.5 | HS2-00002WUM4 | IDR 212.5 | HS2-00002WUM4 | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-000030KBB - C23-115-0004 | PE 0003 - Routewide Information Package | PE 0003 | HS2-000030KBB | #N/A | #N/A | #N/A
212.5 | HS2-00002WUM5 | IDR 212.5 | HS2-00002WUM5 | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-000030KBC - C23-071-0001 | PE 0003 - Routewide Information Package | PE 0003 | HS2-000030KBC | #N/A | #N/A | #N/A
212.5 | HS2-00002WUM6 | IDR 212.5 | HS2-00002WUM6 | 2024-11-05 | 10 - Complete | 2024-11-21 |  | HS2-000030KBD - C23-071-0002 | PE 0003 - Routewide Information Package | PE 0003 | HS2-000030KBD | #N/A | #N/A | #N/A
212.5 | HS2-00002WUM7 | IDR 212.5 | HS2-00002WUM7 | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-000030KBE - C23-071-0003 | PE 0003 - Routewide Information Package | PE 0003 | HS2-000030KBE | #N/A | #N/A | #N/A
212.5 | HS2-00002WUM8 | IDR 212.5 | HS2-00002WUM8 | 2024-11-05 | 10 - Complete | 2024-11-21 |  | HS2-000031GXU - Greatworth Park Bat House | PE 0003 - Routewide Information Package | PE 0003 | HS2-000031GXU | #N/A | #N/A | #N/A
212.5 | HS2-00002WUM9 | IDR 212.5 | HS2-00002WUM9 | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-0000325TL - C23-071-0004 | PE 0003 - Routewide Information Package | PE 0003 | HS2-0000325TL | #N/A | #N/A | #N/A
212.5 | HS2-00002WULP | IDR 212.5 | HS2-00002WULP | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-0000326GV - C23-080-0001 | PE 0003 - Routewide Information Package | PE 0003 | HS2-0000326GV | #N/A | #N/A | #N/A
212.5 | HS2-00002WULQ | IDR 212.5 | HS2-00002WULQ | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-00002EKZM - Ladbroke Ecological Mitigation Site (F) | PE 0001 - EK PEP | PE 0001 | HS2-00002EKZM | #N/A | #N/A | #N/A
212.5 | HS2-00002WULR | IDR 212.5 | HS2-00002WULR | 2024-11-05 | 10 - Complete | 2024-11-20 |  | HS2-000030TCZ - UTX Claydon East Junction | PE 0001 - EK PEP | PE 0001 | HS2-000030TCZ | #N/A | #N/A | #N/A
212.5 | HS2-00002WULS | IDR 212.5 | HS2-00002WULS | 2024-11-05 | 10 - Complete | 2024-11-19 |  | HS2-000030TD0 - UTX Claydon Reception East Junction | PE 0001 - EK PEP | PE 0001 | HS2-000030TD0 | #N/A | #N/A | #N/A
212.5 | HS2-00002WULT | IDR 212.5 | HS2-00002WULT | 2024-11-05 | 10 - Complete | 2024-11-21 |  | HS2-000030TD1 - UTX Claydon Reception West Junction | PE 0001 - EK PEP | PE 0001 | HS2-000030TD1 | #N/A | #N/A | #N/A
212.5 | HS2-00002WULU | IDR 212.5 | HS2-00002WULU | 2024-11-05 | 10 - Complete | 0 |  | HS2-000030TD2 - UTX Claydon West Junction | PE 0001 - EK PEP | PE 0001 | HS2-000030TD2 | #N/A | #N/A | #N/A
212.5 | HS2-00002WULV | IDR 212.5 | HS2-00002WULV | 2024-11-05 | 10 - Complete | 2024-11-21 |  | HS2-000030TD3 - UTX Claydon Junction | PE 0001 - EK PEP | PE 0001 | HS2-000030TD3 | #N/A | #N/A | #N/A
212.5 | HS2-00002WULW | IDR 212.5 | HS2-00002WULW | 2024-11-05 | 10 - Complete | 2024-11-21 |  | HS2-00002TTL1 - Calvert Infrastructure Maintenance Depot Group Monitoring System | IM 0004 - Early Works Instrumentation and Monitoring Package 4 | IM 0004 | HS2-00002TTL1 | #N/A | #N/A | #N/A
212.5 | HS2-00002WULX | IDR 212.5 | HS2-00002WULX | 2024-11-05 | 10 - Complete | 2024-11-21 |  | HS2-00002TTHP - Aylesbury South Cutting Group Monitoring System | IM 0004 - Early Works Instrumentation and Monitoring Package 4 | IM 0004 | HS2-00002TTHP | #N/A | #N/A | #N/A
212.5 | HS2-00002WULY | IDR 212.5 | HS2-00002WULY | 2024-11-05 | 10 - Complete | 2024-11-25 |  | HS2-00002TTHT - Whaddon Hill Cutting Group Monitoring System | IM 0004 - Early Works Instrumentation and Monitoring Package 4 | IM 0004 | HS2-00002TTHT | #N/A | #N/A | #N/A
212.5 | HS2-00002WUMA | IDR 212.5 | HS2-00002WUMA | 2024-11-05 | 10 - Complete | 2024-11-25 |  | HS2-00002TTHW - Thame Valley North Embankment Group Monitoring System | IM 0004 - Early Works Instrumentation and Monitoring Package 4 | IM 0004 | HS2-00002TTHW | #N/A | #N/A | #N/A
212.5 | HS2-00002WUMB | IDR 212.5 | HS2-00002WUMB | 2024-11-05 | 10 - Complete | 2024-11-25 |  | HS2-00002TTHX - Putlowes Cutting Group Monitoring System | IM 0004 - Early Works Instrumentation and Monitoring Package 4 | IM 0004 | HS2-00002TTHX | #N/A | #N/A | #N/A
212.5 | HS2-00002WUMC | IDR 212.5 | HS2-00002WUMC | 2024-11-05 | 10 - Complete | 2024-11-25 |  | HS2-00002TTJ8 - Twyford Embankment Group Monitoring System | IM 0004 - Early Works Instrumentation and Monitoring Package 4 | IM 0004 | HS2-00002TTJ8 | #N/A | #N/A | #N/A
212.5 | HS2-00002WUMD | IDR 212.5 | HS2-00002WUMD | 2024-11-05 | 10 - Complete | 2024-11-25 |  | HS2-00002TTKT - Ladbroke Grove Cutting Group Monitoring System | IM 0004 - Early Works Instrumentation and Monitoring Package 4 | IM 0004 | HS2-00002TTKT | #N/A | #N/A | #N/A
212.5 | HS2-00002WUME | IDR 212.5 | HS2-00002WUME | 2024-11-05 | 10 - Complete | 2024-11-25 |  | HS2-00002TTKV - Ladbroke Cutting Group Monitoring System | IM 0004 - Early Works Instrumentation and Monitoring Package 4 | IM 0004 | HS2-00002TTKV | #N/A | #N/A | #N/A
212.5 | HS2-00002WUMF | IDR 212.5 | HS2-00002WUMF | 2024-11-05 | 10 - Complete | 2024-11-28 |  | HS2-00002TTJV - Brackley South Cutting Group Monitoring System | IM 0003 - Early Works Instrumentation and Monitoring Package 3 | IM 0003 | HS2-00002TTJV | #N/A | #N/A | #N/A
212.5 | HS2-00002WUMG | IDR 212.5 | HS2-00002WUMG | 2024-11-05 | 10 - Complete | 2024-11-28 |  | HS2-00002TTHM - Wendover North Cutting Group Monitoring System | IM 0002 - Early Works Instrumentation and Monitoring Package 2 | IM 0002 | HS2-00002TTHM | #N/A | #N/A | #N/A
212.5 | HS2-00002WUMH | IDR 212.5 | HS2-00002WUMH | 2024-11-05 | 10 - Complete | 2024-11-28 |  | HS2-00002TTJH - Chetwode Cutting Group Monitoring System | IM 0002 - Early Works Instrumentation and Monitoring Package 2 | IM 0002 | HS2-00002TTJH | #N/A | #N/A | #N/A
212.5 | HS2-00002WUMJ | IDR 212.5 | HS2-00002WUMJ | 2024-11-05 | 10 - Complete | 2024-11-28 |  | HS2-00002TTKK - Boddington Cutting Group Monitoring System | IM 0002 - Early Works Instrumentation and Monitoring Package 2 | IM 0002 | HS2-00002TTKK | #N/A | #N/A | #N/A
212.5 | HS2-00002WUMK | IDR 212.5 | HS2-00002WUMK | 2024-11-05 | 10 - Complete | 2024-11-28 |  | HS2-00002TTHR - Aylesbury North Cutting Group Monitoring System | IM 0001 - Early Works Instrumentation and Monitoring Package 1 | IM 0001 | HS2-00002TTHR | #N/A | #N/A | #N/A
212.5 | HS2-00002WUML | IDR 212.5 | HS2-00002WUML | 2024-11-05 | 10 - Complete | 2024-11-28 |  | HS2-00002TTHZ - Waddesdon South Cutting Group Monitoring System | IM 0001 - Early Works Instrumentation and Monitoring Package 1 | IM 0001 | HS2-00002TTHZ | #N/A | #N/A | #N/A
215.03 | HS2-00003KUM9 | IDR 215.03 | HS2-00003KUM9 | 2024-11-05 | 10 - Complete | 2024-11-14 |  | HS2-00002TTHB - Greatworth Green Tunnel Group Monitoring System | IM 0001 - Early Works Instrumentation and Monitoring Package 1 | IM 0001 | HS2-00002TTHB | #N/A | #N/A | #N/A
UFDR 217.B | HS2-00002C3X7 | UFDR 217.B | HS2-00002C3X7 | 2024-11-05 | 10 - Complete | 2024-12-04 |  | HS2-00002TTK2 - Thorpe Mandeville Embankment Group Monitoring System | IM 0001 - Early Works Instrumentation and Monitoring Package 1 | IM 0001 | HS2-00002TTK2 | #N/A | #N/A | #N/A
234.05 | HS2-000020351 | IDR 234.05 | HS2-000020351 | 2024-11-05 | 10 - Complete | 2024-12-04 |  | HS2-00002TTKE - Aston le Walls Embankment Group Monitoring System | IM 0001 - Early Works Instrumentation and Monitoring Package 1 | IM 0001 | HS2-00002TTKE | #N/A | #N/A | #N/A
215.03 | HS2-00003124D | IDR 215.03 | HS2-00003124D | 2024-11-05 | 10 - Complete | 2024-11-11 |  | HS2-00002TTKG - Highfurlong Brook Embankment Group Monitoring System | IM 0001 - Early Works Instrumentation and Monitoring Package 1 | IM 0001 | HS2-00002TTKG | #N/A | #N/A | #N/A
215.03 | HS2-00003FV0H | IDR 215.03 | HS2-00003FV0H | 2024-11-05 | 10 - Complete | 2024-11-11 |  | HS2-00002CTKS - Mill Pond Embankment Boundary Perimeter Fence Line | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-00002CTKS | #N/A | #N/A | #N/A
201.0-1 | HS2-00002Y849 | IDR 201.0-1 | HS2-00002Y849 | 2024-11-06 | 10 - Complete | 2024-11-27 |  | HS2-00002CTKT - Mill Pond Embankment Security Fence Line | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-00002CTKT | #N/A | #N/A | #N/A
215.03 | HS2-00003KUM8 | IDR 215.03 | HS2-00003KUM8 | 2024-11-07 | 10 - Complete | 2024-11-14 |  | HS2-000001104 - Mill Pond Embankment | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-000001104 | #N/A | #N/A | #N/A
223.4 | HS2-000001329 | IDR 223.4 | HS2-000001329 | 2025-03-28 | 30 - Sent back to team | 0 |  | HS2-00002CTKW - River Itchen Diversion | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-00002CTKW | #N/A | #N/A | #N/A
220 | HS2-000001050 | IDR 220 | HS2-000001050 | 2024-11-08 | 50 - HOLD | 0 |  | HS2-000001105 - River Itchen Viaduct | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-000001105 | #N/A | #N/A | #N/A
220 | HS2-000001052 | IDR 220 | HS2-000001052 | 2024-11-08 | 50 - HOLD | 0 |  | HS2-00002DVEB - River Itchen Viaduct Planting | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-00002DVEB | #N/A | #N/A | #N/A
233.01-3 | HS2-00003JRGA | IDR 233.01-3 | HS2-00003JRGA | 2024-11-08 | 10 - Complete | 2024-11-15 |  | HS2-000020AVK - Footpath SM24 Diversion | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-000020AVK | #N/A | #N/A | #N/A
215.03 | HS2-00003JAYB | IDR 215.03 | HS2-00003JAYB | 2024-11-08 | 10 - Complete | 2024-11-15 |  | HS2-00002BVNU - C3.T.79 Catchment | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-00002BVNU | #N/A | #N/A | #N/A
213.07-1 | HS2-00002CT73 | IDR 213.07-1 | HS2-00002CT73 | 2024-11-11 | 10 - Complete | 2024-12-10 |  | HS2-000001106 - Leamington Road Embankment | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-000001106 | #N/A | #N/A | #N/A
213.07-1 | HS2-00002CT72 | IDR 213.07-1 | HS2-00002CT72 | 2024-11-11 | 10 - Complete | 2024-12-10 |  | HS2-00002WUTR - Mill Pond Embankment Planting-East Plot 1 | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-00002WUTR | #N/A | #N/A | #N/A
212.4 | HS2-00002Y47A | IDR 212.4 | HS2-00002Y47A | 2024-11-11 | 10 - Complete | 2025-01-09 |  | HS2-00002WUTT - Mill Pond Embankment Planting-West Plot 1 | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-00002WUTT | #N/A | #N/A | #N/A
212.5 | HS2-00003JKXR | IDR 212.5 | HS2-00003JKXR | 2024-11-11 | 10 - Complete | 2024-11-19 |  | HS2-00002Y03R - C3.L.79 Catchment | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-00002Y03R | #N/A | #N/A | #N/A
233.01-3 | HS2-00003JRG9 | IDR 233.01-3 | HS2-00003JRG9 | 2024-11-12 | 10 - Complete | 2024-11-15 |  | HS2-000031G3Q - River Itchen Viaduct Bearing Access Stairs | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-000031G3Q | #N/A | #N/A | #N/A
216.01-2 | HS2-00002VK46 | IDR 216.01-2 | HS2-00002VK46 | 2024-11-12 | 10 - Complete | 0 |  | HS2-00003A04E - River Itchen Viaduct Group Ditch Crossing 01 | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-00003A04E | #N/A | #N/A | #N/A
216.01-2 | HS2-00002ZJQJ | IDR 216.01-2 | HS2-00002ZJQJ | 2024-11-12 | 10 - Complete | 0 |  | HS2-00003A04F - River Itchen Viaduct Group Ditch Crossing 02 | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-00003A04F | #N/A | #N/A | #N/A
233.01-3 | HS2-000020NXK | IDR 233.01-3 | HS2-000020NXK | 2024-11-12 | 10 - Complete | 2024-12-02 |  | HS2-00003CCK9 - Mill Pond Embankment Landscape Earthworks | IDR 239.04 - River Itchen Viaduct Group Full Package | IDR 239.04 | HS2-00003CCK9 | #N/A | #N/A | #N/A
233.01-3 | HS2-000020NXM | IDR 233.01-3 | HS2-000020NXM | 2024-11-12 | 10 - Complete | 2024-12-02 |  | HS2-00002BVNK - C3.L.78 Catchment | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002BVNK | #N/A | #N/A | #N/A
233.01-3 | HS2-000035Q99 | IDR 233.01-3 | HS2-000035Q99 | 2024-11-12 | 10 - Complete | 2024-12-03 |  | HS2-00002BVNM - Southam Cutting Landscape Earthworks | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002BVNM | #N/A | #N/A | #N/A
238.02 | HS2-00002J4YY | IDR 238.02 | HS2-00002J4YY | 2024-11-12 | 10 - Complete | 2024-11-21 |  | HS2-00002CTKN - C3.T.77 Catchment | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002CTKN | #N/A | #N/A | #N/A
215.03 | HS2-00003H6P1 | IDR 215.03 | HS2-00003H6P1 | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-00002CTKP - Southam Cutting Boundary Perimeter Fence Line | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002CTKP | #N/A | #N/A | #N/A
215.03 | HS2-00003H6P2 | IDR 215.03 | HS2-00003H6P2 | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-00002CTKQ - Southam Cutting Security Fence Line | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002CTKQ | #N/A | #N/A | #N/A
215.03 | HS2-00003H6P3 | IDR 215.03 | HS2-00003H6P3 | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-00002TTKX - Southam Cutting Group Monitoring System | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002TTKX | #N/A | #N/A | #N/A
215.03 | HS2-00003H6P4 | IDR 215.03 | HS2-00003H6P4 | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-000001103 - Southam Cutting | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-000001103 | #N/A | #N/A | #N/A
215.03 | HS2-00003H6P5 | IDR 215.03 | HS2-00003H6P5 | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-000020P3A - The Fields House Accommodation Access Road | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-000020P3A | #N/A | #N/A | #N/A
215.03 | HS2-00003H6P6 | IDR 215.03 | HS2-00003H6P6 | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-000025B3X - B4451 Kineton Road Realignment | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-000025B3X | #N/A | #N/A | #N/A
215.03 | HS2-00003H6P7 | IDR 215.03 | HS2-00003H6P7 | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-00002C3Z5 - B4451 Kineton Road Drainage System | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002C3Z5 | #N/A | #N/A | #N/A
215.03 | HS2-00003H6P8 | IDR 215.03 | HS2-00003H6P8 | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-00002V04H - Southam Cutting Access Stairs 1 | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002V04H | #N/A | #N/A | #N/A
215.03 | HS2-00003H6P9 | IDR 215.03 | HS2-00003H6P9 | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-00002EKZP - Southam Ecological Mitigation Site (B) | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002EKZP | #N/A | #N/A | #N/A
215.03 | HS2-00003H6PA | IDR 215.03 | HS2-00003H6PA | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-00002EKZQ - Southam Ecological Mitigation Site (C) | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002EKZQ | #N/A | #N/A | #N/A
215.03 | HS2-00003H6PB | IDR 215.03 | HS2-00003H6PB | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-000020P3J - Maintenance Access Road to Pond (Off Leamington Road) | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-000020P3J | #N/A | #N/A | #N/A
215.03 | HS2-00003H6PC | IDR 215.03 | HS2-00003H6PC | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-00002WUTM - Southam Cutting Planting-East Plot 1 | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002WUTM | #N/A | #N/A | #N/A
215.03 | HS2-00003H6PD | IDR 215.03 | HS2-00003H6PD | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-00002WUTN - Southam Cutting Planting-East Plot 2 | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002WUTN | #N/A | #N/A | #N/A
215.03 | HS2-00003H6PE | IDR 215.03 | HS2-00003H6PE | 2024-11-12 | 10 - Complete | 2024-11-14 |  | HS2-00002WUTP - Southam Cutting Planting-West Plot 1 | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002WUTP | #N/A | #N/A | #N/A
213.07-1 | HS2-0000307ZS | IDR 213.07-1 | HS2-0000307ZS | 2024-11-12 | 10 - Complete | 2024-12-19 |  | HS2-00002WUTQ - Southam Cutting Planting-West Plot 2 | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-00002WUTQ | #N/A | #N/A | #N/A
213.07-1 | HS2-00002Z3NH | IDR 213.07-1 | HS2-00002Z3NH | 2024-11-12 | 10 - Complete | 2024-12-19 |  | HS2-000030RKU - Southam Cutting Ditch Crossing 1 | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-000030RKU | #N/A | #N/A | #N/A
212.5 | HS2-00003HWH6 | IDR 212.5 | HS2-00003HWH6 | 2024-11-13 | 10 - Complete | 2024-11-21 |  | HS2-000030RKV - Leamington Pond Retaining Wall | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-000030RKV | #N/A | #N/A | #N/A
212.5 | HS2-00003HWH5 | IDR 212.5 | HS2-00003HWH5 | 2024-11-13 | 10 - Complete | 2024-11-21 |  | HS2-000031F3K - Southam Cutting Group Utilities Protection Slab | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-000031F3K | #N/A | #N/A | #N/A
212.5 | HS2-00003HWH4 | IDR 212.5 | HS2-00003HWH4 | 2024-11-13 | 10 - Complete | 2024-11-21 |  | HS2-0000367HD - Southam Ecological Mitigation Site (D) (LS129) | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-0000367HD | #N/A | #N/A | #N/A
212.5 | HS2-00003LQUL | IDR 212.5 | HS2-00003LQUL | 2024-11-13 | 10 - Complete | 2024-11-22 |  | HS2-000038CDK - Southam Cutting Access Stairs 2 | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-000038CDK | #N/A | #N/A | #N/A
212.5 | HS2-00003LQUM | IDR 212.5 | HS2-00003LQUM | 2024-11-13 | 10 - Complete | 2024-11-22 |  | HS2-000038CDL - Southam Cutting Access Stairs 3 | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-000038CDL | #N/A | #N/A | #N/A
214.01-2 | HS2-00002BJTY | IDR 214.01-2 | HS2-00002BJTY | 2024-11-13 | 30 - Sent back to team | 0 |  | HS2-000038CDN - Southam Cutting Access Stairs 4 | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-000038CDN | #N/A | #N/A | #N/A
214.01-2 | HS2-00002BJTU | IDR 214.01-2 | HS2-00002BJTU | 2024-11-13 | 50 - HOLD | 0 |  | HS2-000038CDP - Southam Cutting Access Stairs 5 | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-000038CDP | #N/A | #N/A | #N/A
214.01-2 | HS2-00002BJTX | IDR 214.01-2 | HS2-00002BJTX | 2024-11-13 | 50 - HOLD | 0 |  | HS2-000038CDR - Southam Cutting Ditch Crossing 2 | IDR 239.02-2 - Southam Cutting Remaining Assets | IDR 239.02-2 | HS2-000038CDR | #N/A | #N/A | #N/A
214.01-2 | HS2-00002CT82 | IDR 214.01-2 | HS2-00002CT82 | 2024-11-13 | 50 - HOLD | 0 |  | HS2-000001466 - B4451 Kineton Road Overbridge | IDR 239.02-1 - B4451 Kineton Road Overbridge | IDR 239.02-1 | HS2-000001466 | #N/A | #N/A | #N/A
229.01-2 | HS2-00002CTF9 | IDR 229.01-2 | HS2-00002CTF9 | 2024-11-13 | 10 - Complete | 2024-12-10 |  | HS2-000001102 - Southam Embankment | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-000001102 | #N/A | #N/A | #N/A
229.01-2 | HS2-00003B2GD | IDR 229.01-2 | HS2-00003B2GD | 2024-11-13 | 10 - Complete | 2024-12-18 |  | HS2-00002EKZN - Southam Ecological Mitigation Site (A) | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-00002EKZN | #N/A | #N/A | #N/A
221.5 | HS2-00002Y4JJ | IDR 221.5 | HS2-00002Y4JJ | 2024-11-13 | 10 - Complete | 2024-11-14 |  | HS2-00002BVNH - Southam Embankment Landscape Earthworks | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-00002BVNH | #N/A | #N/A | #N/A
UFDR 229.D | HS2-000020CJ5 | UFDR 229.D | HS2-000020CJ5 | 2024-11-13 | 10 - Complete | 2024-11-21 |  | HS2-00002CTKK - Southam Embankment Boundary Perimeter Fence Line | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-00002CTKK | #N/A | #N/A | #N/A
UFDR 229.D | HS2-000020CJ4 | UFDR 229.D | HS2-000020CJ4 | 2024-11-13 | 10 - Complete | 2024-11-21 |  | HS2-00002CTKL - Southam Embankment Security Fence Line | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-00002CTKL | #N/A | #N/A | #N/A
UFDR 229.D | HS2-000020CJ3 | UFDR 229.D | HS2-000020CJ3 | 2024-11-13 | 10 - Complete | 2024-11-21 |  | HS2-00002TTKW - Southam Embankment Group Monitoring System | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-00002TTKW | #N/A | #N/A | #N/A
UFDR 229.D | HS2-00003KLDE | UFDR 229.D | HS2-00003KLDE | 2024-11-13 | 10 - Complete | 2024-11-21 |  | HS2-00002WUTE - Southam Embankment Planting-East Plot 1 | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-00002WUTE | #N/A | #N/A | #N/A
UFDR 229.D | HS2-00003KLDD | UFDR 229.D | HS2-00003KLDD | 2024-11-13 | 10 - Complete | 2024-11-21 |  | HS2-00002WUTF - Southam Embankment Planting-East Plot 2 | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-00002WUTF | #N/A | #N/A | #N/A
UFDR 229.D | HS2-00003KLDC | UFDR 229.D | HS2-00003KLDC | 2024-11-13 | 10 - Complete | 2024-11-21 |  | HS2-00002WUTJ - Southam Embankment Planting-West Plot 2 | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-00002WUTJ | #N/A | #N/A | #N/A
UFDR 229.D | HS2-00003CPXB | UFDR 229.D | HS2-00003CPXB | 2024-11-13 | 10 - Complete | 2024-11-21 |  | HS2-00002WUTK - Southam Embankment Planting-West Plot 3 | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-00002WUTK | #N/A | #N/A | #N/A
227 | HS2-00002NNHW | IDR 227 | HS2-00002NNHW | 2024-11-15 | 10 - Complete | 2024-12-04 |  | HS2-000030RKX - C3.L.76-2 Catchment | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-000030RKX | #N/A | #N/A | #N/A
229.01-2 | HS2-00002WUPB | IDR 229.01-2 | HS2-00002WUPB | 2024-11-15 | 10 - Complete | 2024-12-11 |  | HS2-000031F3M - Southam Embankment Ditch Crossing 1 | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-000031F3M | #N/A | #N/A | #N/A
229.01-2 | HS2-00002WUPC | IDR 229.01-2 | HS2-00002WUPC | 2024-11-15 | 10 - Complete | 0 |  | HS2-000038DM5 - Southam Embankment Ditch Crossing 2 | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-000038DM5 | #N/A | #N/A | #N/A
229.01-2 | HS2-00002WUPD | IDR 229.01-2 | HS2-00002WUPD | 2024-11-15 | 10 - Complete | 2024-12-11 |  | HS2-000038DM6 - Southam Embankment Ditch Crossing 3 | IDR 239.01-2 - Southam Embankment Remaining Assets | IDR 239.01-2 | HS2-000038DM6 | #N/A | #N/A | #N/A
229.01-2 | HS2-00002WUPE | IDR 229.01-2 | HS2-00002WUPE | 2024-11-15 | 99 - Cancelled | 0 |  | HS2-000001465 - Southam Culvert | IDR 239.01-1 - Southam Embankment Culverts | IDR 239.01-1 | HS2-000001465 | #N/A | #N/A | #N/A
229.01-2 | HS2-00002WUPF | IDR 229.01-2 | HS2-00002WUPF | 2024-11-15 | 10 - Complete | 2024-12-11 |  | HS2-00002PBEG - Southam Flood Plain Culvert 02 | IDR 239.01-1 - Southam Embankment Culverts | IDR 239.01-1 | HS2-00002PBEG | #N/A | #N/A | #N/A
229.01-2 | HS2-00002WUPG | IDR 229.01-2 | HS2-00002WUPG | 2024-11-15 | 10 - Complete | 2024-12-11 |  | HS2-00002PBEH - Southam Flood Plain Culvert 03 | IDR 239.01-1 - Southam Embankment Culverts | IDR 239.01-1 | HS2-00002PBEH | #N/A | #N/A | #N/A
229.01-2 | HS2-00002WUPH | IDR 229.01-2 | HS2-00002WUPH | 2024-11-15 | 10 - Complete | 2024-12-12 |  | HS2-00002PBEJ - Southam Flood Plain Culvert 04 | IDR 239.01-1 - Southam Embankment Culverts | IDR 239.01-1 | HS2-00002PBEJ | #N/A | #N/A | #N/A
202.1-3 | HS2-00003H07E | IDR 202.1-3 | HS2-00003H07E | 2024-11-15 | 10 - Complete | 2024-12-10 |  | HS2-000001464 - A423 Banbury Road Overbridge | IDR 238.03 - A423 Banbury Road Overbridge - EI-318 Advanced Asset | IDR 238.03 | HS2-000001464 | 2024-12-03 | 10 - Complete | 2024-01-14
202.1-3 | HS2-00003H07D | IDR 202.1-3 | HS2-00003H07D | 2024-11-15 | 10 - Complete | 2024-12-10 |  | HS2-00002CTKB - Windmill Lane Drainage System | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-00002CTKB | #N/A | #N/A | #N/A
201.0-1 | HS2-000001016 | IDR 201.0-1 | HS2-000001016 | 2024-11-15 | 10 - Complete | 2024-11-29 |  | HS2-00002DVE7 - Ladbroke Cutting Planting | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-00002DVE7 | #N/A | #N/A | #N/A
201.0-1 | HS2-00002XQ2N | IDR 201.0-1 | HS2-00002XQ2N | 2024-11-15 | 10 - Complete | 2024-11-29 |  | HS2-00002EKZG - Windmill Lane Green Overbridge Ecological Mitigation Site | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-00002EKZG | #N/A | #N/A | #N/A
222.9 | HS2-00003D830 | IDR 222.9 | HS2-00003D830 | 2024-11-18 | 10 - Complete | 2025-01-03 |  | HS2-00002EKZH - Ladbroke Ecological Mitigation Site (C) | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-00002EKZH | #N/A | #N/A | #N/A
222.9 | HS2-00003D831 | IDR 222.9 | HS2-00003D831 | 2024-11-18 | 10 - Complete | 2025-01-03 |  | HS2-00002N7UU - Ladbroke Cutting Group-Ancillary Culvert 122-AC1 | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-00002N7UU | 2023-12-15 | 10 - Complete | 2023-12-18
222.9 | HS2-00003D84X | IDR 222.9 | HS2-00003D84X | 2024-11-18 | 10 - Complete | 2025-01-03 |  | HS2-00002BK0B - Windmill Lane Realignment | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-00002BK0B | #N/A | #N/A | #N/A
222.9 | HS2-00003D84Y | IDR 222.9 | HS2-00003D84Y | 2024-11-18 | 10 - Complete | 2025-01-03 |  | HS2-00002EKZJ - Ladbroke Ecological Mitigation Site (B) | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-00002EKZJ | #N/A | #N/A | #N/A
233.01-3 | HS2-000020NXG | IDR 233.01-3 | HS2-000020NXG | 2024-11-19 | 10 - Complete | 2024-12-11 |  | HS2-00002VJVV - Ladbroke Hill Farm Accommodation Access Road | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-00002VJVV | #N/A | #N/A | #N/A
UFDR 209.A | HS2-000020CF0 | UFDR 209.A | HS2-000020CF0 | 2024-11-19 | 10 - Complete | 2024-12-02 |  | HS2-000020P27 - Footpath SM90 Diversion | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-000020P27 | #N/A | #N/A | #N/A
UFDR 209.A | HS2-00002SZLY | UFDR 209.A | HS2-00002SZLY | 2025-03-26 | 10 - Complete | 2025-03-27 |  | HS2-00002EKZK - Ladbroke Ecological Mitigation Site (D) | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-00002EKZK | #N/A | #N/A | #N/A
238.02 | HS2-00003LCQC | IDR 238.02 | HS2-00003LCQC | 2024-11-19 | 10 - Complete | 0 |  | HS2-00002EKZL - Ladbroke Ecological Mitigation Site (E) | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-00002EKZL | #N/A | #N/A | #N/A
229.01-2 | HS2-00003B2GE | IDR 229.01-2 | HS2-00003B2GE | 2024-11-19 | 10 - Complete | 2024-12-12 |  | HS2-00003LH5J - Ecological Pond (1) - East Ch. 124+030 | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-00003LH5J | #N/A | #N/A | #N/A
238.02 | HS2-00002CTKE | IDR 238.02 | HS2-00002CTKE | 2024-11-19 | 10 - Complete | 2024-11-22 |  | HS2-00003LH5K - Ecological Pond (1) - East Ch. 124+450 | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-00003LH5K | #N/A | #N/A | #N/A
238.02 | HS2-000020P2P | IDR 238.02 | HS2-000020P2P | 2024-11-19 | 10 - Complete | 2024-11-25 |  | HS2-00003LH5L - Ecological Ponds (2) - West Ch. 124+500 | IDR 238.02-3 - WINDMILL LANE REALIGNMENT AND REMAINING ASSETS FROM LADBROKE CUTTING | IDR 238.02-3 | HS2-00003LH5L | #N/A | #N/A | #N/A
238.02 | HS2-00002C3Z1 | IDR 238.02 | HS2-00002C3Z1 | 2024-11-19 | 10 - Complete | 2024-11-26 |  | HS2-00002BVNE - Ladbroke Cutting Landscape Earthworks | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00002BVNE | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-00002CTKA - C3.L.76 Catchment | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00002CTKA | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-00002CTKC - C3.T.72 Catchment | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00002CTKC | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-00002CTKD - C3.T.74 Catchment | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00002CTKD | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-00002CTKF - Ladbroke Cutting Boundary Perimeter Fence Line | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00002CTKF | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-00002CTKG - Ladbroke Cutting Security Fence Line | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00002CTKG | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-000001101 - Ladbroke Cutting | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-000001101 | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-00002TKV2 - Windmill Lane Radio Compound UTX | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00002TKV2 | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-000033BZ6 - Maintenance Access Road to GSMR Point 59 (off Windmill Lane) and Compound | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-000033BZ6 | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-00003AQDD - Ladbroke Cutting Access Stairs-1 CH.122+770 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003AQDD | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-00003AQDE - Ladbroke Cutting Access Stairs-2 CH.122+803 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003AQDE | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-00003CCK5 - Ladbroke Cutting Access Stairs-5 CH.124+550 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003CCK5 | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-00003JP9K - Drainage of Maintenance Access Road to GSMR Point 59 (off Windmill Lane) and Compound | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003JP9K | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-00003JP9L - Ladbroke Cutting Access Stairs-3 CH.122+884 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003JP9L | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-00003JP9M - Ladbroke Cutting Access Stairs-4 CH.124+560 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003JP9M | #N/A | #N/A | #N/A
229.01-2 | HS2-000025B2F | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0 |  | HS2-00003JPBM - Ladbroke Cutting Ditch Crossing 01 CH.122+550 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003JPBM | #N/A | #N/A | #N/A
212.4 | HS2-00003B93V | IDR 212.4 | HS2-00003B93V | 2024-11-20 | 10 - Complete | 2025-01-08 |  | HS2-00003JPBN - Ladbroke Cutting Ditch Crossing 02 CH.123+530 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003JPBN | #N/A | #N/A | #N/A
UFDR 216.I | HS2-00002TTR2 | UFDR 216.I | HS2-00002TTR2 | 2024-11-20 | 10 - Complete | 2024-12-02 |  | HS2-00003JPBP - Ladbroke Cutting Ditch Crossing 03 CH.124+150 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003JPBP | #N/A | #N/A | #N/A
216.01-2 | HS2-00002NNHQ | IDR 216.01-2 | HS2-00002NNHQ | 2024-11-20 | 10 - Complete | 2024-12-13 |  | HS2-00003JPBQ - Ladbroke Cutting Ditch Crossing 04 CH.122+620 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003JPBQ | #N/A | #N/A | #N/A
217.03 | HS2-000001314 | IDR 217.03 | HS2-000001314 | 2024-11-20 | 50 - HOLD | 0 |  | HS2-00003JPBR - Ladbroke Cutting Ditch Crossing 05 CH.124+060 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003JPBR | #N/A | #N/A | #N/A
238.02 | HS2-00003EB33 | IDR 238.02 | HS2-00003EB33 | 2024-11-20 | 10 - Complete | 2024-11-25 |  | HS2-00003JPBS - Ladbroke Cutting Ditch Crossing 06 CH.124+540 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003JPBS | #N/A | #N/A | #N/A
212.5 | HS2-00003LGKP | IDR 212.5 | HS2-00003LGKP | 2024-11-20 | 10 - Complete | 2024-11-22 |  | HS2-00003K2XW - Ladbroke Cutting Ditch Crossing 07 CH.123+275 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003K2XW | #N/A | #N/A | #N/A
224.7 | HS2-00003HF3T | IDR 224.7 | HS2-00003HF3T | 2024-11-20 | 10 - Complete | 2024-11-29 |  | HS2-00003K2XX - Ladbroke Cutting Ditch Crossing 08 CH.123+470 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003K2XX | #N/A | #N/A | #N/A
212.5 | HS2-00002CT5A | IDR 212.5 | HS2-00002CT5A | 2024-11-20 | 10 - Complete | 2024-11-27 |  | HS2-00003K2XY - Ladbroke Cutting Ditch Crossing 09 CH.123+840 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003K2XY | #N/A | #N/A | #N/A
212.5 | HS2-00002CT5C | IDR 212.5 | HS2-00002CT5C | 2024-11-20 | 10 - Complete | 2024-11-26 |  | HS2-00003K2XZ - Ladbroke Cutting Ditch Crossing 10 CH.124+050 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003K2XZ | #N/A | #N/A | #N/A
212.5 | HS2-00002CT5H | IDR 212.5 | HS2-00002CT5H | 2024-11-20 | 10 - Complete | 2024-12-05 |  | HS2-00003KHCM - Ladbroke Cutting Pipe 01 CH.123+650 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003KHCM | #N/A | #N/A | #N/A
212.5 | HS2-00002GUW0 | IDR 212.5 | HS2-00002GUW0 | 2024-11-20 | 10 - Complete | 2024-11-26 |  | HS2-00003KHCN - Ladbroke Cutting Pipe 02 CH.124+550 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003KHCN | #N/A | #N/A | #N/A
212.5 | HS2-00002NL60 | IDR 212.5 | HS2-00002NL60 | 2024-11-20 | 10 - Complete | 2024-12-03 |  | HS2-00003KHCP - Ladbroke Cutting Ditch Crossing 11 CH.122+850 | IDR 238.02-2 - Ladbroke Cutting | IDR 238.02-2 | HS2-00003KHCP | #N/A | #N/A | #N/A
212.5 | HS2-00002CT5Q | IDR 212.5 | HS2-00002CT5Q | 2024-11-20 | 10 - Complete | 2024-11-26 |  | HS2-00003H6PG - Ladbroke Cutting Ancillary Pipe Culvert 2 | IDR 238.02_2 - Ladbroke Cutting Phase 2 - A423 Banbury Road Realignment | IDR 238.02_2 | HS2-00003H6PG | 2024-11-26 | 10 - Complete | 0
212.5 | HS2-00002CT5S | IDR 212.5 | HS2-00002CT5S | 2024-11-20 | 10 - Complete | 2024-11-26 |  | HS2-000001463 - Windmill Lane Green Overbridge | IDR 238.02_1 - Ladbroke Cutting Phase 1 - Windmill Lane Green Overbridge | IDR 238.02_1 | HS2-000001463 | 2024-11-28 | 10 - Complete | 2024-11-29
212.5 | HS2-00002CT5U | IDR 212.5 | HS2-00002CT5U | 2024-11-20 | 10 - Complete | 2024-11-28 |  | HS2-00002CTKE - Footpath SM33 Diversion (west of HS2) | IDR 238.02 - Ladbroke Cutting Phase 3 - Remainder | IDR 238.02 | HS2-00002CTKE | 2024-11-19 | 10 - Complete | 2024-11-22
212.5 | HS2-00002CT5W | IDR 212.5 | HS2-00002CT5W | 2024-11-20 | 10 - Complete | 2024-11-27 |  | HS2-000020P2G - Maintenance Access Road to Pond (Off A423 Banbury Road South) | IDR 238.02 - Ladbroke Cutting Phase 3 - Remainder | IDR 238.02 | HS2-000020P2G | 2024-11-21 | 10 - Complete | 2024-11-22
238.02 | HS2-000020P2N | IDR 238.02 | HS2-000020P2N | 2024-11-21 | 10 - Complete | 0 |  | HS2-000025B3T - Accommodation Access Road (Off A423 Banbury Road) | IDR 238.02 - Ladbroke Cutting Phase 3 - Remainder | IDR 238.02 | HS2-000025B3T | 2024-11-21 | 10 - Complete | 2024-11-22
238.02 | HS2-000025B3T | IDR 238.02 | HS2-000025B3T | 2024-11-21 | 10 - Complete | 2024-11-22 |  | HS2-000020P2N - Maintenance Access Road to Pond (Off A423 Banbury Road North) | IDR 238.02 - Ladbroke Cutting Phase 3 - Remainder | IDR 238.02 | HS2-000020P2N | 2024-11-21 | 10 - Complete | 0
238.02 | HS2-000025B3V | IDR 238.02 | HS2-000025B3V | 2024-11-21 | 10 - Complete | 2024-11-26 |  | HS2-000020P2P - Footpath SM89 Extension | IDR 238.02 - Ladbroke Cutting Phase 3 - Remainder | IDR 238.02 | HS2-000020P2P | 2024-11-19 | 10 - Complete | 2024-11-25
213.07-1 | HS2-00003CPW1 | IDR 213.07-1 | HS2-00003CPW1 | 2024-11-21 | 10 - Complete | 0 |  | HS2-000025B3V - A423 Banbury Road Realignment | IDR 238.02 - Ladbroke Cutting Phase 3 - Remainder | IDR 238.02 | HS2-000025B3V | 2024-11-21 | 10 - Complete | 2024-11-26
213.07-1 | HS2-00003CPW2 | IDR 213.07-1 | HS2-00003CPW2 | 2024-11-21 | 10 - Complete | 0 |  | HS2-00002C3Z1 - A423 Banbury Road Drainage System | IDR 238.02 - Ladbroke Cutting Phase 3 - Remainder | IDR 238.02 | HS2-00002C3Z1 | 2024-11-19 | 10 - Complete | 2024-11-26
213.07-1 | HS2-00003CPW4 | IDR 213.07-1 | HS2-00003CPW4 | 2024-11-21 | 10 - Complete | 0 |  | HS2-00002N7UV - Southam Embankment Group-Ancillary Culvert 124-AC1 | IDR 238.02 - Ladbroke Cutting Phase 3 - Remainder | IDR 238.02 | HS2-00002N7UV | 2024-01-23 | 10 - Complete | 2024-01-24
213.07-1 | HS2-00003CPW5 | IDR 213.07-1 | HS2-00003CPW5 | 2024-11-21 | 10 - Complete | 0 |  | HS2-00002YNH8 - Ladbroke Cutting Culvert 124-AC3 | IDR 238.02 - Ladbroke Cutting Phase 3 - Remainder | IDR 238.02 | HS2-00002YNH8 | 2024-11-26 | 10 - Complete | 0
213.07-1 | HS2-00003CPW6 | IDR 213.07-1 | HS2-00003CPW6 | 2024-11-21 | 10 - Complete | 2024-12-12 |  | HS2-000037830 - Ladbroke Cutting Ancillary Pipe Culvert | IDR 238.02 - Ladbroke Cutting Phase 3 - Remainder | IDR 238.02 | HS2-000037830 | 2024-03-19 | 10 - Complete | 2024-03-21
213.07-1 | HS2-00003CPW9 | IDR 213.07-1 | HS2-00003CPW9 | 2024-11-21 | 10 - Complete | 2024-12-12 |  | HS2-00003AQDJ - Ladbroke Cutting Group-A423 Banbury Road Existing Ancillary Culvert 1 | IDR 238.02 - Ladbroke Cutting Phase 3 - Remainder | IDR 238.02 | HS2-00003AQDJ | 2024-01-19 | 10 - Complete | 2024-01-22
213.07-1 | HS2-00003CPWA | IDR 213.07-1 | HS2-00003CPWA | 2024-11-21 | 10 - Complete | 2024-12-12 |  | HS2-00003EB33 - Ladbroke Cutting Culvert 124-AC3-Watercourse Tie In | IDR 238.02 - Ladbroke Cutting Phase 3 - Remainder | IDR 238.02 | HS2-00003EB33 | 2024-11-20 | 10 - Complete | 2024-11-25
213.07-1 | HS2-00003CPWB | IDR 213.07-1 | HS2-00003CPWB | 2024-11-21 | 10 - Complete | 2024-12-12 |  | HS2-00003LCQC - Ladbroke Cutting Landscape Earthwork Tie Ins (below A423 Banbury Road Overbridge) | IDR 238.02 - Ladbroke Cutting Phase 3 - Remainder | IDR 238.02 | HS2-00003LCQC | 2024-11-19 | 10 - Complete | 0
213.07-1 | HS2-00003CPWE | IDR 213.07-1 | HS2-00003CPWE | 2024-11-21 | 10 - Complete | 0 |  | HS2-000001100 - Ladbroke Grove Embankment | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-000001100 | 2024-02-21 | 10 - Complete | 2024-02-27
213.07-1 | HS2-00003CPWF | IDR 213.07-1 | HS2-00003CPWF | 2024-11-21 | 10 - Complete | 0 |  | HS2-00002BVN8 - C3.L.73 Catchment | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-00002BVN8 | 2025-03-03 | 10 - Complete | 2025-03-07
213.07-1 | HS2-00003CPWG | IDR 213.07-1 | HS2-00003CPWG | 2024-11-21 | 10 - Complete | 0 |  | HS2-00002BVNA - Ladbroke Grove Embankment Landscape Earthworks | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-00002BVNA | 2024-02-21 | 10 - Complete | 2024-02-28
213.07-1 | HS2-00003CPWJ | IDR 213.07-1 | HS2-00003CPWJ | 2024-11-21 | 10 - Complete | 2024-12-12 |  | HS2-00002CTK7 - Ladbroke Grove Embankment Boundary Perimeter Fence Line | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-00002CTK7 | 2024-09-06 | 10 - Complete | 2024-09-25
213.07-1 | HS2-00003CPWL | IDR 213.07-1 | HS2-00003CPWL | 2024-11-21 | 10 - Complete | 2024-12-12 |  | HS2-00002CTK8 - Ladbroke Grove Embankment Security Fence Line | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-00002CTK8 | 2024-09-06 | 10 - Complete | 2024-09-30
213.07-1 | HS2-00003CPWN | IDR 213.07-1 | HS2-00003CPWN | 2024-11-21 | 10 - Complete | 2024-12-12 |  | HS2-00002CTK9 - Ladbroke Watercourse Diversion | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-00002CTK9 | 2024-05-09 | 10 - Complete | 2024-05-14
213.07-1 | HS2-00003CPWQ | IDR 213.07-1 | HS2-00003CPWQ | 2024-11-21 | 10 - Complete | 2024-12-12 |  | HS2-00002TG2Q - Ladbroke Grove Access Track | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-00002TG2Q | 2024-02-08 | 10 - Complete | 2024-02-20
213.07-1 | HS2-00003CPWS | IDR 213.07-1 | HS2-00003CPWS | 2024-11-21 | 10 - Complete | 0 |  | HS2-000001462 - Ladbroke Culvert | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-000001462 | 2024-01-02 | 10 - Complete | 2024-01-18
213.07-1 | HS2-00003CPWV | IDR 213.07-1 | HS2-00003CPWV | 2024-11-21 | 10 - Complete | 0 |  | HS2-00002YNH7 - Ladbroke Grove Embankment Culvert 122-AC3 | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-00002YNH7 | 2024-01-10 | 10 - Complete | 2024-01-19
212.5 | HS2-00002CT53 | IDR 212.5 | HS2-00002CT53 | 2024-11-21 | 10 - Complete | 2024-11-28 |  | HS2-00003DL20 - Ladbroke Grove Embankment 122-DC1 | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-00003DL20 | 2024-02-02 | 10 - Complete | 2024-02-07
212.5 | HS2-00002CT55 | IDR 212.5 | HS2-00002CT55 | 2024-11-21 | 10 - Complete | 2024-11-28 |  | HS2-00003DL21 - Ladbroke Grove Embankment 122-DC2 | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-00003DL21 | 2024-02-02 | 10 - Complete | 2024-02-07
233.01-3 | HS2-000035Q9C | IDR 233.01-3 | HS2-000035Q9C | 2024-11-21 | 10 - Complete | 2024-12-04 |  | HS2-00003DL22 - Ladbroke Grove Embankment 122-DC3 | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-00003DL22 | 2024-02-02 | 10 - Complete | 2024-02-07
215.01-2 | HS2-000001044 | IDR 215.01-2 | HS2-000001044 | 2024-11-21 | 10 - Complete | 2025-01-07 |  | HS2-00003KFPL - Ladbroke Grove Embankment 121-DC6 | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-00003KFPL | 2024-07-22 | 10 - Complete | 2024-08-01
224.7 | HS2-00003HF3P | IDR 224.7 | HS2-00003HF3P | 2024-11-21 | 10 - Complete | 2024-12-03 |  | HS2-00003KFPM - Ladbroke Grove Embankment 121-DC5 | IDR 238.01 - Ladbroke Grove Embankment | IDR 238.01 | HS2-00003KFPM | 2024-07-18 | 10 - Complete | 2024-08-08
224.7 | HS2-00003HF3Q | IDR 224.7 | HS2-00003HF3Q | 2024-11-21 | 10 - Complete | 2024-12-03 |  | HS2-00002CTHC - Chipping Warden Green Tunnel Boundary Perimeter Fence Line | IDR 237.06 - Ladbroke Grove and Chipping Warden Green Tunnel Areas - Landscape planting and Fencing | IDR 237.06 | HS2-00002CTHC | #N/A | #N/A | #N/A
224.7 | HS2-00003HF3R | IDR 224.7 | HS2-00003HF3R | 2024-11-21 | 10 - Complete | 2024-12-03 |  | HS2-00002EKZD - Chipping Warden Ecological Mitigation Site | IDR 237.06 - Ladbroke Grove and Chipping Warden Green Tunnel Areas - Landscape planting and Fencing | IDR 237.06 | HS2-00002EKZD | #N/A | #N/A | #N/A
224.7 | HS2-00003HF3S | IDR 224.7 | HS2-00003HF3S | 2024-11-21 | 10 - Complete | 2024-12-03 |  | HS2-00002EKZE - Aston Le Walls Ecological Mitigation Site | IDR 237.06 - Ladbroke Grove and Chipping Warden Green Tunnel Areas - Landscape planting and Fencing | IDR 237.06 | HS2-00002EKZE | #N/A | #N/A | #N/A
202.1-3 | HS2-00003J169 | IDR 202.1-3 | HS2-00003J169 | 2024-11-21 | 10 - Complete | 0 |  | HS2-00003KPUT - Chipping Warden Green Tunnel Areas - Landscape Planting and Fencing - Planting Plot | IDR 237.06 - Ladbroke Grove and Chipping Warden Green Tunnel Areas - Landscape planting and Fencing | IDR 237.06 | HS2-00003KPUT | #N/A | #N/A | #N/A
202.1-3 | HS2-00003J16A | IDR 202.1-3 | HS2-00003J16A | 2024-11-21 | 10 - Complete | 0 |  | HS2-00003KPUU - Ladbroke Grove Cutting and Embankment Areas - Landscape Planting and Fencing - Planting Plot | IDR 237.06 - Ladbroke Grove and Chipping Warden Green Tunnel Areas - Landscape planting and Fencing | IDR 237.06 | HS2-00003KPUU | #N/A | #N/A | #N/A
220.3 | HS2-00002EK7A | IDR 220.3 | HS2-00002EK7A | 2024-11-22 | 10 - Complete | 2024-12-10 |  | HS2-000001461 - Ladbroke Grove Farm Accommodation Overbridge | IDR 237.05-3 - Ladbroke Grove Cutting - Ladbroke Grove Farm Accommodation Overbridge | IDR 237.05-3 | HS2-000001461 | 2024-02-21 | 10 - Complete | 2024-02-23
229.01 | HS2-00002BVKJ | IDR 229.01 | HS2-00002BVKJ | 2024-12-18 | 10 - Complete | 2025-01-10 |  | HS2-000001460 - Lower Radbourne Farm Accommodation Overbridge | IDR 237.05-2 - Ladbroke Grove Cutting - Lower Radbourne Farm Accommodation Overbridge | IDR 237.05-2 | HS2-000001460 | 2024-02-08 | 10 - Complete | 2024-02-23
229.01-2 | HS2-00003JRG8 | IDR 229.01-2 | HS2-00003JRG8 | 2024-11-22 | 10 - Complete | 2024-12-19 |  | HS2-00002TMWF - Ladbroke Grove Cutting Access Stairs | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00002TMWF | 2024-03-01 | 10 - Complete | 2024-03-04
237.05 | HS2-000032216 | IDR 237.05 | HS2-000032216 | 2024-11-26 | 10 - Complete | 2025-01-10 |  | HS2-000020P0N - Maintenance Access Road to Pond (Off Lower Radbourne Farm Access Road East) | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-000020P0N | 2024-11-26 | 10 - Complete | 2025-01-10
UFDR 209.A | HS2-000020CF1 | UFDR 209.A | HS2-000020CF1 | 2025-03-25 | 10 - Complete | 2025-03-27 |  | HS2-00002BVMZ - C3.L.69 Catchment | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00002BVMZ | 2024-04-22 | 10 - Complete | 2024-05-01
201.0-1 | HS2-00003JN84 | IDR 201.0-1 | HS2-00003JN84 | 2024-11-26 | 10 - Complete | 2024-12-02 |  | HS2-000020P0U - Radbourne Lane Realignment | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-000020P0U | 2024-03-01 | 10 - Complete | 2024-03-05
201.0-1 | HS2-000020N9Q | IDR 201.0-1 | HS2-000020N9Q | 2024-11-26 | 10 - Complete | 2024-11-29 |  | HS2-000020P0W - Maintenance Access Road to Pond (Off Radbourne Lane South) | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-000020P0W | 2025-01-09 | 10 - Complete | 2025-01-16
201.0-1 | HS2-00002CT2K | IDR 201.0-1 | HS2-00002CT2K | 2024-11-26 | 10 - Complete | 2024-12-02 |  | HS2-00002BVN5 - Ladbroke Grove Cutting Landscape Earthworks | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00002BVN5 | 2024-02-28 | 10 - Complete | 2024-03-01
201.0-1 | HS2-00002CT2L | IDR 201.0-1 | HS2-00002CT2L | 2024-11-26 | 10 - Complete | 0 |  | HS2-00002CTK3 - C3.T.71 Catchment | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00002CTK3 | 2024-03-13 | 10 - Complete | 2024-03-22
201.0-1 | HS2-00002CT2N | IDR 201.0-1 | HS2-00002CT2N | 2024-11-26 | 10 - Complete | 0 |  | HS2-00002CTK4 - Radbourne ATS Access Road | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00002CTK4 | 2024-12-12 | 30 - Sent back to team | 0
237.05 | HS2-000020P0N | IDR 237.05 | HS2-000020P0N | 2024-11-26 | 10 - Complete | 2025-01-10 |  | HS2-00002CTK5 - Ladbroke Grove Cutting Boundary Perimeter Fence Line | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00002CTK5 | 2024-05-14 | 10 - Complete | 2024-05-16
238.02 | HS2-000001463 | IDR 238.02 | HS2-000001463 | 2024-11-28 | 10 - Complete | 2024-11-29 |  | HS2-00002CTK6 - Ladbroke Grove Cutting Security Fence Line | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00002CTK6 | 2024-03-21 | 10 - Complete | 2024-04-12
238.02 | HS2-00002YNH8 | IDR 238.02 | HS2-00002YNH8 | 2024-11-26 | 10 - Complete | 0 |  | HS2-000001099 - Ladbroke Grove Cutting | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-000001099 | 2024-05-14 | 10 - Complete | 2024-05-15
238.02 | HS2-00003H6PG | IDR 238.02 | HS2-00003H6PG | 2024-11-26 | 10 - Complete | 0 |  | HS2-00002TMFE - Radbourne ATS Telecoms | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00002TMFE | 2024-03-27 | 10 - Complete | 2024-04-03
201.0-1 | HS2-00002WUJ5 | IDR 201.0-1 | HS2-00002WUJ5 | 2024-11-28 | 10 - Complete | 2024-12-03 |  | HS2-000020P16 - Lower Radbourne Farm Accommodation Access Realignment | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-000020P16 | 2024-04-10 | 10 - Complete | 2024-04-17
201.0-1 | HS2-00002WUJ6 | IDR 201.0-1 | HS2-00002WUJ6 | 2024-11-28 | 10 - Complete | 2024-12-04 |  | HS2-00002CX3B - Lower Radbourne and Ladbroke Farm Access Drainage System | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00002CX3B | 2024-03-28 | 10 - Complete | 2024-04-02
201.0-1 | HS2-00002WUJ7 | IDR 201.0-1 | HS2-00002WUJ7 | 2024-11-28 | 10 - Complete | 2024-12-04 |  | HS2-00002TKV0 - Perturbation crossover UTX | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00002TKV0 | 2024-03-26 | 10 - Complete | 2024-04-02
201.0-1 | HS2-00002WUJ8 | IDR 201.0-1 | HS2-00002WUJ8 | 2024-11-28 | 10 - Complete | 2024-12-04 |  | HS2-000020P1F - Ladbroke Grove Farm Accommodation Access Realignment | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-000020P1F | 2024-12-05 | 10 - Complete | 2024-01-14
201.0-1 | HS2-00002WUJH | IDR 201.0-1 | HS2-00002WUJH | 2024-11-28 | 10 - Complete | 2024-12-04 |  | HS2-00002CX39 - Ladbroke Grove Farm Access Drainage System | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00002CX39 | 2024-02-16 | 10 - Complete | 2024-02-22
201.0-1 | HS2-00002WUJJ | IDR 201.0-1 | HS2-00002WUJJ | 2024-11-28 | 10 - Complete | 2024-12-04 |  | HS2-000032216 - Maintenance Access Road to Switch and Crossing MS2.11 | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-000032216 | 2024-11-26 | 10 - Complete | 2025-01-10
201.0-1 | HS2-00002WUJK | IDR 201.0-1 | HS2-00002WUJK | 2024-11-28 | 10 - Complete | 2024-12-04 |  | HS2-00003B93P - Ladbroke Grove Cutting 120 - DC1 | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00003B93P | 2024-04-04 | 10 - Complete | 2024-04-07
201.0-1 | HS2-00002WUJL | IDR 201.0-1 | HS2-00002WUJL | 2024-11-28 | 10 - Complete | 2024-12-04 |  | HS2-00003B93Q - Ladbroke Grove Cutting 121 - DC2 | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00003B93Q | 2024-04-04 | 10 - Complete | 2024-04-07
224.7 | HS2-00003BPLH | IDR 224.7 | HS2-00003BPLH | 2024-11-28 | 10 - Complete | 2024-12-06 |  | HS2-00003B93R - Ladbroke Grove Cutting 121 - DC3 | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00003B93R | 2024-04-04 | 10 - Complete | 2024-04-07
224.7 | HS2-00003BPLM | IDR 224.7 | HS2-00003BPLM | 2024-11-28 | 10 - Complete | 2024-12-06 |  | HS2-00003D82S - Ladbroke Grove Cutting 121-DC5 | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00003D82S | 2024-07-25 | 10 - Complete | 2024-08-02
224.7 | HS2-00003BPLQ | IDR 224.7 | HS2-00003BPLQ | 2024-11-28 | 10 - Complete | 0 |  | HS2-00003G3SJ - Ladbroke Grove Cutting Access Stairs CH.121+020 | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00003G3SJ | 2024-03-01 | 10 - Complete | 2024-03-04
224.7 | HS2-00003HF3W | IDR 224.7 | HS2-00003HF3W | 2024-11-28 | 10 - Complete | 2024-12-10 |  | HS2-00003KFPU - Radbourne ATS UTX 1 | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00003KFPU | 2024-07-09 | 10 - Complete | 2024-07-11
222.9 | HS2-00002CTBS | IDR 222.9 | HS2-00002CTBS | 2024-11-28 | 10 - Complete | 2025-01-07 |  | HS2-00003KFPV - Radbourne ATS UTX 2 | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00003KFPV | 2024-07-09 | 10 - Complete | 2024-07-11
222.9 | HS2-00002CTBU | IDR 222.9 | HS2-00002CTBU | 2024-11-28 | 10 - Complete | 2025-01-07 |  | HS2-00003KFPW - Radbourne ATS UTX 3 | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00003KFPW | 2024-07-09 | 10 - Complete | 2024-07-11
229.01-2 | HS2-00002EK7T | IDR 229.01-2 | HS2-00002EK7T | 2024-11-29 | 10 - Complete | 2024-12-17 |  | HS2-00003KFPX - Radbourne ATS UTX 4 | IDR 237.05 - Ladbroke Grove Cutting - Non Overbridges | IDR 237.05 | HS2-00003KFPX | 2024-07-09 | 10 - Complete | 2024-07-11
201.0-1 | HS2-00002XQ2P | IDR 201.0-1 | HS2-00002XQ2P | 2024-11-29 | 10 - Complete | 2024-12-03 |  | HS2-00002BVN1 - Lower Radbourne Embankment Landscape Earthworks | IDR 237.04 - Lower Radbourne Embankment | IDR 237.04 | HS2-00002BVN1 | #N/A | #N/A | #N/A
214.07 | HS2-00003L0M2 | IDR 214.07 | HS2-00003L0M2 | 2024-12-02 | 10 - Complete | 2025-01-08 |  | HS2-00002CTK1 - Lower Radbourne Embankment Boundary Perimeter Fence Line | IDR 237.04 - Lower Radbourne Embankment | IDR 237.04 | HS2-00002CTK1 | #N/A | #N/A | #N/A
216.01 | HS2-00002BJUG | IDR 216.01 | HS2-00002BJUG | 2025-06-27 | 10 - Complete | 2025-07-02 |  | HS2-00002CTK2 - Lower Radbourne Embankment Security Fence Line | IDR 237.04 - Lower Radbourne Embankment | IDR 237.04 | HS2-00002CTK2 | #N/A | #N/A | #N/A
216.01 | HS2-00002BJUF | IDR 216.01 | HS2-00002BJUF | 2025-06-27 | 10 - Complete | 2025-07-02 |  | HS2-00002TG2Y - Lower Radbourne Embankment dowmain Access Stair | IDR 237.04 - Lower Radbourne Embankment | IDR 237.04 | HS2-00002TG2Y | #N/A | #N/A | #N/A
216.01 | HS2-00002BJUE | IDR 216.01 | HS2-00002BJUE | 2024-12-02 | 10 - Complete | 2025-01-09 |  | HS2-000001098 - Lower Radbourne Embankment | IDR 237.04 - Lower Radbourne Embankment | IDR 237.04 | HS2-000001098 | #N/A | #N/A | #N/A
216.01 | HS2-00002CT90 | IDR 216.01 | HS2-00002CT90 | 2024-12-02 | 10 - Complete | 2025-01-09 |  | HS2-000038VY1 - Lower Radbourne Embankment upmain Access Stair | IDR 237.04 - Lower Radbourne Embankment | IDR 237.04 | HS2-000038VY1 | #N/A | #N/A | #N/A
216.01 | HS2-000020NKK | IDR 216.01 | HS2-000020NKK | 2024-12-02 | 10 - Complete | 2025-01-08 |  | HS2-000038VY2 - Lower Radbourne North Viaduct Bearing Access Stair | IDR 237.04 - Lower Radbourne Embankment | IDR 237.04 | HS2-000038VY2 | #N/A | #N/A | #N/A
233.01-3 | HS2-00003J16B | IDR 233.01-3 | HS2-00003J16B | 2024-12-02 | 10 - Complete | 2024-12-09 |  | HS2-000001097 - Lower Radbourne North Viaduct | IDR 237.03 - Lower Radbourne North Viaduct | IDR 237.03 | HS2-000001097 | #N/A | #N/A | #N/A
229.01-1 | HS2-00003JRG7 | IDR 229.01-1 | HS2-00003JRG7 | 2024-12-02 | 10 - Complete | 2025-01-17 |  | HS2-0000300BU - Lower Radbourne North Viaduct Embankment transition zone to South abutment | IDR 237.03 - Lower Radbourne North Viaduct | IDR 237.03 | HS2-0000300BU | #N/A | #N/A | #N/A
238.03 | HS2-000001464 | IDR 238.03 | HS2-000001464 | 2024-12-03 | 10 - Complete | 2024-01-14 |  | HS2-00002U6LP - Bridleway SM229 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002U6LP | 2024-01-10 | 10 - Complete | 2024-01-12
UFDR 211.A | HS2-00003KFPK | UFDR 211.A | HS2-00003KFPK | 2024-12-03 | 10 - Complete | 2024-12-12 |  | HS2-000020P0J - Bridleway SM96 Realignment | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-000020P0J | 2023-12-18 | 10 - Complete | 2024-01-05
201.0-1 | HS2-00002WUJ1 | IDR 201.0-1 | HS2-00002WUJ1 | 2024-11-29 | 10 - Complete | 2024-12-05 |  | HS2-00002BVMV - Upper Radbourne Embankment Landscape Earthworks | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002BVMV | 2024-02-13 | 10 - Complete | 2024-02-16
201.0-1 | HS2-00002WUJ3 | IDR 201.0-1 | HS2-00002WUJ3 | 2024-11-29 | 10 - Complete | 2024-12-05 |  | HS2-00002CTJT - C3.T.70 Catchment | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002CTJT | 2023-12-15 | 10 - Complete | 2023-12-18
201.0-1 | HS2-00002WUJD | IDR 201.0-1 | HS2-00002WUJD | 2024-11-29 | 10 - Complete | 2024-12-05 |  | HS2-00002CTJU - Footpath SM96a Realignment | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002CTJU | 2023-12-18 | 10 - Complete | 2024-01-05
201.0-1 | HS2-00002WUJE | IDR 201.0-1 | HS2-00002WUJE | 2024-11-29 | 10 - Complete | 2024-12-05 |  | HS2-00002CTJV - Upper Radbourne Embankment Boundary Perimeter Fence Line | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002CTJV | 2023-12-12 | 10 - Complete | 2023-12-14
201.0-1 | HS2-00002WUJF | IDR 201.0-1 | HS2-00002WUJF | 2024-11-29 | 10 - Complete | 2024-12-05 |  | HS2-00002CTJW - Upper Radbourne Embankment Security Fence Line | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002CTJW | 2023-12-12 | 10 - Complete | 2023-12-14
201.0-1 | HS2-00002WUJG | IDR 201.0-1 | HS2-00002WUJG | 2024-11-29 | 10 - Complete | 2024-12-05 |  | HS2-000001096 - Upper Radbourne Embankment | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-000001096 | 2024-02-13 | 10 - Complete | 2024-02-16
216.01 | HS2-00002CT8T | IDR 216.01 | HS2-00002CT8T | 2025-05-30 | 10 - Complete | 2025-06-04 |  | HS2-00002EL0S - C3.L.81 Catchment | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002EL0S | 2023-12-15 | 10 - Complete | 2023-12-18
214.01 | HS2-00002CW0M | IDR 214.01 | HS2-00002CW0M | 2024-12-05 | 10 - Complete | 2024-01-14 |  | HS2-00002CTJZ - Lower Radbourne North Watercourse Diversion | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002CTJZ | 2024-07-05 | 10 - Complete | 2024-07-31
237.05 | HS2-000020P1F | IDR 237.05 | HS2-000020P1F | 2024-12-05 | 10 - Complete | 2024-01-14 |  | HS2-00002WURR - Oxford Canal South Embankment Planting-East Plot 1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WURR | 2024-02-09 | 10 - Complete | 2024-02-13
219.1 | HS2-00002CT9Z | IDR 219.1 | HS2-00002CT9Z | 2025-02-24 | 10 - Complete | 2025-02-25 |  | HS2-00002WURS - Oxford Canal South Embankment Planting-East Plot 2 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WURS | 2024-02-09 | 10 - Complete | 2024-02-13
233.01-3 | HS2-00002CTH6 | IDR 233.01-3 | HS2-00002CTH6 | 2024-12-06 | 10 - Complete | 2024-12-11 |  | HS2-00002WURT - Oxford Canal South Embankment Planting-West Plot 1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WURT | 2024-02-09 | 10 - Complete | 2024-02-13
234.01 | HS2-00002CTHK | IDR 234.01 | HS2-00002CTHK | 2024-12-09 | 10 - Complete | 2025-01-09 |  | HS2-00002WURU - Oxford Canal South Embankment Planting-West Plot 2 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WURU | 2024-02-09 | 10 - Complete | 2024-02-13
202.5-2 | HS2-000001023 | IDR 202.5-2 | HS2-000001023 | 2024-12-10 | 10 - Complete | 2024-12-13 |  | HS2-00002WURV - Oxford Canal South Embankment Planting-West Plot 3 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WURV | 2024-02-09 | 10 - Complete | 2024-02-13
218.02-1 | HS2-00002NSXP | IDR 218.02-1 | HS2-00002NSXP | 2024-12-10 | 10 - Complete | 2024-01-21 |  | HS2-00002WURW - Oxford Canal Viaduct Planting-Plot 1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WURW | 2024-02-09 | 10 - Complete | 2024-02-13
218.02-1 | HS2-00002NSXQ | IDR 218.02-1 | HS2-00002NSXQ | 2024-12-10 | 10 - Complete | 2025-01-09 |  | HS2-00002WURX - Oxford Canal Viaduct Planting-Plot 2 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WURX | 2024-02-09 | 10 - Complete | 2024-02-13
233.01-2 | HS2-00002TMFA | IDR 233.01-2 | HS2-00002TMFA | 2024-12-12 | 10 - Complete | 2024-01-14 |  | HS2-00002WURY - Oxford Canal Viaduct Planting-Plot 3 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WURY | 2024-02-09 | 10 - Complete | 2024-02-13
233.01-2 | HS2-00002TMFB | IDR 233.01-2 | HS2-00002TMFB | 2024-12-12 | 10 - Complete | 2025-01-22 |  | HS2-00002WURZ - Oxford Canal Viaduct Planting-Plot 4 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WURZ | 2024-02-09 | 10 - Complete | 2024-02-13
233.01-2 | HS2-00002TMFC | IDR 233.01-2 | HS2-00002TMFC | 2024-12-12 | 10 - Complete | 2024-01-14 |  | HS2-00002WUS0 - Oxford Canal North Embankment Planting-East Plot 1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUS0 | 2024-02-09 | 10 - Complete | 2024-02-13
UFDR 211.A | HS2-000031J4L | UFDR 211.A | HS2-000031J4L | 2024-12-12 | 10 - Complete | 2024-12-16 |  | HS2-00002WUS1 - Oxford Canal North Embankment Planting-East Plot 2 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUS1 | 2024-02-09 | 10 - Complete | 2024-02-13
UFDR 211.A | HS2-000020CFE | UFDR 211.A | HS2-000020CFE | 2024-12-12 | 10 - Complete | 2024-12-13 |  | HS2-00002WUS2 - Oxford Canal North Embankment Planting-East Plot 3 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUS2 | 2024-02-09 | 10 - Complete | 2024-02-13
UFDR 211.A | HS2-00003KUMA | UFDR 211.A | HS2-00003KUMA | 2024-12-12 | 10 - Complete | 2024-12-13 |  | HS2-00002WUS3 - Oxford Canal North Embankment Planting-East Plot 4 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUS3 | 2024-02-09 | 10 - Complete | 2024-02-13
237.05 | HS2-00002CTK4 | IDR 237.05 | HS2-00002CTK4 | 2024-12-12 | 30 - Sent back to team | 0 |  | HS2-00002WUS4 - Oxford Canal North Embankment Planting-West Plot 1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUS4 | 2024-02-09 | 10 - Complete | 2024-02-13
229.01-2 | HS2-000020361 | IDR 229.01-2 | HS2-000020361 | 2024-12-12 | 10 - Complete | 2024-12-17 |  | HS2-00002WUS5 - Oxford Canal North Embankment Planting-West Plot 2 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUS5 | 2024-02-09 | 10 - Complete | 2024-02-13
229.01-2 | HS2-00003JAYC | IDR 229.01-2 | HS2-00003JAYC | 2024-12-12 | 10 - Complete | 2025-01-02 |  | HS2-00002WUS6 - Oxford Canal North Embankment Planting-West Plot 3 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUS6 | 2024-02-09 | 10 - Complete | 2024-02-13
222.9 | HS2-00003K85R | IDR 222.9 | HS2-00003K85R | 2024-12-16 | 10 - Complete | 2025-01-08 |  | HS2-00002WUS7 - Oxford Canal North Embankment Planting-West Plot 4 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUS7 | 2024-02-09 | 10 - Complete | 2024-02-13
UFDR 209.A | HS2-000020CF1 | UFDR 209.A | HS2-000020CF1 | 2024-12-18 | 10 - Complete | 2024-12-20 |  | HS2-00002WUS8 - Lower Radbourne South Viaduct Planting-East Plot 1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUS8 | 2024-02-09 | 10 - Complete | 2024-02-13
229.01 | HS2-00002BVKJ | IDR 229.01 | HS2-00002BVKJ | 2024-12-18 | 10 - Complete | 2025-01-10 |  | HS2-00002WUS9 - Lower Radbourne South Viaduct Planting-West Plot 1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUS9 | 2024-02-09 | 10 - Complete | 2024-02-13
214.01-1 | HS2-000001308 | IDR 214.01-1 | HS2-000001308 | 2024-12-19 | 30 - Sent back to team | 0 |  | HS2-00002WUSA - Upper Radbourne Embankment Planting-East Plot 1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUSA | 2024-02-09 | 10 - Complete | 2024-02-13
222.9 | HS2-000039DS9 | IDR 222.9 | HS2-000039DS9 | 2024-12-19 | 10 - Complete | 2025-01-03 |  | HS2-00002WUSB - Upper Radbourne Embankment Planting-East Plot 2 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUSB | 2024-02-09 | 10 - Complete | 2024-02-13
UFDR 211.B | HS2-000020CFD | UFDR 211.B | HS2-000020CFD | 2024-12-20 | 10 - Complete | 2025-01-10 |  | HS2-00002WUSC - Upper Radbourne Embankment Planting-West Plot 1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUSC | 2024-02-09 | 10 - Complete | 2024-02-13
UFDR 211.B | HS2-000020CFC | UFDR 211.B | HS2-000020CFC | 2024-12-20 | 10 - Complete | 2025-01-10 |  | HS2-00002WUSD - Upper Radbourne Embankment Planting-West Plot 2 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUSD | 2024-02-09 | 10 - Complete | 2024-02-13
217.04 | HS2-000031NVA | IDR 217.04 | HS2-000031NVA | 2024-12-20 | 10 - Complete | 2025-01-10 |  | HS2-00002WUSE - Lower Radbourne North Viaduct Planting-Plot 1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUSE | 2024-02-09 | 10 - Complete | 2024-02-13
230.01-3 | HS2-00002CTFN | IDR 230.01-3 | HS2-00002CTFN | 2025-02-06 | 10 - Complete | 2025-02-20 |  | HS2-00002WUSF - Lower Radbourne North Viaduct Planting-Plot 2 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUSF | 2024-02-09 | 10 - Complete | 2024-02-13
229.01-1 | HS2-00002TMF4 | IDR 229.01-1 | HS2-00002TMF4 | 2024-12-23 | 10 - Complete | 2025-01-17 |  | HS2-00002WUSG - Lower Radbourne Embankment Planting-East Plot 1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUSG | 2024-02-09 | 10 - Complete | 2024-02-13
229.01-1 | HS2-00002TMF2 | IDR 229.01-1 | HS2-00002TMF2 | 2024-12-23 | 10 - Complete | 2025-01-15 |  | HS2-00002WUSH - Lower Radbourne Embankment Planting-East Plot 2 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUSH | 2024-02-09 | 10 - Complete | 2024-02-13
229.01-1 | HS2-00002TMF1 | IDR 229.01-1 | HS2-00002TMF1 | 2024-12-23 | 10 - Complete | 2025-01-14 |  | HS2-00002WUSJ - Lower Radbourne Embankment Planting-West Plot 1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUSJ | 2024-02-09 | 10 - Complete | 2024-02-13
229.01-1 | HS2-00002TMF3 | IDR 229.01-1 | HS2-00002TMF3 | 2024-12-23 | 10 - Complete | 2025-01-17 |  | HS2-00002WUSK - Lower Radbourne Embankment Planting-West Plot 2 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002WUSK | 2024-02-09 | 10 - Complete | 2024-02-13
214.08 | HS2-00002TZT8 | IDR 214.08 | HS2-00002TZT8 | 2025-01-27 | 10 - Complete | 2025-01-30 |  | HS2-00002YNH5 - Crossing of Bridleway SM229 to River Itchen Tributary | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00002YNH5 | 2025-02-18 | 30 - Sent back to team | 0
233.01-2 | HS2-00002CX3A | IDR 233.01-2 | HS2-00002CX3A | 2025-01-08 | 10 - Complete | 2025-01-17 |  | HS2-00003D9CP - Upper Radbourne Embankment Access Stairs CH.120+015 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00003D9CP | 2023-12-11 | 10 - Complete | 2024-01-16
234.01 | HS2-00002U4NE | IDR 234.01 | HS2-00002U4NE | 2025-01-09 | 10 - Complete | 2025-01-16 |  | HS2-00003D9CQ - Upper Radbourne Embankment Access Stairs CH.120+027 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00003D9CQ | 2023-12-11 | 10 - Complete | 2024-01-16
237.05 | HS2-000020P0W | IDR 237.05 | HS2-000020P0W | 2025-01-09 | 10 - Complete | 2025-01-16 |  | HS2-00003D9CR - Upper Radbourne Embankment Access Stairs CH.120+031 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00003D9CR | 2023-12-11 | 10 - Complete | 2024-01-17
213.05 | HS2-00002CW0N | IDR 213.05 | HS2-00002CW0N | 2025-01-10 | 10 - Complete | 2025-01-17 |  | HS2-00003D9CS - Upper Radbourne Embankment Access Stairs CH.120+390 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00003D9CS | 2023-12-11 | 10 - Complete | 2024-01-16
215.02-2 | HS2-00002CX36 | IDR 215.02-2 | HS2-00002CX36 | 2025-01-10 | 10 - Complete | 2025-01-17 |  | HS2-00003D9CT - Upper Radbourne Embankment Access Stairs CH.120+395 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00003D9CT | 2023-12-11 | 10 - Complete | 2024-01-16
229.01-2 | HS2-000020NW0 | IDR 229.01-2 | HS2-000020NW0 | 2025-01-13 | 10 - Complete | 2025-01-15 |  | HS2-00003D9CU - Upper Radbourne Embankment Access Stairs CH.120+410 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00003D9CU | 2023-12-11 | 10 - Complete | 2024-01-17
229.01-2 | HS2-000025B2E | IDR 229.01-2 | HS2-000025B2E | 2025-05-23 | 10 - Complete | 2025-05-28 |  | HS2-00003GSK0 - Lower Radbourne Embankment Ecology Pond-1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00003GSK0 | 2024-10-22 | 10 - Complete | 2024-10-24
229.01-2 | HS2-000025B2G | IDR 229.01-2 | HS2-000025B2G | 2025-05-23 | 10 - Complete | 2025-06-02 |  | HS2-00003GSK1 - Oxford Canal North Embankment Ecology Pond-1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00003GSK1 | 2024-10-22 | 10 - Complete | 2024-10-24
229.01-2 | HS2-000039DSF | IDR 229.01-2 | HS2-000039DSF | 2025-01-13 | 99 - Cancelled | 0 |  | HS2-00003GSK2 - Oxford Canal North Embankment Ecology Pond-2 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00003GSK2 | 2024-10-22 | 10 - Complete | 2024-10-24
213.02-1 | HS2-00002BVGF | IDR 213.02-1 | HS2-00002BVGF | 2025-01-15 | 10 - Complete | 2025-02-04 |  | HS2-00003GSK3 - Oxford Canal South Embankment Ecology Pond-1 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00003GSK3 | 2024-10-22 | 10 - Complete | 2024-10-24
213.02-1 | HS2-00002CT77 | IDR 213.02-1 | HS2-00002CT77 | 2025-01-15 | 10 - Complete | 2025-01-22 |  | HS2-00003GSK4 - Oxford Canal South Embankment Ecology Pond-2 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00003GSK4 | 2024-10-22 | 10 - Complete | 2024-10-24
213.02-1 | HS2-00002CT7S | IDR 213.02-1 | HS2-00002CT7S | 2025-03-18 | 10 - Complete | 2025-03-25 |  | HS2-00003GSK5 - Oxford Canal South Embankment Ecology Pond-3 | IDR 237.02 - Upper Radbourne Embankment | IDR 237.02 | HS2-00003GSK5 | 2024-10-22 | 10 - Complete | 2024-10-24
213.02-1 | HS2-00002CT7A | IDR 213.02-1 | HS2-00002CT7A | 2025-03-18 | 10 - Complete | 2025-03-25 |  | HS2-00002EL01 - Flood Conveyance Area-119 | IDR 237.01 - Lower Radbourne South Viaduct | IDR 237.01 | HS2-00002EL01 | #N/A | #N/A | #N/A
213.02-1 | HS2-00002CT78 | IDR 213.02-1 | HS2-00002CT78 | 2025-01-15 | 10 - Complete | 2025-02-04 |  | HS2-00002CTJS - Lower Radbourne South Watercourse Diversion | IDR 237.01 - Lower Radbourne South Viaduct | IDR 237.01 | HS2-00002CTJS | #N/A | #N/A | #N/A
229.01-2 | HS2-00003AQDA | IDR 229.01-2 | HS2-00003AQDA | 2025-01-16 | 10 - Complete | 2025-01-20 |  | HS2-000001095 - Lower Radbourne South Viaduct | IDR 237.01 - Lower Radbourne South Viaduct | IDR 237.01 | HS2-000001095 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002ZM28 - Lower Radbourne South Viaduct-Embankment transition zone to North abutment | IDR 237.01 - Lower Radbourne South Viaduct | IDR 237.01 | HS2-00002ZM28 | #N/A | #N/A | #N/A
[8 empty] | HS2-000025B3J - Accommodation Access Road (Under Oxford Canal Viaduct) | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-000025B3J | 2023-11-13 | 10 - Complete | 2023-11-16
[8 empty] | HS2-000020P08 - Bridleway SM116 Realignment | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-000020P08 | 2023-11-13 | 10 - Complete | 2023-11-22
[8 empty] | HS2-00002BVMP - Oxford Canal North Embankment Landscape Earthworks | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00002BVMP | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTJL - C3.T.67 Catchment | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00002CTJL | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTJN - Oxford Canal North Embankment Boundary Perimeter Fence Line | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00002CTJN | 2023-12-05 | 10 - Complete | 2023-12-06
[8 empty] | HS2-00002CTJP - Oxford Canal North Embankment Security Fence Line | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00002CTJP | 2023-12-05 | 10 - Complete | 2023-12-06
[8 empty] | HS2-000001094 - Oxford Canal North Embankment | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-000001094 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EL0R - C3.L.80 Catchment | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00002EL0R | #N/A | #N/A | #N/A
[8 empty] | HS2-00002U6LN - Bridleway SM95 Extension | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00002U6LN | 2023-11-29 | 10 - Complete | 2023-12-05
[8 empty] | HS2-000020P0F - Maintenance Access Road to Pond (Off Wills Pastures Road) | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-000020P0F | 2023-11-29 | 10 - Complete | 2023-12-05
[8 empty] | HS2-00003D9CV - Oxford Canal North Embankment Access Stairs CH.118+727 | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00003D9CV | 2023-12-06 | 10 - Complete | 2023-12-07
[8 empty] | HS2-00003D9CW - Oxford Canal North Embankment Access Stairs CH.118+730 | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00003D9CW | 2023-12-06 | 10 - Complete | 2023-12-07
[8 empty] | HS2-00003D9CX - Oxford Canal North Embankment Access Stairs CH.119+900 | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00003D9CX | 2023-12-06 | 10 - Complete | 2023-12-07
[8 empty] | HS2-00003D9CY - Oxford Canal North Embankment Access Stairs CH.119+904 | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00003D9CY | 2023-12-06 | 10 - Complete | 2023-12-07
[8 empty] | HS2-00003GEF2 - Oxford Canal North Embankment 119-DC1 | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00003GEF2 | 2023-12-06 | 10 - Complete | 2023-12-08
[8 empty] | HS2-00003GEF3 - Oxford Canal North Embankment 119-DC2 | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00003GEF3 | 2023-12-06 | 10 - Complete | 2023-12-08
[8 empty] | HS2-00003GEF4 - Oxford Canal North Embankment 119-DC3 | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00003GEF4 | 2023-12-06 | 10 - Complete | 2023-12-08
[8 empty] | HS2-00003GEF5 - Oxford Canal North Embankment 119-DC4 | IDR 236.03 - Oxford Canal North Embankment | IDR 236.03 | HS2-00003GEF5 | 2023-12-06 | 10 - Complete | 2023-12-08
[8 empty] | HS2-000001093 - Oxford Canal Viaduct | IDR 236.02 - Oxford Canal Viaduct | IDR 236.02 | HS2-000001093 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001092 - Oxford Canal South Embankment | IDR 236.01_1 - Oxford Canal South Embankment - Phase 1 (Earthworks) | IDR 236.01_1 | HS2-000001092 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVMF - Oxford Canal South Embankment Landscape Earthworks | IDR 236.01_1 - Oxford Canal South Embankment - Phase 1 (Earthworks) | IDR 236.01_1 | HS2-00002BVMF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVM9 - C3.L.64 Catchment | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00002BVM9 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTJB - C3.T.63 Catchment | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00002CTJB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VXUM - Oxford Canal South Embankment Group-Ancillary Culvert 117-AC1 | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00002VXUM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVMD - C3.L.66 Catchment | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00002BVMD | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTJF - Oxford Canal South Embankment Boundary Perimeter Fence Line | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00002CTJF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTJG - Oxford Canal South Embankment Security Fence Line | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00002CTJG | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VK3N - Oxford Canal South Culvert | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00002VK3N | #N/A | #N/A | #N/A
[8 empty] | HS2-00002V04G - Oxford Canal South Embankment Access Stairs to Culvert Down Main | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00002V04G | 2023-11-17 | 10 - Complete | 2023-11-21
[8 empty] | HS2-000001458 - Footpath SM116a Underpass | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-000001458 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020P01 - Footpath SM116a Diversion | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-000020P01 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CX3G - Footpath SM116a Drainage System | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00002CX3G | #N/A | #N/A | #N/A
[8 empty] | HS2-000020P06 - Maintenance Access Road to Pond (Off Wormleighton Road) | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-000020P06 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVMJ - C3.T.65 Catchment | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00002BVMJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002XCBC - Oxford Canal South Embankment Ditch Crossing 1 | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00002XCBC | 2023-10-31 | 10 - Complete | 2023-11-10
[8 empty] | HS2-000030XBN - Oxford Canal South Embankment Canal Bank Surface Water Outfall Tank | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-000030XBN | #N/A | #N/A | #N/A
[8 empty] | HS2-00003B585 - Oxford Canal South Embankment Ditch Crossing 2 | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00003B585 | 2023-11-01 | 10 - Complete | 2023-11-10
[8 empty] | HS2-00003B5AL - Oxford Canal South Embankment Access Stairs to Culvert Up Main | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00003B5AL | 2023-11-17 | 10 - Complete | 2023-11-21
[8 empty] | HS2-00003B5AM - Oxford Canal South Embankment Access Stairs to Underpass Down Main | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00003B5AM | 2023-11-21 | 10 - Complete | 2023-11-23
[8 empty] | HS2-00003B5AP - Oxford Canal South Embankment Access Stairs to Underpass Up Main | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00003B5AP | 2023-11-21 | 10 - Complete | 2023-11-23
[8 empty] | HS2-00003B5AR - Oxford Canal South Embankment Access Stairs to Viaduct Down Main | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00003B5AR | 2023-11-21 | 10 - Complete | 2023-11-23
[8 empty] | HS2-00003B5AU - Oxford Canal South Embankment Access Stairs to Viaduct Up Main | IDR 236.01 - Oxford Canal South Embankment - Phase 2 (Full Package) | IDR 236.01 | HS2-00003B5AU | 2023-11-21 | 10 - Complete | 2023-11-23
[8 empty] | HS2-000001455 - Banbury Road Overbridge (Boddington) | IDR 235.02 - Banbury Road O/B | IDR 235.02 | HS2-000001455 | 2024-09-19 | 10 - Complete | 2024-09-25
[8 empty] | HS2-00002J4YX - Maintenance Access Road to Pond (off Realigned Banbury Road (East side of HS2)) | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002J4YX | 2025-02-14 | 10 - Complete | 2025-02-18
[8 empty] | HS2-00002U7JR - Boddington Cutting Group-Ancillary Culvert 115-AC8 | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002U7JR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4YW - Diverted Claydon Road (Off Banbury Warwick Road) | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002J4YW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002U7JS - Lower Boddington Embankment-Ancillary Culvert 115-AC9 | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002U7JS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4YU - Banbury Road Realignment (east side of HS2) | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002J4YU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002UU9P - Accommodation Access Road (Off Diverted Claydon Road) | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002UU9P | #N/A | #N/A | #N/A
[8 empty] | HS2-00002U7JQ - Boddington Cutting Group-Ancillary Culvert 115-AC7 | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002U7JQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002U7JM - Lower Boddington Embankment Group-Ancillary Culvert 115-AC4 | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002U7JM | #N/A | #N/A | #N/A
[8 empty] | HS2-000025B3A - Hill Farm Accommodation Access Road | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-000025B3A | 2025-02-14 | 10 - Complete | 2025-02-18
[8 empty] | HS2-000025B3B - Banbury Road Warwick Road (Boddington) Realignment | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-000025B3B | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CUCM - Banbury Road Warwick Road (Boddington) Drainage System | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002CUCM | 2024-02-29 | 10 - Complete | 2024-03-01
[8 empty] | HS2-000025B3C - Wormleighton Maintenance Loop Access Road West (Off Claydon Road) and HS2 pond access road | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-000025B3C | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7UP - Lower Boddington Embankment Group-Ancillary Culvert 115-AC2 | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002N7UP | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7UQ - Lower Boddington Embankment Group-Ancillary Culvert 115-AC3 | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002N7UQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002U7JN - Boddington Cutting Group-Ancillary Culvert 116-AC2 | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002U7JN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4YV - Stoneton Lane Realignment | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002J4YV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002U7JT - Boddington Cutting Group-Ancillary Culvert 116-AC3 | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00002U7JT | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NZU - Boddington ATS Access Road | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-000020NZU | 2025-02-14 | 10 - Complete | 2025-02-18
[8 empty] | HS2-00003LGKV - H4a VRS Transition Foundation Banbury Road | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00003LGKV | 2024-10-23 | 10 - Complete | 2024-10-25
[8 empty] | HS2-00003LUNQ - Farm Accommodation Access Road (Off Diverted Claydon Road) | IDR 235.01-1 - Boddington Cutting - Part 1 Phase 2 | IDR 235.01-1 | HS2-00003LUNQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVMB - Boddington Cutting Landscape Earthworks | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002BVMB | 2024-01-15 | 10 - Complete | 2024-02-07
[8 empty] | HS2-00002CTJD - Boddington Cutting Boundary Perimeter Fence Line | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002CTJD | 2024-04-10 | 10 - Complete | 2024-04-16
[8 empty] | HS2-00002CTJE - Boddington Cutting Security Fence Line | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002CTJE | 2024-04-10 | 10 - Complete | 2024-04-17
[8 empty] | HS2-00002TMFD - Boddington ATS Telecoms | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002TMFD | 2024-02-28 | 10 - Complete | 2024-02-29
[8 empty] | HS2-000001091 - Boddington Cutting | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-000001091 | 2024-04-03 | 10 - Complete | 2024-04-07
[8 empty] | HS2-00002EKZ6 - Stoneton Lane Green Overbridge Ecological Mitigation Site | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002EKZ6 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020134 - Stoneton Lane Green Overbridge | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-000020134 | 2024-10-23 | 10 - Complete | 2024-11-13
[8 empty] | HS2-00002N7UR - Boddington Cutting Group-Ancillary Culvert 116-AC1 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002N7UR | 2023-12-05 | 10 - Complete | 2023-12-13
[8 empty] | HS2-00002TKUY - Boddington Rail System Compound (ATS) UTX 1 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002TKUY | 2024-06-19 | 10 - Complete | 2024-06-20
[8 empty] | HS2-000020NZW - Footpath SM101 Realignment | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-000020NZW | 2024-02-07 | 10 - Complete | 2024-02-13
[8 empty] | HS2-00002CX3F - Footpath SM101 Drainage System | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002CX3F | 2024-02-05 | 10 - Complete | 2024-02-13
[8 empty] | HS2-00002EKZ7 - Wormleighton-Footpath SM101 green overbridge Ecological Mitigation Site | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002EKZ7 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001456 - Footpath SM101 Green Overbridge | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-000001456 | 2025-03-07 | 10 - Complete | 2025-03-19
[8 empty] | HS2-00002TKUZ - Oxford Canal Radio Compound UTX | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002TKUZ | 2024-03-26 | 10 - Complete | 2024-04-02
[8 empty] | HS2-00002WUR6 - Boddington Cutting Planting-East Plot 1 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WUR6 | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WUR7 - Boddington Cutting Planting-East Plot 2 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WUR7 | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WUR8 - Boddington Cutting Planting-East Plot 3 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WUR8 | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WUR9 - Boddington Cutting Planting-East Plot 4 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WUR9 | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WURA - Boddington Cutting Planting-East Plot 5 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURA | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WURB - Boddington Cutting Planting-East Plot 6 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURB | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WURC - Boddington Cutting Planting-East Plot 7 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURC | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WURD - Boddington Cutting Planting-East Plot 8 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURD | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WURE - Boddington Cutting Planting-West Plot 1 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURE | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WURF - Boddington Cutting Planting-West Plot 2 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURF | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WURG - Boddington Cutting Planting-West Plot 3 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURG | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WURH - Boddington Cutting Planting-West Plot 4 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURH | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WURJ - Boddington Cutting Planting-West Plot 5 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURJ | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WURK - Boddington Cutting Planting-West Plot 6 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURK | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WURL - Boddington Cutting Planting-West Plot 7 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURL | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WURM - Boddington Cutting Planting-West Plot 8 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURM | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-00002WURN - Boddington Cutting Planting-West Plot 9 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURN | 2024-05-31 | 10 - Complete | 2024-06-11
[8 empty] | HS2-00002WURP - Boddington Cutting Planting-West Plot 10 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURP | 2024-05-31 | 10 - Complete | 2024-06-11
[8 empty] | HS2-00002WURQ - Boddington Cutting Planting-West Plot 11 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00002WURQ | 2024-05-31 | 10 - Complete | 2024-06-11
[8 empty] | HS2-000039DSA - Glyn Davies Wood-Fox Covert (Bat Licence) Ecological Mitigation Site | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-000039DSA | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GEES - Boddington Cutting (Banbury Road OB) 116-DC1 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003GEES | 2024-03-11 | 10 - Complete | 2024-03-13
[8 empty] | HS2-00003GEET - Boddington Cutting (Banbury Road OB) 115-DC2 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003GEET | 2024-03-11 | 10 - Complete | 2024-03-13
[8 empty] | HS2-00003GEEU - Boddington Cutting (Banbury Road OB) 115-DC3 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003GEEU | 2024-03-11 | 10 - Complete | 2024-03-13
[8 empty] | HS2-00003GEEX - Boddington Cutting (Stoneton Lane Green Bridge) 116-DC 3 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003GEEX | 2024-03-28 | 10 - Complete | 2024-04-03
[8 empty] | HS2-00003GEEY - Boddington Cutting (Footpath SM101 Green OB) 117-DC1 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003GEEY | 2024-03-04 | 10 - Complete | 2024-03-06
[8 empty] | HS2-00003GEEZ - Boddington Cutting (Footpath SM101 Green OB) 117-DC2 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003GEEZ | 2024-03-04 | 10 - Complete | 2024-03-06
[8 empty] | HS2-00003GEF0 - Boddington Cutting (Footpath SM101 Green OB) 117-DC3 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003GEF0 | 2024-03-04 | 10 - Complete | 2024-03-06
[8 empty] | HS2-00003GEF1 - Boddington Cutting (Oxford Canal Radio Compound UTX) 117-DC1 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003GEF1 | 2024-03-04 | 10 - Complete | 2024-03-06
[8 empty] | HS2-00003GJJH - Althorpe Estate Clean Water Pipe | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003GJJH | 2024-01-25 | 10 - Complete | 2024-04-02
[8 empty] | HS2-00003GJJR - Boddington Cutting Access Stairs CH.115.880 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003GJJR | 2024-03-05 | 10 - Complete | 2024-03-13
[8 empty] | HS2-00003GJJS - Boddington Cutting Access Stairs CH.115.930 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003GJJS | 2024-03-05 | 10 - Complete | 2024-03-13
[8 empty] | HS2-00003GJJT - Boddington Cutting Access Stairs CH.115.940 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003GJJT | 2024-03-05 | 10 - Complete | 2024-03-13
[8 empty] | HS2-00003H075 - Boddington Cutting (Banbury Road OB) 115-DC4 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003H075 | 2024-03-13 | 10 - Complete | 2024-03-19
[8 empty] | HS2-00003H076 - Boddington Cutting (Banbury Road OB) 115-DC5 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003H076 | 2024-03-13 | 10 - Complete | 2024-03-19
[8 empty] | HS2-00003H077 - Boddington Cutting (Footpath SM101 Green OB) 117-DC4 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003H077 | 2024-03-04 | 10 - Complete | 2024-03-06
[8 empty] | HS2-00003JG3Y - Wormleighton Sidings UTX 1 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003JG3Y | 2024-04-05 | 10 - Complete | 2024-04-09
[8 empty] | HS2-00003JG3Z - Wormleighton Sidings UTX 2 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003JG3Z | 2024-04-05 | 10 - Complete | 2024-04-08
[8 empty] | HS2-00003K85S - Boddington Rail System Compound (ATS) UTX 2 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003K85S | 2024-06-10 | 10 - Complete | 2024-06-18
[8 empty] | HS2-00003LA5C - Boddington ATS URX 1 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003LA5C | 2024-11-05 | 10 - Complete | 2024-11-12
[8 empty] | HS2-00003LA5D - Boddington ATS URX 2 | IDR 235.01 - Boddington Cutting - Remainder Phase 2 | IDR 235.01 | HS2-00003LA5D | 2024-11-05 | 10 - Complete | 2024-11-12
[8 empty] | HS2-00002BVM2 - C3.L.60 Catchment | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002BVM2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TG2U - Maintenance Access Road (Off Claydon Road SW) | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002TG2U | #N/A | #N/A | #N/A
[8 empty] | HS2-000001090 - Lower Boddington Embankment | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-000001090 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVM5 - C3.L.62 Catchment | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002BVM5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVM7 - Lower Boddington Embankment Landscape Earthworks | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002BVM7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTJ4 - Lower Boddington Embankment Boundary Perimeter Fence Line | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002CTJ4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTJ5 - Lower Boddington Embankment Security Fence Line | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002CTJ5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TG2V - Lower Boddington Embankment Up Main Access Stair-1 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002TG2V | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TGP5 - Lower Boddington Embankment 114-DC1 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002TGP5 | 2024-05-08 | 10 - Complete | 2024-05-09
[8 empty] | HS2-00002TGP6 - Claydon Road Crossover UTX | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002TGP6 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001374 - Cedars Farm Culvert | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-000001374 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CX3K - Cedars Farm Access Drainage System | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002CX3K | #N/A | #N/A | #N/A
[8 empty] | HS2-000025B35 - Cedars Farm Accommodation Access | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-000025B35 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TG29 - Lower Boddington Embankment Ancillary Culvert 114-AC1 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002TG29 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020351 - Cedars Farm Accommodation Overbridge | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-000020351 | 2024-11-05 | 10 - Complete | 2024-12-04
[8 empty] | HS2-00002TG2S - Maintenance Access Road to Pond off Banbury Road (Fir Tree House) | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002TG2S | #N/A | #N/A | #N/A
[8 empty] | HS2-000001375 - Nursery Site Canal Feeder Culvert | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-000001375 | 2024-08-07 | 10 - Complete | 2024-08-21
[8 empty] | HS2-00002KRAR - Nursery Site Canal Feeder Culvert Watercourse Diversion | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002KRAR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002SXNF - C3.T.82 Catchment | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002SXNF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TKUW - GSM-R Point 56 Radio Compound UTX | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002TKUW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7UN - Lower Boddington Embankment Group-Ancillary Culvert 115-AC1 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00002N7UN | 2024-07-18 | 10 - Complete | 2024-08-02
[8 empty] | HS2-000031J4K - Boddington Canal Feeder-Flood Conveyance Ditch | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-000031J4K | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A346 - Lower Boddington Embankment 114-DC2 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A346 | 2024-05-08 | 10 - Complete | 2024-05-09
[8 empty] | HS2-00003A347 - Lower Boddington Embankment 114-DC3 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A347 | 2024-05-08 | 10 - Complete | 2024-05-10
[8 empty] | HS2-00003A348 - Lower Boddington Embankment 114-DC6 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A348 | 2024-05-08 | 10 - Complete | 2024-05-10
[8 empty] | HS2-00003A349 - Lower Boddington Embankment 114-DC7 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A349 | 2024-05-08 | 10 - Complete | 2024-05-10
[8 empty] | HS2-00003A34A - Lower Boddington Embankment 115-DC4 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A34A | 2024-05-08 | 10 - Complete | 2024-05-10
[8 empty] | HS2-00003A34B - Lower Boddington Embankment 115-DC5 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A34B | 2024-05-08 | 10 - Complete | 2024-05-10
[8 empty] | HS2-00003A34D - Lower Boddington Embankment Down Main Access Stair-1 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A34D | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A34E - Lower Boddington Embankment Down Main Access Stair-2 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A34E | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A34F - Lower Boddington Embankment Up Main Access Stair-2 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A34F | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A34G - Lower Boddington Embankment Up Main Access Stair-3 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A34G | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A34H - Lower Boddington Embankment Down Main Access Stair-3 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A34H | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A34J - Lower Boddington Embankment Down Main Access Stair-4 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A34J | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A34K - Lower Boddington Embankment Up Main Access Stair-4 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A34K | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A34L - Lower Boddington Embankment Up Main Access Stair-5 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A34L | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A34M - Lower Boddington Embankment Down Main Access Stair-5 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003A34M | #N/A | #N/A | #N/A
[8 empty] | HS2-00003LAXN - Lower Boddington Embankment Ancilary Culvert 115-AC10 | IDR 234.05 - Lower Boddington Embankment | IDR 234.05 | HS2-00003LAXN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUQQ - Lower Boddington Cutting Planting-East Plot 1 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUQQ | 2024-05-22 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00002WUQR - Lower Boddington Cutting Planting-East Plot 2 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUQR | 2024-05-22 | 10 - Complete | 2024-05-23
[8 empty] | HS2-00002WUQS - Lower Boddington Cutting Planting-East Plot 3 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUQS | 2024-05-22 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00002WUQT - Lower Boddington Cutting Planting-West Plot 1 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUQT | 2024-05-22 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00002WUQU - Lower Boddington Cutting Planting-West Plot 2 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUQU | 2024-05-22 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00002WUQV - Lower Boddington Cutting Planting-West Plot 3 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUQV | 2024-05-22 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00002WUQW - Lower Boddington Cutting Planting-West Plot 4 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUQW | 2024-05-22 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00002WUQX - Lower Boddington Cutting Planting-West Plot 5 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUQX | 2024-05-22 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00002WUQY - Lower Boddington Embankment Planting-East Plot 1 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUQY | 2024-05-22 | 10 - Complete | 2024-05-23
[8 empty] | HS2-00002WUQZ - Lower Boddington Embankment Planting-East Plot 2 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUQZ | 2024-05-22 | 10 - Complete | 2024-05-23
[8 empty] | HS2-00002WUR1 - Lower Boddington Embankment Planting-East Plot 4 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUR1 | 2024-05-22 | 10 - Complete | 2024-05-23
[8 empty] | HS2-00002WUR2 - Lower Boddington Embankment Planting-East Plot 5 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUR2 | 2024-05-22 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00002WUR3 - Lower Boddington Embankment Planting-West Plot 1 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUR3 | 2024-05-22 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00002WUR4 - Lower Boddington Embankment Planting-West Plot 2 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUR4 | 2024-05-22 | 10 - Complete | 2024-05-28
[8 empty] | HS2-00002WUR5 - Lower Boddington Embankment Planting-West Plot 3 | IDR 234.04-2 - Lower Boddington cutting - Landscape Planting | IDR 234.04-2 | HS2-00002WUR5 | 2024-05-22 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00002BVLZ - C3.T.61 Catchment | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-00002BVLZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVM4 - Lower Boddington Cutting Landscape Earthworks | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-00002BVM4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTHZ - Claydon Road Drainage System | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-00002CTHZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTJ0 - Footpath AC2 Northern Diversion | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-00002CTJ0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTJ1 - Lower Boddington Cutting Boundary Perimeter Fence Line | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-00002CTJ1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTJ2 - Lower Boddington Cutting Security Fence Line | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-00002CTJ2 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001089 - Lower Boddington Cutting | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-000001089 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001345 - Claydon Road Overbridge | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-000001345 | 2024-09-11 | 10 - Complete | 2024-09-16
[8 empty] | HS2-00002TG2W - Lower Boddington Cutting Access Stairs | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-00002TG2W | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NYQ - Maintenance Access Road to Pond (Off Claydon Road) | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-000020NYQ | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NYR - Footpath AC1 Diversion | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-000020NYR | #N/A | #N/A | #N/A
[8 empty] | HS2-000025B34 - Claydon Road Realignment | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-000025B34 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DVEF - Footpath AC2 Southern Diversion | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-00002DVEF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TGP3 - Lower Boddington Cutting 113-DC2 | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-00002TGP3 | 2024-09-26 | 10 - Complete | 2024-10-07
[8 empty] | HS2-00002TG2T - Maintenance Access Road (Off Claydon Road NE) | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-00002TG2T | #N/A | #N/A | #N/A
[8 empty] | HS2-00003LAXL - Lower Boddington Cutting 113-DC3 | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-00003LAXL | 2024-09-26 | 10 - Complete | 2024-09-27
[8 empty] | HS2-00003LAXM - Lower Boddington Cutting 113-DC5 | IDR 234.04 - Lower Boddington Cutting | IDR 234.04 | HS2-00003LAXM | 2024-09-26 | 10 - Complete | 2024-10-03
[8 empty] | HS2-000020NYF - Accommodation Access Road (Under Highfurlong Brook Viaduct) | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-000020NYF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVM1 - Highfurlong Brook Embankment Landscape Earthworks | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-00002BVM1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTHT - C3.L.58 Catchment | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-00002CTHT | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTHU - Highfurlong Brook Embankment Boundary Perimeter Fence Line | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-00002CTHU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTHW - Highfurlong Brook Embankment Security Fence Line | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-00002CTHW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TG26 - Highfurlong Brook Embankment Ancillary Culvert 113-AC1 | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-00002TG26 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TG27 - Highfurlong Brook Embankment Ancillary Culvert 113-AC2 | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-00002TG27 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001088 - Highfurlong Brook Embankment | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-000001088 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TG2Z - Highfurlong Brook Embankment 113-DC2 | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-00002TG2Z | 2024-08-09 | 10 - Complete | 2024-08-20
[8 empty] | HS2-00002TGPC - Highfurlong Brook Embankment Access Stairs | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-00002TGPC | 2024-09-17 | 10 - Complete | 2024-09-20
[8 empty] | HS2-00002TG28 - Highfurlong Brook Embankment Ancillary Culvert 113-AC3 | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-00002TG28 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003E24L - Highfurlong Brook Embankment Access Stairs-CH.113+108 | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-00003E24L | 2024-09-17 | 10 - Complete | 2024-09-20
[8 empty] | HS2-00003JN82 - Highfurlong Brook Embankment 113-DC1 | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-00003JN82 | 2024-07-08 | 10 - Complete | 2024-07-15
[8 empty] | HS2-00003JN83 - Highfurlong Brook Embankment 113-DC3 | IDR 234.03 - Highfurlong Brook Embankment - Phase 2 (Full Package) | IDR 234.03 | HS2-00003JN83 | 2024-07-08 | 10 - Complete | 2024-07-15
[8 empty] | HS2-00002WUQF - Highfurlong Brook Viaduct Planting-East Plot 1 | IDR 234.02-2 - Highfurlong Brook Viaduct - Landscape Planting | IDR 234.02-2 | HS2-00002WUQF | 2024-07-26 | 10 - Complete | 2024-08-02
[8 empty] | HS2-00002WUQG - Highfurlong Brook Viaduct Planting-East Plot 2 | IDR 234.02-2 - Highfurlong Brook Viaduct - Landscape Planting | IDR 234.02-2 | HS2-00002WUQG | 2024-07-26 | 10 - Complete | 2024-08-02
[8 empty] | HS2-00002WUQH - Highfurlong Brook Viaduct Planting-West Plot 1 | IDR 234.02-2 - Highfurlong Brook Viaduct - Landscape Planting | IDR 234.02-2 | HS2-00002WUQH | 2024-07-26 | 10 - Complete | 2024-08-08
[8 empty] | HS2-00002WUQJ - Highfurlong Brook Viaduct Planting-West Plot 2 | IDR 234.02-2 - Highfurlong Brook Viaduct - Landscape Planting | IDR 234.02-2 | HS2-00002WUQJ | 2024-07-26 | 10 - Complete | 2024-08-08
[8 empty] | HS2-00002WUQK - Highfurlong Brook Embankment Planting-East Plot 1 | IDR 234.02-2 - Highfurlong Brook Viaduct - Landscape Planting | IDR 234.02-2 | HS2-00002WUQK | 2024-07-26 | 10 - Complete | 2024-08-02
[8 empty] | HS2-00002WUQL - Highfurlong Brook Embankment Planting-East Plot 2 | IDR 234.02-2 - Highfurlong Brook Viaduct - Landscape Planting | IDR 234.02-2 | HS2-00002WUQL | 2024-07-26 | 10 - Complete | 2024-08-02
[8 empty] | HS2-00002WUQM - Highfurlong Brook Embankment Planting-West Plot 1 | IDR 234.02-2 - Highfurlong Brook Viaduct - Landscape Planting | IDR 234.02-2 | HS2-00002WUQM | 2024-07-26 | 10 - Complete | 2024-08-08
[8 empty] | HS2-00002WUQN - Highfurlong Brook Embankment Planting-West Plot 2 | IDR 234.02-2 - Highfurlong Brook Viaduct - Landscape Planting | IDR 234.02-2 | HS2-00002WUQN | 2024-07-26 | 10 - Complete | 2024-08-02
[8 empty] | HS2-00002WUQP - Highfurlong Brook Embankment Planting-West Plot 3 | IDR 234.02-2 - Highfurlong Brook Viaduct - Landscape Planting | IDR 234.02-2 | HS2-00002WUQP | 2024-07-26 | 10 - Complete | 2024-08-02
[8 empty] | HS2-000039DSC - Lower Boddington Copse (Bat Licence) Ecological Mitigation Site | IDR 234.02-2 - Highfurlong Brook Viaduct - Landscape Planting | IDR 234.02-2 | HS2-000039DSC | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTHS - Highfurlong Brook Diversion | IDR 234.02 - Highfurlong Brook Viaduct | IDR 234.02 | HS2-00002CTHS | 2024-02-28 | 10 - Complete | 2024-02-28
[8 empty] | HS2-000001087 - Highfurlong Brook Viaduct | IDR 234.02 - Highfurlong Brook Viaduct | IDR 234.02 | HS2-000001087 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTHK - C3.L.57 Catchment | IDR 234.01 - Aston Le Walls Embankment - Phase 2 (Full Package) | IDR 234.01 | HS2-00002CTHK | 2024-12-09 | 10 - Complete | 2025-01-09
[8 empty] | HS2-00002CTHL - C3.T.56 Catchment | IDR 234.01 - Aston Le Walls Embankment - Phase 2 (Full Package) | IDR 234.01 | HS2-00002CTHL | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTHM - Aston Le Walls Embankment Boundary Perimeter Fence Line | IDR 234.01 - Aston Le Walls Embankment - Phase 2 (Full Package) | IDR 234.01 | HS2-00002CTHM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTHP - Aston Le Walls Embankment Security Fence Line | IDR 234.01 - Aston Le Walls Embankment - Phase 2 (Full Package) | IDR 234.01 | HS2-00002CTHP | #N/A | #N/A | #N/A
[8 empty] | HS2-000001086 - Aston Le Walls Embankment | IDR 234.01 - Aston Le Walls Embankment - Phase 2 (Full Package) | IDR 234.01 | HS2-000001086 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002U4NE - Aston Le Walls Embankment Group-Ancillary Culvert 112-AC1 | IDR 234.01 - Aston Le Walls Embankment - Phase 2 (Full Package) | IDR 234.01 | HS2-00002U4NE | 2025-01-09 | 10 - Complete | 2025-01-16
[8 empty] | HS2-00002U4ND - Aston Le Walls Embankment Group-Ancillary Culvert 112-AC2 | IDR 234.01 - Aston Le Walls Embankment - Phase 2 (Full Package) | IDR 234.01 | HS2-00002U4ND | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TGPB - Aston Le Walls Embankment Access Stairs | IDR 234.01 - Aston Le Walls Embankment - Phase 2 (Full Package) | IDR 234.01 | HS2-00002TGPB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RE08 - Flood Compensation Area-112 | IDR 234.01 - Aston Le Walls Embankment - Phase 2 (Full Package) | IDR 234.01 | HS2-00002RE08 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003AL3L - Aston Le Walls Embankment Access Stairs-East | IDR 234.01 - Aston Le Walls Embankment - Phase 2 (Full Package) | IDR 234.01 | HS2-00003AL3L | #N/A | #N/A | #N/A
[8 empty] | HS2-000000161 - Chipping Warden Green Tunnel | IDR 233.02 - Chipping Warden Green Tunnel - Stage 2 Advanced Works | IDR 233.02 | HS2-000000161 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTH6 - Culworth Road Bridleway and Footpath AE28 Realignment | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00002CTH6 | 2024-12-06 | 10 - Complete | 2024-12-11
[8 empty] | HS2-000020NXG - Blackgrounds Farm Accommodation Access Realignment (off Culworth Road-west of HS2) | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-000020NXG | 2024-11-19 | 10 - Complete | 2024-12-11
[8 empty] | HS2-000020NXK - Culworth Road Turning Head | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-000020NXK | 2024-11-12 | 10 - Complete | 2024-12-02
[8 empty] | HS2-00002CX3P - Culworth Road Bridleway and Chipping Warden South Portal Access Road Drainage System | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00002CX3P | 2024-07-30 | 10 - Complete | 2024-08-13
[8 empty] | HS2-000020NXM - Chipping Warden South Portal Access Road (Off Culworth Road) | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-000020NXM | 2024-11-12 | 10 - Complete | 2024-12-02
[8 empty] | HS2-00002TMF8 - Chipping Warden Green Tunnel South Portal Building Fire-fighting Water | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00002TMF8 | 2024-05-20 | 10 - Complete | 2024-05-21
[8 empty] | HS2-00002TMF9 - Chipping Warden Green Tunnel South Portal Building Telecoms | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00002TMF9 | 2024-05-07 | 10 - Complete | 2024-06-12
[8 empty] | HS2-000025B2P - Chipping Warden Tunnel South Portal Building | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-000025B2P | 2024-09-03 | 10 - Complete | 0
[8 empty] | HS2-00002NJ07 - Chipping Warden Green Tunnel South Portal | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00002NJ07 | 2024-09-05 | 10 - Complete | 2024-11-08
[8 empty] | HS2-00002EK7X - Chipping Warden Green Tunnel South Portal UTX | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00002EK7X | 2024-05-03 | 10 - Complete | 2024-05-10
[8 empty] | HS2-000025B2Q - Footpath AE20 AE21 Reinstatement | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-000025B2Q | 2024-09-19 | 10 - Complete | 2024-11-27
[8 empty] | HS2-00003124M - Chipping Warden Green Tunnel Landscape Earthworks South | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003124M | 2024-09-12 | 10 - Complete | 2024-11-25
[8 empty] | HS2-000035Q9C - Old Airfield Perimeter Track | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-000035Q9C | 2024-11-21 | 10 - Complete | 2024-12-04
[8 empty] | HS2-000035Q99 - Footpath AE16 | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-000035Q99 | 2024-11-12 | 10 - Complete | 2024-12-03
[8 empty] | HS2-000035Q9A - Footpath AE17 | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-000035Q9A | 2024-10-25 | 10 - Complete | 2024-11-05
[8 empty] | HS2-000035Q9B - Chipping Warden Green Tunnel-Edgcote Cutting Transition Zone Earthworks | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-000035Q9B | 2024-09-12 | 10 - Complete | 2024-11-15
[8 empty] | HS2-0000386TE - C3.T.83 Catchment | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-0000386TE | 2024-08-06 | 10 - Complete | 2024-08-20
[8 empty] | HS2-00003B93W - Chipping Warden Green Tunnel Access Stair CH.110.025 | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003B93W | 2024-07-25 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00003B93X - Chipping Warden Green Tunnel Access Stair CH.112.225 | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003B93X | 2024-08-09 | 10 - Complete | 2024-08-15
[8 empty] | HS2-00003CPYT - Blackgrounds Farm Accommodation Access Road Drainage System | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003CPYT | 2024-09-26 | 10 - Complete | 2024-09-30
[8 empty] | HS2-00003FV0K - Chipping Warden Green Tunnel Access Stairs CH.109.810 | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003FV0K | 2024-07-25 | 10 - Complete | 2024-08-08
[8 empty] | HS2-00003FV0Q - Chipping Warden Green Tunnel South Portal-Ditch Crossing 3 | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003FV0Q | 2024-10-11 | 10 - Complete | 2024-10-14
[8 empty] | HS2-00003FV0R - Chipping Warden Green Tunnel South Portal-Ditch Crossing 4 | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003FV0R | 2024-10-25 | 10 - Complete | 2024-11-05
[8 empty] | HS2-00003H5JH - Footpath AE12 | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003H5JH | 2024-10-25 | 10 - Complete | 2024-11-05
[8 empty] | HS2-00003J16B - Chipping Warden North Portal-Ditch Crossing 3 | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003J16B | 2024-12-02 | 10 - Complete | 2024-12-09
[8 empty] | HS2-00003JRG9 - Chipping Warden Green Tunnel South Portal-Evacuation Walkways | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003JRG9 | 2024-11-12 | 10 - Complete | 2024-11-15
[8 empty] | HS2-00003JRGA - Chipping Warden Green Tunnel North Portal-Evacuation Walkways | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003JRGA | 2024-11-08 | 10 - Complete | 2024-11-15
[8 empty] | HS2-00003LA5E - Old Airfield Perimeter Track Drainage System | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003LA5E | 2024-10-15 | 10 - Complete | 2024-10-17
[8 empty] | HS2-00003LCQD - Blackgrounds Farm Private Water Main | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003LCQD | 2024-10-28 | 10 - Complete | 2024-11-06
[8 empty] | HS2-00003LCQE - Blackgrounds Farm LV Supply | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003LCQE | 2024-10-28 | 10 - Complete | 2024-11-25
[8 empty] | HS2-00003LGKW - Chipping Warden Green Tunnel South Security Fence | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003LGKW | 2024-10-30 | 10 - Complete | 2024-11-11
[8 empty] | HS2-00003LGKX - Chipping Warden Green Tunnel North Security Fence | IDR 233.01-3 - Chipping Warden Green Tunnel - Associated Assets South - Part 3 | IDR 233.01-3 | HS2-00003LGKX | 2024-10-30 | 10 - Complete | 2024-11-08
[8 empty] | HS2-00002J4YT - Reinstatement of accommodation access road to Valley View Farm | IDR 233.01-2 - Chipping Warden Green Tunnel - Associated Assets North | IDR 233.01-2 | HS2-00002J4YT | #N/A | #N/A | #N/A
[8 empty] | HS2-000020364 - Appletree Lane Reinstatement | IDR 233.01-2 - Chipping Warden Green Tunnel - Associated Assets North | IDR 233.01-2 | HS2-000020364 | 2025-02-06 | 10 - Complete | 2025-02-12
[8 empty] | HS2-00002CX3A - Appletree Lane Drainage System | IDR 233.01-2 - Chipping Warden Green Tunnel - Associated Assets North | IDR 233.01-2 | HS2-00002CX3A | 2025-01-08 | 10 - Complete | 2025-01-17
[8 empty] | HS2-00002TMFA - Chipping Warden Green Tunnel North Portal Building Fire Fighting Water | IDR 233.01-2 - Chipping Warden Green Tunnel - Associated Assets North | IDR 233.01-2 | HS2-00002TMFA | 2024-12-12 | 10 - Complete | 2024-01-14
[8 empty] | HS2-00002TMFB - Chipping Warden Green Tunnel North Portal Building Telecoms | IDR 233.01-2 - Chipping Warden Green Tunnel - Associated Assets North | IDR 233.01-2 | HS2-00002TMFB | 2024-12-12 | 10 - Complete | 2025-01-22
[8 empty] | HS2-00002TMFC - Chipping Warden MPATS Telecoms | IDR 233.01-2 - Chipping Warden Green Tunnel - Associated Assets North | IDR 233.01-2 | HS2-00002TMFC | 2024-12-12 | 10 - Complete | 2024-01-14
[8 empty] | HS2-000020NXY - Chipping Warden Green Tunnel North Portal Midpoint ATS Pond and Accommodation Access Road (Off Appletree Lane) | IDR 233.01-2 - Chipping Warden Green Tunnel - Associated Assets North | IDR 233.01-2 | HS2-000020NXY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTHF - Chipping Warden Tunnel North Portal Building | IDR 233.01-2 - Chipping Warden Green Tunnel - Associated Assets North | IDR 233.01-2 | HS2-00002CTHF | 2025-01-23 | 10 - Complete | 2025-02-07
[8 empty] | HS2-00002NJ06 - Chipping Warden Green Tunnel North Portal | IDR 233.01-2 - Chipping Warden Green Tunnel - Associated Assets North | IDR 233.01-2 | HS2-00002NJ06 | 2024-04-10 | 10 - Complete | 2024-05-02
[8 empty] | HS2-00002EK85 - Chipping Warden Green Tunnel North Portal and Chipping Warden MPATS UTX | IDR 233.01-2 - Chipping Warden Green Tunnel - Associated Assets North | IDR 233.01-2 | HS2-00002EK85 | 2024-03-28 | 10 - Complete | 2024-04-03
[8 empty] | HS2-00003124L - Chipping Warden Green Tunnel Landscape Earthworks North | IDR 233.01-2 - Chipping Warden Green Tunnel - Associated Assets North | IDR 233.01-2 | HS2-00003124L | #N/A | #N/A | #N/A
[8 empty] | HS2-00003AQDH - Chipping Warden North Portal-Ditch Crossing 2 | IDR 233.01-2 - Chipping Warden Green Tunnel - Associated Assets North | IDR 233.01-2 | HS2-00003AQDH | 2024-09-09 | 10 - Complete | 2024-09-20
[8 empty] | HS2-00003B93N - Chipping Warden North Portal-Ditch Crossing 1 | IDR 233.01-2 - Chipping Warden Green Tunnel - Associated Assets North | IDR 233.01-2 | HS2-00003B93N | 2024-06-07 | 10 - Complete | 2024-06-12
[8 empty] | HS2-00002BVLS - Chipping Warden Green Tunnel Landscape Earthworks | IDR 233.01 - Chipping Warden Green Tunnel - A361 | IDR 233.01 | HS2-00002BVLS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EF97 - A361 Byfield Road Realignment | IDR 233.01 - Chipping Warden Green Tunnel - A361 | IDR 233.01 | HS2-00002EF97 | 2024-04-25 | 10 - Complete | 2024-05-09
[8 empty] | HS2-00002YKZ9 - A361 Byfield Road Drainage System | IDR 233.01 - Chipping Warden Green Tunnel - A361 | IDR 233.01 | HS2-00002YKZ9 | 2024-06-19 | 10 - Complete | 2024-07-02
[8 empty] | HS2-000030K81 - Chipping Warden Surface Water Sewer | IDR 232.04 - Chipping Warden Surface Water Sewer | IDR 232.04 | HS2-000030K81 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVLM - C3.L.49 Catchment | IDR 232.03 - Edgcote Cutting | IDR 232.03 | HS2-00002BVLM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTH7 - Edgcote Cutting Boundary Perimeter Fence Line | IDR 232.03 - Edgcote Cutting | IDR 232.03 | HS2-00002CTH7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTH9 - Edgcote Cutting Security Fence Line | IDR 232.03 - Edgcote Cutting | IDR 232.03 | HS2-00002CTH9 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DVEK - Edgcote Cutting Landscape Earthworks | IDR 232.03 - Edgcote Cutting | IDR 232.03 | HS2-00002DVEK | #N/A | #N/A | #N/A
[8 empty] | HS2-000001085 - Edgcote Cutting | IDR 232.03 - Edgcote Cutting | IDR 232.03 | HS2-000001085 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUQ2 - Edgcote Cutting Planting-East Plot 1 | IDR 232.03 - Edgcote Cutting | IDR 232.03 | HS2-00002WUQ2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUQ3 - Edgcote Cutting Planting-East Plot 2 | IDR 232.03 - Edgcote Cutting | IDR 232.03 | HS2-00002WUQ3 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUQ4 - Edgcote Cutting Planting-West Plot 1 | IDR 232.03 - Edgcote Cutting | IDR 232.03 | HS2-00002WUQ4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUQ5 - Edgcote Cutting Planting-West Plot 2 | IDR 232.03 - Edgcote Cutting | IDR 232.03 | HS2-00002WUQ5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUQ6 - Edgcote Cutting Planting-West Plot 3 | IDR 232.03 - Edgcote Cutting | IDR 232.03 | HS2-00002WUQ6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003B9TJ - Accommodation Access Road to Blackgrounds Farm East | IDR 232.03 - Edgcote Cutting | IDR 232.03 | HS2-00003B9TJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003G2C8 - Edgcote Cutting Ditch Crossing 01 | IDR 232.03 - Edgcote Cutting | IDR 232.03 | HS2-00003G2C8 | #N/A | #N/A | #N/A
[8 empty] | HS2-000025B2N - Maintenance Access Road to Pond (Off Welsh Road) | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-000025B2N | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVLJ - C3.L.46 Catchment | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-00002BVLJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGZ - C3.L.47 Catchment | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-00002CTGZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTH0 - C3.L.48 Catchment | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-00002CTH0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTH1 - C3.T.45 catchment | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-00002CTH1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTH2 - Edgcote North Embankment Boundary Perimeter Fence Line | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-00002CTH2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTH4 - Edgcote North Embankment Security Fence Line | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-00002CTH4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TTKC - Edgcote North Embankment Group Monitoring System | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-00002TTKC | #N/A | #N/A | #N/A
[8 empty] | HS2-000001084 - Edgcote North Embankment | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-000001084 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUPY - Edgcote North Embankment Planting-East Plot 1 | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-00002WUPY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUPZ - Edgcote North Embankment Planting-East Plot 2 | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-00002WUPZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUQ0 - Edgcote North Embankment Planting-West Plot 1 | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-00002WUQ0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUQ1 - Edgcote North Embankment Planting-West Plot 2 | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-00002WUQ1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002ZGDE - Osierbed Spinney Watercourse Diversion | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-00002ZGDE | #N/A | #N/A | #N/A
[8 empty] | HS2-000030RKW - Edgcote North Embankment Group Utilities Protection Slab | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-000030RKW | #N/A | #N/A | #N/A
[8 empty] | HS2-000032Q2M - Edgcote North Embankment Group Channel | IDR 232.02-2 - Edgcote North Embankment Remaining Assets | IDR 232.02-2 | HS2-000032Q2M | #N/A | #N/A | #N/A
[8 empty] | HS2-000001443 - Osierbed Spinney Culvert | IDR 232.02-1 - Osierbed Spinney Culvert | IDR 232.02-1 | HS2-000001443 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EL0J - Edgecote Registered Battlefield | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002EL0J | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGU - Wardington Road Realignment | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002CTGU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGV - Edgcote Viaduct Boundary Perimeter Fence Line | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002CTGV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGX - Edgcote Viaduct Security Fence Line | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002CTGX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGY - River Cherwell Diversion | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002CTGY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKZ1 - Edgcote Ecological Mitigation Site (A) | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002EKZ1 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001083 - Edgcote Viaduct | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-000001083 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKZ2 - Trafford Bridge Ecological Mitigation Site | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002EKZ2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EL0K - Trafford Bridge Listed Building | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002EL0K | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKZ3 - Edgcote Ecological Mitigation Site (B) | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002EKZ3 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NXB - Footpath AE5 Diversion | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-000020NXB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUPU - Edgcote Viaduct Planting-East Plot 1 | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002WUPU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUPV - Edgcote Viaduct Planting-East Plot 2 | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002WUPV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUPW - Edgcote Viaduct Planting-West Plot 1 | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002WUPW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUPX - Edgcote Viaduct Planting-West Plot 2 | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002WUPX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002ZH4B - Edgcote Viaduct North Access Stairs | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002ZH4B | #N/A | #N/A | #N/A
[8 empty] | HS2-00002ZH4C - Edgcote Viaduct South Access Stairs 1 | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002ZH4C | #N/A | #N/A | #N/A
[8 empty] | HS2-00002ZH4D - Edgcote Viaduct North Transition Earthworks | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002ZH4D | #N/A | #N/A | #N/A
[8 empty] | HS2-00002ZH4E - Edgcote Viaduct South Transition Earthworks | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00002ZH4E | #N/A | #N/A | #N/A
[8 empty] | HS2-000030RKQ - Edgcote Viaduct Group Ditch Crossings | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-000030RKQ | #N/A | #N/A | #N/A
[8 empty] | HS2-000033BZ5 - Edgcote Viaduct-Flood Compensation Area | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-000033BZ5 | #N/A | #N/A | #N/A
[8 empty] | HS2-000039DSH - Edgcote Viaduct South Access Stairs 2 | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-000039DSH | #N/A | #N/A | #N/A
[8 empty] | HS2-000039DSJ - Edgcote Viaduct South Access Stairs 3 | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-000039DSJ | #N/A | #N/A | #N/A
[8 empty] | HS2-000039DSK - Edgcote Viaduct North Access Stairs 2 | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-000039DSK | #N/A | #N/A | #N/A
[8 empty] | HS2-00003KR5G - Footpath AE5 Osierbed Spinney Crossing | IDR 232.01 - Edgcote Viaduct (Full Package) | IDR 232.01 | HS2-00003KR5G | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVLC - C3.L.44 Catchment | IDR 231.03 - Edgcote South Embankment | IDR 231.03 | HS2-00002BVLC | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGQ - C3.T.43 Catchment | IDR 231.03 - Edgcote South Embankment | IDR 231.03 | HS2-00002CTGQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGR - Edgcote South Embankment Boundary Perimeter Fence Line | IDR 231.03 - Edgcote South Embankment | IDR 231.03 | HS2-00002CTGR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGT - Edgcote South Embankment Security Fence Line | IDR 231.03 - Edgcote South Embankment | IDR 231.03 | HS2-00002CTGT | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DVDM - Edgcote South Embankment Planting | IDR 231.03 - Edgcote South Embankment | IDR 231.03 | HS2-00002DVDM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TTKA - Edgcote South Embankment Group Monitoring System | IDR 231.03 - Edgcote South Embankment | IDR 231.03 | HS2-00002TTKA | #N/A | #N/A | #N/A
[8 empty] | HS2-000001082 - Edgcote South Embankment | IDR 231.03 - Edgcote South Embankment | IDR 231.03 | HS2-000001082 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002YNBE - Edgcote South Embankment Culvert | IDR 231.03 - Edgcote South Embankment | IDR 231.03 | HS2-00002YNBE | #N/A | #N/A | #N/A
[8 empty] | HS2-000030RKS - Edgcote South Embankment Group Ditch Crossings | IDR 231.03 - Edgcote South Embankment | IDR 231.03 | HS2-000030RKS | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NWV - Maintenance Access to Pond (Off Bridleway AG10 SW) | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-000020NWV | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NWW - Danes Moor ATS Access Road | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-000020NWW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGM - Culworth Cutting Boundary Perimeter Fence Line | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00002CTGM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGP - Culworth Cutting Security Fence Line | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00002CTGP | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DVDL - Culworth Cutting Planting | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00002DVDL | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TTK9 - Culworth Cutting Group Monitoring System | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00002TTK9 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001081 - Culworth Cutting | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-000001081 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TMF7 - Danes Moor ATS Telecoms | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00002TMF7 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NWZ - Bridleway AG10 Diversion | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-000020NWZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CX3L - Bridleway AG10 Drainage System | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00002CX3L | #N/A | #N/A | #N/A
[8 empty] | HS2-000025B2L - Maintenance Access Road to Pond (Off Bridleway AG10 NW) | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-000025B2L | #N/A | #N/A | #N/A
[8 empty] | HS2-000025B2M - Bridleway AG10 Accommodation Access Road | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-000025B2M | #N/A | #N/A | #N/A
[8 empty] | HS2-00003JQLX - Culworth Cutting Ditch Crossing 01 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003JQLX | #N/A | #N/A | #N/A
[8 empty] | HS2-00003JQLY - Culworth Cutting Ditch Crossing 02 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003JQLY | #N/A | #N/A | #N/A
[8 empty] | HS2-00003JQLZ - Culworth Cutting Ditch Crossing 03 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003JQLZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003JQM0 - Culworth Cutting Ditch Crossing 04 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003JQM0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003JQM1 - Culworth Cutting Ditch Crossing 05 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003JQM1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003K2XR - Culworth Cutting Access Stairs 01 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003K2XR | #N/A | #N/A | #N/A
[8 empty] | HS2-00003K2XS - Culworth Cutting Access Stairs 02 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003K2XS | #N/A | #N/A | #N/A
[8 empty] | HS2-00003K2XT - Culworth Cutting Access Stairs 03 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003K2XT | #N/A | #N/A | #N/A
[8 empty] | HS2-00003K2XU - Culworth Cutting Access Stairs 04 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003K2XU | #N/A | #N/A | #N/A
[8 empty] | HS2-00003K2XV - Culworth Cutting Access Stairs 05 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003K2XV | #N/A | #N/A | #N/A
[8 empty] | HS2-00003L6DF - Danes Moor ATS UTX HV | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003L6DF | #N/A | #N/A | #N/A
[8 empty] | HS2-00003L6DG - Danes Moor ATS UTX LV1 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003L6DG | #N/A | #N/A | #N/A
[8 empty] | HS2-00003L6DH - Danes Moor ATS UTX LV2 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003L6DH | #N/A | #N/A | #N/A
[8 empty] | HS2-00003LA58 - Culworth Cutting Ditch Crossing 06 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003LA58 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003LA59 - Culworth Cutting Ditch Crossing 07 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003LA59 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003LA5A - Culworth Cutting Ditch Crossing 08 | IDR 231.02-2 - Culworth Cutting Remaining Assets | IDR 231.02-2 | HS2-00003LA5A | #N/A | #N/A | #N/A
[8 empty] | HS2-000001344 - Bridleway AG10 Accommodation Overbridge | IDR 231.02-1 - Bridleway AG10 Accommodation Overbridge | IDR 231.02-1 | HS2-000001344 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGJ - Culworth Embankment Boundary Perimeter Fence Line | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-00002CTGJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGL - Culworth Embankment Security Fence Line | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-00002CTGL | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DVDK - Culworth Embankment Planting | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-00002DVDK | #N/A | #N/A | #N/A
[8 empty] | HS2-000001080 - Culworth Embankment | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-000001080 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CX3N - Bridleway AG9 Drainage System | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-00002CX3N | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7UL - Culworth Embankment Group-Ancillary Culvert 107-AC2 | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-00002N7UL | #N/A | #N/A | #N/A
[8 empty] | HS2-000001442 - Hill Farm Culvert | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-000001442 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002KRAS - Hill Farm Culvert Watercourse Diversion | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-00002KRAS | #N/A | #N/A | #N/A
[8 empty] | HS2-00003301D - Culworth Embankment Culvert | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-00003301D | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A04H - Culworth Embankment Group Ditch Crossing 01 | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-00003A04H | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A04J - Culworth Embankment Group Ditch Crossing 02 | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-00003A04J | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A04M - Culworth Embankment Group Ditch Crossing 03 | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-00003A04M | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A04K - Culworth Embankment Group Ditch Crossing 04 | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-00003A04K | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A04L - Culworth Embankment Group Ditch Crossing 05 | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-00003A04L | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A36D - Culworth Embankment Group Ditch Crossing 06 | IDR 231.01-2 - Culworth Embankment Stage 2 | IDR 231.01-2 | HS2-00003A36D | #N/A | #N/A | #N/A
[8 empty] | HS2-000025B2K - Bridleway AG9 Diversion | IDR 231.01 - Culworth Embankment AG9 | IDR 231.01 | HS2-000025B2K | #N/A | #N/A | #N/A
[8 empty] | HS2-00002SZLV - Bridleway AG9 Overbridge Impact Protection Walls | IDR 231.01 - Culworth Embankment AG9 | IDR 231.01 | HS2-00002SZLV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RE02 - Culworth Embankment Group-Ancillary Culvert 107-AC5 | IDR 231.01 - Culworth Embankment AG9 | IDR 231.01 | HS2-00002RE02 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001343 - Bridleway AG9 Overbridge | IDR 231.01 - Culworth Embankment AG9 | IDR 231.01 | HS2-000001343 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003KFPY - Lower Thorpe Area Landscaping and Fencing Boundary/Perimeter Fence Line | IDR 230.07 - Lower Thorpe Area - Landscape planting and Fencing | IDR 230.07 | HS2-00003KFPY | #N/A | #N/A | #N/A
[8 empty] | HS2-00003KFPZ - Lower Thorpe Area Landscaping and Fencing Security Fence Line | IDR 230.07 - Lower Thorpe Area - Landscape planting and Fencing | IDR 230.07 | HS2-00003KFPZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003KFQ0 - Lower Thorpe Area Landscaping and Fencing Planting Plot | IDR 230.07 - Lower Thorpe Area - Landscape planting and Fencing | IDR 230.07 | HS2-00003KFQ0 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001342 - Culworth Grounds Accommodation Overbridge | IDR 230.06-1 - Lower Thorpe North Cutting - Culworth Grounds Accommodation Overbridge | IDR 230.06-1 | HS2-000001342 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKZW - Lower Thorpe Ecological Mitigation Site (B) | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00002EKZW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VBQF - Maintenance Access Road to WPD (off Culworth Grounds Accommodation Access Realignment) | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00002VBQF | #N/A | #N/A | #N/A
[8 empty] | HS2-000025B2J - Culworth Grounds Accommodation Access Realignment | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-000025B2J | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CX3M - Culworth Grounds Access Drainage System | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00002CX3M | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVL3 - C3.L.38 catchment | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00002BVL3 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGB - Lower Thorpe North Cutting Boundary Perimeter Fence Line | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00002CTGB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGD - Lower Thorpe North Cutting Security Fence Line | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00002CTGD | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DVDJ - Lower Thorpe North Cutting Planting | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00002DVDJ | #N/A | #N/A | #N/A
[8 empty] | HS2-000001079 - Lower Thorpe North Cutting | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-000001079 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VBQE - Maintenance Access Road to GSMR (off Culworth Grounds Accommodation Access Realignment) | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00002VBQE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TKUV - Lower Thorpe Radio UTX | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00002TKUV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGE - C3.L.40 Catchment | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00002CTGE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTGH - C3.T.39 Catchment | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00002CTGH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RE01 - Culworth Embankment Group-Ancillary Culvert 107-AC4 | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00002RE01 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RDZZ - Culworth Embankment Group-Ancillary Culvert 107-AC3 | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00002RDZZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D8VZ - Minor Tributary of Culworth Brook-Watercourse realignment | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00003D8VZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003EB2Y - Lower Thorpe North Cutting Group-Ancillary Culvert 105-AC3 | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00003EB2Y | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GJJW - Maintenance Access to WPD-Retaining wall | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00003GJJW | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GPKS - Ditch Crossing 01 LTNC east cutting | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00003GPKS | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GPKT - Ditch Crossing 02 Culworth Grounds Accommodation | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00003GPKT | #N/A | #N/A | #N/A
[8 empty] | HS2-00003JQLV - Ditch Crossing 03-LTNC east cutting | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00003JQLV | #N/A | #N/A | #N/A
[8 empty] | HS2-00003LENS - Lower Thorpe Maintenance Access Road | IDR 230.06 - Lower Thorpe North Cutting - (EI-1022 - De-scoped from ASC and transferred to Typsa) | IDR 230.06 | HS2-00003LENS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTFX - Lower Thorpe South Embankment Noise Barrier Line | IDR 230.05-2 - Lower Thorpe North Embankment (Phase 2 Noise Barrier) | IDR 230.05-2 | HS2-00002CTFX | 2024-08-29 | 10 - Complete | 2024-09-06
[8 empty] | HS2-00002CTG0 - Lower Thorpe South Cutting Noise Barrier Line | IDR 230.05-2 - Lower Thorpe North Embankment (Phase 2 Noise Barrier) | IDR 230.05-2 | HS2-00002CTG0 | 2024-08-28 | 10 - Complete | 2024-09-25
[8 empty] | HS2-00002TGPD - Lower Thorpe South Embankment Ditch Crossings | IDR 230.05-2 - Lower Thorpe North Embankment (Phase 2 Noise Barrier) | IDR 230.05-2 | HS2-00002TGPD | 2024-05-22 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00002CTG8 - Lower Thorpe North Embankment Noise Barrier Line | IDR 230.05-2 - Lower Thorpe North Embankment (Phase 2 Noise Barrier) | IDR 230.05-2 | HS2-00002CTG8 | 2024-10-28 | 10 - Complete | 2024-10-30
[8 empty] | HS2-00002TTH0 - Lower Thorpe North Embankment Ditch Crossing | IDR 230.05-2 - Lower Thorpe North Embankment (Phase 2 Noise Barrier) | IDR 230.05-2 | HS2-00002TTH0 | 2024-10-22 | 10 - Complete | 2024-10-24
[8 empty] | HS2-00002CTG6 - C3.T.37 Catchment | IDR 230.05 - Lower Thorpe North Embankment Group | IDR 230.05 | HS2-00002CTG6 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001078 - Lower Thorpe North Embankment | IDR 230.05 - Lower Thorpe North Embankment Group | IDR 230.05 | HS2-000001078 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001440 - Lower Thorpe Drop Inlet Culvert | IDR 230.05 - Lower Thorpe North Embankment Group | IDR 230.05 | HS2-000001440 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001441 - Culworth Grounds Culvert | IDR 230.05 - Lower Thorpe North Embankment Group | IDR 230.05 | HS2-000001441 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NW8 - Maintenance Access Road to Pond (Off Banbury Lane NE) | IDR 230.04 - Lower Thorpe South Cutting Group | IDR 230.04 | HS2-000020NW8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVKX - C3.L.32 Catchment | IDR 230.04 - Lower Thorpe South Cutting Group | IDR 230.04 | HS2-00002BVKX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RE04 - Maintenance Access Road to Pond (Off Banbury Lane NE) Drainage System | IDR 230.04 - Lower Thorpe South Cutting Group | IDR 230.04 | HS2-00002RE04 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001077 - Lower Thorpe South Cutting | IDR 230.04 - Lower Thorpe South Cutting Group | IDR 230.04 | HS2-000001077 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTFV - C3.L.31 Catchment | IDR 230.03 - Lower Thorpe South Embankment Group | IDR 230.03 | HS2-00002CTFV | #N/A | #N/A | #N/A
[8 empty] | HS2-000001076 - Lower Thorpe South Embankment | IDR 230.03 - Lower Thorpe South Embankment Group | IDR 230.03 | HS2-000001076 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001075 - Lower Thorpe Viaduct | IDR 230.02 - Lower Thorpe Viaduct - Phase 2 (Full Package) | IDR 230.02 | HS2-000001075 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTFN - C3.T.29 Catchment | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002CTFN | 2025-02-06 | 10 - Complete | 2025-02-20
[8 empty] | HS2-00002CTFQ - Thorpe Mandeville Embankment Noise Barrier Line | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002CTFQ | 2024-05-22 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00002EKZV - Lower Thorpe Ecological Mitigation Site (A) | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002EKZV | 2024-08-01 | 10 - Complete | 2024-08-05
[8 empty] | HS2-00002TGPA - Thorpe Mandeville Embankment Access Stairs | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002TGPA | 2024-05-30 | 10 - Complete | 2024-06-05
[8 empty] | HS2-00002WUPJ - Thorpe Mandeville Embankment Planting-East Plot 1 | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002WUPJ | 2024-07-03 | 10 - Complete | 2024-07-17
[8 empty] | HS2-00002WUPK - Thorpe Mandeville Embankment Planting-East Plot 2 | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002WUPK | 2024-07-03 | 10 - Complete | 2024-07-17
[8 empty] | HS2-00002WUPL - Thorpe Mandeville Embankment Planting-West Plot 1 | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002WUPL | 2024-07-03 | 10 - Complete | 2024-07-17
[8 empty] | HS2-00002WUPM - Thorpe Mandeville Embankment Planting-West Plot 2 | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002WUPM | 2024-07-03 | 10 - Complete | 2024-07-17
[8 empty] | HS2-00002WUPN - Lower Thorpe Viaduct Planting-Plot 1 | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002WUPN | 2024-07-03 | 10 - Complete | 2024-07-11
[8 empty] | HS2-00002WUPP - Lower Thorpe Viaduct Planting-Plot 2 | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002WUPP | 2024-07-03 | 10 - Complete | 2024-07-11
[8 empty] | HS2-00002WUPQ - Lower Thorpe Viaduct Planting-Plot 3 | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002WUPQ | 2024-07-03 | 10 - Complete | 2024-07-12
[8 empty] | HS2-00002WUPR - Lower Thorpe Viaduct Planting-Plot 4 | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002WUPR | 2024-07-03 | 10 - Complete | 2024-07-12
[8 empty] | HS2-00002WUPS - Lower Thorpe Viaduct Planting-Plot 5 | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002WUPS | 2024-07-03 | 10 - Complete | 2024-07-12
[8 empty] | HS2-00002WUPT - Lower Thorpe Viaduct Planting-Plot 6 | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00002WUPT | 2024-07-03 | 10 - Complete | 2024-07-12
[8 empty] | HS2-00003AL3P - Thorpe Mandeville Embankment Access Stairs-West | IDR 230.01-3 - Thorpe Mandeville Embankment - Noise Barrier | IDR 230.01-3 | HS2-00003AL3P | 2024-05-30 | 10 - Complete | 2024-06-05
[8 empty] | HS2-00002CTF4 - C3.L.24 Catchment | IDR 230.01-2 - Thorpe Mandeville Embankment - Part 2 | IDR 230.01-2 | HS2-00002CTF4 | 2024-01-17 | 10 - Complete | 2024-01-19
[8 empty] | HS2-00002CTFP - Thorpe Mandeville Embankment Boundary Perimeter Fence Line | IDR 230.01-2 - Thorpe Mandeville Embankment - Part 2 | IDR 230.01-2 | HS2-00002CTFP | 2023-12-21 | 10 - Complete | 2023-12-22
[8 empty] | HS2-00002CTFR - Thorpe Mandeville Embankment Security Fence Line | IDR 230.01-2 - Thorpe Mandeville Embankment - Part 2 | IDR 230.01-2 | HS2-00002CTFR | 2023-12-21 | 10 - Complete | 2024-01-05
[8 empty] | HS2-000020NW9 - Maintenance Access Road to Pond (Off Banbury Lane SW) | IDR 230.01-2 - Thorpe Mandeville Embankment - Part 2 | IDR 230.01-2 | HS2-000020NW9 | 2023-11-17 | 10 - Complete | 2023-11-23
[8 empty] | HS2-00002CTFU - Culworth Brook Diversion | IDR 230.01-2 - Thorpe Mandeville Embankment - Part 2 | IDR 230.01-2 | HS2-00002CTFU | 2024-02-20 | 10 - Complete | 2024-02-22
[8 empty] | HS2-00002PRWV - Lower Thorpe Viaduct Group Ancillary Culvert 105-AC4 | IDR 230.01-2 - Thorpe Mandeville Embankment - Part 2 | IDR 230.01-2 | HS2-00002PRWV | 2023-11-02 | 10 - Complete | 2023-11-07
[8 empty] | HS2-00003D82U - Thorpe Mandeville Embankment 105-DC1 | IDR 230.01-2 - Thorpe Mandeville Embankment - Part 2 | IDR 230.01-2 | HS2-00003D82U | 2024-01-19 | 10 - Complete | 2024-02-06
[8 empty] | HS2-00003D82V - Thorpe Mandeville Embankment 105-DC2 | IDR 230.01-2 - Thorpe Mandeville Embankment - Part 2 | IDR 230.01-2 | HS2-00003D82V | 2024-01-19 | 10 - Complete | 2024-02-06
[8 empty] | HS2-000001074 - Thorpe Mandeville Embankment | IDR 230.01 - Thorpe Mandeville Embankment - Part 1 | IDR 230.01 | HS2-000001074 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7UG - Thorpe Mandeville Embankment Culvert 105-S1 | IDR 230.01 - Thorpe Mandeville Embankment - Part 1 | IDR 230.01 | HS2-00002N7UG | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVKC - Greatworth North Embankment Landscape Earthworks | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002BVKC | 2024-10-11 | 10 - Complete | 2024-10-16
[8 empty] | HS2-00002CTES - C3.L.20 Catchment | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002CTES | 2024-08-26 | 10 - Complete | 2024-09-10
[8 empty] | HS2-00002CTET - C3.L.21 Catchment | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002CTET | 2024-09-30 | 10 - Complete | 2024-10-04
[8 empty] | HS2-00002CTEU - Greatworth North Embankment Boundary Perimeter Fence Line | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002CTEU | 2024-10-25 | 10 - Complete | 2024-10-30
[8 empty] | HS2-00002CTEW - Greatworth North Embankment Security Fence Line | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002CTEW | 2024-09-16 | 10 - Complete | 2024-10-23
[8 empty] | HS2-000001071 - Greatworth North Embankment | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-000001071 | 2024-10-18 | 10 - Complete | 2024-10-23
[8 empty] | HS2-00002N7U9 - Greatworth North Embankment Group-Ancillary Culvert 101-AC1 | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002N7U9 | 2024-04-26 | 10 - Complete | 2024-05-08
[8 empty] | HS2-000001438 - Greatworth Hall Culvert | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-000001438 | 2024-01-30 | 10 - Complete | 2024-02-01
[8 empty] | HS2-00002BVKF - Greatworth North Cutting Landscape Earthworks | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002BVKF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTEY - C3.T.22 Catchment | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002CTEY | 2024-09-03 | 10 - Complete | 2024-09-11
[8 empty] | HS2-00002CTEZ - Greatworth ATS and South Portal Building Access Road (Off Helmdon Road West) | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002CTEZ | 2024-09-19 | 10 - Complete | 2024-10-03
[8 empty] | HS2-00002CTF0 - Greatworth North Cutting Boundary Perimeter Fence Line | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002CTF0 | 2024-09-16 | 10 - Complete | 2024-10-30
[8 empty] | HS2-00002CTF2 - Greatworth North Cutting Security Fence Line | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002CTF2 | 2024-09-16 | 10 - Complete | 2024-10-23
[8 empty] | HS2-000001072 - Greatworth North Cutting | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-000001072 | 2024-08-28 | 10 - Complete | 2024-09-18
[8 empty] | HS2-00002N7UB - Greatworth North Cutting Group-Ancillary Culvert 101-AC3 | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002N7UB | 2024-05-14 | 10 - Complete | 2024-05-17
[8 empty] | HS2-00002N7UC - Greatworth North Cutting Group-Ancillary Culvert 101-AC4 | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002N7UC | 2024-03-20 | 10 - Complete | 2024-03-27
[8 empty] | HS2-000020NVF - Footpath AN13 Extension | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-000020NVF | 2024-09-13 | 10 - Complete | 2024-10-04
[8 empty] | HS2-00002CTF5 - Helmdon Road Drainage System | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002CTF5 | 2024-09-18 | 10 - Complete | 2024-10-04
[8 empty] | HS2-000025B2D - Maintenance Access Road to Pond and MAP (Off Helmdon Road East) and Farm Accommodation Access | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-000025B2D | 2024-09-19 | 10 - Complete | 2024-10-03
[8 empty] | HS2-000020358 - Helmdon Road Realignment | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-000020358 | 2024-09-30 | 10 - Complete | 2024-10-04
[8 empty] | HS2-00002N7UD - Greatworth Green Tunnel Group-Ancillary Culvert 102-AC1 | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00002N7UD | 2024-03-19 | 10 - Complete | 2024-03-22
[8 empty] | HS2-00003124E - Greatworth North Embankment and Cutting Access Stairs | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00003124E | 2024-07-30 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00003B2GH - Greatworth North Embankment Cutting 101-DC3 | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00003B2GH | 2024-02-26 | 10 - Complete | 2024-02-28
[8 empty] | HS2-00003B2GJ - Greatworth North Embankment Cutting 101-DC4 | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00003B2GJ | 2024-03-06 | 10 - Complete | 2024-03-12
[8 empty] | HS2-00003B2GK - Greatworth North Embankment Cutting 102-DC5 | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00003B2GK | 2024-04-29 | 10 - Complete | 2024-05-07
[8 empty] | HS2-00003JYH2 - Greatworth North Embankment Planting-Plot 1 | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00003JYH2 | 2024-10-31 | 10 - Complete | 2024-11-07
[8 empty] | HS2-00003JYH3 - Greatworth North Embankment Planting-Plot 2 | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00003JYH3 | 2024-10-31 | 10 - Complete | 2024-11-07
[8 empty] | HS2-00003JYH4 - Greatworth North Embankment Planting-Plot 3 | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00003JYH4 | 2024-10-31 | 10 - Complete | 2024-11-07
[8 empty] | HS2-00003JYH5 - Greatworth North Cutting Planting-Plot 1 | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00003JYH5 | 2024-10-31 | 10 - Complete | 2024-11-07
[8 empty] | HS2-00003JYH6 - Greatworth North Cutting Planting-Plot 2 | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00003JYH6 | 2024-10-31 | 10 - Complete | 2024-11-07
[8 empty] | HS2-00003JYH7 - Greatworth North Cutting Planting-Plot 3 | IDR 229.03 - Greatworth North Embankment and Cutting | IDR 229.03 | HS2-00003JYH7 | 2024-10-31 | 10 - Complete | 2024-11-07
[8 empty] | HS2-000000160 - Greatworth Green Tunnel | IDR 229.02 - Greatworth Green Tunnel - Stage 2 Advanced Works | IDR 229.02 | HS2-000000160 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTF3 - Greatworth Green Tunnel North Portal Access Road Retaining Wall 1 | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002CTF3 | 2024-08-15 | 10 - Complete | 2024-09-12
[8 empty] | HS2-00002CTF6 - Sulgrave Road Drainage System | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002CTF6 | 2024-10-22 | 10 - Complete | 2024-10-25
[8 empty] | HS2-00002CTF9 - Greatworth Green Tunnel Boundary Perimeter Fence Line South | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002CTF9 | 2024-11-13 | 10 - Complete | 2024-12-10
[8 empty] | HS2-000020361 - Sulgrave Road Reinstatement | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-000020361 | 2024-12-12 | 10 - Complete | 2024-12-17
[8 empty] | HS2-000025B2E - Greatworth Green Tunnel North Portal Buildings Access Road | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-000025B2E | 2025-05-23 | 10 - Complete | 2025-05-28
[8 empty] | HS2-000025B2F - Greatworth Green Tunnel North Portal Building | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-000025B2F | 2024-11-19 | 10 - Complete | 0
[8 empty] | HS2-00002BVKJ - Greatworth Green Tunnel High Mileage Portal Mitigation Earthworks | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002BVKJ | 2024-12-18 | 10 - Complete | 2025-01-10
[8 empty] | HS2-000020NW0 - Footpath BB3 Diversion | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-000020NW0 | 2025-01-13 | 10 - Complete | 2025-01-15
[8 empty] | HS2-000025B2G - Banbury Road (Thorpe Mandeville) Realignment | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-000025B2G | 2025-05-23 | 10 - Complete | 2025-06-02
[8 empty] | HS2-00002CUCC - Banbury Road Drainage System | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002CUCC | 2024-10-23 | 10 - Complete | 2024-11-04
[8 empty] | HS2-00002TMF5 - Greatworth Green Tunnel North Portal Building Fire-fighting Water | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002TMF5 | 2024-08-13 | 10 - Complete | 2024-08-21
[8 empty] | HS2-00002TMF6 - Greatworth Green Tunnel North Portal Building Telecoms | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002TMF6 | 2024-08-13 | 10 - Complete | 2024-08-22
[8 empty] | HS2-00002NJ04 - Greatworth Green Tunnel North Portal | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002NJ04 | 2024-10-21 | 10 - Complete | 2025-01-08
[8 empty] | HS2-00002EK7T - Greatworth Green Tunnel North Portal UTX | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002EK7T | 2024-11-29 | 10 - Complete | 2024-12-17
[8 empty] | HS2-00002WUPB - Greatworth Green Tunnel Planting-Plot 4 | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002WUPB | 2024-11-15 | 10 - Complete | 2024-12-11
[8 empty] | HS2-00002WUPC - Greatworth Green Tunnel Planting-Plot 5 | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002WUPC | 2024-11-15 | 10 - Complete | 0
[8 empty] | HS2-00002WUPD - Greatworth Green Tunnel Planting-Plot 6 | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002WUPD | 2024-11-15 | 10 - Complete | 2024-12-11
[8 empty] | HS2-00002WUPE - Greatworth Green Tunnel Planting-Plot 7 | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002WUPE | 2024-11-15 | 99 - Cancelled | 0
[8 empty] | HS2-00002WUPF - Greatworth Green Tunnel Planting-Plot 8 | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002WUPF | 2024-11-15 | 10 - Complete | 2024-12-11
[8 empty] | HS2-00002WUPG - Greatworth Green Tunnel Planting-Plot 9 | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002WUPG | 2024-11-15 | 10 - Complete | 2024-12-11
[8 empty] | HS2-00002WUPH - Greatworth Green Tunnel Planting-Plot 10 | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00002WUPH | 2024-11-15 | 10 - Complete | 2024-12-12
[8 empty] | HS2-000039DSF - Greatworth Park Bat House (Bat licence) Ecological Site Management Plan | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-000039DSF | 2025-01-13 | 99 - Cancelled | 0
[8 empty] | HS2-00003AQDA - Thorpe Mandeville Embankment Transition Zone Earthworks | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00003AQDA | 2025-01-16 | 10 - Complete | 2025-01-20
[8 empty] | HS2-00003B2GD - Greatworth Green Tunnel Boundary Perimeter Fence Line North | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00003B2GD | 2024-11-13 | 10 - Complete | 2024-12-18
[8 empty] | HS2-00003B2GE - Greatworth Green Tunnel Security Fence Line North | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00003B2GE | 2024-11-19 | 10 - Complete | 2024-12-12
[8 empty] | HS2-00003FV0F - Greatworth Green Tunnel Access Stairs CH.102.100 | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00003FV0F | 2024-08-19 | 10 - Complete | 2024-08-29
[8 empty] | HS2-00003FV0G - Greatworth Green Tunnel Access Stairs CH.104.600 | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00003FV0G | 2024-08-19 | 10 - Complete | 2024-08-29
[8 empty] | HS2-00003JAYC - Deans Barn Access Track (off Sulgrave Road) | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00003JAYC | 2024-12-12 | 10 - Complete | 2025-01-02
[8 empty] | HS2-00003JRG7 - Greatworth Green Tunnel South Portal-Evacuation Walkways | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00003JRG7 | 2024-12-02 | 10 - Complete | 2025-01-17
[8 empty] | HS2-00003JRG8 - Greatworth Green Tunnel North Portal-Evacuation Walkways | IDR 229.01-2 - Greatworth Green Tunnel Portal North | IDR 229.01-2 | HS2-00003JRG8 | 2024-11-22 | 10 - Complete | 2024-12-19
[8 empty] | HS2-00002EK7K - Greatworth Green Tunnel South Portal UTX | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-00002EK7K | 2024-03-20 | 10 - Complete | 2024-03-28
[8 empty] | HS2-00002TMF1 - Greatworth ATS Telecoms | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-00002TMF1 | 2024-12-23 | 10 - Complete | 2025-01-14
[8 empty] | HS2-00002TMF2 - Greatworth Green Tunnel South Portal Building Fire-fighting Water | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-00002TMF2 | 2024-12-23 | 10 - Complete | 2025-01-15
[8 empty] | HS2-00002TMF3 - Greatworth Green Tunnel South Portal Building Electric | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-00002TMF3 | 2024-12-23 | 10 - Complete | 2025-01-17
[8 empty] | HS2-00002TMF4 - Greatworth Green Tunnel South Portal Building Telecoms | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-00002TMF4 | 2024-12-23 | 10 - Complete | 2025-01-17
[8 empty] | HS2-000025B2C - Greatworth Green Tunnel South Portal Building | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-000025B2C | 2025-02-19 | 10 - Complete | 2025-02-28
[8 empty] | HS2-00002CTF7 - Footpath AN39 Reinstatement | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-00002CTF7 | 2024-04-22 | 10 - Complete | 2024-05-03
[8 empty] | HS2-00002CTF8 - Footpath AN4 Reinstatement | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-00002CTF8 | 2024-04-22 | 10 - Complete | 2024-05-03
[8 empty] | HS2-00002HCE5 - Greatworth Green Tunnel Low Mileage Portal Mitigation Earthworks | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-00002HCE5 | 2024-07-29 | 10 - Complete | 2024-08-14
[8 empty] | HS2-00002NJ05 - Greatworth Green Tunnel South Portal | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-00002NJ05 | 2024-06-04 | 10 - Complete | 2024-07-29
[8 empty] | HS2-000020359 - Greatworth Park Access Reinstatement | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-000020359 | 2025-02-19 | 10 - Complete | 2025-02-26
[8 empty] | HS2-000020NVL - Footpath AN40 Diversion | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-000020NVL | 2024-06-14 | 10 - Complete | 2024-06-24
[8 empty] | HS2-00002C3YS - B4525 Welsh Road Drainage System | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-00002C3YS | 2025-02-17 | 10 - Complete | 2025-02-20
[8 empty] | HS2-00002HQ9E - Welsh Road Mitigation Earthworks | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-00002HQ9E | 2024-07-26 | 10 - Complete | 2024-08-13
[8 empty] | HS2-000020360 - B4525 Welsh Road | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-000020360 | 2025-02-19 | 10 - Complete | 2025-02-24
[8 empty] | HS2-000037YM1 - Greatworth North Cutting Transition Earthworks to South Portal | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-000037YM1 | 2024-07-26 | 10 - Complete | 2024-08-16
[8 empty] | HS2-00003B5FS - Greatworth Access Road Drainage System | IDR 229.01-1 - Greatworth Green Tunnel Portal South | IDR 229.01-1 | HS2-00003B5FS | 2025-02-20 | 10 - Complete | 2025-02-21
[8 empty] | HS2-000001436 - Helmdon Culvert | IDR 228.2 - AN37 Overbridge and Helmdon Culvert | IDR 228.2 | HS2-000001436 | 2024-03-05 | 10 - Complete | 2024-03-07
[8 empty] | HS2-000020NUE - Bridleway AN37 Accommodation Access Road | IDR 228.2 - AN37 Overbridge and Helmdon Culvert | IDR 228.2 | HS2-000020NUE | 2024-07-05 | 10 - Complete | 2024-07-16
[8 empty] | HS2-00002CTEL - Bridleway AN37 AN28 and AX1 Diversion | IDR 228.2 - AN37 Overbridge and Helmdon Culvert | IDR 228.2 | HS2-00002CTEL | 2024-07-05 | 10 - Complete | 2024-07-16
[8 empty] | HS2-00002CX3J - Bridleway AN37 AN28 and AX1 Drainage System | IDR 228.2 - AN37 Overbridge and Helmdon Culvert | IDR 228.2 | HS2-00002CX3J | 2024-06-10 | 99 - Cancelled | 0
[8 empty] | HS2-000001339 - Bridleway AN37 Accommodation Overbridge | IDR 228.2 - AN37 Overbridge and Helmdon Culvert | IDR 228.2 | HS2-000001339 | 2024-08-22 | 10 - Complete | 2024-10-03
[8 empty] | HS2-00002BVK8 - Greatworth South Cutting Landscape Earthworks | IDR 228.1 - Bridleway AN14 Accommodation Overbridge & Greatworth South Cutting | IDR 228.1 | HS2-00002BVK8 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001070 - Greatworth South Cutting | IDR 228.1 - Bridleway AN14 Accommodation Overbridge & Greatworth South Cutting | IDR 228.1 | HS2-000001070 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CX3Q - Bridleway AN14 Drainage System | IDR 228.1 - Bridleway AN14 Accommodation Overbridge & Greatworth South Cutting | IDR 228.1 | HS2-00002CX3Q | 2024-05-01 | 10 - Complete | 2024-05-16
[8 empty] | HS2-000025B2B - Bridleway AN14 Diversion | IDR 228.1 - Bridleway AN14 Accommodation Overbridge & Greatworth South Cutting | IDR 228.1 | HS2-000025B2B | #N/A | #N/A | #N/A
[8 empty] | HS2-000001340 - Bridleway AN14 Accommodation Overbridge | IDR 228.1 - Bridleway AN14 Accommodation Overbridge & Greatworth South Cutting | IDR 228.1 | HS2-000001340 | 2024-08-22 | 10 - Complete | 2024-10-04
[8 empty] | HS2-00003BPM6 - Clean Water Pipe CFA_14_13 | IDR 228.1 - Bridleway AN14 Accommodation Overbridge & Greatworth South Cutting | IDR 228.1 | HS2-00003BPM6 | 2024-02-28 | 10 - Complete | 2024-03-18
[8 empty] | HS2-00002VXUJ - Maintenance Access Road to GSMR (off Maintenance Access Road to Pond Radstone) and Compound | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002VXUJ | 2024-01-18 | 10 - Complete | 2024-01-25
[8 empty] | HS2-00002BVK3 - C3.T.13 Catchment | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002BVK3 | 2024-01-19 | 10 - Complete | 2024-02-01
[8 empty] | HS2-00002CTEC - Greatworth South Embankment Boundary Perimeter Fence Line | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002CTEC | 2024-02-14 | 10 - Complete | 2024-02-19
[8 empty] | HS2-00002CTEE - Greatworth South Embankment Security Fence Line | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002CTEE | 2024-02-14 | 10 - Complete | 2024-02-16
[8 empty] | HS2-00002DVEJ - Greatworth South Embankment Landscape Earthworks | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002DVEJ | 2024-02-16 | 10 - Complete | 2024-02-23
[8 empty] | HS2-000001069 - Greatworth South Embankment | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-000001069 | 2024-02-21 | 10 - Complete | 2024-02-23
[8 empty] | HS2-000020NUC - Maintenance Access Road to Pond (Off Radstone Road) | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-000020NUC | 2024-01-18 | 10 - Complete | 2024-01-24
[8 empty] | HS2-00002NNHX - Helmdon Culvert Watercourse Diversion | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002NNHX | 2024-02-01 | 10 - Complete | 2024-02-16
[8 empty] | HS2-00002CTEF - C3.L.14 Catchment | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002CTEF | 2024-01-19 | 10 - Complete | 2024-02-01
[8 empty] | HS2-00002CTEG - C3.L.15 Catchment | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002CTEG | 2024-01-19 | 10 - Complete | 2024-01-30
[8 empty] | HS2-00002CTEK - C3.L.18 Catchment | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002CTEK | 2024-01-19 | 10 - Complete | 2024-02-08
[8 empty] | HS2-00002CTEM - Greatworth South Cutting Boundary Perimeter Fence Line | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002CTEM | 2024-02-14 | 10 - Complete | 2024-02-19
[8 empty] | HS2-00002CTEP - Greatworth South Cutting Security Fence Line | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002CTEP | 2024-02-14 | 10 - Complete | 2024-02-15
[8 empty] | HS2-000001338 - Footpath AN22 Accommodation Overbridge | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-000001338 | 2024-06-18 | 10 - Complete | 2024-08-01
[8 empty] | HS2-00002BVK9 - Footpath AN22 Diversion | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002BVK9 | 2024-01-26 | 10 - Complete | 2024-01-29
[8 empty] | HS2-00002CX3H - Footpath AN22 Drainage System | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002CX3H | 2024-01-19 | 10 - Complete | 2024-01-30
[8 empty] | HS2-00002EKZT - Halse Copse Ecological Mitigation Site | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002EKZT | #N/A | #N/A | #N/A
[8 empty] | HS2-000001437 - Greatworth Dry Valley Drop Inlet Culvert | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-000001437 | 2024-02-14 | 10 - Complete | 2024-02-25
[8 empty] | HS2-00002YGQ6 - Greatworth South Embankment Radio Compound UTX | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00002YGQ6 | #N/A | #N/A | #N/A
[8 empty] | HS2-000032TBV - Maintenance Access Road to Pond (Off Radstone Road) Drainage System | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-000032TBV | 2024-01-19 | 10 - Complete | 2024-01-30
[8 empty] | HS2-000033GP5 - Clean Water Pipe CFA_15_01 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-000033GP5 | 2023-12-22 | 10 - Complete | 2024-01-05
[8 empty] | HS2-000039DSB - Halse Copse East (Bat Licence) Ecological Mitigation Site | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-000039DSB | #N/A | #N/A | #N/A
[8 empty] | HS2-00003B2GL - Greatworth South Embankment Planting Plot 1 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GL | 2024-02-01 | 10 - Complete | 2024-02-12
[8 empty] | HS2-00003B2GM - Greatworth South Embankment Planting Plot 2 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GM | 2024-02-01 | 10 - Complete | 2024-02-09
[8 empty] | HS2-00003B2GN - Greatworth South Cutting Planting Plot 12 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GN | 2024-02-01 | 10 - Complete | 2024-02-09
[8 empty] | HS2-00003B2GP - Greatworth South Cutting Planting Plot 11 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GP | 2024-02-01 | 10 - Complete | 2024-02-09
[8 empty] | HS2-00003B2GQ - Greatworth South Cutting Planting Plot 13 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GQ | 2024-02-01 | 10 - Complete | 2024-02-09
[8 empty] | HS2-00003B2GR - Greatworth South Cutting Planting Plot 14 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GR | 2024-02-01 | 10 - Complete | 2024-02-13
[8 empty] | HS2-00003B2GS - Greatworth South Cutting Planting Plot 8 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GS | 2024-02-01 | 10 - Complete | 2024-02-09
[8 empty] | HS2-00003B2GT - Greatworth South Cutting Planting Plot 7 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GT | 2024-02-01 | 10 - Complete | 2024-02-09
[8 empty] | HS2-00003B2GU - Greatworth South Cutting Planting Plot 9 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GU | 2024-02-01 | 10 - Complete | 2024-02-09
[8 empty] | HS2-00003B2GV - Greatworth South Cutting Planting Plot 10 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GV | 2024-02-01 | 10 - Complete | 2024-02-09
[8 empty] | HS2-00003B2GW - Greatworth South Cutting Planting Plot 3 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GW | 2024-02-01 | 10 - Complete | 2024-02-09
[8 empty] | HS2-00003B2GX - Greatworth South Cutting Planting Plot 4 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GX | 2024-02-01 | 10 - Complete | 2024-02-09
[8 empty] | HS2-00003B2GY - Greatworth South Cutting Planting Plot 5 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GY | 2024-02-01 | 10 - Complete | 2024-02-09
[8 empty] | HS2-00003B2GZ - Greatworth South Cutting Planting Plot 6 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2GZ | 2024-02-01 | 10 - Complete | 2024-02-09
[8 empty] | HS2-00003B2H0 - Greatworth South Cutting Planting Plot 1 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2H0 | 2024-02-01 | 10 - Complete | 2024-02-09
[8 empty] | HS2-00003B2H1 - Greatworth South Cutting Planting Plot 2 | IDR 228 - AN22 Overbridge, Greatworth Dry Valley Drop Inlet Culvert and Combined Greatworth South Cutting Area & Embankment | IDR 228 | HS2-00003B2H1 | 2024-02-01 | 10 - Complete | 2024-02-13
[8 empty] | HS2-000020NU0 - Bridleway AX5 AX18 and AX19 and Accommodation access Realignment | IDR 227.2 - AX18 Accommodation Overbridge | IDR 227.2 | HS2-000020NU0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CX3E - Footpath and Bridleway AX18 AX19 and AX5 Drainage System | IDR 227.2 - AX18 Accommodation Overbridge | IDR 227.2 | HS2-00002CX3E | #N/A | #N/A | #N/A
[8 empty] | HS2-000001337 - Bridleway AX18 Overbridge | IDR 227.2 - AX18 Accommodation Overbridge | IDR 227.2 | HS2-000001337 | 2024-05-17 | 10 - Complete | 2024-05-21
[8 empty] | HS2-00002J4YP - Bridleway AX19 Diversion | IDR 227.2 - AX18 Accommodation Overbridge | IDR 227.2 | HS2-00002J4YP | #N/A | #N/A | #N/A
[8 empty] | HS2-00002V04T - Radstone Road Overbridge West Northamptonshire Council Telecoms | IDR 227.1 - Radstone road Overbridge (Superstructures) & Radstone Road Culvert | IDR 227.1 | HS2-00002V04T | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7X2 - Radstone Road-Ancillary Culvert 097-AC2 | IDR 227.1 - Radstone road Overbridge (Superstructures) & Radstone Road Culvert | IDR 227.1 | HS2-00002N7X2 | 2024-04-19 | 10 - Complete | 2024-04-25
[8 empty] | HS2-000025B28 - Radstone Road Realignment | IDR 227.1 - Radstone road Overbridge (Superstructures) & Radstone Road Culvert | IDR 227.1 | HS2-000025B28 | 2024-04-24 | 10 - Complete | 2024-04-29
[8 empty] | HS2-000025B29 - Maintenance Access Road to Pond (Off Radstone Road East) | IDR 227.1 - Radstone road Overbridge (Superstructures) & Radstone Road Culvert | IDR 227.1 | HS2-000025B29 | 2024-04-24 | 10 - Complete | 2024-04-29
[8 empty] | HS2-00002CQQF - Radstone Road Drainage System | IDR 227.1 - Radstone road Overbridge (Superstructures) & Radstone Road Culvert | IDR 227.1 | HS2-00002CQQF | 2024-04-10 | 10 - Complete | 2024-04-15
[8 empty] | HS2-000001336 - Radstone Road Overbridge | IDR 227.1 - Radstone road Overbridge (Superstructures) & Radstone Road Culvert | IDR 227.1 | HS2-000001336 | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-00003B5FR - HSRS Day 2 Power Supply Additional Ducts Radstone Rd Overbridge | IDR 227.1 - Radstone road Overbridge (Superstructures) & Radstone Road Culvert | IDR 227.1 | HS2-00003B5FR | 2024-04-04 | 10 - Complete | 2024-04-07
[8 empty] | HS2-00002CTDW - C3.T.8 Catchment | IDR 227 - Brackley Embankment & Brackley North Cutting & Brackley culvert | IDR 227 | HS2-00002CTDW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DVEH - Brackley Embankment Landscape Earthworks | IDR 227 - Brackley Embankment & Brackley North Cutting & Brackley culvert | IDR 227 | HS2-00002DVEH | #N/A | #N/A | #N/A
[8 empty] | HS2-000001067 - Brackley Embankment | IDR 227 - Brackley Embankment & Brackley North Cutting & Brackley culvert | IDR 227 | HS2-000001067 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001435 - Brackley Culvert | IDR 227 - Brackley Embankment & Brackley North Cutting & Brackley culvert | IDR 227 | HS2-000001435 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NNHW - Brackley Culvert Watercourse Diversion | IDR 227 - Brackley Embankment & Brackley North Cutting & Brackley culvert | IDR 227 | HS2-00002NNHW | 2024-11-15 | 10 - Complete | 2024-12-04
[8 empty] | HS2-000001068 - Brackley North Cutting | IDR 227 - Brackley Embankment & Brackley North Cutting & Brackley culvert | IDR 227 | HS2-000001068 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVK2 - Brackley North Cutting Landscape Earthworks | IDR 227 - Brackley Embankment & Brackley North Cutting & Brackley culvert | IDR 227 | HS2-00002BVK2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CQQG - C3.L.10 Catchment | IDR 227 - Brackley Embankment & Brackley North Cutting & Brackley culvert | IDR 227 | HS2-00002CQQG | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CQQH - C3.T.11 Catchment | IDR 227 - Brackley Embankment & Brackley North Cutting & Brackley culvert | IDR 227 | HS2-00002CQQH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CQQJ - C3.L.12 Catchment | IDR 227 - Brackley Embankment & Brackley North Cutting & Brackley culvert | IDR 227 | HS2-00002CQQJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTE4 - Brackley South Cutting Boundary Perimeter Fence Line | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00002CTE4 | 2024-09-13 | 10 - Complete | 2024-09-23
[8 empty] | HS2-00002CTE6 - Brackley South Cutting Security Fence Line | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00002CTE6 | 2024-09-13 | 10 - Complete | 2024-09-24
[8 empty] | HS2-00002EKZB - Helmdon disused railway SSSI Ecological Mitigation Site | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00002EKZB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKZC - Radstone-Footpath AX15 Green Overbridge Ecological Mitigation Site | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00002EKZC | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTE9 - Brackley Embankment Boundary Perimeter Fence Line | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00002CTE9 | 2024-09-13 | 10 - Complete | 2024-09-20
[8 empty] | HS2-00002CTEB - Brackley Embankment Security Fence Line | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00002CTEB | 2024-09-13 | 10 - Complete | 2024-09-24
[8 empty] | HS2-00002BVK1 - Brackley North Cutting Security Fence Line | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00002BVK1 | 2024-09-13 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00002CQQK - Brackley North Cutting Boundary Perimeter Fence Line | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00002CQQK | 2024-09-13 | 10 - Complete | 2024-09-20
[8 empty] | HS2-000031EF5 - 97-SL2 Brackley Embankment Vehicular Bridge | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-000031EF5 | 2024-08-13 | 10 - Complete | 2024-08-22
[8 empty] | HS2-000031EF6 - 98-SL1 Brackley North Cutting Vehicular Slab | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-000031EF6 | 2024-08-13 | 10 - Complete | 2024-08-22
[8 empty] | HS2-0000386UJ - 97-SL2 Brackley Embankment Vehicular Bridge-Earthworks Transition | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-0000386UJ | 2024-08-26 | 10 - Complete | 2024-09-03
[8 empty] | HS2-000039DSE - Radstone-Fox Covert (Bat licence) Ecological Mitigation Site | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-000039DSE | #N/A | #N/A | #N/A
[8 empty] | HS2-00003CPXC - Brackley North Cutting Planting Plot 1 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXC | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXD - Brackley North Cutting Planting Plot 2 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXD | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXF - Brackley North Cutting Planting Plot 3 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXF | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXG - Brackley North Cutting Planting Plot 4 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXG | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXH - Brackley North Cutting Planting Plot 5 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXH | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXJ - Brackley North Cutting Planting Plot 6 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXJ | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXL - Brackley North Cutting Planting Plot 7 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXL | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXM - Brackley North Cutting Planting Plot 8 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXM | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXN - Brackley North Cutting Planting Plot 9 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXN | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXQ - Brackley North Cutting Planting Plot 10 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXQ | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXR - Brackley North Cutting Planting Plot 11 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXR | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXS - Brackley Embankment Planting Plot 1 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXS | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXT - Brackley Embankment Planting Plot 2 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXT | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXV - Brackley Embankment Planting Plot 3 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXV | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXW - Brackley Embankment Planting Plot 4 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXW | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXX - Brackley Embankment Planting Plot 5 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXX | 2024-09-16 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CPXZ - Brackley South Cutting Planting Plot 1 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPXZ | 2024-09-16 | 10 - Complete | 2024-09-16
[8 empty] | HS2-00003CPY0 - Brackley South Cutting Planting Plot 2 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPY0 | 2024-09-16 | 10 - Complete | 2024-09-17
[8 empty] | HS2-00003CPY1 - Brackley South Cutting Planting Plot 3 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPY1 | 2024-09-16 | 10 - Complete | 2024-09-17
[8 empty] | HS2-00003CPY3 - Brackley South Cutting Planting Plot 4 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPY3 | 2024-09-16 | 10 - Complete | 2024-09-17
[8 empty] | HS2-00003CPY4 - Brackley South Cutting Planting Plot 5 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPY4 | 2024-09-16 | 10 - Complete | 2024-09-17
[8 empty] | HS2-00003CPY5 - Brackley South Cutting Planting Plot 6 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPY5 | 2024-09-16 | 10 - Complete | 2024-09-18
[8 empty] | HS2-00003CPY6 - Brackley South Cutting Planting Plot 7 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPY6 | 2024-09-16 | 10 - Complete | 2024-09-18
[8 empty] | HS2-00003CPY8 - Brackley South Cutting Planting Plot 8 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPY8 | 2024-09-16 | 10 - Complete | 2024-09-18
[8 empty] | HS2-00003CPY9 - Brackley South Cutting Planting Plot 9 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPY9 | 2024-09-16 | 10 - Complete | 2024-09-18
[8 empty] | HS2-00003CPYA - Brackley South Cutting Planting Plot 10 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPYA | 2024-09-16 | 10 - Complete | 2024-09-18
[8 empty] | HS2-00003CPYC - Brackley South Cutting Planting Plot 11 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPYC | 2024-09-16 | 10 - Complete | 2024-09-18
[8 empty] | HS2-00003CPYD - Brackley South Cutting Planting Plot 12 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPYD | 2024-09-16 | 10 - Complete | 2024-09-18
[8 empty] | HS2-00003CPYE - Brackley South Cutting Planting Plot 13 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPYE | 2024-09-16 | 10 - Complete | 2024-09-18
[8 empty] | HS2-00003CPYF - Brackley South Cutting Planting Plot 14 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPYF | 2024-09-16 | 10 - Complete | 2024-09-18
[8 empty] | HS2-00003CPYH - Brackley South Cutting Planting Plot 15 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPYH | 2024-09-16 | 10 - Complete | 2024-09-18
[8 empty] | HS2-00003CPYJ - Brackley South Cutting Planting Plot 16 | IDR 226.5 - Brackley Area - Ancillary Civils Fencing and Landscape Planting | IDR 226.5 | HS2-00003CPYJ | 2024-09-16 | 10 - Complete | 2024-09-18
[8 empty] | HS2-00002RE06 - Footpath AX15 Overbridge Realignment | IDR 226.3 - Footpath AX15 Overbridge | IDR 226.3 | HS2-00002RE06 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CX3D - Footpath AX15 AX17 and AX14 Drainage System | IDR 226.3 - Footpath AX15 Overbridge | IDR 226.3 | HS2-00002CX3D | #N/A | #N/A | #N/A
[8 empty] | HS2-00002SXNG - Footpath AX15 Diversion (West of HS2) | IDR 226.3 - Footpath AX15 Overbridge | IDR 226.3 | HS2-00002SXNG | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4YQ - Bridleway AX14 Diversion (west of HS2) | IDR 226.3 - Footpath AX15 Overbridge | IDR 226.3 | HS2-00002J4YQ | #N/A | #N/A | #N/A
[8 empty] | HS2-000001335 - Footpath AX15 Overbridge | IDR 226.3 - Footpath AX15 Overbridge | IDR 226.3 | HS2-000001335 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4YR - Footpath AX15 and AX7 Diversion (east of HS2) | IDR 226.3 - Footpath AX15 Overbridge | IDR 226.3 | HS2-00002J4YR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7X1 - Brackley Embankment-Ancillary Culvert 097-AC1 | IDR 226.3 - Footpath AX15 Overbridge | IDR 226.3 | HS2-00002N7X1 | 2024-01-08 | 10 - Complete | 2024-01-11
[8 empty] | HS2-000020NTD - Bridleway AX16 Diversion | IDR 226.2 - Bridleway AX16 Accommodation Overbridge | IDR 226.2 | HS2-000020NTD | 2024-01-24 | 10 - Complete | 2024-01-29
[8 empty] | HS2-00002GUVX - Bridleway AX16 Accommodation Drainage | IDR 226.2 - Bridleway AX16 Accommodation Overbridge | IDR 226.2 | HS2-00002GUVX | 2024-01-25 | 10 - Complete | 2024-01-30
[8 empty] | HS2-00002VXUH - Maintenance Access Road to GSMR (off Bridleway AX16 Diversion) and Compound | IDR 226.2 - Bridleway AX16 Accommodation Overbridge | IDR 226.2 | HS2-00002VXUH | 2024-01-24 | 10 - Complete | 2024-01-29
[8 empty] | HS2-000001334 - Bridleway AX16 Accommodation Overbridge | IDR 226.2 - Bridleway AX16 Accommodation Overbridge | IDR 226.2 | HS2-000001334 | 2025-01-28 | 10 - Complete | 2025-02-12
[8 empty] | HS2-00002Y4JL - Brackley South Cutting Radio Compound UTX | IDR 226.2 - Bridleway AX16 Accommodation Overbridge | IDR 226.2 | HS2-00002Y4JL | 2025-01-24 | 10 - Complete | 2025-01-30
[8 empty] | HS2-000025B1Z - Maintenance Access Road to Whitfield ATS and Pond (Off A43 Oxford Road West) | IDR 226.1 - A43 Oxford road Overbridge & Whitfield ATS | IDR 226.1 | HS2-000025B1Z | 2024-07-23 | 10 - Complete | 2024-07-24
[8 empty] | HS2-00002BVJR - C3.L.7 Catchment | IDR 226.1 - A43 Oxford road Overbridge & Whitfield ATS | IDR 226.1 | HS2-00002BVJR | 2024-07-23 | 10 - Complete | 2024-07-26
[8 empty] | HS2-00002CTDV - Whitfield ATS | IDR 226.1 - A43 Oxford road Overbridge & Whitfield ATS | IDR 226.1 | HS2-00002CTDV | 2024-07-15 | 10 - Complete | 2024-07-24
[8 empty] | HS2-000025B20 - Footpath BD8 Diversion | IDR 226.1 - A43 Oxford road Overbridge & Whitfield ATS | IDR 226.1 | HS2-000025B20 | 2024-07-23 | 10 - Complete | 2024-07-25
[8 empty] | HS2-00002EK7G - Whitfield ATS UTX | IDR 226.1 - A43 Oxford road Overbridge & Whitfield ATS | IDR 226.1 | HS2-00002EK7G | 2025-02-03 | 10 - Complete | 2025-02-17
[8 empty] | HS2-00002TMF0 - Whitfield ATS Telecoms | IDR 226.1 - A43 Oxford road Overbridge & Whitfield ATS | IDR 226.1 | HS2-00002TMF0 | 2023-11-28 | 10 - Complete | 2023-12-04
[8 empty] | HS2-00002N7WZ - Brackley South Cutting-Ancillary Culvert 096-AC1 | IDR 226.1 - A43 Oxford road Overbridge & Whitfield ATS | IDR 226.1 | HS2-00002N7WZ | 2024-07-23 | 10 - Complete | 2024-07-26
[8 empty] | HS2-00002N7X0 - Brackley South Cutting-Ancillary Culvert 096-AC2 | IDR 226.1 - A43 Oxford road Overbridge & Whitfield ATS | IDR 226.1 | HS2-00002N7X0 | 2024-07-23 | 10 - Complete | 2024-07-26
[8 empty] | HS2-000025B21 - A43 Oxford Road Re-alignment | IDR 226.1 - A43 Oxford road Overbridge & Whitfield ATS | IDR 226.1 | HS2-000025B21 | 2024-07-23 | 10 - Complete | 2024-07-25
[8 empty] | HS2-00002C3YF - A43 Oxford Road Drainage System | IDR 226.1 - A43 Oxford road Overbridge & Whitfield ATS | IDR 226.1 | HS2-00002C3YF | 2024-07-23 | 10 - Complete | 2024-07-25
[8 empty] | HS2-000001333 - A43 Oxford Road Overbridge | IDR 226.1 - A43 Oxford road Overbridge & Whitfield ATS | IDR 226.1 | HS2-000001333 | 2024-05-24 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00002Y89A - Brackley South Cutting-Field Access (off A43 Oxford Road) | IDR 226.1 - A43 Oxford road Overbridge & Whitfield ATS | IDR 226.1 | HS2-00002Y89A | 2024-07-23 | 10 - Complete | 2024-07-26
[8 empty] | HS2-000001066 - Brackley South Cutting | IDR 226 - Brackley South Cutting | IDR 226 | HS2-000001066 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVJU - C3.L.9 Catchment | IDR 226 - Brackley South Cutting | IDR 226 | HS2-00002BVJU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DVEG - Brackley South Cutting Landscape Earthworks | IDR 226 - Brackley South Cutting | IDR 226 | HS2-00002DVEG | #N/A | #N/A | #N/A
[8 empty] | HS2-000001063 - Turweston Embankment | IDR 225_1 - Turweston Viaduct (Phase 1) | IDR 225_1 | HS2-000001063 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001064 - Turweston Viaduct | IDR 225_1 - Turweston Viaduct (Phase 1) | IDR 225_1 | HS2-000001064 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001065 - Helmdon Embankment | IDR 225_1 - Turweston Viaduct (Phase 1) | IDR 225_1 | HS2-000001065 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002YGQD - Turweston Structural Backfill A2 Retaining Wall | IDR 225_1 - Turweston Viaduct (Phase 1) | IDR 225_1 | HS2-00002YGQD | #N/A | #N/A | #N/A
[8 empty] | HS2-00002YGQE - Turweston Structural Backfill A0 Retaining Wall | IDR 225_1 - Turweston Viaduct (Phase 1) | IDR 225_1 | HS2-00002YGQE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTDQ - C3.T.5 Catchment | IDR 225 - Turweston and Helmdon Embankments & Turweston viaduct | IDR 225 | HS2-00002CTDQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTE3 - River Great Ouse Diversion 02 | IDR 225 - Turweston and Helmdon Embankments & Turweston viaduct | IDR 225 | HS2-00002CTE3 | 2024-04-12 | 10 - Complete | 2024-04-22
[8 empty] | HS2-00002EL0A - Flood Compensation Area-096 | IDR 225 - Turweston and Helmdon Embankments & Turweston viaduct | IDR 225 | HS2-00002EL0A | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKY1 - Turweston Ecological Mitigation Site (C) | IDR 224.7 - Turweston Cutting additional Landscape Earthworks | IDR 224.7 | HS2-00002EKY1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPLH - Turweston Cutting Planting Plot 5 | IDR 224.7 - Turweston Cutting additional Landscape Earthworks | IDR 224.7 | HS2-00003BPLH | 2024-11-28 | 10 - Complete | 2024-12-06
[8 empty] | HS2-00003BPLM - Turweston Cutting Planting Plot 6 | IDR 224.7 - Turweston Cutting additional Landscape Earthworks | IDR 224.7 | HS2-00003BPLM | 2024-11-28 | 10 - Complete | 2024-12-06
[8 empty] | HS2-00003BPLQ - Turweston Embankment Planting Plot 1 | IDR 224.7 - Turweston Cutting additional Landscape Earthworks | IDR 224.7 | HS2-00003BPLQ | 2024-11-28 | 10 - Complete | 0
[8 empty] | HS2-00003HF3P - Turweston cutting Additional Landscape Earthworks 1 | IDR 224.7 - Turweston Cutting additional Landscape Earthworks | IDR 224.7 | HS2-00003HF3P | 2024-11-21 | 10 - Complete | 2024-12-03
[8 empty] | HS2-00003HF3Q - Turweston cutting Additional Landscape Earthworks 2 | IDR 224.7 - Turweston Cutting additional Landscape Earthworks | IDR 224.7 | HS2-00003HF3Q | 2024-11-21 | 10 - Complete | 2024-12-03
[8 empty] | HS2-00003HF3R - Turweston cutting Additional Landscape Earthworks 3 | IDR 224.7 - Turweston Cutting additional Landscape Earthworks | IDR 224.7 | HS2-00003HF3R | 2024-11-21 | 10 - Complete | 2024-12-03
[8 empty] | HS2-00003HF3S - Turweston cutting Additional Landscape Earthworks 4 | IDR 224.7 - Turweston Cutting additional Landscape Earthworks | IDR 224.7 | HS2-00003HF3S | 2024-11-21 | 10 - Complete | 2024-12-03
[8 empty] | HS2-00003HF3T - C2.L.110 Catchment | IDR 224.7 - Turweston Cutting additional Landscape Earthworks | IDR 224.7 | HS2-00003HF3T | 2024-11-20 | 10 - Complete | 2024-11-29
[8 empty] | HS2-00003HF3W - Turweston Cutting Additional Landscape Earthworks 1-Boundary-Perimeter Fence Line | IDR 224.7 - Turweston Cutting additional Landscape Earthworks | IDR 224.7 | HS2-00003HF3W | 2024-11-28 | 10 - Complete | 2024-12-10
[8 empty] | HS2-00002CTCG - Grovehill Embankment Boundary Perimeter Fence Line | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00002CTCG | 2025-05-16 | 10 - Complete | 2025-05-20
[8 empty] | HS2-00002CTCJ - Grovehill Embankment Security Fence Line | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00002CTCJ | 2025-05-16 | 10 - Complete | 2025-05-21
[8 empty] | HS2-00002CTCM - Turweston Cutting Boundary Perimeter Fence Line | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00002CTCM | 2025-05-16 | 10 - Complete | 2025-05-21
[8 empty] | HS2-00002CTCP - Turweston Cutting Security Fence Line | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00002CTCP | 2025-05-16 | 10 - Complete | 2025-05-20
[8 empty] | HS2-00002CTDR - Turweston Embankment Boundary Perimeter Fence Line | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00002CTDR | 2024-07-12 | 10 - Complete | 2024-07-22
[8 empty] | HS2-00002CTDT - Turweston Embankment Security Fence Line | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00002CTDT | 2024-07-12 | 10 - Complete | 2024-07-22
[8 empty] | HS2-00002CTDY - Helmdon Embankment Boundary Perimeter Fence Line | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00002CTDY | 2024-07-12 | 10 - Complete | 2024-07-22
[8 empty] | HS2-00002CTE1 - Helmdon Embankment Security Fence Line | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00002CTE1 | 2024-07-12 | 10 - Complete | 2024-07-22
[8 empty] | HS2-000031EF3 - 95-SL1 Turweston Embankment Pedestrian Slab | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-000031EF3 | 2024-07-02 | 10 - Complete | 2024-07-12
[8 empty] | HS2-000031EF4 - 95-SL2 Turweston Viaduct Vehicular Bridge | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-000031EF4 | 2024-07-02 | 10 - Complete | 2024-07-26
[8 empty] | HS2-0000386UG - 95-SL2 Turweston Viaduct Vehicular Bridge-Earthworks Transition | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-0000386UG | 2024-07-03 | 10 - Complete | 2024-07-11
[8 empty] | HS2-0000386UL - Westbury Viaduct Planting Plot 1 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-0000386UL | 2024-07-17 | 10 - Complete | 2024-07-31
[8 empty] | HS2-0000386UM - Westbury Viaduct Planting Plot 2 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-0000386UM | 2024-07-17 | 10 - Complete | 2024-08-01
[8 empty] | HS2-0000386UP - Westbury Viaduct Planting Plot 3 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-0000386UP | 2024-07-17 | 10 - Complete | 2024-07-26
[8 empty] | HS2-0000386UQ - Westbury Viaduct Planting Plot 4 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-0000386UQ | 2024-07-17 | 10 - Complete | 2024-07-26
[8 empty] | HS2-00003BPL5 - Grovehill Embankment Planting Plot 1 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPL5 | 2024-07-17 | 10 - Complete | 2024-07-26
[8 empty] | HS2-00003BPL6 - Grovehill Embankment Planting Plot 2 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPL6 | 2024-07-17 | 10 - Complete | 2024-07-26
[8 empty] | HS2-00003BPL7 - Grovehill Embankment Planting Plot 6 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPL7 | 2024-07-17 | 10 - Complete | 2024-07-30
[8 empty] | HS2-00003BPL8 - Grovehill Embankment Planting Plot 3 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPL8 | 2024-07-17 | 10 - Complete | 2024-07-26
[8 empty] | HS2-00003BPL9 - Grovehill Embankment Planting Plot 4 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPL9 | 2024-07-17 | 10 - Complete | 2024-07-31
[8 empty] | HS2-00003BPLA - Grovehill Embankment Planting Plot 5 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLA | 2024-07-17 | 10 - Complete | 2024-07-24
[8 empty] | HS2-00003BPLB - Turweston Cutting Planting Plot 1 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLB | 2024-07-17 | 10 - Complete | 2024-07-22
[8 empty] | HS2-00003BPLC - Turweston Cutting Planting Plot 9 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLC | 2024-07-17 | 10 - Complete | 2024-07-23
[8 empty] | HS2-00003BPLD - Turweston Cutting Planting Plot 2 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLD | 2024-07-17 | 10 - Complete | 2024-07-25
[8 empty] | HS2-00003BPLE - Turweston Cutting Planting Plot 3 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLE | 2024-07-17 | 10 - Complete | 2024-07-31
[8 empty] | HS2-00003BPLF - Turweston Cutting Planting Plot 8 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLF | 2024-07-17 | 10 - Complete | 2024-07-31
[8 empty] | HS2-00003BPLG - Turweston Cutting Planting Plot 4 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLG | 2024-07-17 | 10 - Complete | 2024-07-29
[8 empty] | HS2-00003BPLJ - Turweston Cutting Planting Plot 10 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLJ | 2024-07-17 | 10 - Complete | 2024-07-26
[8 empty] | HS2-00003BPLK - Turweston Cutting Planting Plot 11 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLK | 2024-07-17 | 10 - Complete | 2024-07-23
[8 empty] | HS2-00003BPLL - Turweston Cutting Planting Plot 12 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLL | 2024-07-17 | 10 - Complete | 2024-07-30
[8 empty] | HS2-00003BPLN - Turweston Cutting Planting Plot 7 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLN | 2024-07-17 | 10 - Complete | 2024-07-23
[8 empty] | HS2-00003BPLP - Turweston Cutting Planting Plot 13 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLP | 2024-07-17 | 10 - Complete | 2024-07-24
[8 empty] | HS2-00003BPLR - Turweston Embankment Planting Plot 5 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLR | 2024-07-17 | 10 - Complete | 2024-07-30
[8 empty] | HS2-00003BPLS - Turweston Embankment Planting Plot 2 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLS | 2024-07-17 | 10 - Complete | 2024-07-31
[8 empty] | HS2-00003BPLT - Turweston Embankment Planting Plot 4 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLT | 2024-07-17 | 10 - Complete | 2024-07-24
[8 empty] | HS2-00003BPLU - Turweston Embankment Planting Plot 3 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLU | 2024-07-17 | 10 - Complete | 2024-07-24
[8 empty] | HS2-00003BPLW - Turweston Viaduct Planting Plot 1 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLW | 2024-07-17 | 10 - Complete | 2024-07-30
[8 empty] | HS2-00003BPLY - Helmdon Embankment Planting Plot 1 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPLY | 2024-07-17 | 10 - Complete | 2024-07-31
[8 empty] | HS2-00003BPM0 - Helmdon Embankment Planting Plot 6 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPM0 | 2024-07-17 | 10 - Complete | 2024-07-30
[8 empty] | HS2-00003BPM1 - Turweston Viaduct Planting Plot 2 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPM1 | 2024-07-17 | 10 - Complete | 2024-07-31
[8 empty] | HS2-00003BPM2 - Helmdon Embankment Planting Plot 2 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPM2 | 2024-07-17 | 10 - Complete | 2024-07-31
[8 empty] | HS2-00003BPM3 - Helmdon Embankment Planting Plot 3 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPM3 | 2024-07-17 | 10 - Complete | 2024-07-24
[8 empty] | HS2-00003BPM4 - Helmdon Embankment Planting Plot 4 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPM4 | 2024-07-17 | 10 - Complete | 2024-07-24
[8 empty] | HS2-00003BPM5 - Helmdon Embankment Planting Plot 5 | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003BPM5 | 2024-07-17 | 10 - Complete | 2024-07-30
[8 empty] | HS2-00003D9D1 - 92-SL2 Westbury Viaduct Vehicular Slab | IDR 224.6 - Westbury Viaduct, Grovehill Embankment, Turweston Area and Helmdon Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 224.6 | HS2-00003D9D1 | 2024-07-02 | 10 - Complete | 2024-07-17
[8 empty] | HS2-000020RU0 - Maintenance Access Road to Pond (Off Turweston Farm Track) | IDR 224.4 - Turweston Green Overbridge | IDR 224.4 | HS2-000020RU0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTCK - C2.L.109 Catchment | IDR 224.4 - Turweston Green Overbridge | IDR 224.4 | HS2-00002CTCK | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJV5 - Bridleway TUW 9 Diversion | IDR 224.4 - Turweston Green Overbridge | IDR 224.4 | HS2-00002BJV5 | 2023-11-30 | 10 - Complete | 2023-12-06
[8 empty] | HS2-000001332 - Turweston Green Overbridge | IDR 224.4 - Turweston Green Overbridge | IDR 224.4 | HS2-000001332 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NPE - Turweston Farm Track (TUW 4) Realignment | IDR 224.4 - Turweston Green Overbridge | IDR 224.4 | HS2-000020NPE | 2023-11-30 | 10 - Complete | 2023-12-06
[8 empty] | HS2-00002CW0F - Turweston Farm Track (TUW 4) Drainage System | IDR 224.4 - Turweston Green Overbridge | IDR 224.4 | HS2-00002CW0F | #N/A | #N/A | #N/A
[8 empty] | HS2-000020RNJ - Footpath TUW 3 Diversion | IDR 224.4 - Turweston Green Overbridge | IDR 224.4 | HS2-000020RNJ | 2023-11-30 | 99 - Cancelled | 0
[8 empty] | HS2-00002BVJK - C3.L.6 Catchment | IDR 224.4 - Turweston Green Overbridge | IDR 224.4 | HS2-00002BVJK | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VXUG - Maintenance Access Road to GSMR (off Maintenance Access Road to Pond Turweston Farm Track) and Compound | IDR 224.4 - Turweston Green Overbridge | IDR 224.4 | HS2-00002VXUG | #N/A | #N/A | #N/A
[8 empty] | HS2-000020RTW - Footpath TUW 7 Diversion | IDR 224.4 - Turweston Green Overbridge | IDR 224.4 | HS2-000020RTW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002Y4JK - Turweston Embankment Radio Compound UTX | IDR 224.4 - Turweston Green Overbridge | IDR 224.4 | HS2-00002Y4JK | #N/A | #N/A | #N/A
[8 empty] | HS2-000033GP4 - Clean Water Pipe CFA_14_14 | IDR 224.4 - Turweston Green Overbridge | IDR 224.4 | HS2-000033GP4 | 2024-02-06 | 10 - Complete | 2024-02-08
[8 empty] | HS2-00002BVJD - C2.L.107 Catchment | IDR 224.3 - Grovehill Embankment | IDR 224.3 | HS2-00002BVJD | #N/A | #N/A | #N/A
[8 empty] | HS2-000001061 - Grovehill Embankment | IDR 224.3 - Grovehill Embankment | IDR 224.3 | HS2-000001061 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DV8R - Grovehill Embankment Landscape Earthworks | IDR 224.3 - Grovehill Embankment | IDR 224.3 | HS2-00002DV8R | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVJG - C2.L.108 Catchment | IDR 224.3 - Grovehill Embankment | IDR 224.3 | HS2-00002BVJG | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTCL - C2.T.106 Catchment | IDR 224.3 - Grovehill Embankment | IDR 224.3 | HS2-00002CTCL | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NNS - Maintenance Access Road to Pond (Off A422 Brackley Road) | IDR 224.2 - Footpath WBB/17 Accomodation & A422 Brackley Road Overbridges | IDR 224.2 | HS2-000020NNS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VNHZ - Grovehill Embankment-Ancillary Culvert 092-AC4 | IDR 224.2 - Footpath WBB/17 Accomodation & A422 Brackley Road Overbridges | IDR 224.2 | HS2-00002VNHZ | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NP0 - Footpath WBB 17 Realignment | IDR 224.2 - Footpath WBB/17 Accomodation & A422 Brackley Road Overbridges | IDR 224.2 | HS2-000020NP0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VNJ0 - Turweston Cutting-Ancillary Culvert 093-AC5 | IDR 224.2 - Footpath WBB/17 Accomodation & A422 Brackley Road Overbridges | IDR 224.2 | HS2-00002VNJ0 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001330 - Footpath WBB 17 Accommodation Overbridge | IDR 224.2 - Footpath WBB/17 Accomodation & A422 Brackley Road Overbridges | IDR 224.2 | HS2-000001330 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CW13 - Footpath WBB 17 Drainage System | IDR 224.2 - Footpath WBB/17 Accomodation & A422 Brackley Road Overbridges | IDR 224.2 | HS2-00002CW13 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VXUF - Maintenance Access Road to GSMR (off Maintenance Access Road to Pond A422) and Compound | IDR 224.2 - Footpath WBB/17 Accomodation & A422 Brackley Road Overbridges | IDR 224.2 | HS2-00002VXUF | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NP1 - Oatleys Farm Accommodation Access Road | IDR 224.2 - Footpath WBB/17 Accomodation & A422 Brackley Road Overbridges | IDR 224.2 | HS2-000020NP1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJV4 - A422 Brackley Road Realignment | IDR 224.2 - Footpath WBB/17 Accomodation & A422 Brackley Road Overbridges | IDR 224.2 | HS2-00002BJV4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002C3Y5 - A422 Brackley Road Drainage System | IDR 224.2 - Footpath WBB/17 Accomodation & A422 Brackley Road Overbridges | IDR 224.2 | HS2-00002C3Y5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EK7F - Turweston Cutting Radio Compound UTX | IDR 224.2 - Footpath WBB/17 Accomodation & A422 Brackley Road Overbridges | IDR 224.2 | HS2-00002EK7F | #N/A | #N/A | #N/A
[8 empty] | HS2-000001331 - A422 Brackley Road Overbridge | IDR 224.2 - Footpath WBB/17 Accomodation & A422 Brackley Road Overbridges | IDR 224.2 | HS2-000001331 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVJJ - Turweston Cutting Landscape Earthworks | IDR 224.1 - Turweston Cutting Phase 2 (Full Package) | IDR 224.1 | HS2-00002BVJJ | #N/A | #N/A | #N/A
[8 empty] | HS2-000001062 - Turweston Cutting | IDR 224.1 - Turweston Cutting Phase 2 (Full Package) | IDR 224.1 | HS2-000001062 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTC2 - Mixbury Embankment Boundary Perimeter Fence Line | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-00002CTC2 | 2024-05-14 | 10 - Complete | 2024-05-15
[8 empty] | HS2-00002CTC4 - Mixbury Embankment Security Fence Line | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-00002CTC4 | 2024-05-03 | 10 - Complete | 2024-05-15
[8 empty] | HS2-00002CTC7 - Mixbury Cutting Boundary Perimeter Fence Line | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-00002CTC7 | 2024-05-14 | 10 - Complete | 2024-05-15
[8 empty] | HS2-00002CTC9 - Mixbury Cutting Security Fence Line | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-00002CTC9 | 2024-05-03 | 10 - Complete | 2024-05-15
[8 empty] | HS2-00002CTCA - Westbury Embankment Boundary Perimeter Line | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-00002CTCA | 2025-05-21 | 10 - Complete | 2025-05-27
[8 empty] | HS2-00002CTCC - Westbury Embankment Security Fence Line | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-00002CTCC | 2025-05-21 | 10 - Complete | 2025-05-27
[8 empty] | HS2-00002YCW9 - 91-SL2 Mixbury Embankment Vehicular Bridge | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-00002YCW9 | 2024-06-12 | 10 - Complete | 2024-06-21
[8 empty] | HS2-000037YLY - 91-SL1 Mixbury Embankment Pedestrian Slab | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-000037YLY | 2024-06-12 | 10 - Complete | 2024-06-21
[8 empty] | HS2-000037YLZ - 91-SL3 Mixbury Embankment Pedestrian Slab | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-000037YLZ | 2024-06-12 | 10 - Complete | 2024-06-21
[8 empty] | HS2-0000386TG - Mixbury Cutting Planting Plot 1 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386TG | 2024-05-29 | 10 - Complete | 2024-06-07
[8 empty] | HS2-0000386TH - Mixbury Cutting Planting Plot 2 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386TH | 2024-05-29 | 10 - Complete | 2024-06-07
[8 empty] | HS2-0000386TK - Mixbury Cutting Planting Plot 3 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386TK | 2024-05-29 | 10 - Complete | 2024-06-07
[8 empty] | HS2-0000386TL - Mixbury Cutting Planting Plot 4 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386TL | 2024-05-29 | 10 - Complete | 2024-06-07
[8 empty] | HS2-0000386TN - Mixbury Cutting Planting Plot 5 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386TN | 2024-05-29 | 10 - Complete | 2024-06-07
[8 empty] | HS2-0000386TP - Mixbury Cutting Planting Plot 6 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386TP | 2024-05-29 | 10 - Complete | 2024-06-07
[8 empty] | HS2-0000386TR - Mixbury Cutting Planting Plot 7 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386TR | 2024-05-29 | 10 - Complete | 2024-06-07
[8 empty] | HS2-0000386TS - Mixbury Embankment Planting Plot 1 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386TS | 2024-05-29 | 10 - Complete | 2024-06-06
[8 empty] | HS2-0000386TU - Mixbury Embankment Planting Plot 2 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386TU | 2024-05-29 | 10 - Complete | 2024-06-06
[8 empty] | HS2-0000386TV - Mixbury Embankment Planting Plot 3 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386TV | 2024-05-29 | 10 - Complete | 2024-06-06
[8 empty] | HS2-0000386TX - Mixbury Embankment Planting Plot 4 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386TX | 2024-05-29 | 10 - Complete | 2024-06-07
[8 empty] | HS2-0000386TY - Westbury Embankment Planting Plot 1 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386TY | 2024-05-29 | 10 - Complete | 2024-06-07
[8 empty] | HS2-0000386U0 - Westbury Embankment Planting Plot 2 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386U0 | 2024-05-29 | 10 - Complete | 2024-06-10
[8 empty] | HS2-0000386U1 - Westbury Embankment Planting Plot 3 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386U1 | 2024-05-29 | 10 - Complete | 2024-06-10
[8 empty] | HS2-0000386U3 - Westbury Embankment Planting Plot 4 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386U3 | 2024-05-29 | 10 - Complete | 2024-06-10
[8 empty] | HS2-0000386U4 - Westbury Embankment Planting Plot 5 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386U4 | 2024-05-29 | 10 - Complete | 2024-06-10
[8 empty] | HS2-0000386U6 - Westbury Embankment Planting Plot 6 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386U6 | 2024-05-29 | 10 - Complete | 2024-06-10
[8 empty] | HS2-0000386U7 - Westbury Embankment Planting Plot 7 | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-0000386U7 | 2024-05-29 | 10 - Complete | 2024-06-10
[8 empty] | HS2-000039DSD - Mossycorner Spinney (Bat Licence) Ecological Mitigation Site | IDR 223.8 - Mixbury Area and Westbury Embankment - Ancillary Civils Fencing and Landscape Planting | IDR 223.8 | HS2-000039DSD | 2024-05-22 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00002CTC6 - C2.T.105 Catchment | IDR 223.7 - Westbury Embankment | IDR 223.7 | HS2-00002CTC6 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001059 - Westbury Embankment | IDR 223.7 - Westbury Embankment | IDR 223.7 | HS2-000001059 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DV8Q - Westbury Embankment Landscape Earthworks | IDR 223.7 - Westbury Embankment | IDR 223.7 | HS2-00002DV8Q | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NNN - Flood Compensation Area-092 | IDR 223.7 - Westbury Embankment | IDR 223.7 | HS2-000020NNN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4YM - Bridleway 303 4 Accommodation Access Realignment | IDR 223.4 - Bridleway 303/4 Overbridge | IDR 223.4 | HS2-00002J4YM | 2023-11-02 | 10 - Complete | 2023-11-29
[8 empty] | HS2-00002BJV0 - Bridleway 303 4 and 303 22 Diversions | IDR 223.4 - Bridleway 303/4 Overbridge | IDR 223.4 | HS2-00002BJV0 | 2023-11-24 | 10 - Complete | 2023-11-27
[8 empty] | HS2-000001329 - Bridleway 303 4 Overbridge | IDR 223.4 - Bridleway 303/4 Overbridge | IDR 223.4 | HS2-000001329 | 2025-03-28 | 30 - Sent back to team | 0
[8 empty] | HS2-00002BJV1 - Maintenance Access Road to Pond (Off Bridleway 303 4) 01 | IDR 223.4 - Bridleway 303/4 Overbridge | IDR 223.4 | HS2-00002BJV1 | 2023-11-24 | 10 - Complete | 2023-11-27
[8 empty] | HS2-00002BJV2 - Maintenance Access Road to Pond (Off Bridleway 303 4) 02 | IDR 223.4 - Bridleway 303/4 Overbridge | IDR 223.4 | HS2-00002BJV2 | 2023-11-24 | 10 - Complete | 2023-11-27
[8 empty] | HS2-00002BVJ7 - C2.L.104 Catchment | IDR 223.4 - Bridleway 303/4 Overbridge | IDR 223.4 | HS2-00002BVJ7 | 2023-11-10 | 10 - Complete | 2023-11-29
[8 empty] | HS2-00002BJV3 - Bridleway 303 5 Link | IDR 223.4 - Bridleway 303/4 Overbridge | IDR 223.4 | HS2-00002BJV3 | 2023-11-02 | 10 - Complete | 2023-11-09
[8 empty] | HS2-00002VNJ2 - Westbury Embankment-Ancillary Culvert 092-AC2 | IDR 223.4 - Bridleway 303/4 Overbridge | IDR 223.4 | HS2-00002VNJ2 | 2023-11-09 | 10 - Complete | 2023-11-14
[8 empty] | HS2-00002CTBM - C2.L.99 Catchment | IDR 223.3 - Mixbury Embankment, Mixbury cutting | IDR 223.3 | HS2-00002CTBM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVJ1 - C2.L.101 Catchment | IDR 223.3 - Mixbury Embankment, Mixbury cutting | IDR 223.3 | HS2-00002BVJ1 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001057 - Mixbury Embankment | IDR 223.3 - Mixbury Embankment, Mixbury cutting | IDR 223.3 | HS2-000001057 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001058 - Mixbury Cutting | IDR 223.3 - Mixbury Embankment, Mixbury cutting | IDR 223.3 | HS2-000001058 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVJ6 - Mixbury Cutting Landscape Earthworks | IDR 223.3 - Mixbury Embankment, Mixbury cutting | IDR 223.3 | HS2-00002BVJ6 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001060 - Westbury Viaduct | IDR 223.2 - Westbury Viaduct | IDR 223.2 | HS2-000001060 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002Y0EZ - Westbury Structural Backfill Retaining Wall | IDR 223.2 - Westbury Viaduct | IDR 223.2 | HS2-00002Y0EZ | #N/A | #N/A | #N/A
[8 empty] | HS2-000001434 - Mixbury Culvert | IDR 223.1 - Mixbury Culvert | IDR 223.1 | HS2-000001434 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NNHY - Mixbury Culvert Watercourse Diversion | IDR 223.1 - Mixbury Culvert | IDR 223.1 | HS2-00002NNHY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTBS - Barton to Mixbury Cutting Boundary Perimeter Fence Line | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00002CTBS | 2024-11-28 | 10 - Complete | 2025-01-07
[8 empty] | HS2-00002CTBU - Barton to Mixbury Cutting Security Fence Line | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00002CTBU | 2024-11-28 | 10 - Complete | 2025-01-07
[8 empty] | HS2-000031EF2 - 92-SL1 Westbury Embankment Pedestrian Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-000031EF2 | 2024-09-24 | 10 - Complete | 2024-10-15
[8 empty] | HS2-000037YLP - 87-SL4 Barton to Mixbury Cutting Pedestrian Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-000037YLP | 2024-09-24 | 10 - Complete | 2024-10-04
[8 empty] | HS2-000037YLR - 88-SL1 Barton to Mixbury Cutting Vehicular Bridge | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-000037YLR | 2024-09-24 | 10 - Complete | 2024-10-08
[8 empty] | HS2-000037YLS - 88-SL2 Barton to Mixbury Cutting Vehicular Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-000037YLS | 2024-09-24 | 10 - Complete | 2024-10-03
[8 empty] | HS2-000037YLT - 88-SL3 Barton to Mixbury Cutting Pedestrian Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-000037YLT | 2024-09-24 | 10 - Complete | 2024-10-03
[8 empty] | HS2-0000386UD - 88-SL1 Barton to Mixbury Cutting Vehicular Bridge-Earthworks Transition | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-0000386UD | 2024-10-28 | 10 - Complete | 2024-12-23
[8 empty] | HS2-000039DS9 - Finmere (Bat Licence) Ecological Mitigation Site | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-000039DS9 | 2024-12-19 | 10 - Complete | 2025-01-03
[8 empty] | HS2-00003BPKK - Barton to Mixbury Cutting Planting Plot 13 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKK | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKL - Barton to Mixbury Cutting Planting Plot 1 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKL | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKM - Barton to Mixbury Cutting Planting Plot 2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKM | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKN - Barton to Mixbury Cutting Planting Plot 12 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKN | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKP - Barton to Mixbury Cutting Planting Plot 14 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKP | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKQ - Barton to Mixbury Cutting Planting Plot 15 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKR - Barton to Mixbury Cutting Planting Plot 3 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKR | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKS - Barton to Mixbury Cutting Planting Plot 4 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKS | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKT - Barton to Mixbury Cutting Planting Plot 16 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKT | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKU - Barton to Mixbury Cutting Planting Plot 5 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKU | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKV - Barton to Mixbury Cutting Planting Plot 6 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKV | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKW - Barton to Mixbury Cutting Planting Plot 17 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKW | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKX - Barton to Mixbury Cutting Planting Plot 18 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKX | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKY - Barton to Mixbury Cutting Planting Plot 8 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKY | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPKZ - Barton to Mixbury Cutting Planting Plot 7 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPKZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPL0 - Barton to Mixbury Cutting Planting Plot 19 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPL0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPL1 - Barton to Mixbury Cutting Planting Plot 20 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPL1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPL2 - Barton to Mixbury Cutting Planting Plot 10 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPL2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPL3 - Barton to Mixbury Cutting Planting Plot 9 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPL3 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPL4 - Barton to Mixbury Cutting Planting Plot 11 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003BPL4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D82W - Access stair 82-ST1 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D82W | 2024-10-28 | 10 - Complete | 2024-11-07
[8 empty] | HS2-00003D82X - Access stair 82-ST2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D82X | 2024-10-28 | 10 - Complete | 2024-11-07
[8 empty] | HS2-00003D82Y - Access stair 83-ST1 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D82Y | 2024-10-28 | 10 - Complete | 2024-11-07
[8 empty] | HS2-00003D82Z - Access stair 83-ST2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D82Z | 2024-10-28 | 10 - Complete | 2024-11-07
[8 empty] | HS2-00003D830 - Access stair 84-ST1 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D830 | 2024-11-18 | 10 - Complete | 2025-01-03
[8 empty] | HS2-00003D831 - Access stair 84-ST2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D831 | 2024-11-18 | 10 - Complete | 2025-01-03
[8 empty] | HS2-00003D832 - Access stair 84-ST3 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D832 | 2024-10-28 | 10 - Complete | 2024-11-11
[8 empty] | HS2-00003D833 - Access stair 84-ST4 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D833 | 2024-10-28 | 10 - Complete | 2024-11-08
[8 empty] | HS2-00003D834 - Access stair 84-ST5 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D834 | 2024-10-28 | 10 - Complete | 2024-11-11
[8 empty] | HS2-00003D835 - Access stair 84-ST6 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D835 | 2024-10-28 | 10 - Complete | 2024-11-11
[8 empty] | HS2-00003D836 - Access stair 84-ST7 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D836 | 2024-10-28 | 10 - Complete | 2024-11-11
[8 empty] | HS2-00003D837 - Access stair 84-ST8 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D837 | 2024-10-28 | 10 - Complete | 2024-11-11
[8 empty] | HS2-00003D838 - Access stair 85-ST1 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D838 | 2024-10-28 | 10 - Complete | 2024-11-11
[8 empty] | HS2-00003D839 - Access stair 85-ST2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D839 | 2024-10-28 | 10 - Complete | 2024-11-11
[8 empty] | HS2-00003D83A - Access stair 86-ST1 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83A | 2024-10-28 | 10 - Complete | 2024-11-11
[8 empty] | HS2-00003D83B - Access stair 86-ST2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83B | 2024-10-28 | 10 - Complete | 2024-11-12
[8 empty] | HS2-00003D83C - Access stair 87-ST1 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83C | 2024-10-28 | 10 - Complete | 2024-11-12
[8 empty] | HS2-00003D83D - Access stair 87-ST2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83D | 2024-10-28 | 10 - Complete | 2024-11-12
[8 empty] | HS2-00003D83E - Access stair 88-ST1 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83E | 2024-10-28 | 10 - Complete | 2024-11-12
[8 empty] | HS2-00003D83F - Access stair 88-ST2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83F | 2024-10-28 | 10 - Complete | 2024-11-13
[8 empty] | HS2-00003D83G - Access stair 88-ST3 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83G | 2024-10-28 | 10 - Complete | 2024-11-13
[8 empty] | HS2-00003D83J - Access stair 89-ST1 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83J | 2024-10-28 | 10 - Complete | 2024-11-13
[8 empty] | HS2-00003D83K - Access stair 89-ST2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83K | 2024-10-28 | 10 - Complete | 2025-01-24
[8 empty] | HS2-00003D83L - Access stair 89-ST3 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83L | 2024-10-28 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003D83M - Access stair 89-ST4 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83M | 2024-10-28 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003D83N - Access stair 90-ST1 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83N | 2024-10-28 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003D83P - Access stair 90-ST2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83P | 2024-10-28 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003D83Q - Access stair 91-ST1 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83Q | 2024-10-28 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003D83R - Access stair 91-ST2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83R | 2024-10-28 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003D83S - Access stair 92-ST3 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83S | 2024-10-28 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003D83T - Access stair 92-ST4 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83T | 2024-10-28 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003D83U - Access stair 92-ST5 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83U | 2024-10-28 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003D83V - Access stair 92-ST6 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D83V | 2025-02-20 | 10 - Complete | 2025-02-24
[8 empty] | HS2-00003D841 - Access stair 93-ST6 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D841 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D846 - Access stair 93-ST11 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D846 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D849 - Access stair 93-ST14 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D849 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D84A - Access stair 93-ST15 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D84A | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D84E - Access stair 94-ST4 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D84E | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D84M - Access stair 94-ST11 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D84M | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D84R - Access stair 94-ST15 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D84R | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D84S - Access stair 94-ST16 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D84S | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D84T - Access stair 94-ST17 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D84T | 2024-10-28 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003D84U - Access stair 94-ST18 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D84U | 2024-10-28 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003D84X - Access stair 95-ST2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D84X | 2024-11-18 | 10 - Complete | 2025-01-03
[8 empty] | HS2-00003D84Y - Access stair 95-ST3 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D84Y | 2024-11-18 | 10 - Complete | 2025-01-03
[8 empty] | HS2-00003D84Z - Access stair 95-ST4 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D84Z | 2024-10-28 | 10 - Complete | 2025-01-24
[8 empty] | HS2-00003D850 - Access stair 95-ST5 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D850 | 2024-10-28 | 10 - Complete | 2025-01-24
[8 empty] | HS2-00003D854 - Access stair 97-ST3 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D854 | 2024-10-28 | 10 - Complete | 2025-01-23
[8 empty] | HS2-00003D855 - Access stair 98-ST1 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D855 | 2024-10-28 | 10 - Complete | 2025-01-23
[8 empty] | HS2-00003D857 - Access stair 98-ST3 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D857 | 2024-10-28 | 10 - Complete | 2025-01-23
[8 empty] | HS2-00003D858 - Access stair 98-ST4 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D858 | 2024-10-28 | 10 - Complete | 2025-01-23
[8 empty] | HS2-00003D85A - Access stair 99-ST2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D85A | 2024-10-28 | 10 - Complete | 2025-01-23
[8 empty] | HS2-00003D85B - Access stair 100-ST1 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D85B | 2024-10-28 | 10 - Complete | 2025-01-23
[8 empty] | HS2-00003D85C - Access stair 100-ST2 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D85C | 2024-10-28 | 10 - Complete | 2025-01-23
[8 empty] | HS2-00003D85D - Access stair 100-ST3 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D85D | 2024-10-28 | 10 - Complete | 2025-01-23
[8 empty] | HS2-00003D85E - Access stair 100-ST4 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003D85E | 2024-10-28 | 10 - Complete | 2025-01-23
[8 empty] | HS2-00003FV0S - Access stair 97-ST4 | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003FV0S | 2024-10-28 | 10 - Complete | 2025-01-23
[8 empty] | HS2-00003JAYD - Footpath 308-2 Link | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003JAYD | 2024-10-29 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003JAYE - Footpath 308-3 Link | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003JAYE | 2024-10-29 | 10 - Complete | 2024-11-13
[8 empty] | HS2-00003JYGN - 89-SL1 Barton to Mixbury Cutting GSMR 42 UTX Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003JYGN | 2024-09-24 | 10 - Complete | 2024-10-03
[8 empty] | HS2-00003JYGP - 89-SL2 Barton to Mixbury Cutting GSMR 42 UTX Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003JYGP | 2024-09-24 | 10 - Complete | 2024-09-30
[8 empty] | HS2-00003JYGQ - 89-SL3 Barton to Mixbury Cutting GSMR 42 UTX Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003JYGQ | 2024-09-24 | 10 - Complete | 2024-09-30
[8 empty] | HS2-00003JYGR - 89-SL4 Barton to Mixbury Cutting GSMR 42 UTX Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003JYGR | 2024-09-24 | 10 - Complete | 2024-09-30
[8 empty] | HS2-00003JYGS - 91-SL4 Tibbetts Farm EFATS UTX Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003JYGS | 2024-09-24 | 10 - Complete | 2024-09-27
[8 empty] | HS2-00003JYGT - 91-SL5 Tibbetts Farm EFATS UTX Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003JYGT | 2024-09-24 | 10 - Complete | 2024-09-27
[8 empty] | HS2-00003JYGU - 96-SL1 Whitfield ATS UTX Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003JYGU | 2024-09-24 | 10 - Complete | 2024-09-27
[8 empty] | HS2-00003JYGV - 96-SL2 Whitfield ATS UTX Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003JYGV | 2024-09-24 | 10 - Complete | 2024-09-27
[8 empty] | HS2-00003JYGW - 97-SL1 Brackley South Cutting GSMR 47 UTX Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003JYGW | 2024-09-24 | 10 - Complete | 2024-09-27
[8 empty] | HS2-00003JYGX - 97-SL3 Brackley South Cutting GSMR 47 UTX Slab | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003JYGX | 2024-09-24 | 10 - Complete | 2024-10-01
[8 empty] | HS2-00003KX2T - 84-SL5 Godington West Embankment Vehicular Bridge (IDB) | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003KX2T | 2024-10-17 | 10 - Complete | 2024-10-18
[8 empty] | HS2-00003KX2U - 84-SL6 Godington West Embankment Vehicular Bridge (IDB) | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003KX2U | 2024-10-17 | 10 - Complete | 2024-10-18
[8 empty] | HS2-00003KX2V - 84-SL5 Godington West Embankment Vehicular Bridge (IDB) - Earthworks Transition | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003KX2V | 2024-10-28 | 10 - Complete | 2024-12-23
[8 empty] | HS2-00003KX2W - 84-SL6 Godington West Embankment Vehicular Bridge (IDB) - Earthworks Transition | IDR 222.9 - Barton to Mixbury Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 222.9 | HS2-00003KX2W | 2024-10-28 | 10 - Complete | 2024-12-23
[8 empty] | HS2-00002BJUV - Bridleway 213 7 Diversion | IDR 222.8 - Bridleway 213/7 Overbridge | IDR 222.8 | HS2-00002BJUV | 2024-01-09 | 10 - Complete | 2024-01-11
[8 empty] | HS2-000001325 - Bridleway 213 7 Overbridge | IDR 222.8 - Bridleway 213/7 Overbridge | IDR 222.8 | HS2-000001325 | 2024-01-10 | 10 - Complete | 2024-01-19
[8 empty] | HS2-000020RN0 - A4421 Buckingham Road Realignment | IDR 222.7 - A4421 Buckingham Road Overbridges | IDR 222.7 | HS2-000020RN0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4YL - Existing A4421 Buckingham Road Link-West | IDR 222.7 - A4421 Buckingham Road Overbridges | IDR 222.7 | HS2-00002J4YL | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4YH - Maintenance Access Road to Pond (Off A4421 Buckingham Road-West) | IDR 222.7 - A4421 Buckingham Road Overbridges | IDR 222.7 | HS2-00002J4YH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002C3XT - A4421 Buckingham Road Drainage System | IDR 222.7 - A4421 Buckingham Road Overbridges | IDR 222.7 | HS2-00002C3XT | #N/A | #N/A | #N/A
[8 empty] | HS2-000001324 - A4421 Buckingham Road Overbridge | IDR 222.7 - A4421 Buckingham Road Overbridges | IDR 222.7 | HS2-000001324 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4YK - Existing A4421 Buckingham Road Link-East (Leading to Barton Hartshorn) | IDR 222.7 - A4421 Buckingham Road Overbridges | IDR 222.7 | HS2-00002J4YK | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VXUD - Maintenance Access Road to GSMR (off Widmore Farm Access) and Compound | IDR 222.6 - Bridleway 213/4 Accommodation Overbridge | IDR 222.6 | HS2-00002VXUD | 2024-06-27 | 10 - Complete | 2024-07-08
[8 empty] | HS2-00002BJUW - Bridleway 213 4 Accommodation Access Realignment | IDR 222.6 - Bridleway 213/4 Accommodation Overbridge | IDR 222.6 | HS2-00002BJUW | 2024-06-27 | 10 - Complete | 2024-07-11
[8 empty] | HS2-00002CW0J - Bridleway 213 4 Drainage System | IDR 222.6 - Bridleway 213/4 Accommodation Overbridge | IDR 222.6 | HS2-00002CW0J | 2024-06-18 | 10 - Complete | 2024-06-21
[8 empty] | HS2-000001326 - Bridleway 213 4 Accommodation Overbridge | IDR 222.6 - Bridleway 213/4 Accommodation Overbridge | IDR 222.6 | HS2-000001326 | 2024-06-11 | 10 - Complete | 2024-07-10
[8 empty] | HS2-00002N7WN - Barton to Mixbury Cutting-Ancillary Culvert 089-AC2 | IDR 222.6 - Bridleway 213/4 Accommodation Overbridge | IDR 222.6 | HS2-00002N7WN | 2024-06-12 | 10 - Complete | 2024-06-19
[8 empty] | HS2-00002YGQF - Barton to Mixbury radio compound UTX No2 (GSMR Point 42) | IDR 222.6 - Bridleway 213/4 Accommodation Overbridge | IDR 222.6 | HS2-00002YGQF | 2025-02-03 | 10 - Complete | 2025-02-17
[8 empty] | HS2-00002CTBQ - Featherbed Lane Drainage System | IDR 222.5 - Featherbed Lane Overbridge | IDR 222.5 | HS2-00002CTBQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EK7D - Barton to Mixbury Cutting Radio Compound UTX | IDR 222.5 - Featherbed Lane Overbridge | IDR 222.5 | HS2-00002EK7D | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NMZ - Maintenance access road to Pond (off Tibbets Farm Road) | IDR 222.5 - Featherbed Lane Overbridge | IDR 222.5 | HS2-000020NMZ | #N/A | #N/A | #N/A
[8 empty] | HS2-000020BTF - Tibbetts Farm EFATS | IDR 222.5 - Featherbed Lane Overbridge | IDR 222.5 | HS2-000020BTF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VXUE - Maintenance Access Road to GSMR (off Featherbed Lane Realignment) and Compound (inc Field Access) | IDR 222.5 - Featherbed Lane Overbridge | IDR 222.5 | HS2-00002VXUE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJUY - Featherbed Lane Realignment | IDR 222.5 - Featherbed Lane Overbridge | IDR 222.5 | HS2-00002BJUY | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NN1 - Tibbetts Farm EFATS Access Road (inc Maintenance Access Road to Pond) | IDR 222.5 - Featherbed Lane Overbridge | IDR 222.5 | HS2-000020NN1 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001328 - Featherbed Lane Overbridge | IDR 222.5 - Featherbed Lane Overbridge | IDR 222.5 | HS2-000001328 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TMEZ - Tibbetts Farm EFATS Telecoms | IDR 222.5 - Featherbed Lane Overbridge | IDR 222.5 | HS2-00002TMEZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EK7E - Tibbetts Farm EFATS UTX | IDR 222.5 - Featherbed Lane Overbridge | IDR 222.5 | HS2-00002EK7E | #N/A | #N/A | #N/A
[8 empty] | HS2-00003K85R - Featherbed Lane Realignment retaining wall | IDR 222.5 - Featherbed Lane Overbridge | IDR 222.5 | HS2-00003K85R | 2024-12-16 | 10 - Complete | 2025-01-08
[8 empty] | HS2-00002CTBJ - C2.L.96 Catchment | IDR 222.4 - A421 London Road OB | IDR 222.4 | HS2-00002CTBJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTBL - C2.L.98 Catchment | IDR 222.4 - A421 London Road OB | IDR 222.4 | HS2-00002CTBL | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NMS - Widmore Farm Accommodation Access Road | IDR 222.4 - A421 London Road OB | IDR 222.4 | HS2-000020NMS | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NMT - Warren Farm Accommodation Access Road | IDR 222.4 - A421 London Road OB | IDR 222.4 | HS2-000020NMT | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJUX - A421 London Road Realignment | IDR 222.4 - A421 London Road OB | IDR 222.4 | HS2-00002BJUX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7WQ - Barton to Mixbury Cutting-Ancillary Culvert 089-AC4 | IDR 222.4 - A421 London Road OB | IDR 222.4 | HS2-00002N7WQ | 2024-01-09 | 10 - Complete | 2024-01-11
[8 empty] | HS2-000001327 - A421 London Road Overbridge | IDR 222.4 - A421 London Road OB | IDR 222.4 | HS2-000001327 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002C3XZ - A421 London Road Drainage System | IDR 222.4 - A421 London Road OB | IDR 222.4 | HS2-00002C3XZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVHY - C2.L.93 Catchment | IDR 222.2 - Barton to Mixbury Cutting | IDR 222.2 | HS2-00002BVHY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVJ0 - Barton to Mixbury Cutting Landscape Earthworks | IDR 222.2 - Barton to Mixbury Cutting | IDR 222.2 | HS2-00002BVJ0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTBH - C2.L.95 Catchment | IDR 222.2 - Barton to Mixbury Cutting | IDR 222.2 | HS2-00002CTBH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTBP - C2.T.100 Catchment | IDR 222.2 - Barton to Mixbury Cutting | IDR 222.2 | HS2-00002CTBP | #N/A | #N/A | #N/A
[8 empty] | HS2-000001056 - Barton to Mixbury Cutting | IDR 222.2 - Barton to Mixbury Cutting | IDR 222.2 | HS2-000001056 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002UVYY - Newton Purcell Culvert Watercourse Diversion (downstream channel) | IDR 222.2 - Barton to Mixbury Cutting | IDR 222.2 | HS2-00002UVYY | 2024-07-17 | 10 - Complete | 2024-08-01
[8 empty] | HS2-00002UVYZ - Newton Purcell Culvert Watercourse Diversion (upstream channel) | IDR 222.2 - Barton to Mixbury Cutting | IDR 222.2 | HS2-00002UVYZ | 2024-07-18 | 10 - Complete | 2024-08-01
[8 empty] | HS2-00002N7WH - Barton to Mixbury Cutting-Ancillary Culvert 088-AC2 | IDR 222.2 - Barton to Mixbury Cutting | IDR 222.2 | HS2-00002N7WH | 2024-01-08 | 10 - Complete | 2024-01-10
[8 empty] | HS2-00002UVZ0 - Ancillary Culvert 088-AC1 Watercourse Diversion | IDR 222.2 - Barton to Mixbury Cutting | IDR 222.2 | HS2-00002UVZ0 | 2024-07-17 | 10 - Complete | 2024-08-01
[8 empty] | HS2-000020NMK - Flood Compensation Area-088A | IDR 222.2 - Barton to Mixbury Cutting | IDR 222.2 | HS2-000020NMK | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7WK - Barton to Mixbury Cutting-Ancillary Culvert 088-AC4 | IDR 222.2 - Barton to Mixbury Cutting | IDR 222.2 | HS2-00002N7WK | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7WG - Barton to Mixbury Cutting-Ancillary Culvert 088-AC1 | IDR 222.2 - Barton to Mixbury Cutting | IDR 222.2 | HS2-00002N7WG | 2024-01-09 | 10 - Complete | 2024-01-11
[8 empty] | HS2-00002N7WJ - Barton to Mixbury Cutting-Ancillary Culvert 088-AC3 | IDR 222.2 - Barton to Mixbury Cutting | IDR 222.2 | HS2-00002N7WJ | 2024-01-08 | 10 - Complete | 2024-01-11
[8 empty] | HS2-00002BJUT - Footpath BHA 2 Diversion | IDR 222.1 - Newton Purcell culvert & Footpath BHA/2 | IDR 222.1 | HS2-00002BJUT | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CW0W - Footpath BHA 2 Drainage System | IDR 222.1 - Newton Purcell culvert & Footpath BHA/2 | IDR 222.1 | HS2-00002CW0W | #N/A | #N/A | #N/A
[8 empty] | HS2-000001323 - Footpath BHA 2 Overbridge | IDR 222.1 - Newton Purcell culvert & Footpath BHA/2 | IDR 222.1 | HS2-000001323 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001433 - Newton Purcell Inverted Siphon | IDR 222.1 - Newton Purcell culvert & Footpath BHA/2 | IDR 222.1 | HS2-000001433 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTA8 - Godington East Embankment Boundary Perimeter Fence Line | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002CTA8 | 2024-10-17 | 10 - Complete | 2024-10-30
[8 empty] | HS2-00002CTAA - Godington East Embankment Security Fence Line | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002CTAA | 2024-10-17 | 10 - Complete | 2024-10-23
[8 empty] | HS2-00002CTAF - Godington West Embankment Boundary Perimeter Fence Line | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002CTAF | 2024-10-17 | 10 - Complete | 2024-10-22
[8 empty] | HS2-00002CTAH - Godington West Embankment Security Fence Line | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002CTAH | 2024-10-17 | 10 - Complete | 2024-10-24
[8 empty] | HS2-00002EKXU - Godington Ecological Mitigation Site (A) | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002EKXU | 2024-09-19 | 10 - Complete | 2024-10-11
[8 empty] | HS2-00002CTAN - C2.L.83 Catchment | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002CTAN | 2024-10-18 | 10 - Complete | 2024-10-23
[8 empty] | HS2-00002CTAR - Chetwode Embankment Boundary Perimeter Fence Line | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002CTAR | 2024-10-17 | 10 - Complete | 2024-10-23
[8 empty] | HS2-00002CTAT - Chetwode Embankment Security Fence Line | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002CTAT | 2024-10-17 | 10 - Complete | 2024-10-23
[8 empty] | HS2-00002CTAX - C2.L.86 Catchment | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002CTAX | 2024-09-13 | 10 - Complete | 2024-09-20
[8 empty] | HS2-00002CTB1 - Chetwode Cutting Boundary Perimeter Fence Line | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002CTB1 | 2024-10-17 | 10 - Complete | 2024-10-23
[8 empty] | HS2-00002CTB3 - Chetwode Cutting Security Fence Line | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002CTB3 | 2024-10-17 | 10 - Complete | 2024-10-23
[8 empty] | HS2-00002EK7C - Chetwode ATS UTX | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002EK7C | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVHV - C2.L.87 Catchment | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002BVHV | 2024-09-13 | 10 - Complete | 2024-09-20
[8 empty] | HS2-00002CTB9 - Barton Hartshorn Embankment Boundary Perimeter Fence Line | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002CTB9 | 2024-10-17 | 10 - Complete | 2024-10-23
[8 empty] | HS2-00002CTBB - Barton Hartshorn Embankment Security Fence Line | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002CTBB | 2024-10-17 | 10 - Complete | 2024-10-23
[8 empty] | HS2-00002N7WF - Barton Hartshorn Embankment-Ancillary Culvert 087-AC2 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002N7WF | 2024-09-13 | 10 - Complete | 2024-09-20
[8 empty] | HS2-00002Y0AU - Chetwode Cutting-Ancillary Culvert 085-AC2 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002Y0AU | 2024-10-18 | 10 - Complete | 2024-10-24
[8 empty] | HS2-00002Y4JJ - 087-AC2 Watercourse Diversion | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002Y4JJ | 2024-11-13 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00002YGQ8 - 84-SL2 Chetwode Embankment Vehicular Slab | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002YGQ8 | 2024-07-09 | 10 - Complete | 2024-08-19
[8 empty] | HS2-00002YGQA - 87-SL1 Barton Hartshorn Embankment Pedestrian Slab | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002YGQA | 2024-07-09 | 10 - Complete | 2024-08-20
[8 empty] | HS2-00002YGQC - 85-SL1 Chetwode Cutting Vehicular Slab | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002YGQC | 2024-07-09 | 10 - Complete | 2024-08-19
[8 empty] | HS2-00002YUF9 - Flood Compensation Area-087 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00002YUF9 | 2024-09-13 | 10 - Complete | 2024-09-20
[8 empty] | HS2-000031EF1 - 84-SL1 Godington East Embankment Vehicular Bridge | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-000031EF1 | 2024-07-09 | 10 - Complete | 2024-08-23
[8 empty] | HS2-000037YLH - 84-SL3 Chetwode Embankment Vehicular Slab | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-000037YLH | 2024-07-09 | 10 - Complete | 2024-08-19
[8 empty] | HS2-000037YLK - 86-SL1 Chetwode Cutting Vehicular Slab | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-000037YLK | 2024-07-09 | 10 - Complete | 2024-08-23
[8 empty] | HS2-000037YLM - 87-SL2 Barton Hartshorn Embankment Pedestrian Slab | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-000037YLM | 2024-07-09 | 10 - Complete | 2024-08-20
[8 empty] | HS2-0000386UC - 84-SL1 Godington East Embankment Vehicular Bridge-Earthworks Transition | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-0000386UC | 2024-09-13 | 10 - Complete | 2024-09-20
[8 empty] | HS2-000039DS8 - Barton Hartshorn (Bat Licence) Ecological Mitigation Site | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-000039DS8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003BPJJ - Godington East Embankment Planting Plot 3 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJJ | 2024-10-22 | 10 - Complete | 2024-10-25
[8 empty] | HS2-00003BPJK - Godington East Embankment Planting Plot 1 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJK | 2024-10-22 | 10 - Complete | 2024-10-25
[8 empty] | HS2-00003BPJL - Godington East Embankment Planting Plot 2 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJL | 2024-10-22 | 10 - Complete | 2024-10-30
[8 empty] | HS2-00003BPJM - Godington East Viaduct Planting Plot 3 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJM | 2024-10-22 | 10 - Complete | 2024-10-30
[8 empty] | HS2-00003BPJN - Godington East Viaduct Planting Plot 4 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJN | 2024-10-22 | 10 - Complete | 2024-10-30
[8 empty] | HS2-00003BPJP - Godington East Viaduct Planting Plot 1 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJP | 2024-10-22 | 10 - Complete | 2024-10-29
[8 empty] | HS2-00003BPJQ - Godington East Viaduct Planting Plot 2 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJQ | 2024-10-22 | 10 - Complete | 2024-10-29
[8 empty] | HS2-00003BPJR - Godington West Embankment Planting Plot 3 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJR | 2024-10-22 | 10 - Complete | 2024-10-29
[8 empty] | HS2-00003BPJS - Godington West Embankment Planting Plot 1 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJS | 2024-10-22 | 10 - Complete | 2024-10-29
[8 empty] | HS2-00003BPJT - Godington West Embankment Planting Plot 2 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJT | 2024-10-22 | 10 - Complete | 2024-10-29
[8 empty] | HS2-00003BPJU - Godington West Embankment Planting Plot 4 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJU | 2024-10-22 | 10 - Complete | 2024-11-05
[8 empty] | HS2-00003BPJV - Godington West Viaduct Planting Plot 1 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJV | 2024-10-22 | 10 - Complete | 2024-11-05
[8 empty] | HS2-00003BPJW - Godington West Viaduct Planting Plot 3 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJW | 2024-10-22 | 10 - Complete | 2024-11-05
[8 empty] | HS2-00003BPJX - Godington West Viaduct Planting Plot 2 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJX | 2024-10-22 | 10 - Complete | 2024-11-05
[8 empty] | HS2-00003BPJY - Chetwode Embankment Planting Plot 2 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJY | 2024-10-22 | 10 - Complete | 2024-10-30
[8 empty] | HS2-00003BPJZ - Chetwode Embankment Planting Plot 3 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPJZ | 2024-10-22 | 10 - Complete | 2024-10-30
[8 empty] | HS2-00003BPK0 - Chetwode Embankment Planting Plot 5 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPK0 | 2024-10-22 | 10 - Complete | 2024-11-05
[8 empty] | HS2-00003BPK1 - Chetwode Cutting Planting Plot 2 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPK1 | 2024-10-22 | 10 - Complete | 2024-11-04
[8 empty] | HS2-00003BPK2 - Chetwode Embankment Planting Plot 1 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPK2 | 2024-10-22 | 10 - Complete | 2024-10-29
[8 empty] | HS2-00003BPK3 - Chetwode Embankment Planting Plot 4 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPK3 | 2024-10-22 | 10 - Complete | 2024-10-30
[8 empty] | HS2-00003BPK4 - Chetwode Cutting Planting Plot 8 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPK4 | 2024-10-22 | 10 - Complete | 2024-11-04
[8 empty] | HS2-00003BPK5 - Chetwode Cutting Planting Plot 1 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPK5 | 2024-10-22 | 10 - Complete | 2024-11-04
[8 empty] | HS2-00003BPK6 - Chetwode Cutting Planting Plot 7 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPK6 | 2024-10-22 | 10 - Complete | 2024-11-04
[8 empty] | HS2-00003BPK7 - Chetwode Cutting Planting Plot 10 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPK7 | 2024-10-22 | 10 - Complete | 2024-11-04
[8 empty] | HS2-00003BPK8 - Chetwode Cutting Planting Plot 3 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPK8 | 2024-10-22 | 10 - Complete | 2024-11-04
[8 empty] | HS2-00003BPK9 - Chetwode Cutting Planting Plot 9 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPK9 | 2024-10-22 | 10 - Complete | 2024-11-05
[8 empty] | HS2-00003BPKA - Chetwode Cutting Planting Plot 11 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPKA | 2024-10-22 | 10 - Complete | 2024-10-28
[8 empty] | HS2-00003BPKB - Chetwode Cutting Planting Plot 4 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPKB | 2024-10-22 | 10 - Complete | 2024-11-04
[8 empty] | HS2-00003BPKC - Chetwode Cutting Planting Plot 12 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPKC | 2024-10-22 | 10 - Complete | 2024-10-29
[8 empty] | HS2-00003BPKD - Chetwode Cutting Planting Plot 5 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPKD | 2024-10-22 | 10 - Complete | 2024-11-04
[8 empty] | HS2-00003BPKE - Chetwode Cutting Planting Plot 6 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPKE | 2024-10-22 | 10 - Complete | 2024-11-04
[8 empty] | HS2-00003BPKF - Barton Hartshorn Embankment Planting Plot 4 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPKF | 2024-10-22 | 10 - Complete | 2024-11-07
[8 empty] | HS2-00003BPKG - Barton Hartshorn Embankment Planting Plot 1 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPKG | 2024-10-22 | 10 - Complete | 2024-11-05
[8 empty] | HS2-00003BPKH - Barton Hartshorn Embankment Planting Plot 3 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPKH | 2024-10-22 | 10 - Complete | 2024-11-07
[8 empty] | HS2-00003BPKJ - Barton Hartshorn Embankment Planting Plot 2 | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003BPKJ | 2024-10-22 | 10 - Complete | 2024-11-07
[8 empty] | HS2-00003FV0J - Godington West Ecological Pond | IDR 221.5 - Godington Area and Chetwode Area - Ancillary Civils Fencing and Landscape Planting | IDR 221.5 | HS2-00003FV0J | 2024-09-13 | 10 - Complete | 2024-09-20
[8 empty] | HS2-00002CTB0 - School End Road Drainage System | IDR 221.2 - Footpath CHW/18 Accommodation Overbridge & School End Overbridge | IDR 221.2 | HS2-00002CTB0 | 2024-04-03 | 10 - Complete | 2024-04-05
[8 empty] | HS2-000020357 - The Green Highway Realignment | IDR 221.2 - Footpath CHW/18 Accommodation Overbridge & School End Overbridge | IDR 221.2 | HS2-000020357 | 2024-03-11 | 10 - Complete | 2024-03-12
[8 empty] | HS2-00002QH92 - Footpath CHW 18 Diversion | IDR 221.2 - Footpath CHW/18 Accommodation Overbridge & School End Overbridge | IDR 221.2 | HS2-00002QH92 | 2024-03-11 | 10 - Complete | 2024-03-12
[8 empty] | HS2-00002TMEY - Chetwode ATS Telecoms | IDR 221.2 - Footpath CHW/18 Accommodation Overbridge & School End Overbridge | IDR 221.2 | HS2-00002TMEY | #N/A | #N/A | #N/A
[8 empty] | HS2-000001321 - Footpath CHW 18 Accommodation Overbridge | IDR 221.2 - Footpath CHW/18 Accommodation Overbridge & School End Overbridge | IDR 221.2 | HS2-000001321 | 2024-04-24 | 10 - Complete | 2024-04-25
[8 empty] | HS2-000020NLY - Chetwode ATS Access Road and Maintenance Access Road to Pond (P-RAI-0846) | IDR 221.2 - Footpath CHW/18 Accommodation Overbridge & School End Overbridge | IDR 221.2 | HS2-000020NLY | 2024-03-11 | 10 - Complete | 2024-03-13
[8 empty] | HS2-00002CW0X - Footpath CHW 18 and green Road Closure Drainage System | IDR 221.2 - Footpath CHW/18 Accommodation Overbridge & School End Overbridge | IDR 221.2 | HS2-00002CW0X | 2024-03-14 | 10 - Complete | 2024-03-18
[8 empty] | HS2-000020NLZ - Footpath CHW 18 Accommodation Access Realignment | IDR 221.2 - Footpath CHW/18 Accommodation Overbridge & School End Overbridge | IDR 221.2 | HS2-000020NLZ | 2024-04-03 | 10 - Complete | 2024-04-05
[8 empty] | HS2-00002VXUC - Maintenance Access Road to GSMR (off School End Road Realignment) and Compound | IDR 221.2 - Footpath CHW/18 Accommodation Overbridge & School End Overbridge | IDR 221.2 | HS2-00002VXUC | 2024-04-16 | 10 - Complete | 2024-04-23
[8 empty] | HS2-00002BJUR - School End Road Realignment | IDR 221.2 - Footpath CHW/18 Accommodation Overbridge & School End Overbridge | IDR 221.2 | HS2-00002BJUR | 2024-04-16 | 10 - Complete | 2024-04-19
[8 empty] | HS2-000001322 - School End Overbridge | IDR 221.2 - Footpath CHW/18 Accommodation Overbridge & School End Overbridge | IDR 221.2 | HS2-000001322 | 2024-01-24 | 10 - Complete | 2024-05-01
[8 empty] | HS2-000020NM2 - Maintenance Access Road to Pond (Off School End Road-South) | IDR 221.2 - Footpath CHW/18 Accommodation Overbridge & School End Overbridge | IDR 221.2 | HS2-000020NM2 | 2024-04-16 | 10 - Complete | 2024-04-23
[8 empty] | HS2-000020NM3 - Maintenance Access Road to Pond (Off School End Road-North) | IDR 221.2 - Footpath CHW/18 Accommodation Overbridge & School End Overbridge | IDR 221.2 | HS2-000020NM3 | 2024-04-16 | 10 - Complete | 2024-04-19
[8 empty] | HS2-000020NLR - Flood Compensation Area-084B | IDR 221.1 - Barton Hartshorn Embankment, Chetwode cutting and Chetwode embankment | IDR 221.1 | HS2-000020NLR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVHR - Chetwode Embankment Landscape Earthworks | IDR 221.1 - Barton Hartshorn Embankment, Chetwode cutting and Chetwode embankment | IDR 221.1 | HS2-00002BVHR | #N/A | #N/A | #N/A
[8 empty] | HS2-000001053 - Chetwode Embankment | IDR 221.1 - Barton Hartshorn Embankment, Chetwode cutting and Chetwode embankment | IDR 221.1 | HS2-000001053 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTAP - C2.T.79 Catchment | IDR 221.1 - Barton Hartshorn Embankment, Chetwode cutting and Chetwode embankment | IDR 221.1 | HS2-00002CTAP | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTAQ - C2.T.80 Catchment | IDR 221.1 - Barton Hartshorn Embankment, Chetwode cutting and Chetwode embankment | IDR 221.1 | HS2-00002CTAQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVHS - C2.L.84 Catchment | IDR 221.1 - Barton Hartshorn Embankment, Chetwode cutting and Chetwode embankment | IDR 221.1 | HS2-00002BVHS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVHU - Chetwode Cutting Landscape Earthworks | IDR 221.1 - Barton Hartshorn Embankment, Chetwode cutting and Chetwode embankment | IDR 221.1 | HS2-00002BVHU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTAZ - C2.T.90 Catchment | IDR 221.1 - Barton Hartshorn Embankment, Chetwode cutting and Chetwode embankment | IDR 221.1 | HS2-00002CTAZ | #N/A | #N/A | #N/A
[8 empty] | HS2-000001054 - Chetwode Cutting | IDR 221.1 - Barton Hartshorn Embankment, Chetwode cutting and Chetwode embankment | IDR 221.1 | HS2-000001054 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020864 - Chetwode ATS | IDR 221.1 - Barton Hartshorn Embankment, Chetwode cutting and Chetwode embankment | IDR 221.1 | HS2-000020864 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001055 - Barton Hartshorn Embankment | IDR 221.1 - Barton Hartshorn Embankment, Chetwode cutting and Chetwode embankment | IDR 221.1 | HS2-000001055 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTB8 - C2.T.91 Catchment | IDR 221.1 - Barton Hartshorn Embankment, Chetwode cutting and Chetwode embankment | IDR 221.1 | HS2-00002CTB8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTBN - C2.T.92 Catchment | IDR 221.1 - Barton Hartshorn Embankment, Chetwode cutting and Chetwode embankment | IDR 221.1 | HS2-00002CTBN | #N/A | #N/A | #N/A
[8 empty] | HS2-000001431 - Godington West Culvert | IDR 221 - Godington West & Barton Hartshorn culverts | IDR 221 | HS2-000001431 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002UVZ1 - Padbury Brook Diversion 00 | IDR 221 - Godington West & Barton Hartshorn culverts | IDR 221 | HS2-00002UVZ1 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001432 - Barton Hartshorn Culvert | IDR 221 - Godington West & Barton Hartshorn culverts | IDR 221 | HS2-000001432 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NNHV - Barton Hartshorn Culvert Watercourse Diversion | IDR 221 - Godington West & Barton Hartshorn culverts | IDR 221 | HS2-00002NNHV | 2024-01-29 | 10 - Complete | 2024-03-07
[8 empty] | HS2-000020NLQ - Footpath PBI 9 Diversion | IDR 220.5 - Bridleway CHW/24 & Padbury Brook Watercourse Diversion 01 | IDR 220.5 | HS2-000020NLQ | 2024-06-07 | 10 - Complete | 2024-06-18
[8 empty] | HS2-00002CTAL - Padbury Brook Diversion 01 | IDR 220.5 - Bridleway CHW/24 & Padbury Brook Watercourse Diversion 01 | IDR 220.5 | HS2-00002CTAL | 2024-03-28 | 10 - Complete | 2024-04-04
[8 empty] | HS2-00002BJUL - Maintenance Access Road MAP (Bridleway CHW 24 Upgrade) | IDR 220.5 - Bridleway CHW/24 & Padbury Brook Watercourse Diversion 01 | IDR 220.5 | HS2-00002BJUL | 2024-06-07 | 10 - Complete | 2024-06-14
[8 empty] | HS2-00002J4YG - Bridleway CHW 24 Link | IDR 220.5 - Bridleway CHW/24 & Padbury Brook Watercourse Diversion 01 | IDR 220.5 | HS2-00002J4YG | 2024-06-07 | 10 - Complete | 2024-06-14
[8 empty] | HS2-00002BJUM - Maintenance Access Road to Pond and MAP (Footpath 225 4 Upgrade) | IDR 220.5 - Bridleway CHW/24 & Padbury Brook Watercourse Diversion 01 | IDR 220.5 | HS2-00002BJUM | 2024-06-07 | 10 - Complete | 2024-06-14
[8 empty] | HS2-00002N7W9 - Chetwode Embankment-Ancillary Culvert 084-AC2 | IDR 220.5 - Bridleway CHW/24 & Padbury Brook Watercourse Diversion 01 | IDR 220.5 | HS2-00002N7W9 | 2024-06-04 | 10 - Complete | 2024-06-14
[8 empty] | HS2-00002Y0RV - Bridleway CHW 24 Overbridge | IDR 220.5 - Bridleway CHW/24 & Padbury Brook Watercourse Diversion 01 | IDR 220.5 | HS2-00002Y0RV | 2024-06-12 | 10 - Complete | 2024-06-26
[8 empty] | HS2-00002Y4JH - 084-AC2 Watercourse Diversion | IDR 220.5 - Bridleway CHW/24 & Padbury Brook Watercourse Diversion 01 | IDR 220.5 | HS2-00002Y4JH | 2024-05-01 | 10 - Complete | 2024-05-10
[8 empty] | HS2-000020NL8 - Maintenance Access Road to Pond and MAP (Off Byway PBI 5A) | IDR 220.3 - Restricted Byway PBI/5A Accommodation Overbridge | IDR 220.3 | HS2-000020NL8 | 2024-02-15 | 10 - Complete | 2024-02-21
[8 empty] | HS2-00002EK7A - Cowley Embankment UTX | IDR 220.3 - Restricted Byway PBI/5A Accommodation Overbridge | IDR 220.3 | HS2-00002EK7A | 2024-11-22 | 10 - Complete | 2024-12-10
[8 empty] | HS2-00002J4YN - Footpath PBI 6 Diversion | IDR 220.3 - Restricted Byway PBI/5A Accommodation Overbridge | IDR 220.3 | HS2-00002J4YN | 2024-02-19 | 10 - Complete | 2024-02-23
[8 empty] | HS2-00002VXUA - Maintenance Access Road to Storage Area (off Byway PBI 5A Realignment) | IDR 220.3 - Restricted Byway PBI/5A Accommodation Overbridge | IDR 220.3 | HS2-00002VXUA | 2024-02-19 | 10 - Complete | 2024-02-23
[8 empty] | HS2-000020RMA - Footpath PBI 5 Link | IDR 220.3 - Restricted Byway PBI/5A Accommodation Overbridge | IDR 220.3 | HS2-000020RMA | 2024-02-19 | 10 - Complete | 2024-02-22
[8 empty] | HS2-00002BVH8 - C2.L.73 Catchment | IDR 220.3 - Restricted Byway PBI/5A Accommodation Overbridge | IDR 220.3 | HS2-00002BVH8 | 2024-01-31 | 10 - Complete | 2024-02-02
[8 empty] | HS2-00002VXUB - Maintenance Access Road to GSMR (off Byway PBI 5A Realignment) and Compound | IDR 220.3 - Restricted Byway PBI/5A Accommodation Overbridge | IDR 220.3 | HS2-00002VXUB | 2024-02-19 | 10 - Complete | 2024-02-25
[8 empty] | HS2-00002BJUJ - Byway PBI 5A Realignment | IDR 220.3 - Restricted Byway PBI/5A Accommodation Overbridge | IDR 220.3 | HS2-00002BJUJ | 2024-02-19 | 10 - Complete | 2024-02-22
[8 empty] | HS2-00002CW0Q - Byway PBI 5A Drainage System | IDR 220.3 - Restricted Byway PBI/5A Accommodation Overbridge | IDR 220.3 | HS2-00002CW0Q | 2024-01-31 | 10 - Complete | 2024-02-02
[8 empty] | HS2-00002N7W7 - Twyford Cutting-Ancillary Culvert 083-AC1 | IDR 220.3 - Restricted Byway PBI/5A Accommodation Overbridge | IDR 220.3 | HS2-00002N7W7 | 2024-03-11 | 10 - Complete | 2024-03-18
[8 empty] | HS2-000001320 - Restricted Byway PBI 5A Accommodation Overbridge | IDR 220.3 - Restricted Byway PBI/5A Accommodation Overbridge | IDR 220.3 | HS2-000001320 | 2024-03-26 | 10 - Complete | 2024-04-12
[8 empty] | HS2-000032217 - Twyford Cutting-Ancillary Culvert 083-AC2 | IDR 220.3 - Restricted Byway PBI/5A Accommodation Overbridge | IDR 220.3 | HS2-000032217 | 2024-03-11 | 10 - Complete | 2024-03-18
[8 empty] | HS2-000001430 - Godington East Culvert | IDR 220.2 - Godington East culvert | IDR 220.2 | HS2-000001430 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTAD - Padbury Brook Diversion 02 | IDR 220.2 - Godington East culvert | IDR 220.2 | HS2-00002CTAD | #N/A | #N/A | #N/A
[8 empty] | HS2-000031LLF - Padbury Brook Diversion 02b | IDR 220.2 - Godington East culvert | IDR 220.2 | HS2-000031LLF | #N/A | #N/A | #N/A
[8 empty] | HS2-000001048 - Twyford Cutting | IDR 220.1 - Twyford Cutting, Godington embankments | IDR 220.1 | HS2-000001048 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVHA - Twyford Cutting Landscape Earthworks | IDR 220.1 - Twyford Cutting, Godington embankments | IDR 220.1 | HS2-00002BVHA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTA2 - C2.L.74 Catchment | IDR 220.1 - Twyford Cutting, Godington embankments | IDR 220.1 | HS2-00002CTA2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTA3 - C2.T.71 Catchment | IDR 220.1 - Twyford Cutting, Godington embankments | IDR 220.1 | HS2-00002CTA3 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVHB - C2.L.77 Catchment | IDR 220.1 - Twyford Cutting, Godington embankments | IDR 220.1 | HS2-00002BVHB | #N/A | #N/A | #N/A
[8 empty] | HS2-000001049 - Godington East Embankment | IDR 220.1 - Twyford Cutting, Godington embankments | IDR 220.1 | HS2-000001049 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTA7 - C2.T.75 Catchment | IDR 220.1 - Twyford Cutting, Godington embankments | IDR 220.1 | HS2-00002CTA7 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001051 - Godington West Embankment | IDR 220.1 - Twyford Cutting, Godington embankments | IDR 220.1 | HS2-000001051 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTAE - C2.T.76 Catchment | IDR 220.1 - Twyford Cutting, Godington embankments | IDR 220.1 | HS2-00002CTAE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKY7 - Flood Compensation Area-084A | IDR 220.1 - Twyford Cutting, Godington embankments | IDR 220.1 | HS2-00002EKY7 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001050 - Godington East Viaduct | IDR 220 - Godington viaducts | IDR 220 | HS2-000001050 | 2024-11-08 | 50 - HOLD | 0
[8 empty] | HS2-000001052 - Godington West Viaduct | IDR 220 - Godington viaducts | IDR 220 | HS2-000001052 | 2024-11-08 | 50 - HOLD | 0
[8 empty] | HS2-00002CT9Y - Cowley Embankment Boundary Perimeter Fence Line | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-00002CT9Y | 2024-03-21 | 10 - Complete | 2024-03-27
[8 empty] | HS2-00002CTA0 - Cowley Embankment Security Fence Line | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-00002CTA0 | 2024-03-21 | 10 - Complete | 2024-03-27
[8 empty] | HS2-00002CTA4 - Twyford Cutting Boundary Perimeter Fence Line | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-00002CTA4 | 2024-04-02 | 10 - Complete | 2024-04-03
[8 empty] | HS2-00002CTA6 - Twyford Cutting Security Fence Line | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-00002CTA6 | 2024-04-04 | 10 - Complete | 2024-04-08
[8 empty] | HS2-00002YCW4 - 82-SL1 Cowley Embankment Vehicular Bridge | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-00002YCW4 | 2024-04-12 | 10 - Complete | 2024-05-03
[8 empty] | HS2-000031EEZ - 82-SL2 Cowley Embankment Pedestrian Bridge | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000031EEZ | 2024-05-28 | 10 - Complete | 2024-05-29
[8 empty] | HS2-000031EF0 - 83-SL1 Twyford Cutting Pedestrian Slab | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000031EF0 | 2024-04-12 | 10 - Complete | 2024-05-08
[8 empty] | HS2-000033GP3 - Clean Water Pipe CFA_13_08 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033GP3 | 2024-04-05 | 10 - Complete | 2024-04-15
[8 empty] | HS2-000033XXN - Cowley Embankment Planting Plot 1 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XXN | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XXP - Cowley Embankment Planting Plot 2 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XXP | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XXQ - Cowley Embankment Planting Plot 3 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XXQ | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XXR - Cowley Embankment Planting Plot 4 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XXR | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XXS - Cowley Embankment Planting Plot 5 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XXS | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XXT - Cowley Embankment Planting Plot 6 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XXT | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XXU - Twyford Cutting Planting Plot 1 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XXU | 2024-04-15 | 10 - Complete | 2024-04-23
[8 empty] | HS2-000033XXV - Twyford Cutting Planting Plot 2 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XXV | 2024-04-15 | 10 - Complete | 2024-04-23
[8 empty] | HS2-000033XXW - Twyford Cutting Planting Plot 3 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XXW | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XXX - Twyford Cutting Planting Plot 4 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XXX | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XXY - Twyford Cutting Planting Plot 5 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XXY | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XXZ - Twyford Cutting Planting Plot 6 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XXZ | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XY0 - Twyford Cutting Planting Plot 7 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XY0 | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XY1 - Twyford Cutting Planting Plot 8 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XY1 | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XY2 - Twyford Viaduct Planting Plot 1 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XY2 | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XY3 - Twyford Viaduct Planting Plot 2 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XY3 | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XY4 - Twyford Viaduct Planting Plot 3 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XY4 | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000033XY5 - Twyford Viaduct Planting Plot 4 | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000033XY5 | 2024-04-15 | 10 - Complete | 2024-04-24
[8 empty] | HS2-000037YLE - 83-SL4 Twyford Cutting Vehicular Slab | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000037YLE | 2024-04-12 | 10 - Complete | 2024-04-30
[8 empty] | HS2-000037YLG - 83-SL5 Twyford Cutting Vehicular Slab | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-000037YLG | 2024-04-12 | 10 - Complete | 2024-04-30
[8 empty] | HS2-0000386U9 - 82-SL1 Cowley Embankment Vehicular Bridge-Earthworks Transition | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-0000386U9 | 2024-03-14 | 10 - Complete | 2024-03-27
[8 empty] | HS2-0000386UA - 82-SL2 Cowley Embankment Pedestrian Bridge-Earthworks Transition | IDR 219.3 - Cowley Embankment, Twyford Viaduct and Twyford Cutting - Ancillary Civils Fencing and Landscape Planting | IDR 219.3 | HS2-0000386UA | 2024-04-17 | 10 - Complete | 2024-04-22
[8 empty] | HS2-00002CT9V - Padbury Brook Diversion 03 | IDR 219.2 - Padbury Brook Watercourse Diversion 03 | IDR 219.2 | HS2-00002CT9V | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT9Z - Cowley Embankment Noise Barrier Line | IDR 219.1 - Noise Barriers | IDR 219.1 | HS2-00002CT9Z | 2025-02-24 | 10 - Complete | 2025-02-25
[8 empty] | HS2-00002CTB2 - Chetwode Cutting Noise Barrier Line | IDR 219.1 - Noise Barriers | IDR 219.1 | HS2-00002CTB2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTBA - Barton Hartshorn Embankment Noise Barrier Line | IDR 219.1 - Noise Barriers | IDR 219.1 | HS2-00002CTBA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTBT - Barton to Mixbury Cutting Noise Barrier Line | IDR 219.1 - Noise Barriers | IDR 219.1 | HS2-00002CTBT | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTCN - Turweston Cutting Noise Barrier Line | IDR 219.1 - Noise Barriers | IDR 219.1 | HS2-00002CTCN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTDS - Turweston Embankment Noise Barrier Line | IDR 219.1 - Noise Barriers | IDR 219.1 | HS2-00002CTDS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTDZ - Helmdon Embankment Noise Barrier Line | IDR 219.1 - Noise Barriers | IDR 219.1 | HS2-00002CTDZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTE5 - Brackley South Cutting Noise Barrier Line | IDR 219.1 - Noise Barriers | IDR 219.1 | HS2-00002CTE5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTEA - Brackley Embankment Noise Barrier Line | IDR 219.1 - Noise Barriers | IDR 219.1 | HS2-00002CTEA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CQQL - Brackley North Cutting Noise Barrier Line | IDR 219.1 - Noise Barriers | IDR 219.1 | HS2-00002CQQL | #N/A | #N/A | #N/A
[8 empty] | HS2-000001046 - Twyford Viaduct | IDR 219 - Cowley Embankment & Twyford viaduct | IDR 219 | HS2-000001046 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001047 - Cowley Embankment | IDR 219 - Cowley Embankment & Twyford viaduct | IDR 219 | HS2-000001047 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DV8P - Cowley Embankment Landscape Earthworks | IDR 219 - Cowley Embankment & Twyford viaduct | IDR 219 | HS2-00002DV8P | #N/A | #N/A | #N/A
[8 empty] | HS2-000020C1K - Flood Compensation Area-082 | IDR 219 - Cowley Embankment & Twyford viaduct | IDR 219 | HS2-000020C1K | #N/A | #N/A | #N/A
[8 empty] | HS2-00002KRAL - IMD West Culvert Watercourse Diversion | IDR 218.02-1 - IMD East and West Watercourse Diversion and UTXs | IDR 218.02-1 | HS2-00002KRAL | 2023-11-21 | 10 - Complete | 2023-11-27
[8 empty] | HS2-00002KRAM - IMD East Culvert Watercourse Diversion | IDR 218.02-1 - IMD East and West Watercourse Diversion and UTXs | IDR 218.02-1 | HS2-00002KRAM | 2023-11-21 | 10 - Complete | 2023-11-21
[8 empty] | HS2-00002NSXP - OXD Security Fence Line | IDR 218.02-1 - IMD East and West Watercourse Diversion and UTXs | IDR 218.02-1 | HS2-00002NSXP | 2024-04-17 | 99 - Cancelled | 0
[8 empty] | HS2-00002NSXQ - OXD Boundary Perimeter Fence Line | IDR 218.02-1 - IMD East and West Watercourse Diversion and UTXs | IDR 218.02-1 | HS2-00002NSXQ | 2024-08-19 | 10 - Complete | 2024-08-29
[8 empty] | HS2-00002VK47 - EWR culvert watercourse diversion MAS crossing | IDR 218.02-1 - IMD East and West Watercourse Diversion and UTXs | IDR 218.02-1 | HS2-00002VK47 | 2024-09-10 | 10 - Complete | 2024-09-20
[8 empty] | HS2-00002TMWU - Calvert IMD Crossover UTX No 1 | IDR 218.02-1 - IMD East and West Watercourse Diversion and UTXs | IDR 218.02-1 | HS2-00002TMWU | 2023-11-20 | 10 - Complete | 2023-11-22
[8 empty] | HS2-00002TMWV - Calvert IMD Crossover UTX No 2 | IDR 218.02-1 - IMD East and West Watercourse Diversion and UTXs | IDR 218.02-1 | HS2-00002TMWV | 2023-11-20 | 10 - Complete | 2023-11-23
[8 empty] | HS2-00002TMWW - Calvert IMD Crossover UTX No 3 | IDR 218.02-1 - IMD East and West Watercourse Diversion and UTXs | IDR 218.02-1 | HS2-00002TMWW | 2023-11-20 | 10 - Complete | 2023-11-23
[8 empty] | HS2-0000307ZQ - IMD East Watercourse Pedestrian Crossing 1 | IDR 218.02-1 - IMD East and West Watercourse Diversion and UTXs | IDR 218.02-1 | HS2-0000307ZQ | 2024-10-14 | 10 - Complete | 2024-10-17
[8 empty] | HS2-0000307ZR - IMD East Watercourse Pedestrian Crossing 2 | IDR 218.02-1 - IMD East and West Watercourse Diversion and UTXs | IDR 218.02-1 | HS2-0000307ZR | 2024-10-17 | 10 - Complete | 2024-10-24
[8 empty] | HS2-00002CTD9 - Calvert Infrastructure Maintenance Depot Boundary Perimeter Fence Line | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00002CTD9 | 2024-04-24 | 10 - Complete | 2024-05-03
[8 empty] | HS2-00002CTDA - Calvert Infrastructure Maintenance Depot Security Fence Line | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00002CTDA | 2024-04-24 | 10 - Complete | 2024-05-03
[8 empty] | HS2-00002D2S2 - Calvert IMD Landscape Earthworks | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00002D2S2 | 2024-03-28 | 10 - Complete | 2024-04-02
[8 empty] | HS2-00002TPZ5 - Portway Culvert and Pond access | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00002TPZ5 | 2024-06-10 | 10 - Complete | 2024-06-12
[8 empty] | HS2-000020NKT - Maintenance Access Road to Pond 02 (Off IMD access) | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-000020NKT | 2024-04-17 | 10 - Complete | 2024-05-09
[8 empty] | HS2-00002VK41 - Portway Culvert Access Road Bridge MAS | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00002VK41 | 2024-05-07 | 10 - Complete | 2024-05-10
[8 empty] | HS2-00002CT9N - Twyford Embankment Boundary Perimeter Fence Line | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00002CT9N | 2024-04-24 | 10 - Complete | 2024-05-03
[8 empty] | HS2-00002CT9P - Twyford Embankment Noise Barrier Line | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00002CT9P | 2024-05-07 | 10 - Complete | 2024-05-13
[8 empty] | HS2-00002CT9Q - Twyford Embankment Security Fence Line | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00002CT9Q | 2024-04-24 | 10 - Complete | 2024-05-03
[8 empty] | HS2-00002YXB3 - Twyford Viaduct Access Point Staircase Upmain Ch82275 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00002YXB3 | 2024-04-09 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002YXB4 - Twyford Viaduct Access Point Staircase Downmain Ch82280 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00002YXB4 | 2024-04-09 | 10 - Complete | 2024-04-30
[8 empty] | HS2-000031248 - TWY 16 Footpath Crossing | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-000031248 | 2024-07-05 | 10 - Complete | 2024-07-11
[8 empty] | HS2-00003124A - Footpath SCL 6 Diversion | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003124A | 2024-06-10 | 10 - Complete | 2024-06-12
[8 empty] | HS2-00003124B - Maintenance Access to Calvert IMD Sewage Pumping Station | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003124B | 2024-04-17 | 10 - Complete | 2024-05-09
[8 empty] | HS2-00003124C - Calvert IMD Access Road | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003124C | 2024-05-14 | 10 - Complete | 2024-05-15
[8 empty] | HS2-00003124G - Portway Culvert Chamber Access Downmain 80955 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003124G | 2024-04-09 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00003124H - Twyford East Culvert Chamber Access Downmain 81712 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003124H | 2024-04-09 | 10 - Complete | 2024-05-01
[8 empty] | HS2-00003124J - West Street Overbridge Downmain 81140 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003124J | 2024-04-09 | 10 - Complete | 2024-05-01
[8 empty] | HS2-00003124K - West Street Overbridge Upmain 81230 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003124K | 2024-04-09 | 10 - Complete | 2024-05-01
[8 empty] | HS2-000035UXF - IMD Access Road Drainage system | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-000035UXF | 2025-02-06 | 10 - Complete | 2025-03-27
[8 empty] | HS2-00003B92J - Twyford Embankment planting Plot 1 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92J | 2024-06-04 | 10 - Complete | 2024-06-05
[8 empty] | HS2-00003B92K - Twyford Embankment planting Plot 2 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92K | 2024-05-24 | 10 - Complete | 2024-06-03
[8 empty] | HS2-00003B92L - Twyford Embankment planting Plot 3 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92L | 2024-06-04 | 10 - Complete | 2024-06-05
[8 empty] | HS2-00003B92M - Twyford Embankment planting Plot 4 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92M | 2024-05-24 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00003B92N - Twyford Embankment planting Plot 5 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92N | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B92Q - Twyford Embankment planting Plot 7 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92Q | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B92R - Twyford Embankment planting Plot 8 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92R | 2024-05-24 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00003B92S - Twyford Embankment planting Plot 9 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92S | 2024-05-24 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00003B92T - Twyford Embankment planting Plot 10 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92T | 2024-05-24 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00003B92U - Twyford Embankment planting Plot 11 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92U | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B92V - Twyford Embankment planting Plot 12 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92V | 2024-05-24 | 10 - Complete | 2024-06-03
[8 empty] | HS2-00003B92W - Twyford Embankment planting Plot 13 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92W | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B92X - Twyford Embankment planting Plot 14 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92X | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B92Z - Calvert Infrastructure Maintenance Depot Plot 1 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B92Z | 2024-05-24 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00003B930 - Calvert Infrastructure Maintenance Depot Plot 2 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B930 | 2024-05-24 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00003B931 - Calvert Infrastructure Maintenance Depot Plot 3 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B931 | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B932 - Calvert Infrastructure Maintenance Depot Plot 4 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B932 | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B933 - Calvert Infrastructure Maintenance Depot Plot 5 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B933 | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B934 - Calvert Infrastructure Maintenance Depot Plot 6 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B934 | 2024-05-24 | 10 - Complete | 2024-05-29
[8 empty] | HS2-00003B935 - Calvert Cutting Planting Plot 1 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B935 | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B936 - Calvert Cutting Planting Plot 2 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B936 | 2024-05-24 | 10 - Complete | 2024-06-03
[8 empty] | HS2-00003B937 - Calvert Cutting Planting Plot 3 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B937 | 2024-05-24 | 10 - Complete | 2024-06-03
[8 empty] | HS2-00003B938 - Calvert Cutting Planting Plot 4 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B938 | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B939 - Calvert Cutting Planting Plot 5 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B939 | 2024-05-24 | 10 - Complete | 2024-06-03
[8 empty] | HS2-00003B93A - Calvert Cutting Planting Plot 6 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B93A | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B93B - Calvert Cutting Planting Plot 7 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B93B | 2024-05-24 | 10 - Complete | 2024-06-03
[8 empty] | HS2-00003B93C - Calvert Cutting Planting Plot 8 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B93C | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B93D - Calvert Cutting Planting Plot 9 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B93D | 2024-05-24 | 10 - Complete | 2024-06-03
[8 empty] | HS2-00003B93F - Calvert Cutting Planting Plot 11 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B93F | 2024-05-24 | 10 - Complete | 2024-06-03
[8 empty] | HS2-00003B93G - Calvert Cutting Planting Plot 12 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B93G | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B93H - Calvert Cutting Planting Plot 13 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B93H | 2024-05-24 | 10 - Complete | 2024-06-03
[8 empty] | HS2-00003B93J - Calvert Cutting Planting Plot 14 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B93J | 2024-06-04 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00003B93K - Calvert Cutting Planting Plot 15 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B93K | 2024-05-24 | 10 - Complete | 2024-06-03
[8 empty] | HS2-00003B93L - Calvert Cutting Planting Plot 16 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B93L | 2024-05-24 | 10 - Complete | 2024-06-03
[8 empty] | HS2-00003B93M - Calvert Cutting Planting Plot 17 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003B93M | 2025-03-27 | 10 - Complete | 2025-04-01
[8 empty] | HS2-00003CCJX - Maintenance Access Road to Pond 1003 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003CCJX | 2024-04-17 | 10 - Complete | 2024-05-09
[8 empty] | HS2-00003CCJY - Maintenance Access Road to Pond 0992 | IDR 218.02 - Infrastructure Maintenance Depot Landscaping | IDR 218.02 | HS2-00003CCJY | 2024-04-24 | 10 - Complete | 2024-05-07
[8 empty] | HS2-00002NNHP - Twyford East Culvert Watercourse Diversion | IDR 218.01-2 - Twyford Watercourse | IDR 218.01-2 | HS2-00002NNHP | 2024-01-30 | 10 - Complete | 2024-02-07
[8 empty] | HS2-00002CT9X - C2.T.67 Catchment | IDR 218.01-2 - Twyford Watercourse | IDR 218.01-2 | HS2-00002CT9X | 2024-01-30 | 10 - Complete | 2024-02-02
[8 empty] | HS2-00002Y0EY - Catchment C2.T.66.3 | IDR 218.01-2 - Twyford Watercourse | IDR 218.01-2 | HS2-00002Y0EY | 2024-01-18 | 10 - Complete | 2024-01-19
[8 empty] | HS2-000033GN1 - OXD 27 Access Track Crossing 1 | IDR 218.01-2 - Twyford Watercourse | IDR 218.01-2 | HS2-000033GN1 | 2024-02-05 | 10 - Complete | 2024-02-08
[8 empty] | HS2-00002LLZ5 - Maintenance access track (off IMD) | IDR 218.01 - Twyford Embankment | IDR 218.01 | HS2-00002LLZ5 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001045 - Twyford Embankment | IDR 218.01 - Twyford Embankment | IDR 218.01 | HS2-000001045 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001373 - Portway Culvert | IDR 218.01 - Twyford Embankment | IDR 218.01 | HS2-000001373 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NL0 - Footpath TWY 18 Diversion | IDR 218.01 - Twyford Embankment | IDR 218.01 | HS2-000020NL0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVH1 - Twyford Embankment Landscape Earthworks | IDR 218.01 - Twyford Embankment | IDR 218.01 | HS2-00002BVH1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT9L - C2.L.69 Catchment | IDR 218.01 - Twyford Embankment | IDR 218.01 | HS2-00002CT9L | #N/A | #N/A | #N/A
[8 empty] | HS2-000001428 - Twyford East Culvert | IDR 218.01 - Twyford Embankment | IDR 218.01 | HS2-000001428 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NL7 - Footpaths TWY 16 and 17 Realignment | IDR 218.01 - Twyford Embankment | IDR 218.01 | HS2-000020NL7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVH5 - C2.L.70 Catchment | IDR 218.01 - Twyford Embankment | IDR 218.01 | HS2-00002BVH5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003JYGY - IMD Temporary Railhead | IDR 217.05 - IMD Temporary Railhead | IDR 217.05 | HS2-00003JYGY | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NK6 - Footpath SCL 7 8 and 9 Diversion | IDR 217.04 - Footpath SCL/8 Overbridge | IDR 217.04 | HS2-000020NK6 | 2024-01-24 | 10 - Complete | 2024-02-19
[8 empty] | HS2-000001313 - Footpath SCL 8 Overbridge | IDR 217.04 - Footpath SCL/8 Overbridge | IDR 217.04 | HS2-000001313 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NNHR - Balancing Pond Access off IMD (near Addison Road) | IDR 217.04 - Footpath SCL/8 Overbridge | IDR 217.04 | HS2-00002NNHR | #N/A | #N/A | #N/A
[8 empty] | HS2-000031NVA - Footpath SCL 8 Overbridge Drainage system | IDR 217.04 - Footpath SCL/8 Overbridge | IDR 217.04 | HS2-000031NVA | 2024-12-20 | 10 - Complete | 2025-01-10
[8 empty] | HS2-00002CT8S - Addison Road Drainage System | IDR 217.03 - Addison Road Overbridge - Full | IDR 217.03 | HS2-00002CT8S | 2025-05-01 | 10 - Complete | 2025-05-02
[8 empty] | HS2-00002CT8Z - WPD Electrical Substation Access Road | IDR 217.03 - Addison Road Overbridge - Full | IDR 217.03 | HS2-00002CT8Z | #N/A | #N/A | #N/A
[8 empty] | HS2-000001314 - Addison Road Overbridge | IDR 217.03 - Addison Road Overbridge - Full | IDR 217.03 | HS2-000001314 | 2024-11-20 | 50 - HOLD | 0
[8 empty] | HS2-000020NKE - Addison Road Realignment | IDR 217.03 - Addison Road Overbridge - Full | IDR 217.03 | HS2-000020NKE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7XY - Addison Road Land Drainage-Ancillary Culvert No. 1 | IDR 217.03 - Addison Road Overbridge - Full | IDR 217.03 | HS2-00002N7XY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7XA - Addison Road Highway Drainage-Ancillary Culvert No. 5 | IDR 217.03 - Addison Road Overbridge - Full | IDR 217.03 | HS2-00002N7XA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7C - C2.OXD.T.514 Catchment | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002CT7C | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT88 - IMD West Culvert (IMD South Culvert) | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002CT88 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT89 - IMD East Culvert (IMD North Culvert) | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002CT89 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT8N - C2.OXD.L.512 Catchment | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002CT8N | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT8P - C2.OXD.L.513 Catchment | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002CT8P | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT96 - Charndon Lodge Network Rail Access Point | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002CT96 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT97 - Claydon Junction Network Rail Access Point | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002CT97 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CX38 - C2.OXD.T.522 Catchment | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002CX38 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJU4 - MCJ4 Earthwork | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002BJU4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TTGZ - MCJ4 Mitigation Earthworks | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002TTGZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002HQ9G - Shepherds Furze Network Rail Culvert | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002HQ9G | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJUB - OXD Earthworks | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002BJUB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTD2 - Calvert Infrastructure Maintenance Depot Earthwork Platform | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002CTD2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTD5 - C2.IMD.T.518 Catchment | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002CTD5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTD6 - C2.IMD.T.519 Catchment | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002CTD6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NKP9 - OXD 27 Claydon Junction Highway Access | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002NKP9 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002KRAK - EWR culvert Watercourse Diversion | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002KRAK | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NL3 - East West Rail Culvert | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-000020NL3 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7B - C2.OXD.T.510 Catchment | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002CT7B | #N/A | #N/A | #N/A
[8 empty] | HS2-00002HUS0 - C2.OXD.T.511 Catchment | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002HUS0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WJB3 - Claydon Junction Access Point Pedestrian Crossing | IDR 217.02 - OXD and MCJ Earthworks Final | IDR 217.02 | HS2-00002WJB3 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001316 - East West Rail Overbridge | IDR 217.01 - EWR bridge and Charndon Lodge | IDR 217.01 | HS2-000001316 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001372 - Charndon Lodge Underbridge | IDR 217.01 - EWR bridge and Charndon Lodge | IDR 217.01 | HS2-000001372 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT8U - West Street Drainage System | IDR 216.01-2 - Ancillary works, Accesses and Water Course Diversion | IDR 216.01-2 | HS2-00002CT8U | 2025-03-26 | 10 - Complete | 2025-03-27
[8 empty] | HS2-00002CW0B - Sailing Club Access | IDR 216.01-2 - Ancillary works, Accesses and Water Course Diversion | IDR 216.01-2 | HS2-00002CW0B | 2024-10-22 | 10 - Complete | 2024-11-12
[8 empty] | HS2-00002NNHQ - Portway Culvert Watercourse Diversion | IDR 216.01-2 - Ancillary works, Accesses and Water Course Diversion | IDR 216.01-2 | HS2-00002NNHQ | 2024-11-20 | 10 - Complete | 2024-12-13
[8 empty] | HS2-00002N7XW - Perry Hill Road Watercourse-Ancillary Culvert | IDR 216.01-2 - Ancillary works, Accesses and Water Course Diversion | IDR 216.01-2 | HS2-00002N7XW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VK46 - Twyford East Ditch Crossing MAS | IDR 216.01-2 - Ancillary works, Accesses and Water Course Diversion | IDR 216.01-2 | HS2-00002VK46 | 2024-11-12 | 10 - Complete | 0
[8 empty] | HS2-00002YYN3 - TWY 4 footpath diversion | IDR 216.01-2 - Ancillary works, Accesses and Water Course Diversion | IDR 216.01-2 | HS2-00002YYN3 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002ZJQJ - TWY 4 Footpath Crossing | IDR 216.01-2 - Ancillary works, Accesses and Water Course Diversion | IDR 216.01-2 | HS2-00002ZJQJ | 2024-11-12 | 10 - Complete | 0
[8 empty] | HS2-00002ZLSY - Perry Hill Culvert Watercourse Diversion | IDR 216.01-2 - Ancillary works, Accesses and Water Course Diversion | IDR 216.01-2 | HS2-00002ZLSY | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D82Q - Sailing Club Access Drainage Culvert | IDR 216.01-2 - Ancillary works, Accesses and Water Course Diversion | IDR 216.01-2 | HS2-00003D82Q | 2023-12-07 | 10 - Complete | 2023-12-09
[8 empty] | HS2-00003D82R - Sailing Club Access Security Gate | IDR 216.01-2 - Ancillary works, Accesses and Water Course Diversion | IDR 216.01-2 | HS2-00003D82R | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT8T - Perry Hill Road Drainage System | IDR 216.01 - Perry Hill and West Street | IDR 216.01 | HS2-00002CT8T | 2025-05-30 | 10 - Complete | 2025-06-04
[8 empty] | HS2-00002CT90 - Charndon Lodge Pumping Station and Pond Access Road | IDR 216.01 - Perry Hill and West Street | IDR 216.01 | HS2-00002CT90 | 2024-12-02 | 10 - Complete | 2025-01-09
[8 empty] | HS2-00002CT9B - Charndon Lodge Pumping Station | IDR 216.01 - Perry Hill and West Street | IDR 216.01 | HS2-00002CT9B | 2023-10-31 | 10 - Complete | 2024-12-13
[8 empty] | HS2-000020NKK - Portway Farm ATS Access Road off Perry Hill Road | IDR 216.01 - Perry Hill and West Street | IDR 216.01 | HS2-000020NKK | 2024-12-02 | 10 - Complete | 2025-01-08
[8 empty] | HS2-00002NKPA - OXD 28 Charndon Lodge Highway Access | IDR 216.01 - Perry Hill and West Street | IDR 216.01 | HS2-00002NKPA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJUE - Maintenance Access Road to Pond 01 (Off IMD access) | IDR 216.01 - Perry Hill and West Street | IDR 216.01 | HS2-00002BJUE | 2024-12-02 | 10 - Complete | 2025-01-09
[8 empty] | HS2-00002BJUF - IMD Access off Perry Hill | IDR 216.01 - Perry Hill and West Street | IDR 216.01 | HS2-00002BJUF | 2025-06-27 | 10 - Complete | 2025-07-02
[8 empty] | HS2-000001317 - Perry Hill Overbridge | IDR 216.01 - Perry Hill and West Street | IDR 216.01 | HS2-000001317 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJUG - Perry Hill Road Realignment | IDR 216.01 - Perry Hill and West Street | IDR 216.01 | HS2-00002BJUG | 2025-06-27 | 10 - Complete | 2025-07-02
[8 empty] | HS2-000020RM2 - West Street Realignment | IDR 216.01 - Perry Hill and West Street | IDR 216.01 | HS2-000020RM2 | 2025-04-16 | 10 - Complete | 2025-04-25
[8 empty] | HS2-000001318 - West Street Overbridge | IDR 216.01 - Perry Hill and West Street | IDR 216.01 | HS2-000001318 | 2024-08-28 | 10 - Complete | 2024-10-14
[8 empty] | HS2-000020NL1 - Field Access track (Off West Street) | IDR 216.01 - Perry Hill and West Street | IDR 216.01 | HS2-000020NL1 | 2025-04-16 | 10 - Complete | 2025-04-25
[8 empty] | HS2-000020356 - Sewage Works Accomodation and Pond Access Road | IDR 216.01 - Perry Hill and West Street | IDR 216.01 | HS2-000020356 | 2025-04-16 | 10 - Complete | 2025-04-25
[8 empty] | HS2-00002CT92 - Calvert Cutting Boundary Perimeter Fence Line | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00002CT92 | 2024-10-18 | 10 - Complete | 2024-10-28
[8 empty] | HS2-00002CT93 - Calvert Cutting Noise Barrier Line | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00002CT93 | 2024-08-28 | 10 - Complete | 2024-09-10
[8 empty] | HS2-00002CT94 - Calvert Cutting Security Fence Line | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00002CT94 | 2024-10-18 | 10 - Complete | 2024-10-24
[8 empty] | HS2-00002TTH1 - Calvert Cutting Ancillary Accesses | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00002TTH1 | 2024-10-31 | 10 - Complete | 2024-11-06
[8 empty] | HS2-00002TUPK - Sheephouse Wood Bat Mitigation Structure Telecoms | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00002TUPK | 2024-06-25 | 10 - Complete | 2024-08-16
[8 empty] | HS2-00002VK40 - Shepherds Furze Watercourse Crossing MAS | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00002VK40 | 2024-09-02 | 10 - Complete | 2024-09-26
[8 empty] | HS2-00002Y8VS - School Hill Green Overbridge Maintenance Access Point Staircase Downmain Ch79020 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00002Y8VS | 2024-08-12 | 10 - Complete | 2024-08-27
[8 empty] | HS2-00002Y8VT - East West Rail Overbridge Maintenance Access Point Staircase Downmain Ch80070 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00002Y8VT | 2024-08-12 | 10 - Complete | 2024-08-23
[8 empty] | HS2-00002Y8VU - Perry Hill Overbridge Maintenance Access Point Downmain Ch80800 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00002Y8VU | 2024-08-15 | 10 - Complete | 2024-08-27
[8 empty] | HS2-00002YPE6 - Calvert Green Overbridge Maintenance Access Point Staircase Downmain Ch78400 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00002YPE6 | 2024-08-12 | 10 - Complete | 2024-08-27
[8 empty] | HS2-00002YPEG - GSMR Point 37 Access Road Crossing No. 1 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00002YPEG | 2024-09-02 | 10 - Complete | 2024-09-26
[8 empty] | HS2-00002YPEH - GSMR Point 37 Access Road Crossing No. 2 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00002YPEH | 2024-09-02 | 10 - Complete | 2024-09-26
[8 empty] | HS2-00002YXB6 - Shepherds Furze Culvert Emergency Access Point Staircase Downmain Ch79340 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00002YXB6 | 2024-08-12 | 10 - Complete | 2024-08-23
[8 empty] | HS2-00003124D - Calvert Footpath and Cycleway-north section | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003124D | 2024-11-05 | 10 - Complete | 2024-11-11
[8 empty] | HS2-00003D9CD - Perry Hill OB access staircase Upmain Ch80800 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003D9CD | 2024-08-15 | 10 - Complete | 2024-08-27
[8 empty] | HS2-00003D9CF - IMD West Culvert Access staircase Downmain Ch99674 OXD Line | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003D9CF | 2024-08-12 | 10 - Complete | 2024-08-23
[8 empty] | HS2-00003FV0H - IMD East Access Road | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003FV0H | 2024-11-05 | 10 - Complete | 2024-11-11
[8 empty] | HS2-00003GEER - C2.L.65 Catchment | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003GEER | 2024-10-28 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003GL96 - Calvert IMD.22 UTX No. 3 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003GL96 | 2024-08-12 | 10 - Complete | 2024-08-23
[8 empty] | HS2-00003GL97 - Calvert IMD.22 UTX No. 4 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003GL97 | 2024-08-12 | 10 - Complete | 2024-08-28
[8 empty] | HS2-00003GNA3 - OXD Ancillary Accesses | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003GNA3 | 2024-10-31 | 10 - Complete | 2024-11-06
[8 empty] | HS2-00003GNA4 - IMD Ancillary Accesses | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003GNA4 | 2024-10-31 | 10 - Complete | 2024-11-07
[8 empty] | HS2-00003GNA5 - Calvert Green Overbridge NR Access point Downmain Ch21800 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003GNA5 | 2024-09-26 | 10 - Complete | 2024-09-27
[8 empty] | HS2-00003GSJY - Shepherds Furze Watercourse Crossing 2 MAS | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003GSJY | 2024-09-02 | 10 - Complete | 2024-09-26
[8 empty] | HS2-00003GSJZ - C2.OXD.T.522 Catchment MAS Crossing | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003GSJZ | 2024-09-02 | 10 - Complete | 2024-09-26
[8 empty] | HS2-00003H07F - Pond Access Road Staircase Downmain 81175 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H07F | 2024-08-15 | 10 - Complete | 2024-08-28
[8 empty] | HS2-00003H6P1 - Calvert Cutting planting Plot 18 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6P1 | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003H6P2 - Calvert Cutting planting Plot 19 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6P2 | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003H6P3 - Calvert Cutting planting Plot 20 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6P3 | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003H6P4 - Calvert Cutting planting Plot 21 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6P4 | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003H6P5 - Calvert Cutting planting Plot 22 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6P5 | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003H6P6 - Calvert Cutting planting Plot 23 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6P6 | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003H6P7 - Calvert Cutting planting Plot 24 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6P7 | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003H6P8 - Calvert Cutting planting Plot 25 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6P8 | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003H6P9 - Calvert Cutting planting Plot 26 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6P9 | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003H6PA - Calvert Cutting planting Plot 27 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6PA | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003H6PB - Calvert Cutting planting Plot 28 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6PB | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003H6PC - Calvert Cutting planting Plot 29 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6PC | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003H6PD - Calvert Cutting planting Plot 30 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6PD | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003H6PE - Calvert Cutting planting Plot 31 | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003H6PE | 2024-11-12 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003JAYB - Addison Road to School Hill Public Footpath | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003JAYB | 2024-11-08 | 10 - Complete | 2024-11-15
[8 empty] | HS2-00003KUM8 - Calvert Bridleway - North Section | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003KUM8 | 2024-11-07 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003KUM9 - Addison Road to School Hill Footpath Drainage | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003KUM9 | 2024-11-05 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003LGKQ - P-RAI-0786 Ditch Crossing MAS | IDR 215.03 - Calvert Cutting Noise Barrier + Planting, Fencing and Ancillary Civils | IDR 215.03 | HS2-00003LGKQ | 2024-11-01 | 10 - Complete | 2024-11-11
[8 empty] | HS2-00002CT8R - School Hill Road Drainage System | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002CT8R | 2024-01-23 | 10 - Complete | 2024-01-24
[8 empty] | HS2-00002CT8V - C2.T.65 Catchment | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002CT8V | 2024-08-22 | 10 - Complete | 2024-09-05
[8 empty] | HS2-00002CT8Y - Maintenance Access Road to Pond (Off School Hill Road West) | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002CT8Y | 2025-01-29 | 10 - Complete | 2025-02-12
[8 empty] | HS2-00002CX35 - C2.T.66.1 Catchment | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002CX35 | 2024-08-21 | 10 - Complete | 2024-09-05
[8 empty] | HS2-00002CX36 - C2.T.66.2 Catchment | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002CX36 | 2025-01-10 | 10 - Complete | 2025-01-17
[8 empty] | HS2-00002EK76 - Calvert IMD connection UTX No1 | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002EK76 | 2023-12-15 | 10 - Complete | 2023-12-18
[8 empty] | HS2-00002NNHZ - School Hill Network Rail Compound Access | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002NNHZ | 2023-12-20 | 10 - Complete | 2024-01-09
[8 empty] | HS2-000020NK2 - Maintenance Access Road to Pond (Off School Hill Road East) | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-000020NK2 | 2025-01-29 | 10 - Complete | 2025-02-10
[8 empty] | HS2-00002BJU3 - School Hill Road Realignment | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002BJU3 | 2025-01-29 | 10 - Complete | 2025-02-10
[8 empty] | HS2-00002TMWR - Portway Farm ATS UTX No 1 | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002TMWR | 2023-12-15 | 10 - Complete | 2023-12-18
[8 empty] | HS2-00002TMWS - Portway Farm ATS UTX No 2 | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002TMWS | 2023-12-15 | 10 - Complete | 2023-12-18
[8 empty] | HS2-00002Y8VF - GSMR Compount Point 37 UTX No. 1 | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002Y8VF | 2023-12-15 | 10 - Complete | 2023-12-20
[8 empty] | HS2-00002Y8VG - GSMR Compount Point 37 UTX No. 2 | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002Y8VG | 2023-12-15 | 10 - Complete | 2023-12-18
[8 empty] | HS2-00002Y8VH - GSMR Compount Point 37 UTX No. 3 | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002Y8VH | 2023-12-15 | 10 - Complete | 2023-12-18
[8 empty] | HS2-00002Y8VJ - GSMR Compount Point 37 UTX No. 4 | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002Y8VJ | 2023-12-15 | 10 - Complete | 2023-12-18
[8 empty] | HS2-00002Y8VM - Calvert IMD.22 UTX No. 1 | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002Y8VM | 2023-12-15 | 10 - Complete | 2023-12-18
[8 empty] | HS2-00002Y8VN - Calvert IMD.22 UTX No. 2 | IDR 215.02-2 - School Hill UTX | IDR 215.02-2 | HS2-00002Y8VN | 2023-12-15 | 10 - Complete | 2023-12-18
[8 empty] | HS2-000001311 - Calvert Green Overbridge | IDR 215.02 - School Hill Green & Calvert Green Overbridges | IDR 215.02 | HS2-000001311 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002T427 - Calvert Green Bridge Embankment | IDR 215.02 - School Hill Green & Calvert Green Overbridges | IDR 215.02 | HS2-00002T427 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001312 - School Hill Green Overbridge | IDR 215.02 - School Hill Green & Calvert Green Overbridges | IDR 215.02 | HS2-000001312 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT80 - C2.FCC.L.507 Catchment | IDR 215.01-2 - Calvert Cutting & School Hill Culvert | IDR 215.01-2 | HS2-00002CT80 | 2024-09-19 | 10 - Complete | 2024-10-08
[8 empty] | HS2-00002BVGV - Calvert Cutting Landscape Earthworks | IDR 215.01-2 - Calvert Cutting & School Hill Culvert | IDR 215.01-2 | HS2-00002BVGV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT8B - School Hill Culvert | IDR 215.01-2 - Calvert Cutting & School Hill Culvert | IDR 215.01-2 | HS2-00002CT8B | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT8Q - C2.L.63 Catchment | IDR 215.01-2 - Calvert Cutting & School Hill Culvert | IDR 215.01-2 | HS2-00002CT8Q | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT8W - C2.MCJ.T.508 Catchment | IDR 215.01-2 - Calvert Cutting & School Hill Culvert | IDR 215.01-2 | HS2-00002CT8W | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CX37 - C2.MCJ.T.523 Catchment | IDR 215.01-2 - Calvert Cutting & School Hill Culvert | IDR 215.01-2 | HS2-00002CX37 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001044 - Calvert Cutting | IDR 215.01-2 - Calvert Cutting & School Hill Culvert | IDR 215.01-2 | HS2-000001044 | 2024-11-21 | 10 - Complete | 2025-01-07
[8 empty] | HS2-00002GRJN - EWR Access Road | IDR 215.01-2 - Calvert Cutting & School Hill Culvert | IDR 215.01-2 | HS2-00002GRJN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NNHN - Shepherds Furze Culvert Watercourse Diversion | IDR 215.01-2 - Calvert Cutting & School Hill Culvert | IDR 215.01-2 | HS2-00002NNHN | #N/A | #N/A | #N/A
[8 empty] | HS2-000001425 - Shepherds Furze Culvert | IDR 215.01 - Shepherds Furze & Calvert Cutting Retaining Wall | IDR 215.01 | HS2-000001425 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJUC - Calvert Retaining Wall West | IDR 215.01 - Shepherds Furze & Calvert Cutting Retaining Wall | IDR 215.01 | HS2-00002BJUC | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CW17 - Greatmoor Road (Part of CAG 2) Drainage System | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00002CW17 | 2025-05-22 | 10 - Complete | 2025-05-28
[8 empty] | HS2-00002BJTZ - Calvert Footpath and Cycle route (south off HS2) | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00002BJTZ | 2024-06-12 | 10 - Complete | 2024-07-30
[8 empty] | HS2-00002DRXL - Footpath CAG 2 Realignment | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00002DRXL | 2025-04-29 | 10 - Complete | 2025-05-29
[8 empty] | HS2-000020NJ5 - Footpath CAG 2 Diversion | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-000020NJ5 | 2024-06-12 | 10 - Complete | 2024-07-29
[8 empty] | HS2-00002EK75 - SWBMS North UTX | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00002EK75 | 2025-10-01 | #N/A | #N/A
[8 empty] | HS2-00002NSXL - SWBMS Emergency Access Track East | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00002NSXL | 2024-06-19 | 10 - Complete | 2024-07-29
[8 empty] | HS2-00002NSXM - SWBMS Emergency Access Track West | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00002NSXM | 2024-06-19 | 10 - Complete | 2024-07-29
[8 empty] | HS2-00002CT8K - C2.L.64 Catchment | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00002CT8K | 2024-06-12 | 10 - Complete | 2024-07-09
[8 empty] | HS2-00002EKXN - Sheephouse Wood-Footpath SCL 13 Green Overbridge Ecological Mitigation Site | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00002EKXN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002XQ2Q - SWBMS Boundary Perimeter Fence Line | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00002XQ2Q | 2025-05-01 | 10 - Complete | 0
[8 empty] | HS2-00002XQ2R - SWBMS Security Fence Line | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00002XQ2R | 2025-05-02 | 10 - Complete | 2025-05-02
[8 empty] | HS2-000031B3U - SWBMS Emergency Intervention stairs | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-000031B3U | 2024-07-11 | 10 - Complete | 2024-07-23
[8 empty] | HS2-00003CPYK - SWBMS Landscape Planting | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00003CPYK | 2025-06-06 | 10 - Complete | 2025-06-17
[8 empty] | HS2-00003CPYM - SWBMS HS2 NR Fence | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00003CPYM | 2024-08-08 | 10 - Complete | 2024-08-28
[8 empty] | HS2-00003CPYN - SCL 13 Green Overbridge Restraint System | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00003CPYN | 2024-07-11 | 10 - Complete | 2024-07-25
[8 empty] | HS2-00003CPYP - SWBMS South UTX | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00003CPYP | 2025-09-26 | 10 - Complete | 0
[8 empty] | HS2-00003CPYQ - SWBMS Cable Routing | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00003CPYQ | 2025-09-26 | 30 - Sent back to team | 0
[8 empty] | HS2-00003CPYS - SWBMS Ancillary Civils | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00003CPYS | 2024-06-19 | 10 - Complete | 2024-08-22
[8 empty] | HS2-00003E24K - SCL 13 Landscape Planting | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00003E24K | 2025-06-06 | 10 - Complete | 2025-06-17
[8 empty] | HS2-00003HWH8 - Sheephouse Wood Bat Mitigation Structure Telecoms Section 2 | IDR 214.10 - SWBMS Supplementary Design | IDR 214.10 | HS2-00003HWH8 | 2024-07-18 | 10 - Complete | 2024-08-02
[8 empty] | HS2-00002TTH6 - FCC PRoW Bridleway Diversion | IDR 214.09 - FCC PROW Realignment | IDR 214.09 | HS2-00002TTH6 | 2024-04-15 | 10 - Complete | 2024-04-17
[8 empty] | HS2-00003G3SK - FCC PRoW Bridleway Diversion Drainage | IDR 214.09 - FCC PROW Realignment | IDR 214.09 | HS2-00003G3SK | 2024-04-15 | 10 - Complete | 2024-04-17
[8 empty] | HS2-00002BVGS - FCC Operational Sidings | IDR 214.08 - Greatmoor (FCC) Sidings (structure & drainage) | IDR 214.08 | HS2-00002BVGS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7K - C2.L.62 Catchment | IDR 214.08 - Greatmoor (FCC) Sidings (structure & drainage) | IDR 214.08 | HS2-00002CT7K | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7Z - C2.FCC.T.506 Catchment | IDR 214.08 - Greatmoor (FCC) Sidings (structure & drainage) | IDR 214.08 | HS2-00002CT7Z | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TZT8 - FCC Sidings Foul Water Drainage | IDR 214.08 - Greatmoor (FCC) Sidings (structure & drainage) | IDR 214.08 | HS2-00002TZT8 | 2025-01-27 | 10 - Complete | 2025-01-30
[8 empty] | HS2-00002DV8T - FCC Substation | IDR 214.08 - Greatmoor (FCC) Sidings (structure & drainage) | IDR 214.08 | HS2-00002DV8T | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NSXR - FCC Sidings Environmental Barrier | IDR 214.08 - Greatmoor (FCC) Sidings (structure & drainage) | IDR 214.08 | HS2-00002NSXR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NSXS - FCC Sidings Security Fence Line | IDR 214.08 - Greatmoor (FCC) Sidings (structure & drainage) | IDR 214.08 | HS2-00002NSXS | #N/A | #N/A | #N/A
[8 empty] | HS2-00003E24N - Greatmoor Operational Sidings Track | IDR 214.08 - Greatmoor (FCC) Sidings (structure & drainage) | IDR 214.08 | HS2-00003E24N | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7M - Woodlands Cutting Boundary Perimeter Fence Line | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002CT7M | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7P - Woodlands Cutting Security Fence Line | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002CT7P | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT81 - Maintenance Access Road to Pond (Connecting CAG 2 and GUN 28) | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002CT81 | 2025-02-17 | 10 - Complete | 2025-02-19
[8 empty] | HS2-00002CT83 - Grendon Underwood Embankment Boundary Perimeter Fence Line | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002CT83 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT85 - Grendon Underwood Embankment Security Fence Line | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002CT85 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VK3Y - Greatmoor Slab Crossing | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002VK3Y | 2024-08-01 | 10 - Complete | 2024-08-21
[8 empty] | HS2-00002Y8V9 - Quainton ATFS UTX 1 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002Y8V9 | 2024-05-24 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00002Y8VA - Quainton ATFS UTX 2 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002Y8VA | 2024-05-24 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00002Y8VB - Quainton ATFS UTX 3 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002Y8VB | 2024-05-24 | 10 - Complete | 2024-06-12
[8 empty] | HS2-00002Y8VC - Quainton ATFS UTX 4 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002Y8VC | 2024-05-24 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00002Y8VD - Quainton ATFS UTX 5 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002Y8VD | 2024-05-24 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00002Y8VE - Quainton ATFS UTX 6 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002Y8VE | 2024-05-24 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00002YXB0 - Adams Accommodation Overbridge Access Point Staircase Downmain Ch74540 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002YXB0 | 2024-06-17 | 10 - Complete | 2024-07-04
[8 empty] | HS2-00002YXB5 - Edgcott Road NR Access Point Staircase Upmain Ch74200 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002YXB5 | 2024-07-03 | 10 - Complete | 2024-07-05
[8 empty] | HS2-00002Z3NJ - CAG 2 Realignment Pedestrian Crossing | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00002Z3NJ | 2024-08-01 | 10 - Complete | 2024-08-23
[8 empty] | HS2-0000300BT - GUN 28 Accommodation Green Overbridge Access Point Staircase Downmain | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-0000300BT | 2024-06-17 | 10 - Complete | 2024-07-09
[8 empty] | HS2-000031GXR - Grendon Underwood Ditch Crossing | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-000031GXR | 2024-08-01 | 10 - Complete | 2024-08-22
[8 empty] | HS2-00003B2G9 - Quainton ATFS UTX 7 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003B2G9 | 2024-05-24 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00003B2GA - Quainton ATFS UTX 8 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003B2GA | 2024-05-24 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00003B2GB - Quainton ATFS UTX 9 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003B2GB | 2024-05-24 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00003B2GC - Quainton ATFS UTX 10 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003B2GC | 2024-05-24 | 10 - Complete | 2024-05-30
[8 empty] | HS2-00003H07G - Greatmoor No.3 Headwall Access Stairs Downmain 76515 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H07G | 2024-06-17 | 10 - Complete | 2024-08-05
[8 empty] | HS2-00003H5JJ - River Ray Culvert Headwall Access Stairs Downmain 74535 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JJ | 2024-06-17 | 10 - Complete | 2024-07-05
[8 empty] | HS2-00003H5JK - Grendon Underwood Embankment Planting-Plot 1 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JK | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JL - Grendon Underwood Embankment Planting-Plot 2 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JL | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JM - Grendon Underwood Embankment Planting-Plot 3 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JM | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JN - Grendon Underwood Embankment Planting-Plot 4 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JN | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JP - Grendon Underwood Embankment Planting-Plot 5 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JP | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JQ - Grendon Underwood Embankment Planting-Plot 6 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JR - Grendon Underwood Embankment Planting-Plot 7 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JR | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JS - Grendon Underwood Embankment Planting-Plot 8 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JS | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JT - Grendon Underwood Embankment Planting-Plot 9 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JT | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JU - Grendon Underwood Embankment Planting-Plot 10 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JU | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JV - Grendon Underwood Embankment Planting-Plot 11 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JV | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JW - Grendon Underwood Embankment Planting-Plot 12 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JW | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JX - Woodlands Cutting Planting-Plot 1 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JX | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JY - Woodlands Cutting Planting-Plot 2 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JY | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5JZ - Woodlands Cutting Planting-Plot 3 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5JZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H5K0 - Woodlands Cutting Planting-Plot 4 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003H5K0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003HWH3 - QUA-36 Accommodation Green Overbridge Access Stairs Downmain ch75325 | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003HWH3 | 2024-06-17 | 10 - Complete | 2024-07-05
[8 empty] | HS2-00003JYH0 - Woodlands Cutting Ancillary Earthworks | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003JYH0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003JYH1 - Grendon Underwood Embankment Ancillary Earthworks | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003JYH1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003L0M2 - Woodlands Farm Ecological Mitigation Site | IDR 214.07 - Grendon and Woodlands, Fencing, Ancillary Civils and Planting, Fencing package 4 | IDR 214.07 | HS2-00003L0M2 | 2024-12-02 | 10 - Complete | 2025-01-08
[8 empty] | HS2-000001309 - Sheephouse Wood Bat Mitigation Structure | IDR 214.06 - Sheephouse Wood Bat Mitigation Structure - Full | IDR 214.06 | HS2-000001309 | 2025-04-08 | 10 - Complete | 2025-04-09
[8 empty] | HS2-00002KRAJ - Greatmoor No. 4 Culvert Watercourse Diversion | IDR 214.06 - Sheephouse Wood Bat Mitigation Structure - Full | IDR 214.06 | HS2-00002KRAJ | #N/A | #N/A | #N/A
[8 empty] | HS2-000001370 - Muxwell Brook Culvert | IDR 214.06 - Sheephouse Wood Bat Mitigation Structure - Full | IDR 214.06 | HS2-000001370 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001310 - Footpath SCL 13 Green Overbridge | IDR 214.06 - Sheephouse Wood Bat Mitigation Structure - Full | IDR 214.06 | HS2-000001310 | 2024-10-25 | 10 - Complete | 2024-11-06
[8 empty] | HS2-00002BJU2 - Footpath SCL 13 Realignment | IDR 214.06 - Sheephouse Wood Bat Mitigation Structure - Full | IDR 214.06 | HS2-00002BJU2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003LH5M - Mega Ditch Retaining Wall Access Steps | IDR 214.06 - Sheephouse Wood Bat Mitigation Structure - Full | IDR 214.06 | HS2-00003LH5M | #N/A | #N/A | #N/A
[8 empty] | HS2-00003LH5N - Muxwell Brook Crossing Slab | IDR 214.06 - Sheephouse Wood Bat Mitigation Structure - Full | IDR 214.06 | HS2-00003LH5N | #N/A | #N/A | #N/A
[8 empty] | HS2-00002HCE4 - Mega Ditch Culvert | IDR 214.05 - Sheephouse Wood Bat Mitigation Structure - Earthworks & Culverts | IDR 214.05 | HS2-00002HCE4 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001369 - Footpath CAG 2 Underbridge | IDR 214.05 - Sheephouse Wood Bat Mitigation Structure - Earthworks & Culverts | IDR 214.05 | HS2-000001369 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001371 - Greatmoor No. 4 Culvert | IDR 214.05 - Sheephouse Wood Bat Mitigation Structure - Earthworks & Culverts | IDR 214.05 | HS2-000001371 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001424 - Sheephouse Wood North Culvert | IDR 214.05 - Sheephouse Wood Bat Mitigation Structure - Earthworks & Culverts | IDR 214.05 | HS2-000001424 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002XPHN - SWBMS Earthworks | IDR 214.05 - Sheephouse Wood Bat Mitigation Structure - Earthworks & Culverts | IDR 214.05 | HS2-00002XPHN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VJVU - Footpath QUA 35 diversion | IDR 214.04 - Bridleway QUA/36 Accommodation Green Overbridge | IDR 214.04 | HS2-00002VJVU | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NHM - Maintenance Access Road to Pond (Off Bridleway QUA 36) | IDR 214.04 - Bridleway QUA/36 Accommodation Green Overbridge | IDR 214.04 | HS2-000020NHM | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NHP - Access Road to MAP (Off Greatmoor Road) | IDR 214.04 - Bridleway QUA/36 Accommodation Green Overbridge | IDR 214.04 | HS2-000020NHP | #N/A | #N/A | #N/A
[8 empty] | HS2-000001307 - Bridleway QUA 36 Accommodation Green Overbridge | IDR 214.04 - Bridleway QUA/36 Accommodation Green Overbridge | IDR 214.04 | HS2-000001307 | 2023-11-10 | 99 - Cancelled | 0
[8 empty] | HS2-00002BJTV - Bridleway QUA 36 Diversion | IDR 214.04 - Bridleway QUA/36 Accommodation Green Overbridge | IDR 214.04 | HS2-00002BJTV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CW0P - Bridleway QUA 36 Drainage System | IDR 214.04 - Bridleway QUA/36 Accommodation Green Overbridge | IDR 214.04 | HS2-00002CW0P | #N/A | #N/A | #N/A
[8 empty] | HS2-000001422 - Greatmoor No. 2 Culvert | IDR 214.03-3 - Greatmoor No. 2, No. 3 Culverts | IDR 214.03-3 | HS2-000001422 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001423 - Greatmoor No. 3 Culvert | IDR 214.03-3 - Greatmoor No. 2, No. 3 Culverts | IDR 214.03-3 | HS2-000001423 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001418 - Woodlands Culvert | IDR 214.03-2 - Adams Accommodation, River Ray, Woodlands Culvert | IDR 214.03-2 | HS2-000001418 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NHH - River Ray Culvert | IDR 214.03-2 - Adams Accommodation, River Ray, Woodlands Culvert | IDR 214.03-2 | HS2-000020NHH | #N/A | #N/A | #N/A
[8 empty] | HS2-000001419 - Adams Accommodation Underbridge | IDR 214.03-2 - Adams Accommodation, River Ray, Woodlands Culvert | IDR 214.03-2 | HS2-000001419 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7W - C2.MCJ.T.503 Catchment | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002CT7W | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7G - C2.L.57 Catchment | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002CT7G | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7H - C2.L.59 Catchment | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002CT7H | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVGL - Woodlands Cutting Landscape Earthworks | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002BVGL | #N/A | #N/A | #N/A
[8 empty] | HS2-000001042 - Woodlands Cutting | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-000001042 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NH2 - Field Access Road (Off Edgcott Road) | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-000020NH2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QH94 - Edgcott Road Network Rail Access Point (Woodlands Cutting) | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002QH94 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVGJ - C2.L.55 Catchment | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002BVGJ | #N/A | #N/A | #N/A
[8 empty] | HS2-000001043 - Grendon Underwood Embankment | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-000001043 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002KRAP - Grendon Underwood Embankment Landscape Earthworks | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002KRAP | 2024-10-21 | 10 - Complete | 2024-10-30
[8 empty] | HS2-00002CT7J - C2.L.61 Catchment | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002CT7J | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT86 - Greatmoor Sidings Network Rail Access Point | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002CT86 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002KRAN - River Ray Culvert Watercourse Diversion | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002KRAN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJTS - Adams Accommodation Access Realignment | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002BJTS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CW0D - Adams Accommodation Drainage System | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002CW0D | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7T - C2.T.56 Catchment | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002CT7T | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7U - C2.T.58 Catchment | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002CT7U | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7X - C2.MCJ.T.504 Catchment | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002CT7X | #N/A | #N/A | #N/A
[8 empty] | HS2-000001420 - Finemere Wood Culvert Extension | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-000001420 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVGR - Finemere Wood Pond Retaining Wall | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002BVGR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7V - C2.T.60 Catchment | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002CT7V | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7Y - C2.MCJ.T.505 Catchment | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002CT7Y | #N/A | #N/A | #N/A
[8 empty] | HS2-00002U7K0 - Greatmoor Operational Sidings Earthworks | IDR 214.03-1 - Grendon Underwood Embankment (76.650-74.950) | IDR 214.03-1 | HS2-00002U7K0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7L - Access Road to National Grid Sub-Station | IDR 214.02-2 - Edgcott Road Highway Realignment | IDR 214.02-2 | HS2-00002CT7L | #N/A | #N/A | #N/A
[8 empty] | HS2-00002KRAQ - Access road to Quainton ATFS | IDR 214.02-2 - Edgcott Road Highway Realignment | IDR 214.02-2 | HS2-00002KRAQ | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NH1 - Edgcott Road Realignment | IDR 214.02-2 - Edgcott Road Highway Realignment | IDR 214.02-2 | HS2-000020NH1 | 2024-07-30 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00002CW0V - Edgcott road Drainage System | IDR 214.02-2 - Edgcott Road Highway Realignment | IDR 214.02-2 | HS2-00002CW0V | #N/A | #N/A | #N/A
[8 empty] | HS2-000001306 - Edgcott Road Overbridge | IDR 214.02-1 - Edgcott Road Overbridge | IDR 214.02-1 | HS2-000001306 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT82 - Access Road to Greatmoor Sidings NR Access point | IDR 214.01-2 - Bridleway GUN 28/ Accommodation Green Overbridge - approach earthworks & Greatmoor Rd HW diversion | IDR 214.01-2 | HS2-00002CT82 | 2024-11-13 | 50 - HOLD | 0
[8 empty] | HS2-00002BJTU - Greatmoor Road Realignment | IDR 214.01-2 - Bridleway GUN 28/ Accommodation Green Overbridge - approach earthworks & Greatmoor Rd HW diversion | IDR 214.01-2 | HS2-00002BJTU | 2024-11-13 | 50 - HOLD | 0
[8 empty] | HS2-00002NHZB - Greatmoor Road Megaditch Ancillary Culvert | IDR 214.01-2 - Bridleway GUN 28/ Accommodation Green Overbridge - approach earthworks & Greatmoor Rd HW diversion | IDR 214.01-2 | HS2-00002NHZB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJTX - Bridleway GUN 28 Diversion | IDR 214.01-2 - Bridleway GUN 28/ Accommodation Green Overbridge - approach earthworks & Greatmoor Rd HW diversion | IDR 214.01-2 | HS2-00002BJTX | 2024-11-13 | 50 - HOLD | 0
[8 empty] | HS2-00002CW0M - Bridleway GUN 28 Drainage System | IDR 214.01-2 - Bridleway GUN 28/ Accommodation Green Overbridge - approach earthworks & Greatmoor Rd HW diversion | IDR 214.01-2 | HS2-00002CW0M | 2024-12-05 | 10 - Complete | 2024-01-14
[8 empty] | HS2-00002BJTY - FCC Sidings Access Road | IDR 214.01-2 - Bridleway GUN 28/ Accommodation Green Overbridge - approach earthworks & Greatmoor Rd HW diversion | IDR 214.01-2 | HS2-00002BJTY | 2024-11-13 | 30 - Sent back to team | 0
[8 empty] | HS2-00002NKP6 - FCC Access Road Retaining Wall | IDR 214.01-2 - Bridleway GUN 28/ Accommodation Green Overbridge - approach earthworks & Greatmoor Rd HW diversion | IDR 214.01-2 | HS2-00002NKP6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002Z6BC - Bridleway GUN 28 Diversion-Slab Crossing | IDR 214.01-2 - Bridleway GUN 28/ Accommodation Green Overbridge - approach earthworks & Greatmoor Rd HW diversion | IDR 214.01-2 | HS2-00002Z6BC | #N/A | #N/A | #N/A
[8 empty] | HS2-000001308 - Bridleway GUN 28 Accommodation Green Overbridge | IDR 214.01-1 - Bridleway GUN 28/ Accommodation Green Overbridge - bridge | IDR 214.01-1 | HS2-000001308 | 2024-12-19 | 30 - Sent back to team | 0
[8 empty] | HS2-00002CT7E - Doddershall Embankment Boundary Perimeter Fence Line | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00002CT7E | 2024-07-18 | 10 - Complete | 2024-08-08
[8 empty] | HS2-00002CT7F - Doddershall Embankment Security Fence Line | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00002CT7F | 2024-06-10 | 10 - Complete | 2024-06-18
[8 empty] | HS2-00002VK42 - P-RAI-0725 Ditch Crossing MAS | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00002VK42 | 2024-08-08 | 10 - Complete | 2024-08-23
[8 empty] | HS2-00002VK43 - P-RAI-0724 Ditch Crossing MAS | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00002VK43 | 2024-08-08 | 10 - Complete | 2024-08-21
[8 empty] | HS2-00002VK3Q - Doddershall Access Track Crossing 1 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00002VK3Q | 2024-08-14 | 10 - Complete | 2024-08-21
[8 empty] | HS2-00002VK3X - Doddershall No.4 Culvert Headwall MAS | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00002VK3X | 2024-08-08 | 10 - Complete | 2024-08-21
[8 empty] | HS2-00002VK4D - Doddershall Access Track Crossing 2 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00002VK4D | 2024-08-14 | 10 - Complete | 2024-08-21
[8 empty] | HS2-00002Y0EX - Doddershall Access Track Crossing 3 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00002Y0EX | 2024-08-14 | 10 - Complete | 2024-08-21
[8 empty] | HS2-00002YPE7 - Network Rail Doddershall Access Point Staircase Upmain Ch27020 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00002YPE7 | 2024-05-30 | 10 - Complete | 2024-05-31
[8 empty] | HS2-00002YPE8 - Network Rail Doddershall Access Point Staircase Upmain Ch26440 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00002YPE8 | 2024-05-30 | 10 - Complete | 2024-06-03
[8 empty] | HS2-00002YPE9 - Footpath QUA _26 Accommodation Underbridge Staircase Downmain Ch73620 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00002YPE9 | 2024-06-06 | 10 - Complete | 2024-06-18
[8 empty] | HS2-00002YPEA - Bridleway QUA 28A Accommodation Overbridge Maintenance Access Point Staircase Downmain Ch72938 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00002YPEA | 2024-05-30 | 10 - Complete | 2024-06-04
[8 empty] | HS2-00002Z6NL - Doddershall No. 1 Crossing | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00002Z6NL | 2024-08-08 | 10 - Complete | 2024-08-21
[8 empty] | HS2-000031247 - Footpath QUA 26 Diversion Crossing 2 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-000031247 | 2024-08-08 | 10 - Complete | 2024-08-21
[8 empty] | HS2-000031B3V - Box Culvert No.1 Access Staircase Downmain Ch72633 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-000031B3V | 2024-05-30 | 10 - Complete | 2024-06-04
[8 empty] | HS2-000031B3W - Box Culvert No.1 Access Staircase Downmain Ch72560 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-000031B3W | 2024-05-30 | 10 - Complete | 2024-06-04
[8 empty] | HS2-000031B3X - Box Culvert No.4 Access Staircase Downmain Ch73190 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-000031B3X | 2024-05-30 | 10 - Complete | 2024-06-04
[8 empty] | HS2-000031B3Y - Box Culvert No.4,6 and 7 Access Staircase Downmain Ch73300 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-000031B3Y | 2024-05-30 | 10 - Complete | 2024-06-04
[8 empty] | HS2-000031B3Z - Box Culvert No.6 Access Staircase Downmain Ch73410 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-000031B3Z | 2024-05-30 | 10 - Complete | 2024-06-04
[8 empty] | HS2-000031B40 - Box Culvert No.7 Access Staircase Downmain Ch73465 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-000031B40 | 2024-05-30 | 10 - Complete | 2024-06-04
[8 empty] | HS2-000031B41 - Woods Drop Inlet Culvert Access Staircase Downmain Ch73650 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-000031B41 | 2024-06-06 | 10 - Complete | 2024-06-18
[8 empty] | HS2-00003CPWX - Doddershall Embankment Planting Plot 1 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00003CPWX | 2024-07-30 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00003CPWY - Doddershall Embankment Planting Plot 2 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00003CPWY | 2024-07-30 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00003CPWZ - Doddershall Embankment Planting Plot 3 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00003CPWZ | 2024-07-30 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00003CPX1 - Doddershall Embankment Planting Plot 4 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00003CPX1 | 2024-07-30 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00003CPX2 - Doddershall Embankment Planting Plot 5 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00003CPX2 | 2024-07-30 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00003CPX3 - Doddershall Embankment Planting Plot 6 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00003CPX3 | 2024-07-30 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00003CPX4 - Doddershall Embankment Planting Plot 7 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00003CPX4 | 2024-07-30 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00003CPX6 - Doddershall Embankment Planting Plot 8 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00003CPX6 | 2024-07-30 | 10 - Complete | 2024-08-12
[8 empty] | HS2-00003CPX7 - Doddershall Embankment Planting Plot 9 | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00003CPX7 | 2024-07-30 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00003H6PF - P-RAI-0724 Ditch Pedestrian Crossing | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00003H6PF | 2024-08-08 | 10 - Complete | 2024-08-21
[8 empty] | HS2-00003HWH0 - Doddershall Embankment Ancillary Earthworks | IDR 213.08 - Doddershall Embankment - Fencing, Ancillary Civils and Planting | IDR 213.08 | HS2-00003HWH0 | 2024-08-21 | 10 - Complete | 2024-08-28
[8 empty] | HS2-00002D88S - Tetchwick Brook Watercourse Diversion | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00002D88S | 2024-05-14 | 10 - Complete | 2024-06-07
[8 empty] | HS2-00002CT72 - Quainton Cutting Boundary Perimeter Fence Line | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00002CT72 | 2024-11-11 | 10 - Complete | 2024-12-10
[8 empty] | HS2-00002CT73 - Quainton Cutting Security Fence Line | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00002CT73 | 2024-11-11 | 10 - Complete | 2024-12-10
[8 empty] | HS2-00002Z3NH - Station Road Maintenance Crossing 1 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00002Z3NH | 2024-11-12 | 10 - Complete | 2024-12-19
[8 empty] | HS2-0000307ZS - Station Road Cycle Track Crossing 2 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-0000307ZS | 2024-11-12 | 10 - Complete | 2024-12-19
[8 empty] | HS2-000032LLS - NR Flood Relief Culvert 1 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-000032LLS | 2024-08-28 | 10 - Complete | 2024-09-16
[8 empty] | HS2-000032LLT - NR Flood Relief Culvert 2 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-000032LLT | 2024-08-28 | 10 - Complete | 2024-09-19
[8 empty] | HS2-000032LLU - NR Flood Relief Culvert 3 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-000032LLU | 2024-08-28 | 10 - Complete | 2024-09-19
[8 empty] | HS2-000032LLV - NR Flood Relief Culvert 4 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-000032LLV | 2024-08-28 | 10 - Complete | 2024-09-19
[8 empty] | HS2-000032LLW - NR Watercourse Culvert | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-000032LLW | 2024-08-28 | 10 - Complete | 2024-09-19
[8 empty] | HS2-00003CCJZ - TB-Flood Compensation Area 071 A | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CCJZ | 2024-05-14 | 10 - Complete | 2024-05-16
[8 empty] | HS2-00003CCK0 - TB-Flood Compensation Area 071 B | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CCK0 | 2024-10-15 | 10 - Complete | 2024-10-18
[8 empty] | HS2-00003CCK1 - TB-Flood Compensation Area 071 C | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CCK1 | 2024-06-05 | 10 - Complete | 2024-06-07
[8 empty] | HS2-00003CPW1 - Quainton Cutting Planting Plot 1 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPW1 | 2024-11-21 | 10 - Complete | 0
[8 empty] | HS2-00003CPW2 - Quainton Cutting Planting Plot 2 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPW2 | 2024-11-21 | 10 - Complete | 0
[8 empty] | HS2-00003CPW4 - Quainton Cutting Planting Plot 3 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPW4 | 2024-11-21 | 10 - Complete | 0
[8 empty] | HS2-00003CPW5 - Quainton Cutting Planting Plot 4 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPW5 | 2024-11-21 | 10 - Complete | 0
[8 empty] | HS2-00003CPW6 - Quainton Cutting Planting Plot 5 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPW6 | 2024-11-21 | 10 - Complete | 2024-12-12
[8 empty] | HS2-00003CPW9 - Quainton Cutting Planting Plot 7 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPW9 | 2024-11-21 | 10 - Complete | 2024-12-12
[8 empty] | HS2-00003CPWA - Quainton Cutting Planting Plot 8 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPWA | 2024-11-21 | 10 - Complete | 2024-12-12
[8 empty] | HS2-00003CPWB - Quainton Cutting Planting Plot 9 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPWB | 2024-11-21 | 10 - Complete | 2024-12-12
[8 empty] | HS2-00003CPWD - Quainton Cutting Planting Plot 10 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPWD | #N/A | #N/A | #N/A
[8 empty] | HS2-00003CPWE - Quainton Cutting Planting Plot 11 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPWE | 2024-11-21 | 10 - Complete | 0
[8 empty] | HS2-00003CPWF - Quainton Cutting Planting Plot 12 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPWF | 2024-11-21 | 10 - Complete | 0
[8 empty] | HS2-00003CPWG - Quainton Cutting Planting Plot 13 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPWG | 2024-11-21 | 10 - Complete | 0
[8 empty] | HS2-00003CPWJ - Quainton Cutting Planting Plot 14 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPWJ | 2024-11-21 | 10 - Complete | 2024-12-12
[8 empty] | HS2-00003CPWL - Quainton Cutting Planting Plot 16 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPWL | 2024-11-21 | 10 - Complete | 2024-12-12
[8 empty] | HS2-00003CPWN - Quainton Cutting Planting Plot 17 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPWN | 2024-11-21 | 10 - Complete | 2024-12-12
[8 empty] | HS2-00003CPWQ - Quainton Cutting Planting Plot 19 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPWQ | 2024-11-21 | 10 - Complete | 2024-12-12
[8 empty] | HS2-00003CPWS - Quainton Cutting Planting Plot 20 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPWS | 2024-11-21 | 10 - Complete | 0
[8 empty] | HS2-00003CPWV - Quainton Cutting Planting Plot 23 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003CPWV | 2024-11-21 | 10 - Complete | 0
[8 empty] | HS2-00003HWH2 - Earthworks Transition for NR flood relief and watercourse culverts | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003HWH2 | 2024-05-08 | 10 - Complete | 2024-05-20
[8 empty] | HS2-00003JN81 - Tetchwick Brook Flood Compensation Areas Bund Culvert | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003JN81 | 2024-08-28 | 10 - Complete | 2024-09-12
[8 empty] | HS2-00003LH5P - Station Road Culvert No.5 and No.16 Headwall Access Stairs Upmain 71825 | IDR 213.07-1 - Quainton Cutting Ancillary Civils Fencing and Planting | IDR 213.07-1 | HS2-00003LH5P | 2024-10-18 | 10 - Complete | 2024-10-28
[8 empty] | HS2-00002KRAE - Doddershall No. 4 Culvert Watercourse Diversion | IDR 213.06 - Footpath QUA/26 Accommodation Underbridge | IDR 213.06 | HS2-00002KRAE | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NGG - Maintenance Access Road to Pond (Off Edgcott Road) | IDR 213.06 - Footpath QUA/26 Accommodation Underbridge | IDR 213.06 | HS2-000020NGG | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJTN - Footpath QUA 26 Diversion | IDR 213.06 - Footpath QUA/26 Accommodation Underbridge | IDR 213.06 | HS2-00002BJTN | 2024-10-15 | 10 - Complete | 2024-10-23
[8 empty] | HS2-00002CW0Z - Footpath QUA 26 Drainage System | IDR 213.06 - Footpath QUA/26 Accommodation Underbridge | IDR 213.06 | HS2-00002CW0Z | 2024-02-08 | 10 - Complete | 2024-02-14
[8 empty] | HS2-000001367 - Footpath QUA 26 Accommodation Underbridge | IDR 213.06 - Footpath QUA/26 Accommodation Underbridge | IDR 213.06 | HS2-000001367 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002KRAH - Woods Drop Inlet Culvert Watercourse Diversion | IDR 213.06 - Footpath QUA/26 Accommodation Underbridge | IDR 213.06 | HS2-00002KRAH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002Z6NM - Footpath QUA 26 Diversion Crossing | IDR 213.06 - Footpath QUA/26 Accommodation Underbridge | IDR 213.06 | HS2-00002Z6NM | 2024-07-30 | 10 - Complete | 2024-08-20
[8 empty] | HS2-000031F3L - QUA 26 to Edgcott Road Cycleway | IDR 213.06 - Footpath QUA/26 Accommodation Underbridge | IDR 213.06 | HS2-000031F3L | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT7D - Bridleway QUA 28A Diversion | IDR 213.05 - Bridleway QUA/28A Overbridge | IDR 213.05 | HS2-00002CT7D | 2025-03-14 | 10 - Complete | 2025-03-20
[8 empty] | HS2-00002CW0N - Bridleway QUA 28A Drainage System | IDR 213.05 - Bridleway QUA/28A Overbridge | IDR 213.05 | HS2-00002CW0N | 2025-01-10 | 10 - Complete | 2025-01-17
[8 empty] | HS2-000001305 - Bridleway QUA 28A Overbridge | IDR 213.05 - Bridleway QUA/28A Overbridge | IDR 213.05 | HS2-000001305 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NGC - Footpath QUA 24A 1 Diversion | IDR 213.05 - Bridleway QUA/28A Overbridge | IDR 213.05 | HS2-000020NGC | 2025-03-14 | 10 - Complete | 2025-03-21
[8 empty] | HS2-00002TUPT - Station Road Cycle Track | IDR 213.04 - Station Road (HS2) Overbridge | IDR 213.04 | HS2-00002TUPT | #N/A | #N/A | #N/A
[8 empty] | HS2-000001304 - Station Road Overbridge | IDR 213.04 - Station Road (HS2) Overbridge | IDR 213.04 | HS2-000001304 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002ULAA - Station Road Underpass | IDR 213.04 - Station Road (HS2) Overbridge | IDR 213.04 | HS2-00002ULAA | #N/A | #N/A | #N/A
[8 empty] | HS2-000032V92 - Station Road Cycle Track Drainage system | IDR 213.04 - Station Road (HS2) Overbridge | IDR 213.04 | HS2-000032V92 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001414 - Doddershall No. 4 Culvert | IDR 213.03 - Doddershall No.4 & Woods Drop Inlet | IDR 213.03 | HS2-000001414 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT75 - Woods Drop Inlet Culvert | IDR 213.03 - Doddershall No.4 & Woods Drop Inlet | IDR 213.03 | HS2-00002CT75 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001411 - Doddershall No. 1 Culvert | IDR 213.02-3 - Doddershall Culverts No.1, No.6 & No.7 | IDR 213.02-3 | HS2-000001411 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001416 - Doddershall No. 6 Culvert | IDR 213.02-3 - Doddershall Culverts No.1, No.6 & No.7 | IDR 213.02-3 | HS2-000001416 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001417 - Doddershall No. 7 Culvert | IDR 213.02-3 - Doddershall Culverts No.1, No.6 & No.7 | IDR 213.02-3 | HS2-000001417 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT79 - C2.MCJ.T.501 Catchment | IDR 213.02-2 - Quainton Cutting | IDR 213.02-2 | HS2-00002CT79 | 2024-10-04 | 10 - Complete | 2024-10-18
[8 empty] | HS2-000001040 - Quainton Cutting | IDR 213.02-2 - Quainton Cutting | IDR 213.02-2 | HS2-000001040 | 2024-08-26 | 10 - Complete | 2024-09-05
[8 empty] | HS2-00002CT76 - C2.T.49 Catchment | IDR 213.02-2 - Quainton Cutting | IDR 213.02-2 | HS2-00002CT76 | 2024-10-04 | 99 - Cancelled | 0
[8 empty] | HS2-00002BVGE - Quainton Cutting Landscape Earthworks | IDR 213.02-2 - Quainton Cutting | IDR 213.02-2 | HS2-00002BVGE | 2024-03-12 | 10 - Complete | 2024-03-15
[8 empty] | HS2-00002NNJ3 - Quainton Highway Access | IDR 213.02-2 - Quainton Cutting | IDR 213.02-2 | HS2-00002NNJ3 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVGC - C2.L.50 Catchment | IDR 213.02-2 - Quainton Cutting | IDR 213.02-2 | HS2-00002BVGC | 2024-03-14 | 10 - Complete | 2024-03-18
[8 empty] | HS2-000001041 - Doddershall Embankment | IDR 213.02-1 - Doddershall Embankment | IDR 213.02-1 | HS2-000001041 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVGH - Doddershall Embankment Landscape Earthworks | IDR 213.02-1 - Doddershall Embankment | IDR 213.02-1 | HS2-00002BVGH | 2024-10-21 | 10 - Complete | 2024-10-30
[8 empty] | HS2-00002CT77 - C2.T.51 Catchment | IDR 213.02-1 - Doddershall Embankment | IDR 213.02-1 | HS2-00002CT77 | 2025-01-15 | 10 - Complete | 2025-01-22
[8 empty] | HS2-00002CT7A - C2.MCJ.T.502 Catchment | IDR 213.02-1 - Doddershall Embankment | IDR 213.02-1 | HS2-00002CT7A | 2025-03-18 | 10 - Complete | 2025-03-25
[8 empty] | HS2-00002CT78 - C2.T.53 Catchment | IDR 213.02-1 - Doddershall Embankment | IDR 213.02-1 | HS2-00002CT78 | 2025-01-15 | 10 - Complete | 2025-02-04
[8 empty] | HS2-00002KRAF - Doddershall No. 6 Culvert Watercourse Diversion | IDR 213.02-1 - Doddershall Embankment | IDR 213.02-1 | HS2-00002KRAF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002KRAG - Doddershall No. 7 Culvert Watercourse Diversion | IDR 213.02-1 - Doddershall Embankment | IDR 213.02-1 | HS2-00002KRAG | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NNJ2 - Doddershall Highway Access | IDR 213.02-1 - Doddershall Embankment | IDR 213.02-1 | HS2-00002NNJ2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVGF - C2.L.52 Catchment | IDR 213.02-1 - Doddershall Embankment | IDR 213.02-1 | HS2-00002BVGF | 2025-01-15 | 10 - Complete | 2025-02-04
[8 empty] | HS2-00002CT7S - C2.T.54 Catchment | IDR 213.02-1 - Doddershall Embankment | IDR 213.02-1 | HS2-00002CT7S | 2025-03-18 | 10 - Complete | 2025-03-25
[8 empty] | HS2-00002CT6W - Maintenance Access Road to Pond (Off Southern End of Station Road) | IDR 213.01-1 - Station Rd Highways | IDR 213.01-1 | HS2-00002CT6W | 2025-06-27 | 10 - Complete | 2025-07-01
[8 empty] | HS2-00002CT6X - Maintenance Access Road to Pond (Off North End of Station Road) 02 | IDR 213.01-1 - Station Rd Highways | IDR 213.01-1 | HS2-00002CT6X | 2025-06-27 | 10 - Complete | 2025-07-02
[8 empty] | HS2-000020NF2 - Station Road Realignment (including Buckingham Road and Fidlers Field Road) | IDR 213.01-1 - Station Rd Highways | IDR 213.01-1 | HS2-000020NF2 | 2024-06-10 | 99 - Cancelled | 0
[8 empty] | HS2-00002CW1G - Station Road Drainage System | IDR 213.01-1 - Station Rd Highways | IDR 213.01-1 | HS2-00002CW1G | 2025-04-24 | 10 - Complete | 2025-06-27
[8 empty] | HS2-00002N7Y6 - Station Road Watercourse-Ancillary Culvert No. 3 | IDR 213.01-1 - Station Rd Highways | IDR 213.01-1 | HS2-00002N7Y6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJTJ - Maintenance Access Road to Pond (Off North End of Station Road) 01 | IDR 213.01-1 - Station Rd Highways | IDR 213.01-1 | HS2-00002BJTJ | 2025-06-27 | 10 - Complete | 2025-07-01
[8 empty] | HS2-00002N7XV - Station Road Highway Drainage-Ancillary Culvert No. 12 | IDR 213.01-1 - Station Rd Highways | IDR 213.01-1 | HS2-00002N7XV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7Y8 - Station Road Watercourse-Ancillary Culvert No. 5 | IDR 213.01-1 - Station Rd Highways | IDR 213.01-1 | HS2-00002N7Y8 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NFY - Maintenance Access Road to Pond (Off Fidlers Field Road) | IDR 213.01-1 - Station Rd Highways | IDR 213.01-1 | HS2-000020NFY | 2025-06-27 | 10 - Complete | 0
[8 empty] | HS2-00002BJTK - Doddershall House and South Farms Accommodation Access Road | IDR 213.01-1 - Station Rd Highways | IDR 213.01-1 | HS2-00002BJTK | 2024-01-15 | 10 - Complete | 2024-01-18
[8 empty] | HS2-0000316C6 - Station Road Watercourse Ancillary Culvert No.7 | IDR 213.01-1 - Station Rd Highways | IDR 213.01-1 | HS2-0000316C6 | #N/A | #N/A | #N/A
[8 empty] | HS2-000033XXM - Station Road Highway Drainage Ancillary Culvert No. 16 | IDR 213.01-1 - Station Rd Highways | IDR 213.01-1 | HS2-000033XXM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002091V - Station Road National Rail Overbridge | IDR 213.01 - Station Road National Rail Overbridge | IDR 213.01 | HS2-00002091V | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT54 - Aylesbury South Cutting Noise Barrier Line | IDR 212.6 - AA Noise Barrier | IDR 212.6 | HS2-00002CT54 | 2024-08-08 | 10 - Complete | 2024-09-05
[8 empty] | HS2-00002CT5B - Aylesbury Embankment Noise Barrier Line | IDR 212.6 - AA Noise Barrier | IDR 212.6 | HS2-00002CT5B | 2024-08-08 | 10 - Complete | 2024-09-09
[8 empty] | HS2-00002CT5J - Aylesbury North Cutting Noise Barrier Line | IDR 212.6 - AA Noise Barrier | IDR 212.6 | HS2-00002CT5J | 2024-08-08 | 10 - Complete | 2024-08-29
[8 empty] | HS2-00002CT5R - Oxford Road Embankment Noise Barrier Line | IDR 212.6 - AA Noise Barrier | IDR 212.6 | HS2-00002CT5R | 2024-08-08 | 10 - Complete | 2024-09-02
[8 empty] | HS2-00002CT5V - Whaddon Hill Cutting Noise Barrier Line | IDR 212.6 - AA Noise Barrier | IDR 212.6 | HS2-00002CT5V | 2024-08-08 | 10 - Complete | 2024-09-09
[8 empty] | HS2-00002CT5Y - Thame Valley South Embankment Noise Barrier Line | IDR 212.6 - AA Noise Barrier | IDR 212.6 | HS2-00002CT5Y | 2024-08-08 | 10 - Complete | 2024-08-29
[8 empty] | HS2-00002NL60 - Stoke Mandeville Bypass Fencing | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002NL60 | 2024-11-20 | 10 - Complete | 2024-12-03
[8 empty] | HS2-00002CT53 - Aylesbury South Cutting Boundary Perimeter Fence Line | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002CT53 | 2024-11-21 | 10 - Complete | 2024-11-28
[8 empty] | HS2-00002CT55 - Aylesbury South Cutting Security Fence Line | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002CT55 | 2024-11-21 | 10 - Complete | 2024-11-28
[8 empty] | HS2-00002VK4B - Stoke Mandeville Bypass North Pedestrian Ditch Slab | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002VK4B | 2024-09-06 | 10 - Complete | 2024-09-17
[8 empty] | HS2-00002VK4A - Stoke Mandeville Bypass Vehicular Ditch Slab | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002VK4A | 2024-07-26 | 10 - Complete | 2024-08-08
[8 empty] | HS2-00002VK4C - Stoke Mandeville Bypass South Pedestrian Ditch Slab | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002VK4C | 2024-06-25 | 10 - Complete | 2024-07-02
[8 empty] | HS2-00002EKX8 - Aylesbury Ecological Mitigation Site (B) | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002EKX8 | 2024-10-15 | 10 - Complete | 2024-10-21
[8 empty] | HS2-00002CT5A - Aylesbury Embankment Boundary Perimeter Fence Line | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002CT5A | 2024-11-20 | 10 - Complete | 2024-11-27
[8 empty] | HS2-00002CT5C - Aylesbury Embankment Security Fence Line | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002CT5C | 2024-11-20 | 10 - Complete | 2024-11-26
[8 empty] | HS2-00002CT5H - Aylesbury North Cutting Boundary Perimeter Fence Line | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002CT5H | 2024-11-20 | 10 - Complete | 2024-12-05
[8 empty] | HS2-00002GUW0 - Aylesbury North Cutting Security Fence Line | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002GUW0 | 2024-11-20 | 10 - Complete | 2024-11-26
[8 empty] | HS2-00002CT5Q - Oxford Road Embankment Boundary Perimeter Line | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002CT5Q | 2024-11-20 | 10 - Complete | 2024-11-26
[8 empty] | HS2-00002CT5S - Oxford Road Embankment Security Fence Line | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002CT5S | 2024-11-20 | 10 - Complete | 2024-11-26
[8 empty] | HS2-00002EKXA - Hartwell House Ecological Mitigation Site (A) | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002EKXA | 2024-10-15 | 10 - Complete | 2024-10-18
[8 empty] | HS2-00002EKXB - Hartwell House Ecological Mitigation Site (B) | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002EKXB | 2024-10-15 | 10 - Complete | 2024-10-18
[8 empty] | HS2-00002CT5U - Whaddon Hill Cutting Boundary Perimeter Fence Line | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002CT5U | 2024-11-20 | 10 - Complete | 2024-11-28
[8 empty] | HS2-00002CT5W - Whaddon Hill Cutting Security Fence Line | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002CT5W | 2024-11-20 | 10 - Complete | 2024-11-27
[8 empty] | HS2-00002WULP - Aylesbury South Cutting Planting-East Plot 1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WULP | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00002WULQ - Aylesbury South Cutting Planting-East Plot 2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WULQ | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00002WULR - Aylesbury South Cutting Planting-East Plot 3 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WULR | 2024-11-05 | 10 - Complete | 2024-11-20
[8 empty] | HS2-00002WULS - Aylesbury South Cutting Planting-East Plot 4 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WULS | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00002WULT - Aylesbury South Cutting Planting-East Plot 5 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WULT | 2024-11-05 | 10 - Complete | 2024-11-21
[8 empty] | HS2-00002WULU - Aylesbury South Cutting Planting-West Plot 1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WULU | 2024-11-05 | 10 - Complete | 0
[8 empty] | HS2-00002WULV - Aylesbury South Cutting Planting-West Plot 2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WULV | 2024-11-05 | 10 - Complete | 2024-11-21
[8 empty] | HS2-00002WULW - Aylesbury South Cutting Planting-West Plot 3 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WULW | 2024-11-05 | 10 - Complete | 2024-11-21
[8 empty] | HS2-00002WULX - Aylesbury South Cutting Planting-West Plot 4 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WULX | 2024-11-05 | 10 - Complete | 2024-11-21
[8 empty] | HS2-00002WULY - Aylesbury South Cutting Planting-West Plot 5 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WULY | 2024-11-05 | 10 - Complete | 2024-11-25
[8 empty] | HS2-00002WULZ - Aylesbury Embankment Planting-East Plot 1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WULZ | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00002WUM0 - Aylesbury Embankment Planting-East Plot 2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUM0 | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00002WUM1 - Aylesbury Embankment Planting-West Plot 1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUM1 | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00002WUM2 - Aylesbury Embankment Planting-West Plot 2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUM2 | 2024-11-05 | 10 - Complete | 2024-11-21
[8 empty] | HS2-00002WUM3 - Aylesbury North Cutting Planting-East Plot 1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUM3 | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00002WUM4 - Aylesbury North Cutting Planting-East Plot 2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUM4 | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00002WUM5 - Aylesbury North Cutting Planting-East Plot 3 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUM5 | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00002WUM6 - Aylesbury North Cutting Planting-East Plot 4 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUM6 | 2024-11-05 | 10 - Complete | 2024-11-21
[8 empty] | HS2-00002WUM7 - Aylesbury North Cutting Planting-West Plot 1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUM7 | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00002WUM8 - Aylesbury North Cutting Planting-West Plot 2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUM8 | 2024-11-05 | 10 - Complete | 2024-11-21
[8 empty] | HS2-00002WUM9 - Aylesbury North Cutting Planting-West Plot 3 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUM9 | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00002WUMA - Oxford Road Embankment Planting-East Plot 1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUMA | 2024-11-05 | 10 - Complete | 2024-11-25
[8 empty] | HS2-00002WUMB - Oxford Road Embankment Planting-East Plot 2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUMB | 2024-11-05 | 10 - Complete | 2024-11-25
[8 empty] | HS2-00002WUMC - Oxford Road Embankment Planting-West Plot 1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUMC | 2024-11-05 | 10 - Complete | 2024-11-25
[8 empty] | HS2-00002WUMD - Oxford Road Embankment Planting-West Plot 2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUMD | 2024-11-05 | 10 - Complete | 2024-11-25
[8 empty] | HS2-00002WUME - Oxford Road Embankment Planting-West Plot 3 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUME | 2024-11-05 | 10 - Complete | 2024-11-25
[8 empty] | HS2-00002WUMF - Whaddon Hill Cutting Planting-East Plot 1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUMF | 2024-11-05 | 10 - Complete | 2024-11-28
[8 empty] | HS2-00002WUMG - Whaddon Hill Cutting Planting-East Plot 2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUMG | 2024-11-05 | 10 - Complete | 2024-11-28
[8 empty] | HS2-00002WUMH - Whaddon Hill Cutting Planting-West Plot 1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUMH | 2024-11-05 | 10 - Complete | 2024-11-28
[8 empty] | HS2-00002WUMJ - Whaddon Hill Cutting Planting-West Plot 2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUMJ | 2024-11-05 | 10 - Complete | 2024-11-28
[8 empty] | HS2-00002WUMK - Whaddon Hill Cutting Planting-West Plot 3 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUMK | 2024-11-05 | 10 - Complete | 2024-11-28
[8 empty] | HS2-00002WUML - Whaddon Hill Cutting Planting-West Plot 4 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002WUML | 2024-11-05 | 10 - Complete | 2024-11-28
[8 empty] | HS2-00002YD79 - Aylesbury Embankment Pedestrian Ditch Slab No.1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002YD79 | 2024-07-08 | 10 - Complete | 2024-07-09
[8 empty] | HS2-00002YD7F - Aylesbury Embankment Vehicular Ditch Slab No.1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002YD7F | 2024-07-09 | 10 - Complete | 2024-07-17
[8 empty] | HS2-00002ZJQH - SBH 32 Ditch Slab | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00002ZJQH | 2024-07-12 | 10 - Complete | 2024-07-25
[8 empty] | HS2-000030TD7 - Hartwell Pond Access Ditch Slab No.1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-000030TD7 | 2024-08-29 | 10 - Complete | 2024-09-13
[8 empty] | HS2-000030TD8 - Hartwell Pond Access Ditch Slab No.2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-000030TD8 | 2024-08-29 | 10 - Complete | 0
[8 empty] | HS2-000035Q91 - Oxford Road Embankment Ditch Slab No.3 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-000035Q91 | 2024-08-12 | 10 - Complete | 2024-08-23
[8 empty] | HS2-000035Q92 - Oxford Road Embankment Ditch Slab No.4 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-000035Q92 | 2024-06-19 | 10 - Complete | 2024-06-25
[8 empty] | HS2-000035Q93 - Oxford Road Embankment Ditch Slab No.5 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-000035Q93 | 2024-05-30 | 10 - Complete | 2024-06-20
[8 empty] | HS2-000035Q94 - Oxford Road Embankment Ditch Slab No.6 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-000035Q94 | 2024-07-30 | 10 - Complete | 2024-08-13
[8 empty] | HS2-000035Q95 - Oxford Road Embankment Ditch Slab No.7 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-000035Q95 | 2024-07-22 | 10 - Complete | 2024-08-02
[8 empty] | HS2-000035Q98 - Oxford Road Embankment Ditch Slab No.10 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-000035Q98 | 2024-10-16 | 10 - Complete | 2024-10-18
[8 empty] | HS2-00003BPJH - Oxford Road Embankment Ditch Slab No.11 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003BPJH | 2024-09-06 | 10 - Complete | 2024-09-17
[8 empty] | HS2-00003H078 - Aylesbury South Cutting Access Ditch Slab No.1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003H078 | 2024-10-16 | 10 - Complete | 2024-10-18
[8 empty] | HS2-00003H079 - Aylesbury South Cutting Access Ditch Slab No.2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003H079 | 2024-09-06 | 10 - Complete | 2024-09-17
[8 empty] | HS2-00003H07A - Aylesbury North Cutting Access Ditch Slab | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003H07A | 2024-09-06 | 10 - Complete | 2024-09-17
[8 empty] | HS2-00003H07B - Whaddon Hill Cutting Ditch Slab No. 1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003H07B | 2024-08-19 | 10 - Complete | 2024-08-30
[8 empty] | HS2-00003H07C - Whaddon Hill Cutting Ditch Slab No. 2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003H07C | 2024-10-16 | 10 - Complete | 2024-10-18
[8 empty] | HS2-00003HWH4 - SMA-16 Standall’s Farm Footbridge Access Stairs | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003HWH4 | 2024-11-13 | 10 - Complete | 2024-11-21
[8 empty] | HS2-00003HWH5 - SBH-32 Overbridge Access Stairs | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003HWH5 | 2024-11-13 | 10 - Complete | 2024-11-21
[8 empty] | HS2-00003HWH6 - FMA-1 Accommodation Overbridge Access Stairs | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003HWH6 | 2024-11-13 | 10 - Complete | 2024-11-21
[8 empty] | HS2-00003JKXR - Bicester Road Embankment No.5 Ditch Slab | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003JKXR | 2024-11-11 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00003JKXS - Bicester Road Embankment No.6 Ditch Slab | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003JKXS | 2024-08-19 | 10 - Complete | 2024-08-29
[8 empty] | HS2-00003JKXT - Aylesbury South Cutting Access Ditch Slab No.3 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003JKXT | 2024-07-31 | 10 - Complete | 2024-08-14
[8 empty] | HS2-00003KFPN - Aylesbury South Cutting Access Ditch Slab No.4 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003KFPN | 2024-09-06 | 10 - Complete | 2024-09-18
[8 empty] | HS2-00003KFPP - Aylesbury South Cutting Ecology Pond - 1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003KFPP | 2024-10-31 | 10 - Complete | 2024-11-14
[8 empty] | HS2-00003KFPQ - Aylesbury South Cutting Ecology Pond - 2 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003KFPQ | 2024-10-31 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00003KFPR - Aylesbury South Cutting Ecology Pond - 3 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003KFPR | 2024-10-31 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00003KFPS - Aylesbury North Cutting Ecology Pond - 1 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003KFPS | 2024-10-31 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00003KR5H - Ditch slab-1 crossing for HV Cables at GSM-R Compound Point 26 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003KR5H | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00003KR5J - Ditch slab-2 crossing for LV Cables at GSM-R Compound Point 26 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003KR5J | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00003LCQ9 - Ditch slab-3 crossing for HV Cables at GSM-R Compound Point 26 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003LCQ9 | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00003LCQA - Ditch slab-4 crossing for HV Cables at GSM-R Compound Point 26 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003LCQA | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00003LGKN - Ditch slab-5 crossing for HV Cables at GSM-R Compound Point 32 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003LGKN | 2024-11-05 | 10 - Complete | 2024-11-19
[8 empty] | HS2-00003LGKP - Ditch slab-6 crossing for HV Cables at GSM-R Compound Point 32 | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003LGKP | 2024-11-20 | 10 - Complete | 2024-11-22
[8 empty] | HS2-00003LQUL - Thame Valley South Embankment - Access Stairs | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003LQUL | 2024-11-13 | 10 - Complete | 2024-11-22
[8 empty] | HS2-00003LQUM - Thame Valley North Embankment - Access Stairs | IDR 212.5 - Fencing, Landscaping and MAS (Southern L1 Packages) | IDR 212.5 | HS2-00003LQUM | 2024-11-13 | 10 - Complete | 2024-11-22
[8 empty] | HS2-00002CT5X - Thame Valley South Embankment Boundary Perimeter Fence Line | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002CT5X | 2024-04-19 | 10 - Complete | 2024-04-29
[8 empty] | HS2-00002CT5Z - Thame Valley South Embankment Security Fence Line | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002CT5Z | 2024-04-19 | 10 - Complete | 2024-04-29
[8 empty] | HS2-00002CT67 - Thame Valley North Embankment Boundary Perimeter Fence Line | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002CT67 | 2024-04-08 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002CT68 - Putlowes Cutting Boundary Perimeter Fence Line | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002CT68 | 2024-04-19 | 10 - Complete | 2024-04-29
[8 empty] | HS2-00002CT6A - Thame Valley North Embankment Security Fence Line | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002CT6A | 2024-04-08 | 10 - Complete | 2024-04-29
[8 empty] | HS2-00002CT6B - Putlowes Cutting Security Fence Line | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002CT6B | 2024-04-19 | 10 - Complete | 2024-04-29
[8 empty] | HS2-00002CT6D - Bicester Road Embankment Boundary Perimeter Fence Line | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002CT6D | 2024-04-19 | 10 - Complete | 2024-04-29
[8 empty] | HS2-00002CT6E - Bicester Road Embankment Security Fence Line | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002CT6E | 2024-04-19 | 10 - Complete | 2024-04-29
[8 empty] | HS2-00002CT6H - Waddesdon South Cutting Boundary Perimeter Fence Line | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002CT6H | 2024-04-19 | 10 - Complete | 2024-04-29
[8 empty] | HS2-00002CT6K - Waddesdon South Cutting Security Fence Line | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002CT6K | 2024-04-19 | 10 - Complete | 2024-04-29
[8 empty] | HS2-00002WUMM - Thame Valley South Embankment Planting-East Plot 1 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUMM | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUMN - Thame Valley South Embankment Planting-East Plot 2 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUMN | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUMP - Thame Valley South Embankment Planting-West Plot 1 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUMP | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUMQ - Thame Valley South Embankment Planting-West Plot 2 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUMQ | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUMR - Thame Valley Viaduct Planting-Plot 1 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUMR | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUMS - Thame Valley Viaduct Planting-Plot 2 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUMS | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUMT - Thame Valley North Embankment Planting-East Plot 1 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUMT | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUMU - Thame Valley North Embankment Planting-East Plot 2 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUMU | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUMV - Thame Valley North Embankment Planting-West Plot 1 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUMV | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUMW - Thame Valley North Embankment Planting-West Plot 2 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUMW | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUMX - Putlowes Cutting Planting-East Plot 1 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUMX | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUMY - Putlowes Cutting Planting-East Plot 2 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUMY | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUMZ - Putlowes Cutting Planting-West Plot 1 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUMZ | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUN0 - Putlowes Cutting Planting-West Plot 2 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUN0 | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUN1 - Bicester Road Embankment Planting-North Plot 1 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUN1 | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUN2 - Bicester Road Embankment Planting-North Plot 2 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUN2 | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUN3 - Bicester Road Embankment Planting-North Plot 3 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUN3 | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUN4 - Bicester Road Embankment Planting-South Plot 1 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUN4 | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUN5 - Waddesdon South Cutting Planting-East Plot 1 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUN5 | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUN6 - Waddesdon South Cutting Planting-East Plot 2 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUN6 | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUN7 - Waddesdon South Cutting Planting-East Plot 3 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUN7 | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUN8 - Waddesdon South Cutting Planting-East Plot 4 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUN8 | 2024-04-15 | 10 - Complete | 2024-04-26
[8 empty] | HS2-00002WUN9 - Waddesdon South Cutting Planting-East Plot 5 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUN9 | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUNA - Waddesdon South Cutting Planting-East Plot 6 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUNA | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUNB - Waddesdon South Cutting Planting-East Plot 7 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUNB | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUNC - Waddesdon South Cutting Planting-West Plot 1 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUNC | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUND - Waddesdon South Cutting Planting-West Plot 2 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUND | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUNE - Waddesdon South Cutting Planting-West Plot 3 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUNE | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUNF - Waddesdon South Cutting Planting-West Plot 4 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUNF | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUNG - Waddesdon South Cutting Planting-West Plot 5 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUNG | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUNH - Waddesdon South Cutting Planting-West Plot 6 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUNH | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002WUNJ - Waddesdon South Cutting Planting-West Plot 7 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002WUNJ | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00002Y0AT - Bicester Road Embankment No.1 Ditch Slab | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002Y0AT | 2024-03-21 | 10 - Complete | 2024-03-28
[8 empty] | HS2-00002Y479 - Bicester Road Embankment No.2 Ditch Slab | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002Y479 | 2024-03-21 | 10 - Complete | 2024-03-28
[8 empty] | HS2-00002Y47A - Bicester Road Embankment No.3 Ditch Slab | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002Y47A | 2024-11-11 | 10 - Complete | 2025-01-09
[8 empty] | HS2-00002ZM2A - Thame Valley North Embankment No.1 Ditch Slab | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00002ZM2A | 2024-03-26 | 10 - Complete | 2024-04-02
[8 empty] | HS2-0000386T9 - Bicester Road Embankment No.4 Ditch Slab | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-0000386T9 | 2024-03-28 | 10 - Complete | 2024-04-02
[8 empty] | HS2-0000386TB - Wayside Farm Inverted Siphon Maintenance Access Ditch Slab No.1 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-0000386TB | 2024-04-03 | 10 - Complete | 2024-04-07
[8 empty] | HS2-0000386TC - Wayside Farm Inverted Siphon Maintenance Access Ditch Slab No.2 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-0000386TC | 2024-03-28 | 10 - Complete | 2024-04-02
[8 empty] | HS2-000038V0R - Putlowes Cutting Planting-East Plot 3 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-000038V0R | 2024-04-15 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00003B5FW - Cranwell Farm and Bridleway FMA-1 Realignment-Ditch Slab | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00003B5FW | 2024-04-05 | 10 - Complete | 2024-04-12
[8 empty] | HS2-00003B93V - Putlowes Farm Access Road Ditch Slab No.2 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00003B93V | 2024-11-20 | 10 - Complete | 2025-01-08
[8 empty] | HS2-00003GJJL - Oxford Road Embankment Ditch Slab No.14 | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00003GJJL | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GNAD - Needles Farm Clean Water Pipe | IDR 212.4 - Fencing, Landscaping and MAS (Northern L1 Packages) | IDR 212.4 | HS2-00003GNAD | 2024-04-05 | 10 - Complete | 2024-04-09
[8 empty] | HS2-00002EK6X - Marsh Lane Radio Compound UTX | IDR 212.3 - AA GSMR Radio Mast Compounds | IDR 212.3 | HS2-00002EK6X | 2024-03-19 | 10 - Complete | 2024-03-27
[8 empty] | HS2-00002EK6Z - Sedrup Rail Systems Compound (ATS) UTX | IDR 212.3 - AA GSMR Radio Mast Compounds | IDR 212.3 | HS2-00002EK6Z | 2024-03-28 | 10 - Complete | 2024-04-02
[8 empty] | HS2-00002EK71 - Thame Valley North Viaduct Radio Compound UTX | IDR 212.3 - AA GSMR Radio Mast Compounds | IDR 212.3 | HS2-00002EK71 | 2024-03-20 | 10 - Complete | 2024-03-22
[8 empty] | HS2-00002EK72 - Putlowes Rail System Compound (ATS) UTX | IDR 212.3 - AA GSMR Radio Mast Compounds | IDR 212.3 | HS2-00002EK72 | 2024-03-20 | 10 - Complete | 2024-03-22
[8 empty] | HS2-00002EK73 - Briar Hill Farm Radio Compound UTX | IDR 212.3 - AA GSMR Radio Mast Compounds | IDR 212.3 | HS2-00002EK73 | 2024-03-20 | 10 - Complete | 2024-03-25
[8 empty] | HS2-00002Y0AR - Marsh Lane Perturbation Crossover UTX | IDR 212.3 - AA GSMR Radio Mast Compounds | IDR 212.3 | HS2-00002Y0AR | 2024-03-19 | 10 - Complete | 2024-03-22
[8 empty] | HS2-00002YD78 - SMA 9 GSM-R Compound and Access Road | IDR 212.3 - AA GSMR Radio Mast Compounds | IDR 212.3 | HS2-00002YD78 | 2024-03-05 | 10 - Complete | 2024-03-08
[8 empty] | HS2-00002YYN2 - Access to GSM-R Compound Point 33 | IDR 212.3 - AA GSMR Radio Mast Compounds | IDR 212.3 | HS2-00002YYN2 | 2024-03-05 | 10 - Complete | 2024-03-08
[8 empty] | HS2-00002YZKU - GSM-R Compound Point 33 | IDR 212.3 - AA GSMR Radio Mast Compounds | IDR 212.3 | HS2-00002YZKU | 2024-03-05 | 10 - Complete | 2024-03-07
[8 empty] | HS2-00002ZM2B - Putlowes GSM-R Compound and Access Road | IDR 212.3 - AA GSMR Radio Mast Compounds | IDR 212.3 | HS2-00002ZM2B | 2024-03-05 | 10 - Complete | 2024-03-08
[8 empty] | HS2-00003GNAB - Point 32 GSM-R Compound | IDR 212.3 - AA GSMR Radio Mast Compounds | IDR 212.3 | HS2-00003GNAB | 2024-04-02 | 10 - Complete | 2024-04-09
[8 empty] | HS2-000001038 - Waddesdon North Cutting | IDR 212.2 - Waddesdon North Cutting | IDR 212.2 | HS2-000001038 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVG8 - Waddesdon North Cutting West Landscape Earthworks | IDR 212.2 - Waddesdon North Cutting | IDR 212.2 | HS2-00002BVG8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003B5FZ - Maintenance Access Road to Pond (Off Quainton Road) | IDR 212.1-4 - Quainton South Embankment Additional Assets | IDR 212.1-4 | HS2-00003B5FZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H0FP - Quainton South Embankment Ecological Mitigation Site | IDR 212.1-4 - Quainton South Embankment Additional Assets | IDR 212.1-4 | HS2-00003H0FP | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H2JD - Glebe Farm Access Road Boundary Fence | IDR 212.1-4 - Quainton South Embankment Additional Assets | IDR 212.1-4 | HS2-00003H2JD | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H2JE - Glebe Farm Access Road | IDR 212.1-4 - Quainton South Embankment Additional Assets | IDR 212.1-4 | HS2-00003H2JE | #N/A | #N/A | #N/A
[8 empty] | HS2-00003JG40 - Fleet Marston Brook Watercourse Adaptation | IDR 212.1-4 - Quainton South Embankment Additional Assets | IDR 212.1-4 | HS2-00003JG40 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003K2XP - Glebe Farm Access Road Planting | IDR 212.1-4 - Quainton South Embankment Additional Assets | IDR 212.1-4 | HS2-00003K2XP | #N/A | #N/A | #N/A
[8 empty] | HS2-00003K3PD - Glebe Farm Access Road Drainage System | IDR 212.1-4 - Quainton South Embankment Additional Assets | IDR 212.1-4 | HS2-00003K3PD | #N/A | #N/A | #N/A
[8 empty] | HS2-00003K4GT - Quainton South Embankment Access Stairs | IDR 212.1-4 - Quainton South Embankment Additional Assets | IDR 212.1-4 | HS2-00003K4GT | #N/A | #N/A | #N/A
[8 empty] | HS2-00003K4GU - Crossing Over Fleet Marston Brook | IDR 212.1-4 - Quainton South Embankment Additional Assets | IDR 212.1-4 | HS2-00003K4GU | #N/A | #N/A | #N/A
[8 empty] | HS2-00003K4GV - Quainton Ecological Mitigation Site Planting | IDR 212.1-4 - Quainton South Embankment Additional Assets | IDR 212.1-4 | HS2-00003K4GV | #N/A | #N/A | #N/A
[8 empty] | HS2-000001303 - Needles Farm Accommodation Overbridge | IDR 212.1-1 - Needles Farm Accommodation Overbridge | IDR 212.1-1 | HS2-000001303 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003AQD6 - Needles Farm Accommodation Overbridge Stair A1 | IDR 212.1-1 - Needles Farm Accommodation Overbridge | IDR 212.1-1 | HS2-00003AQD6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003AQD7 - Needles Farm Accommodation Overbridge Stair A2 | IDR 212.1-1 - Needles Farm Accommodation Overbridge | IDR 212.1-1 | HS2-00003AQD7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVG6 - C2.L.43 Catchment | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002BVG6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTCX - C2.L.45 Catchment | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002CTCX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CTCY - C2.T.44 Catchment | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002CTCY | #N/A | #N/A | #N/A
[8 empty] | HS2-000001039 - Quainton South Embankment | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-000001039 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVGB - Quainton South Embankment Landscape Earthworks | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002BVGB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT6T - C2.L.46 Catchment | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002CT6T | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT6V - C2.T.48 Catchment | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002CT6V | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT6Y - Quainton South Embankment Boundary Perimeter Line | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002CT6Y | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT70 - Quainton South Embankment Security Fence Line | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002CT70 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NNHT - Little Manor Holding Culvert Watercourse Diversion | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002NNHT | #N/A | #N/A | #N/A
[8 empty] | HS2-000001409 - Little Manor Holding Culvert | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-000001409 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJTH - Needles Farm Accommodation Access Realignment | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002BJTH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CW0E - Needles Farm Access Drainage System | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002CW0E | #N/A | #N/A | #N/A
[8 empty] | HS2-00002GDCZ - Buckinghamshire Railway Centre turning head access | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002GDCZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NL5X - Station Road Substation Turning Head | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002NL5X | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NFH - Maintenance Access Road to Pond (Off Buckingham Road) | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-000020NFH | #N/A | #N/A | #N/A
[8 empty] | HS2-000001410 - Crossroads Farm South Culvert | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-000001410 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7Y4 - Station Road Watercourse-Ancillary Culvert No. 1 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002N7Y4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002091X - Crossroads Farm North Culvert | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00002091X | #N/A | #N/A | #N/A
[8 empty] | HS2-00003A36C - Two-way cycle lane | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003A36C | #N/A | #N/A | #N/A
[8 empty] | HS2-00003B5FY - Maintenance Access Road to Pond (Off Station Road) | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003B5FY | #N/A | #N/A | #N/A
[8 empty] | HS2-00003B5G0 - Maintenance Access Road to Pond C2.T2.48.2 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003B5G0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003CFCP - Quainton South Embankment Ditch Crossing 01 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003CFCP | #N/A | #N/A | #N/A
[8 empty] | HS2-00003CFCR - Quainton South Embankment Ditch Crossing 03 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003CFCR | #N/A | #N/A | #N/A
[8 empty] | HS2-00003DBM6 - Quainton South Embankment Ditch Crossing 04 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003DBM6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003DBM7 - Quainton South Embankment Ditch Crossing 05 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003DBM7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003DBM8 - Quainton South Embankment Ditch Crossing 06 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003DBM8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003DBM9 - Quainton South Embankment Ditch Crossing 07 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003DBM9 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003DBMA - Quainton South Embankment Ditch Crossing 08 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003DBMA | #N/A | #N/A | #N/A
[8 empty] | HS2-00003DBMC - Quainton South Embankment Ditch Crossing 10 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003DBMC | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GYXT - Quainton South Embankment Planting-East Plot | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003GYXT | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GYXU - Quainton South Embankment Planting-West Plot | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003GYXU | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GYXV - Waddesdon North Cutting Planting-East Plot | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003GYXV | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GYXW - Waddesdon North Cutting Planting-West Plot | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003GYXW | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GYXY - Quainton South Embankment Ditch Crossing 12 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003GYXY | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GYXZ - Quainton South Embankment Ditch Crossing 13 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003GYXZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GYY0 - Quainton South Embankment Ditch Crossing 14 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003GYY0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GYY1 - Quainton South Embankment Ditch Crossing 15 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003GYY1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003GYY2 - Quainton South Embankment Ditch Crossing 16 | IDR 212.1 - Quainton South Embankment | IDR 212.1 | HS2-00003GYY2 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001037 - Waddesdon Embankment | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-000001037 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RDZX - C2.L.42.1 | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00002RDZX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKXD - Waddesdon Ecological Mitigation Site | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00002EKXD | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVG5 - Waddesdon Embankment Landscape Earthworks | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00002BVG5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7W5 - Waddesdon Group Ditch Crossing 01 | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00002N7W5 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001366 - Waddesdon Culvert | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-000001366 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT6P - Little Manor Holding Farm Access Road, Haul Road Connection (off WAD 3) and secondary accesses | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00002CT6P | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT6Q - Footpath WAD 3 4 Connection | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00002CT6Q | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT6R - Waddesdon Embankment Boundary Perimeter Fence Line | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00002CT6R | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT6S - Waddesdon Embankment Security Fence Line | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00002CT6S | #N/A | #N/A | #N/A
[8 empty] | TPY-000001570 - Footpath WAD 3 Accommodation Underbridge | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | TPY-000001570 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJTF - Glebe Farm PRoW (WAD 3) Realignment | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00002BJTF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CW14 - Glebe Farm (WAD 3) Drainage System | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00002CW14 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUNK - Waddesdon Embankment Planting | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00002WUNK | #N/A | #N/A | #N/A
[8 empty] | HS2-0000386US - Waddesdon Ditch realignment | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-0000386US | #N/A | #N/A | #N/A
[8 empty] | HS2-0000386ZC - Haul Road Connection (off WAD 4) | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-0000386ZC | #N/A | #N/A | #N/A
[8 empty] | HS2-00003CFCM - Waddesdon Group Access Stair 01 | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00003CFCM | #N/A | #N/A | #N/A
[8 empty] | HS2-00003CVJX - Waddesdon Group Access Stair 02 | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00003CVJX | #N/A | #N/A | #N/A
[8 empty] | HS2-00003DBMH - Waddesdon Group Ditch Crossing 02 | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00003DBMH | #N/A | #N/A | #N/A
[8 empty] | HS2-00003DBMJ - Waddesdon Group Ditch Crossing 03 | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00003DBMJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003DBMK - Waddesdon Group Ditch Crossing 04 | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00003DBMK | #N/A | #N/A | #N/A
[8 empty] | HS2-00003DBML - Waddesdon Group Ditch Crossing 05 | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00003DBML | #N/A | #N/A | #N/A
[8 empty] | HS2-00003EDZC - Waddesdon Group Ditch Crossing 06 | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00003EDZC | #N/A | #N/A | #N/A
[8 empty] | HS2-00003FV0U - Waddesdon Group Ditch Crossing 07 | IDR 211.3 - Waddesdon Embankment | IDR 211.3 | HS2-00003FV0U | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NE6 - Footpath WAD 4 Realignment | IDR 211.2 - Footpath WAD/4 Accommodation Overbridge | IDR 211.2 | HS2-000020NE6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT6G - Glebe Farm Accommodation Access Road | IDR 211.2 - Footpath WAD/4 Accommodation Overbridge | IDR 211.2 | HS2-00002CT6G | #N/A | #N/A | #N/A
[8 empty] | HS2-000001302 - Footpath WAD 4 Accommodation Overbridge | IDR 211.2 - Footpath WAD/4 Accommodation Overbridge | IDR 211.2 | HS2-000001302 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CW12 - Footpath WAD 4 Drainage System | IDR 211.2 - Footpath WAD/4 Accommodation Overbridge | IDR 211.2 | HS2-00002CW12 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002F0X7 - Existing A41 Bicester Road Narrowing | IDR 211.1-4 - A41 Narrowing + junction | IDR 211.1-4 | HS2-00002F0X7 | 2024-05-29 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00002PRX3 - Waddesdon South Cutting Ancillary Culvert 068-AC2 | IDR 211.1-4 - A41 Narrowing + junction | IDR 211.1-4 | HS2-00002PRX3 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NDS - Putlowes ATS Access Road | IDR 211.1-4 - A41 Narrowing + junction | IDR 211.1-4 | HS2-000020NDS | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NDU - Cranwell Farm Access Road | IDR 211.1-4 - A41 Narrowing + junction | IDR 211.1-4 | HS2-000020NDU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002Z3NQ - Existing A41 Bicester Road Narrowing Drainage System | IDR 211.1-4 - A41 Narrowing + junction | IDR 211.1-4 | HS2-00002Z3NQ | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NDK - A41 Bicester Road Realignment-Crossing and west Connection including roundabout | IDR 211.1-3 - A41 Bicester Road Highways | IDR 211.1-3 | HS2-000020NDK | #N/A | #N/A | #N/A
[8 empty] | HS2-00002F0X5 - A41 Bicester Road Realignment-East Connection | IDR 211.1-3 - A41 Bicester Road Highways | IDR 211.1-3 | HS2-00002F0X5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002F0X6 - Blackgrove Road Realignment | IDR 211.1-3 - A41 Bicester Road Highways | IDR 211.1-3 | HS2-00002F0X6 | 2024-05-31 | 10 - Complete | 2024-06-10
[8 empty] | HS2-000020NDR - Maintenance Access Road to Pond (off A41 Bicester Road) | IDR 211.1-3 - A41 Bicester Road Highways | IDR 211.1-3 | HS2-000020NDR | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NDW - Lower Blackgrove Farm Accommodation Access Road | IDR 211.1-3 - A41 Bicester Road Highways | IDR 211.1-3 | HS2-000020NDW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NQD1 - Pond and maintenance access off A41 Bicester Road Realignment (West) | IDR 211.1-3 - A41 Bicester Road Highways | IDR 211.1-3 | HS2-00002NQD1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002C3WX - A41 Bicester Road Drainage System | IDR 211.1-3 - A41 Bicester Road Highways | IDR 211.1-3 | HS2-00002C3WX | #N/A | #N/A | #N/A
[8 empty] | HS2-000001301 - A41 Bicester Road Overbridge | IDR 211.1-2 - A41 Bicester Road Overbridge Phase 2 Full package | IDR 211.1-2 | HS2-000001301 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT6C - C2.L.40 Catchment | IDR 211.1 - Waddesdon South Cutting Phase 2 (Full Package) L3 | IDR 211.1 | HS2-00002CT6C | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVG0 - C2.L.42 Catchment | IDR 211.1 - Waddesdon South Cutting Phase 2 (Full Package) L3 | IDR 211.1 | HS2-00002BVG0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVG2 - Waddesdon South Cutting Landscape Earthworks | IDR 211.1 - Waddesdon South Cutting Phase 2 (Full Package) L3 | IDR 211.1 | HS2-00002BVG2 | 2023-11-14 | 10 - Complete | 2023-11-20
[8 empty] | HS2-00002CT6F - C2.T.41 Catchment | IDR 211.1 - Waddesdon South Cutting Phase 2 (Full Package) L3 | IDR 211.1 | HS2-00002CT6F | #N/A | #N/A | #N/A
[8 empty] | HS2-000001036 - Waddesdon South Cutting | IDR 211.1 - Waddesdon South Cutting Phase 2 (Full Package) L3 | IDR 211.1 | HS2-000001036 | 2023-11-16 | 10 - Complete | 2023-11-17
[8 empty] | HS2-000001407 - Fleet Marston Culvert | IDR 210.2-5 - Fleet Marston Culvert | IDR 210.2-5 | HS2-000001407 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002Y0E7 - Wayside Farm Inverted Siphon Maintenance Access | IDR 210.2-5 - Fleet Marston Culvert | IDR 210.2-5 | HS2-00002Y0E7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VNHX - Wayside Farm Inverted Siphon | IDR 210.2-4 - Wayside Farm Inverted Syphon | IDR 210.2-4 | HS2-00002VNHX | #N/A | #N/A | #N/A
[8 empty] | HS2-000001408 - Cranwell Farm Culvert | IDR 210.2-3 - Cranwell Farm Culvert | IDR 210.2-3 | HS2-000001408 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJT2 - Maintenance Access Road to Pond (off Putlowes Farm Access Track) | IDR 210.2-2 - Putlowes Accommodation Overbridge | IDR 210.2-2 | HS2-00002BJT2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJT6 - Putlowes Farm Access Road Realignment | IDR 210.2-2 - Putlowes Accommodation Overbridge | IDR 210.2-2 | HS2-00002BJT6 | 2024-06-03 | 10 - Complete | 2024-06-18
[8 empty] | HS2-00002CW1D - Putlowes Farm Access Drainage System | IDR 210.2-2 - Putlowes Accommodation Overbridge | IDR 210.2-2 | HS2-00002CW1D | 2024-06-24 | 99 - Cancelled | 0
[8 empty] | HS2-00002F0X3 - Accommodation Access Road (Off Putlowes Farm Access Road) | IDR 210.2-2 - Putlowes Accommodation Overbridge | IDR 210.2-2 | HS2-00002F0X3 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001299 - Putlowes Accommodation Overbridge | IDR 210.2-2 - Putlowes Accommodation Overbridge | IDR 210.2-2 | HS2-000001299 | 2024-03-21 | 10 - Complete | 2024-04-09
[8 empty] | HS2-00002ZM2C - Putlowes Farm Watercourse Diversion | IDR 210.2-2 - Putlowes Accommodation Overbridge | IDR 210.2-2 | HS2-00002ZM2C | 2024-06-03 | 10 - Complete | 2024-06-17
[8 empty] | HS2-00003GNAE - Putlowes Farm Clean Water Pipe | IDR 210.2-2 - Putlowes Accommodation Overbridge | IDR 210.2-2 | HS2-00003GNAE | 2024-05-23 | 10 - Complete | 2024-06-06
[8 empty] | HS2-00002BVFX - C2.L.39 Catchment | IDR 210.2-1 - Bridleway FMA/1 Accommodation Overbridges | IDR 210.2-1 | HS2-00002BVFX | #N/A | #N/A | #N/A
[8 empty] | HS2-000020C10 - Flood Compensation Area-066 | IDR 210.2-1 - Bridleway FMA/1 Accommodation Overbridges | IDR 210.2-1 | HS2-000020C10 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002D88T - Tributary of Fleet Marston Brook Watercourse Diversion | IDR 210.2-1 - Bridleway FMA/1 Accommodation Overbridges | IDR 210.2-1 | HS2-00002D88T | #N/A | #N/A | #N/A
[8 empty] | HS2-000001300 - Bridleway FMA 1 Accommodation Overbridge | IDR 210.2-1 - Bridleway FMA/1 Accommodation Overbridges | IDR 210.2-1 | HS2-000001300 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJT8 - Cranwell Farm and Bridleway FMA 1 Realignment | IDR 210.2-1 - Bridleway FMA/1 Accommodation Overbridges | IDR 210.2-1 | HS2-00002BJT8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CW0T - Cranwell Farm and Bridleway (FMA 1) Drainage System | IDR 210.2-1 - Bridleway FMA/1 Accommodation Overbridges | IDR 210.2-1 | HS2-00002CW0T | #N/A | #N/A | #N/A
[8 empty] | HS2-00002F0X4 - FMA 1 Bridleway Diversion | IDR 210.2-1 - Bridleway FMA/1 Accommodation Overbridges | IDR 210.2-1 | HS2-00002F0X4 | #N/A | #N/A | #N/A
[8 empty] | HS2-000033XXK - Bicester Road Embankment-FMA 1 Landscape Earthworks | IDR 210.2-1 - Bridleway FMA/1 Accommodation Overbridges | IDR 210.2-1 | HS2-000033XXK | #N/A | #N/A | #N/A
[8 empty] | HS2-000001034 - Putlowes Cutting | IDR 210.1-2 - Putlowes Cutting | IDR 210.1-2 | HS2-000001034 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVFU - C2.L.38 Catchment | IDR 210.1-2 - Putlowes Cutting | IDR 210.1-2 | HS2-00002BVFU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVFW - Putlowes Cutting Landscape Earthworks | IDR 210.1-2 - Putlowes Cutting | IDR 210.1-2 | HS2-00002BVFW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT66 - C2.T.37 Catchment | IDR 210.1-1 - Bicester Road Embankment | IDR 210.1-1 | HS2-00002CT66 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001035 - Bicester Road Embankment | IDR 210.1-1 - Bicester Road Embankment | IDR 210.1-1 | HS2-000001035 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVFZ - Bicester Road Embankment Landscape Earthworks | IDR 210.1-1 - Bicester Road Embankment | IDR 210.1-1 | HS2-00002BVFZ | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NCN - Thame Valley Walk (SBH 2) Realignment | IDR 209.3 - Bridleway SBH/2 Overbridge | IDR 209.3 | HS2-000020NCN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CW1H - Thame Valley Walk (SBH 2) Drainage System | IDR 209.3 - Bridleway SBH/2 Overbridge | IDR 209.3 | HS2-00002CW1H | #N/A | #N/A | #N/A
[8 empty] | HS2-000001298 - Bridleway SBH 2 Overbridge | IDR 209.3 - Bridleway SBH/2 Overbridge | IDR 209.3 | HS2-000001298 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJT0 - Whaddon Hill Farm Access (upgrade of SBH 3 1 and SBH 2 4) and Maintenance Access Road to Pond | IDR 209.3 - Bridleway SBH/2 Overbridge | IDR 209.3 | HS2-00002BJT0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT64 - River Thame Watercourse Diversion | IDR 209.2-3 - River Thame Watercourses | IDR 209.2-3 | HS2-00002CT64 | 2023-11-09 | 10 - Complete | 2023-11-17
[8 empty] | HS2-000020C0Z - Flood Compensation Area-065 | IDR 209.2-3 - River Thame Watercourses | IDR 209.2-3 | HS2-000020C0Z | 2023-11-22 | 10 - Complete | 2023-11-24
[8 empty] | HS2-00002Y0AS - Diversion of Bear Brook Overflow Channel | IDR 209.2-3 - River Thame Watercourses | IDR 209.2-3 | HS2-00002Y0AS | 2023-11-17 | 10 - Complete | 2023-11-29
[8 empty] | HS2-00003GL99 - River Thame Watercourses Ground reprofiling | IDR 209.2-3 - River Thame Watercourses | IDR 209.2-3 | HS2-00003GL99 | 2024-01-11 | 10 - Complete | 2024-01-11
[8 empty] | HS2-000001031 - Thame Valley South Embankment | IDR 209.2-2 - Thame Valley Embankments | IDR 209.2-2 | HS2-000001031 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001033 - Thame Valley North Embankment | IDR 209.2-2 - Thame Valley Embankments | IDR 209.2-2 | HS2-000001033 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DV8N - C2.L.33 Catchment | IDR 209.2-2 - Thame Valley Embankments | IDR 209.2-2 | HS2-00002DV8N | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVFT - Thame Valley North Embankment Landscape Earthworks | IDR 209.2-2 - Thame Valley Embankments | IDR 209.2-2 | HS2-00002BVFT | #N/A | #N/A | #N/A
[8 empty] | HS2-000001032 - Thame Valley Viaduct | IDR 209.2-1 - Thame Valley Viaduct - Superstructure (Phase 3 L3) Full Package | IDR 209.2-1 | HS2-000001032 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001030 - Whaddon Hill Cutting | IDR 209.1 - Whaddon Hill Cutting | IDR 209.1 | HS2-000001030 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVFJ - Whaddon Hill Cutting Landscape Earthworks | IDR 209.1 - Whaddon Hill Cutting | IDR 209.1 | HS2-00002BVFJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT5T - C2.T.30 Catchment | IDR 209.1 - Whaddon Hill Cutting | IDR 209.1 | HS2-00002CT5T | 2023-11-22 | 10 - Complete | 2023-11-22
[8 empty] | HS2-00002CT60 - C2.L.31 Catchment | IDR 209.1 - Whaddon Hill Cutting | IDR 209.1 | HS2-00002CT60 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJSK - Maintenance Access Road to Pond (South Arm off Calley Farm-South) | IDR 208.4 - Footpath SBH/34 Overbridge | IDR 208.4 | HS2-00002BJSK | 2024-05-01 | 10 - Complete | 2024-05-09
[8 empty] | HS2-000020NC4 - Maintenance Access Road to Pond (North Arm off Calley Farm-South) | IDR 208.4 - Footpath SBH/34 Overbridge | IDR 208.4 | HS2-000020NC4 | 2024-05-01 | 10 - Complete | 2024-05-07
[8 empty] | HS2-00002N7VS - Aylesbury North Cutting-Ancillary Culvert 061-AC5 | IDR 208.4 - Footpath SBH/34 Overbridge | IDR 208.4 | HS2-00002N7VS | 2024-04-24 | 10 - Complete | 2024-05-03
[8 empty] | HS2-00002N7VT - Aylesbury North Cutting-Ancillary Culvert 061-AC6 | IDR 208.4 - Footpath SBH/34 Overbridge | IDR 208.4 | HS2-00002N7VT | 2024-04-24 | 10 - Complete | 2024-05-03
[8 empty] | HS2-000001295 - Footpath SBH-34 Overbridge | IDR 208.4 - Footpath SBH/34 Overbridge | IDR 208.4 | HS2-000001295 | 2024-04-30 | 10 - Complete | 2024-05-10
[8 empty] | HS2-000020NC7 - Calley Farm (SBH 34) Footpath and Accommodation Access Realignment | IDR 208.4 - Footpath SBH/34 Overbridge | IDR 208.4 | HS2-000020NC7 | 2024-05-08 | 10 - Complete | 2024-05-24
[8 empty] | HS2-00002CW0R - Calley Farm Access (SBH 34) Drainage System | IDR 208.4 - Footpath SBH/34 Overbridge | IDR 208.4 | HS2-00002CW0R | 2024-04-16 | 10 - Complete | 2024-04-30
[8 empty] | HS2-00003GL98 - Flood Compensation Area | IDR 208.4 - Footpath SBH/34 Overbridge | IDR 208.4 | HS2-00003GL98 | 2024-04-26 | 10 - Complete | 2024-05-10
[8 empty] | HS2-00003HWH7 - Hartwell Area diversion Ditch | IDR 208.4 - Footpath SBH/34 Overbridge | IDR 208.4 | HS2-00003HWH7 | 2024-05-10 | 10 - Complete | 2024-05-14
[8 empty] | HS2-00003JQJP - Landscape Bund between Overbridges SBH-19 and SMA-16 UP trackside | IDR 208.4 - Footpath SBH/34 Overbridge | IDR 208.4 | HS2-00003JQJP | 2024-05-29 | 10 - Complete | 2024-05-31
[8 empty] | HS2-000001404 - Lower Hartwell No. 1 Culvert | IDR 208.3 - Lower Hartwell Culverts No. 1 & 2 | IDR 208.3 | HS2-000001404 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001405 - Lower Hartwell No. 2 Culvert | IDR 208.3 - Lower Hartwell Culverts No. 1 & 2 | IDR 208.3 | HS2-000001405 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NNHU - Lower Hartwell No. 2 Culvert Watercourse Diversion | IDR 208.3 - Lower Hartwell Culverts No. 1 & 2 | IDR 208.3 | HS2-00002NNHU | #N/A | #N/A | #N/A
[8 empty] | HS2-0000307ZP - Lower Hartwell No. 1 Culvert Watercourse Diversion | IDR 208.3 - Lower Hartwell Culverts No. 1 & 2 | IDR 208.3 | HS2-0000307ZP | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT5F - C2.T.25 Catchment | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-00002CT5F | 2023-12-11 | 10 - Complete | 2023-12-14
[8 empty] | HS2-000001029 - Oxford Road Embankment | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-000001029 | 2024-01-31 | 10 - Complete | 2024-02-07
[8 empty] | HS2-00002BVFD - C2.L.28 Catchment | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-00002BVFD | 2023-12-12 | 10 - Complete | 2023-12-20
[8 empty] | HS2-00002BVFF - Oxford Road Embankment Landscape Earthworks | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-00002BVFF | 2024-01-31 | 10 - Complete | 2024-02-07
[8 empty] | HS2-00002CT5N - C2.L.29 Catchment | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-00002CT5N | 2023-12-12 | 10 - Complete | 2023-12-20
[8 empty] | HS2-00002CT5P - C2.T.27 Catchment | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-00002CT5P | 2024-10-29 | 10 - Complete | 2024-11-12
[8 empty] | HS2-000020RKT - Footpath SBH 32 Diversion | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-000020RKT | 2024-01-23 | 10 - Complete | 2024-02-07
[8 empty] | HS2-00002SZLX - Footpath SBH 32 Overbridge Impact Protection Walls | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-00002SZLX | 2024-10-29 | 30 - Sent back to team | 0
[8 empty] | HS2-000001297 - Footpath SBH 32 Overbridge | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-000001297 | 2024-01-31 | 10 - Complete | 2024-02-07
[8 empty] | HS2-000020RKU - Maintenance Access Road to Pond (off Aylesbury Park Golf Course Grounds) | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-000020RKU | 2024-01-23 | 10 - Complete | 2024-02-07
[8 empty] | HS2-00002CW19 - Maintenance Access Road to Pond (off Aylesbury Park Golf Course Grounds) Drainage System | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-00002CW19 | 2023-12-15 | 10 - Complete | 2023-12-18
[8 empty] | HS2-00002ZPP3 - Oxford Road Embankment 062-AC1 | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-00002ZPP3 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003B5FT - Maintenance Access Road to Pond (off Old A418 Oxford Road) | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-00003B5FT | 2024-01-23 | 10 - Complete | 2024-02-07
[8 empty] | HS2-00003GNA7 - Lower Hartwell No.1 Culvert Transition and E R | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-00003GNA7 | 2024-02-01 | 10 - Complete | 2024-02-06
[8 empty] | HS2-00003GNA8 - Lower Hartwell No 2 Culvert Transition and E R | IDR 208.2 - Oxford Road Embankment & Footpath SBH/32 Overbridge | IDR 208.2 | HS2-00003GNA8 | 2024-02-01 | 10 - Complete | 2024-02-06
[8 empty] | HS2-00002CT5G - Hartwell Depot Access Road | IDR 208.1-3 - A418 Oxford Road Realignment | IDR 208.1-3 | HS2-00002CT5G | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJSR - Sedrup ATS Access Road | IDR 208.1-3 - A418 Oxford Road Realignment | IDR 208.1-3 | HS2-00002BJSR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002C3WR - A418 Oxford Road Drainage System | IDR 208.1-3 - A418 Oxford Road Realignment | IDR 208.1-3 | HS2-00002C3WR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJSU - Old Oxford Road East Accommodation Access | IDR 208.1-3 - A418 Oxford Road Realignment | IDR 208.1-3 | HS2-00002BJSU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJSV - Old Oxford Road West Accommodation Access | IDR 208.1-3 - A418 Oxford Road Realignment | IDR 208.1-3 | HS2-00002BJSV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJSX - A418 Oxford Road Realignment | IDR 208.1-3 - A418 Oxford Road Realignment | IDR 208.1-3 | HS2-00002BJSX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVFC - Aylesbury North Cutting Landscape Earthworks | IDR 208.1-2 - Aylesbury North Cutting Earthworks & Drainage | IDR 208.1-2 | HS2-00002BVFC | #N/A | #N/A | #N/A
[8 empty] | HS2-000001028 - Aylesbury North Cutting | IDR 208.1-2 - Aylesbury North Cutting Earthworks & Drainage | IDR 208.1-2 | HS2-000001028 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001296 - A418 Oxford Road Overbridge | IDR 208.1-1 - A418 Oxford Road Overbridge (Full Package) Phase 2 L3 | IDR 208.1-1 | HS2-000001296 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT4W - C2.L.22 Catchment | IDR 207.2 - Bridleway SBH/19 Overbridge | IDR 207.2 | HS2-00002CT4W | 2024-07-25 | 10 - Complete | 2024-08-27
[8 empty] | HS2-00002CT4Z - C2.T.21 Catchment | IDR 207.2 - Bridleway SBH/19 Overbridge | IDR 207.2 | HS2-00002CT4Z | 2024-03-05 | 10 - Complete | 2024-03-07
[8 empty] | HS2-000020RKL - Oat Close Bridleway (SBH 19) Realignment | IDR 207.2 - Bridleway SBH/19 Overbridge | IDR 207.2 | HS2-000020RKL | 2024-03-01 | 10 - Complete | 2024-03-06
[8 empty] | HS2-00002CW1B - Oat Close Bridleway (SBH 19) Drainage System | IDR 207.2 - Bridleway SBH/19 Overbridge | IDR 207.2 | HS2-00002CW1B | 2024-07-25 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00002N7VP - Aylesbury Embankment-Ancillary Culvert 060-AC4 | IDR 207.2 - Bridleway SBH/19 Overbridge | IDR 207.2 | HS2-00002N7VP | 2024-03-05 | 10 - Complete | 2024-03-07
[8 empty] | HS2-000001293 - Bridleway SBH 19 Overbridge | IDR 207.2 - Bridleway SBH/19 Overbridge | IDR 207.2 | HS2-000001293 | 2024-03-05 | 10 - Complete | 2024-03-07
[8 empty] | HS2-00002N7VQ - Aylesbury Embankment-Ancillary Culvert 061-AC1 | IDR 207.2 - Bridleway SBH/19 Overbridge | IDR 207.2 | HS2-00002N7VQ | 2024-03-05 | 10 - Complete | 2024-03-07
[8 empty] | HS2-000032LLR - Stoke Brook Enhancements | IDR 207.2 - Bridleway SBH/19 Overbridge | IDR 207.2 | HS2-000032LLR | 2024-02-12 | 10 - Complete | 2024-02-20
[8 empty] | HS2-00003BPJG - Aylesbury Embankment Landscape Earthworks-Oat Close Bridleway (SBH 19) Re-alignment | IDR 207.2 - Bridleway SBH/19 Overbridge | IDR 207.2 | HS2-00003BPJG | 2024-02-26 | 10 - Complete | 2024-02-28
[8 empty] | HS2-00002BVF6 - C2.L.26 Catchment | IDR 207.1 - Aylesbury Embankment | IDR 207.1 | HS2-00002BVF6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVF8 - Aylesbury Embankment Landscape Earthworks | IDR 207.1 - Aylesbury Embankment | IDR 207.1 | HS2-00002BVF8 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001027 - Aylesbury Embankment | IDR 207.1 - Aylesbury Embankment | IDR 207.1 | HS2-000001027 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT57 - C2.T.23 Catchment | IDR 207.1 - Aylesbury Embankment | IDR 207.1 | HS2-00002CT57 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT5D - Sedrup North Watercourse Diversion | IDR 207.1 - Aylesbury Embankment | IDR 207.1 | HS2-00002CT5D | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7VR - Aylesbury Embankment-Ancillary Culvert 061-AC3 | IDR 207.1 - Aylesbury Embankment | IDR 207.1 | HS2-00002N7VR | #N/A | #N/A | #N/A
[8 empty] | HS2-000001403 - Sedrup North Culvert | IDR 207.1 - Aylesbury Embankment | IDR 207.1 | HS2-000001403 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT4T - Princes Risborough To Aylesbury Line Culvert | IDR 206.1-4 - Princes Risborough Realignment (Culvert) | IDR 206.1-4 | HS2-00002CT4T | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT4U - Princes Risborough To Aylesbury Line Underpass | IDR 206.1-3 - Princes Risborough Realignment (Underpass) | IDR 206.1-3 | HS2-00002CT4U | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TG2C - Maintenance Access Road to Pond C2.T.34-PND-0588 | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-00002TG2C | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NSXW - Princes Risborough To Aylesbury Line Security Fence Line | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-00002NSXW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WGEX - Aylesbury South Cutting-Ancillary Culvert 059-AC9 | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-00002WGEX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7VG - Aylesbury South Cutting-Ancillary Culvert 059-AC2 | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-00002N7VG | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NBS - Princes Risborough To Aylesbury Line Earthworks | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-000020NBS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT4Y - Princes Risborough To Aylesbury Line Track Drainage | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-00002CT4Y | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7VH - Aylesbury South Cutting-Ancillary Culvert 059-AC4 | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-00002N7VH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUTU - Princes Risborough To Aylesbury Line Planting-East Plot 1 | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-00002WUTU | 2024-10-29 | 10 - Complete | 2024-11-08
[8 empty] | HS2-00002WUTV - Princes Risborough To Aylesbury Line Planting-East Plot 2 | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-00002WUTV | 2024-10-29 | 10 - Complete | 2024-11-08
[8 empty] | HS2-00002WUTW - Princes Risborough To Aylesbury Line Planting-East Plot 3 | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-00002WUTW | 2024-10-29 | 10 - Complete | 2024-11-08
[8 empty] | HS2-00002WUTX - Princes Risborough To Aylesbury Line Planting-West Plot 1 | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-00002WUTX | 2024-10-29 | 10 - Complete | 2024-11-08
[8 empty] | HS2-00002WUTY - Princes Risborough To Aylesbury Line Planting-West Plot 2 | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-00002WUTY | 2024-10-29 | 10 - Complete | 2024-11-08
[8 empty] | HS2-00002WUTZ - Princes Risborough To Aylesbury Line Planting-West Plot 3 | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-00002WUTZ | 2024-10-29 | 10 - Complete | 2024-11-08
[8 empty] | HS2-00003782Z - Princes Risborough To Aylesbury Line Underpass Existing Surface | IDR 206.1-2 - Princes Risborough Realignment (Full package) | IDR 206.1-2 | HS2-00003782Z | #N/A | #N/A | #N/A
[8 empty] | HS2-000001291 - Princes Risborough To Aylesbury Rail Overbridge | IDR 206.1-1 - PRA Phase 2 (OB) (Remaining Package) | IDR 206.1-1 | HS2-000001291 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NBF - Whitethorn Farm (SMA 9) Footpath and Accommodation Access Realignment | IDR 205.3 - Footpath SMA/9 & SMA/16 Accomodation Overbridges | IDR 205.3 | HS2-000020NBF | 2024-03-07 10:55 | 10 - Complete | 2024-03-07 12:46
[8 empty] | HS2-00002CW1L - Whitethorn Farm Access (SMA 9) Drainage System | IDR 205.3 - Footpath SMA/9 & SMA/16 Accomodation Overbridges | IDR 205.3 | HS2-00002CW1L | 2024-08-09 | 10 - Complete | 2024-08-23
[8 empty] | HS2-00002BJS2 - Footpath SMA 8 2 Link | IDR 205.3 - Footpath SMA/9 & SMA/16 Accomodation Overbridges | IDR 205.3 | HS2-00002BJS2 | 2024-02-09 | 10 - Complete | 2024-02-19
[8 empty] | HS2-000001289 - Footpath SMA 9 Accommodation Overbridge | IDR 205.3 - Footpath SMA/9 & SMA/16 Accomodation Overbridges | IDR 205.3 | HS2-000001289 | 2024-03-01 | 10 - Complete | 2024-03-04
[8 empty] | HS2-00002N7VF - Aylesbury South Cutting-Ancillary Culvert 058-AC9 | IDR 205.3 - Footpath SMA/9 & SMA/16 Accomodation Overbridges | IDR 205.3 | HS2-00002N7VF | 2024-02-21 | 10 - Complete | 2024-02-22
[8 empty] | HS2-000001292 - Footpath SMA 16 Accommodation Overbridge | IDR 205.3 - Footpath SMA/9 & SMA/16 Accomodation Overbridges | IDR 205.3 | HS2-000001292 | 2024-02-20 | 10 - Complete | 2024-02-21
[8 empty] | HS2-00002N7VN - Aylesbury South Cutting-Ancillary Culvert 060-AC2 | IDR 205.3 - Footpath SMA/9 & SMA/16 Accomodation Overbridges | IDR 205.3 | HS2-00002N7VN | 2024-02-19 | 10 - Complete | 2024-02-20
[8 empty] | HS2-00002BJSA - Standalls Farm (SMA 16) Footpath Realignment | IDR 205.3 - Footpath SMA/9 & SMA/16 Accomodation Overbridges | IDR 205.3 | HS2-00002BJSA | 2024-02-20 | 10 - Complete | 2024-02-22
[8 empty] | HS2-00002CW1F - Standalls Farm Access (SMA 16) Drainage System | IDR 205.3 - Footpath SMA/9 & SMA/16 Accomodation Overbridges | IDR 205.3 | HS2-00002CW1F | 2024-07-25 | 10 - Complete | 2024-08-13
[8 empty] | HS2-00002D88V - Footpath ELL 8 1 Tie-in North of Bypass near SMA 9 realignment | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-00002D88V | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT51 - Footpath ELL 2 1 Realignment | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-00002CT51 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT4X - Stoke Mandeville Bypass Drainage System | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-00002CT4X | #N/A | #N/A | #N/A
[8 empty] | HS2-00002U6LQ - Maintenance Access Road off Marsh Lane north of Stoke Mandeville Bypass | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-00002U6LQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4YA - Marsh lane stopping up bellmouth ( North of alignment) | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-00002J4YA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJS5 - A4010 Stoke Mandeville Bypass | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-00002BJS5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002F0XB - Connection to Marsh Lane (Off A4010 Stoke Mandeville Bypass) | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-00002F0XB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002F0XC - Accommodation Access off A4010 Stoke Mandeville Bypass including PRA Crossing | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-00002F0XC | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NBN - Maintenance Access Road to Pond (off Stoke Mandeville Bypass South of Alignment) near PRA Crossing | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-000020NBN | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NBP - Footpath SMA 11 2 East connection | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-000020NBP | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJS6 - Footpath SMA 11 2 West connection | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-00002BJS6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7VL - Aylesbury South Cutting-Ancillary Culvert 059-AC8 | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-00002N7VL | #N/A | #N/A | #N/A
[8 empty] | HS2-00002SXNJ - Stoke Mandeville Bypass Land Drainage | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-00002SXNJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002N7VJ - Aylesbury South Cutting-Ancillary Culvert 059-AC5 | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-00002N7VJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002YL0Q - Stoke Mandeville Bypass Watercourse Diversion | IDR 205.2-2 - A4010 Stoke Mandeville Bypass (Highways and Drainage) | IDR 205.2-2 | HS2-00002YL0Q | #N/A | #N/A | #N/A
[8 empty] | HS2-000001290 - A4010 Stoke Mandeville Bypass Overbridge | IDR 205.2 - A4010 Stoke Mandeville Bypass Overbridge Phase 2 (Full Package including Non-Impact Wall) | IDR 205.2 | HS2-000001290 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001026 - Aylesbury South Cutting | IDR 205.1 - Aylesbury South Cutting | IDR 205.1 | HS2-000001026 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVF5 - Aylesbury South Cutting Landscape Earthworks | IDR 205.1 - Aylesbury South Cutting | IDR 205.1 | HS2-00002BVF5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TGP8 - Princes Risborough To Aylesbury Line Culvert Watercourse Diversion | IDR 205.1 - Aylesbury South Cutting | IDR 205.1 | HS2-00002TGP8 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NBR - Flood Compensation Area-059 | IDR 205.1 - Aylesbury South Cutting | IDR 205.1 | HS2-000020NBR | #N/A | #N/A | #N/A
[8 empty] | HS2-000031J4J - Princes Risborough to Aylesbury Line Flood Bund | IDR 205.1 - Aylesbury South Cutting | IDR 205.1 | HS2-000031J4J | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT38 - Small Dean South Embankment Noise Barrier Line | IDR 204.4-2 - Noise barrier | IDR 204.4-2 | HS2-00002CT38 | 2024-10-07 | 10 - Complete | 2024-10-10
[8 empty] | HS2-00002CT4F - Stoke Mandeville Embankment Noise Barrier Line | IDR 204.4-2 - Noise barrier | IDR 204.4-2 | HS2-00002CT4F | 2024-10-07 | 10 - Complete | 2024-10-10
[8 empty] | HS2-00002CT2R - Wendover Dean South Embankment Noise Barrier Line | IDR 204.4-1 - Noise barrier | IDR 204.4-1 | HS2-00002CT2R | 2024-02-05 | 10 - Complete | 2024-02-13
[8 empty] | HS2-00002CT2W - Wendover Dean North Embankment Noise Barrier Line | IDR 204.4-1 - Noise barrier | IDR 204.4-1 | HS2-00002CT2W | 2024-02-05 | 10 - Complete | 2024-02-14
[8 empty] | HS2-00002CT30 - Rocky Lane Cutting Noise Barrier Line | IDR 204.4-1 - Noise barrier | IDR 204.4-1 | HS2-00002CT30 | 2024-02-05 | 10 - Complete | 2023-02-13
[8 empty] | HS2-00002CT4S - Risborough Road Footpath | IDR 204.3-3 - Risborough Road Realignment & Drainage | IDR 204.3-3 | HS2-00002CT4S | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CW1E - Risborough Road and footpath Drainage System | IDR 204.3-3 - Risborough Road Realignment & Drainage | IDR 204.3-3 | HS2-00002CW1E | #N/A | #N/A | #N/A
[8 empty] | HS2-000001365 - Risborough Road Underpass | IDR 204.3-2 - Risborough Road Underpass | IDR 204.3-2 | HS2-000001365 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002SZLW - Footpath ELL 20 Overbridge Impact Protection Walls | IDR 204.3-1 - Footpath ELL/20 Overbridge | IDR 204.3-1 | HS2-00002SZLW | 2024-02-08 | 10 - Complete | 2024-02-25
[8 empty] | HS2-00002N7V9 - Stoke Mandeville South Embankment-Ancillary Culvert 056-AC8 | IDR 204.3-1 - Footpath ELL/20 Overbridge | IDR 204.3-1 | HS2-00002N7V9 | 2024-02-29 | 10 - Complete | 2024-02-29
[8 empty] | HS2-00002N7VA - Stoke Mandeville South Embankment-Ancillary Culvert 056-AC9 | IDR 204.3-1 - Footpath ELL/20 Overbridge | IDR 204.3-1 | HS2-00002N7VA | 2024-02-19 | 10 - Complete | 2024-03-01
[8 empty] | HS2-00002BJS0 - Nash Lee Orchard (ELL 20) Footpath Realignment | IDR 204.3-1 - Footpath ELL/20 Overbridge | IDR 204.3-1 | HS2-00002BJS0 | 2024-02-28 | 10 - Complete | 2024-03-05
[8 empty] | HS2-00002CW1A - Nash Lee Orchard Footpath (ELL 20) Drainage System | IDR 204.3-1 - Footpath ELL/20 Overbridge | IDR 204.3-1 | HS2-00002CW1A | 2024-01-11 | 10 - Complete | 2024-01-12
[8 empty] | HS2-000001288 - Footpath ELL 20 Overbridge | IDR 204.3-1 - Footpath ELL/20 Overbridge | IDR 204.3-1 | HS2-000001288 | 2024-02-08 | 10 - Complete | 2024-02-22
[8 empty] | HS2-00002ZM6N - Stoke Mandeville South Embankment-Ancillary Culvert 056-AC7 | IDR 204.3-1 - Footpath ELL/20 Overbridge | IDR 204.3-1 | HS2-00002ZM6N | 2024-02-29 | 10 - Complete | 2024-03-01
[8 empty] | HS2-00002CT4D - Stoke Mandeville Embankment Boundary Perimeter Line | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002CT4D | 2024-09-23 | 10 - Complete | 2024-09-24
[8 empty] | HS2-00002CT4H - Stoke Mandeville Embankment Security Fence Line | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002CT4H | 2024-07-26 | 10 - Complete | 2024-08-27
[8 empty] | HS2-00002CT4M - C2.L.19 Catchment | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002CT4M | 2024-09-02 | 10 - Complete | 2024-09-16
[8 empty] | HS2-00002CT4Q - Maintenance Access Road to Pond (off Old Risborough Road) | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002CT4Q | 2024-06-27 | 10 - Complete | 2024-08-06
[8 empty] | HS2-00002CT4R - Footpath SMA 5 Diversion | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002CT4R | 2024-07-26 | 10 - Complete | 2024-08-13
[8 empty] | HS2-00002EKX5 - Risborough Road Ecological Mitigation Site (B) | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002EKX5 | 2024-08-07 | 10 - Complete | 2024-08-22
[8 empty] | HS2-00002EKX6 - Risborough Road Ecological Mitigation Site (A) | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002EKX6 | 2024-08-07 | 10 - Complete | 2024-08-22
[8 empty] | HS2-00002CT52 - Footpath SMA 5 2 Realignment | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002CT52 | 2024-06-27 | 10 - Complete | 2024-08-13
[8 empty] | HS2-00002BJS4 - Maintenance Access Road to Pond (off Stoke House) | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002BJS4 | 2024-06-27 | 10 - Complete | 2024-08-05
[8 empty] | HS2-00002WULF - Stoke Mandeville South Embankment Planting-East Plot 1 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002WULF | 2024-07-23 | 10 - Complete | 2024-08-01
[8 empty] | HS2-00002WULG - Stoke Mandeville South Embankment Planting-East Plot 2 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002WULG | 2024-09-13 | 10 - Complete | 2024-09-16
[8 empty] | HS2-00002WULH - Stoke Mandeville South Embankment Planting-East Plot 3 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002WULH | 2024-07-23 | 10 - Complete | 2024-08-01
[8 empty] | HS2-00002WULK - Stoke Mandeville South Embankment Planting-West Plot 1 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002WULK | 2024-07-23 | 10 - Complete | 2024-08-02
[8 empty] | HS2-00002WULL - Stoke Mandeville South Embankment Planting-West Plot 2 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002WULL | 2024-07-23 | 10 - Complete | 2024-08-02
[8 empty] | HS2-00002WULM - Stoke Mandeville South Embankment Planting-West Plot 3 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002WULM | 2024-07-23 | 10 - Complete | 2024-08-02
[8 empty] | HS2-00002WULN - Stoke Mandeville South Embankment Planting-West Plot 4 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002WULN | 2024-07-23 | 10 - Complete | 2024-08-02
[8 empty] | HS2-00002YNHA - Stoke Brook watercourse diversion at Nash Lee Orchard culvert | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002YNHA | 2024-06-12 | 10 - Complete | 2024-08-16
[8 empty] | HS2-00002YNHB - Stoke Brook watercourse diversion at Mill House South culvert | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002YNHB | 2024-06-12 | 10 - Complete | 2024-08-16
[8 empty] | HS2-00002YNHC - Stoke Brook watercourse diversion at Mill House North culvert | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002YNHC | 2024-06-12 | 10 - Complete | 2024-08-20
[8 empty] | HS2-00002ZPP6 - Stoke Mandeville South Embankment Flood Compensation Area-2R | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00002ZPP6 | 2024-08-07 | 10 - Complete | 2024-08-22
[8 empty] | HS2-000031GXK - Nash Lee Orchard Ditch Slab No.1 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-000031GXK | 2024-08-13 | 10 - Complete | 2024-08-20
[8 empty] | HS2-000031GXL - Nash Lee Orchard Ditch Slab No.2 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-000031GXL | 2024-08-13 | 10 - Complete | 2024-09-11
[8 empty] | HS2-000031GXM - Nash Lee Orchard Ditch Slab No.3 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-000031GXM | 2024-08-13 | 10 - Complete | 2024-09-11
[8 empty] | HS2-000031GXN - Nash Lee Orchard Ditch Slab No.4 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-000031GXN | 2024-08-13 | 10 - Complete | 2024-08-20
[8 empty] | HS2-000031GXP - ELL 20 Ditch Slab No.1 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-000031GXP | 2024-08-13 | 10 - Complete | 0
[8 empty] | HS2-000031GXQ - Risborough Road Ditch Slab No.1 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-000031GXQ | 2024-08-13 | 10 - Complete | 2024-08-16
[8 empty] | HS2-0000325TJ - SMA 5 Footpath Ditch Slab No.1 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-0000325TJ | 2024-08-13 | 10 - Complete | 2024-08-16
[8 empty] | HS2-0000325TK - SMA 5 Footpath Ditch Slab No.2 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-0000325TK | 2024-08-13 | 10 - Complete | 2024-08-16
[8 empty] | HS2-00003CPYU - Stoke House Crossing Ditch Slab No.1 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00003CPYU | 2024-08-13 | 10 - Complete | 2024-08-16
[8 empty] | HS2-00003CPYX - Risborough Road Ditch Slab No.2 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00003CPYX | 2024-08-13 | 10 - Complete | 2024-08-16
[8 empty] | HS2-00003CPYY - Nash Lee Orchard Ditch Slab No.6 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00003CPYY | 2024-08-13 | 10 - Complete | 2024-08-21
[8 empty] | HS2-00003E24P - Stoke Mandeville South Embankment Flood Compensation Area-2L | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00003E24P | 2024-08-07 | 10 - Complete | 2024-08-22
[8 empty] | HS2-00003E24R - Stoke Mandeville South Embankment Flood Compensation Area-3R | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00003E24R | 2024-08-07 | 10 - Complete | 2024-08-22
[8 empty] | HS2-00003JN86 - Stoke Mandeville South Embankment Chalkshire Stream Enhancement | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00003JN86 | 2024-06-03 | 10 - Complete | 2024-06-17
[8 empty] | HS2-00003JQJQ - Risborough Road Underpass Access Stairs No.1 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00003JQJQ | 2024-08-12 | 10 - Complete | 2024-08-16
[8 empty] | HS2-00003JQJR - Risborough Road Underpass Access Stairs No.2 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00003JQJR | 2024-08-12 | 10 - Complete | 2024-08-16
[8 empty] | HS2-00003JQJS - Risborough Road Underpass Access Stairs No.3 | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00003JQJS | 2024-08-12 | 10 - Complete | 2024-08-16
[8 empty] | HS2-00003K2XQ - Nash Lee Orchard Culvert Access Stairs | IDR 204.2-2 - Stoke Mandeville South Embankment Fencing and Landscape Planting | IDR 204.2-2 | HS2-00003K2XQ | 2024-08-12 | 10 - Complete | 2024-08-16
[8 empty] | HS2-00002CT4N - C2.T.18 Catchment | IDR 204.2-1 - Stoke Mandeville South Embankment (LTP zone), Load Transfer Platform, Landscape Earthworks & UTX's | IDR 204.2-1 | HS2-00002CT4N | 2024-03-19 | 10 - Complete | 2024-03-22
[8 empty] | HS2-00002CT4P - C2.T.20 Catchment | IDR 204.2-1 - Stoke Mandeville South Embankment (LTP zone), Load Transfer Platform, Landscape Earthworks & UTX's | IDR 204.2-1 | HS2-00002CT4P | 2024-04-18 | 10 - Complete | 2024-04-19
[8 empty] | HS2-000001025 - Stoke Mandeville South Embankment | IDR 204.2-1 - Stoke Mandeville South Embankment (LTP zone), Load Transfer Platform, Landscape Earthworks & UTX's | IDR 204.2-1 | HS2-000001025 | 2024-03-15 | 10 - Complete | 2024-03-19
[8 empty] | HS2-00002TKV4 - Stoke Mandeville South Embankment Maintenance Siding Access | IDR 204.2-1 - Stoke Mandeville South Embankment (LTP zone), Load Transfer Platform, Landscape Earthworks & UTX's | IDR 204.2-1 | HS2-00002TKV4 | 2024-04-23 | 10 - Complete | 2024-04-24
[8 empty] | TPY-000001569 - Nash Lee Orchard Culvert | IDR 204.2-1 - Stoke Mandeville South Embankment (LTP zone), Load Transfer Platform, Landscape Earthworks & UTX's | IDR 204.2-1 | TPY-000001569 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001399 - Mill House South Culvert | IDR 204.2-1 - Stoke Mandeville South Embankment (LTP zone), Load Transfer Platform, Landscape Earthworks & UTX's | IDR 204.2-1 | HS2-000001399 | 2023-11-17 | 10 - Complete | 2023-11-21
[8 empty] | HS2-000001400 - Mill House North Culvert | IDR 204.2-1 - Stoke Mandeville South Embankment (LTP zone), Load Transfer Platform, Landscape Earthworks & UTX's | IDR 204.2-1 | HS2-000001400 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EK6W - Stoke Mandeville Maintenance Loop UTX No2 | IDR 204.2-1 - Stoke Mandeville South Embankment (LTP zone), Load Transfer Platform, Landscape Earthworks & UTX's | IDR 204.2-1 | HS2-00002EK6W | 2024-03-22 | 10 - Complete | 2024-03-28
[8 empty] | HS2-00002F0X2 - Stoke Mandeville South Embankment Landscape Earthworks | IDR 204.2-1 - Stoke Mandeville South Embankment (LTP zone), Load Transfer Platform, Landscape Earthworks & UTX's | IDR 204.2-1 | HS2-00002F0X2 | 2024-03-15 | 10 - Complete | 2024-03-18
[8 empty] | HS2-000030TD4 - Stoke Mandeville South Embankment Load Transfer Platform (North) | IDR 204.2-1 - Stoke Mandeville South Embankment (LTP zone), Load Transfer Platform, Landscape Earthworks & UTX's | IDR 204.2-1 | HS2-000030TD4 | 2024-03-19 | 10 - Complete | 2024-03-28
[8 empty] | HS2-000030TD5 - Stoke Mandeville South Embankment Load Transfer Platform (South) | IDR 204.2-1 - Stoke Mandeville South Embankment (LTP zone), Load Transfer Platform, Landscape Earthworks & UTX's | IDR 204.2-1 | HS2-000030TD5 | 2024-03-19 | 10 - Complete | 2024-03-28
[8 empty] | HS2-00002BVEZ - Wendover North Cutting Landscape Earthworks | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002BVEZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT49 - C2.L.17 Catchment | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002CT49 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT4C - Wendover North Cutting Boundary Perimeter Fence Line | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002CT4C | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT4G - Wendover North Cutting Security Fence Line | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002CT4G | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJRW - Footpath ELL 25 1 Diversion | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002BJRW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EK6U - Stoke Grove Rail Systems Compound (ATS) UTX | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002EK6U | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NAR - Maintenance Access Road to Pond (Off Nash Lee Road) | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-000020NAR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VBQD - Nash Lee Access Road Ditch Slab | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002VBQD | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUL1 - Wendover North Cutting Planting-East Plot 1 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WUL1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUL2 - Wendover North Cutting Planting-East Plot 2 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WUL2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUL3 - Wendover North Cutting Planting-East Plot 3 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WUL3 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUL4 - Wendover North Cutting Planting-East Plot 4 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WUL4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUL5 - Wendover North Cutting Planting-East Plot 5 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WUL5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUL6 - Wendover North Cutting Planting-East Plot 6 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WUL6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUL7 - Wendover North Cutting Planting-East Plot 7 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WUL7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUL8 - Wendover North Cutting Planting-East Plot 8 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WUL8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUL9 - Wendover North Cutting Planting-West Plot 1 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WUL9 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WULA - Wendover North Cutting Planting-West Plot 2 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WULA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WULB - Wendover North Cutting Planting-West Plot 3 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WULB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WULC - Wendover North Cutting Planting-West Plot 4 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WULC | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WULD - Wendover North Cutting Planting-West Plot 5 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WULD | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WULE - Wendover North Cutting Planting-West Plot 6 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00002WULE | #N/A | #N/A | #N/A
[8 empty] | HS2-000039J1M - Maintenance Access Road to Ponds REG-0562-1 to REG-0562-3 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-000039J1M | #N/A | #N/A | #N/A
[8 empty] | HS2-00003CCK7 - Footpath ELL 25 1 Ditch Slab 2 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00003CCK7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003CCK8 - Footpath ELL 25 1 Ditch Slab 3 | IDR 204.1-2 - Wendover North Cutting C2.L.17 Catchment, Access Road to Ponds, UTXs | IDR 204.1-2 | HS2-00003CCK8 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NAE - Wendover Green Tunnel North Portal Access Road | IDR 204.1-1 - Wendover North Cutting, C2.T.16 Catchment, Wendover North Portal Access, Stoke Grove ATS Maintenenace Sidings, Stoke Grove ATS, UTX's | IDR 204.1-1 | HS2-000020NAE | #N/A | #N/A | #N/A
[8 empty] | HS2-000001024 - Wendover North Cutting | IDR 204.1-1 - Wendover North Cutting, C2.T.16 Catchment, Wendover North Portal Access, Stoke Grove ATS Maintenenace Sidings, Stoke Grove ATS, UTX's | IDR 204.1-1 | HS2-000001024 | 2024-04-17 | 10 - Complete | 2024-05-02
[8 empty] | HS2-00002CW1J - Wendover North cutting Access Drainage System | IDR 204.1-1 - Wendover North Cutting, C2.T.16 Catchment, Wendover North Portal Access, Stoke Grove ATS Maintenenace Sidings, Stoke Grove ATS, UTX's | IDR 204.1-1 | HS2-00002CW1J | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EK6V - Stoke Mandeville Maintenance Loop UTX No1 | IDR 204.1-1 - Wendover North Cutting, C2.T.16 Catchment, Wendover North Portal Access, Stoke Grove ATS Maintenenace Sidings, Stoke Grove ATS, UTX's | IDR 204.1-1 | HS2-00002EK6V | 2024-04-30 | 10 - Complete | 2024-05-07
[8 empty] | HS2-00002BVF0 - C2.T.16 Catchment | IDR 204.1-1 - Wendover North Cutting, C2.T.16 Catchment, Wendover North Portal Access, Stoke Grove ATS Maintenenace Sidings, Stoke Grove ATS, UTX's | IDR 204.1-1 | HS2-00002BVF0 | 2024-04-29 | 10 - Complete | 2024-05-07
[8 empty] | HS2-00002BJS1 - Stoke Grove ATS Maintenance Sidings Northern (Off Nash Lee Lane) | IDR 204.1-1 - Wendover North Cutting, C2.T.16 Catchment, Wendover North Portal Access, Stoke Grove ATS Maintenenace Sidings, Stoke Grove ATS, UTX's | IDR 204.1-1 | HS2-00002BJS1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002Y8VY - Wendover North Cutting-Low Permeability Wall | IDR 204.1-1 - Wendover North Cutting, C2.T.16 Catchment, Wendover North Portal Access, Stoke Grove ATS Maintenenace Sidings, Stoke Grove ATS, UTX's | IDR 204.1-1 | HS2-00002Y8VY | 2024-04-17 | 10 - Complete | 2024-05-02
[8 empty] | HS2-00002YYN4 - Low Permeability Wall Ground Water Catchment | IDR 204.1-1 - Wendover North Cutting, C2.T.16 Catchment, Wendover North Portal Access, Stoke Grove ATS Maintenenace Sidings, Stoke Grove ATS, UTX's | IDR 204.1-1 | HS2-00002YYN4 | 2024-04-29 | 10 - Complete | 2024-05-07
[8 empty] | HS2-000030KBA - Spring Chamber Ground Water Catchment | IDR 204.1-1 - Wendover North Cutting, C2.T.16 Catchment, Wendover North Portal Access, Stoke Grove ATS Maintenenace Sidings, Stoke Grove ATS, UTX's | IDR 204.1-1 | HS2-000030KBA | 2024-04-26 | 10 - Complete | 2024-05-08
[8 empty] | HS2-00002CT4A - B4009 Nash Lee Road Drainage System | IDR 204.0-2 - Nash Lee Road Realignment, Nash Lee Lane Highways Highway Drainage | IDR 204.0-2 | HS2-00002CT4A | 2024-06-13 | 10 - Complete | 2024-07-10
[8 empty] | HS2-00002CT4B - B4009 Nash Lee Road Realignment | IDR 204.0-2 - Nash Lee Road Realignment, Nash Lee Lane Highways Highway Drainage | IDR 204.0-2 | HS2-00002CT4B | 2025-08-26 | 30 - Sent back to team | 0
[8 empty] | HS2-000020NAP - Nash Lee Lane Realignment | IDR 204.0-2 - Nash Lee Road Realignment, Nash Lee Lane Highways Highway Drainage | IDR 204.0-2 | HS2-000020NAP | 2025-08-26 | 30 - Sent back to team | 0
[8 empty] | HS2-000001287 - B4009 Nash Lee Road Overbridge | IDR 204.0-1 - Nash Lee Road Overbridge | IDR 204.0-1 | HS2-000001287 | 2024-09-26 | 10 - Complete | 2024-09-27
[8 empty] | HS2-00002BJRV - Wendover Green Tunnel North Portal Building | IDR 203.2-6 - Wendover Green Tunnel North Portal Building | IDR 203.2-6 | HS2-00002BJRV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EK6T - Wendover Green Tunnel North Portal UTX | IDR 203.2-6 - Wendover Green Tunnel North Portal Building | IDR 203.2-6 | HS2-00002EK6T | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TMER - Wendover Green Tunnel North Portal Building Fire-fighting water | IDR 203.2-6 - Wendover Green Tunnel North Portal Building | IDR 203.2-6 | HS2-00002TMER | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TMES - Wendover Green Tunnel North Portal Building Telecoms | IDR 203.2-6 - Wendover Green Tunnel North Portal Building | IDR 203.2-6 | HS2-00002TMES | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NJ09 - Wendover Green Tunnel South Portal | IDR 203.2-5 - Wendover Green Tunnel South Portal | IDR 203.2-5 | HS2-00002NJ09 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003LXT0 - Wendover Green Tunnel North Portal Evacuation Walkway | IDR 203.2-5 - Wendover Green Tunnel South Portal | IDR 203.2-5 | HS2-00003LXT0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003LXT1 - Wendover Green Tunnel South Portal Evacuation Walkway | IDR 203.2-5 - Wendover Green Tunnel South Portal | IDR 203.2-5 | HS2-00003LXT1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002NJ08 - Wendover Green Tunnel North Portal | IDR 203.2-4 - Wendover Green Tunnel Portals | IDR 203.2-4 | HS2-00002NJ08 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVEW - Wendover Green Tunnel Landscape Earthworks | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002BVEW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT3S - Bacombe Lane Drainage System | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002CT3S | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT3T - Footpath WEN 11 1 Diversion | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002CT3T | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT3U - Wendover Green Tunnel Boundary Perimeter Fence Line | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002CT3U | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT3V - Wendover Green Tunnel Security Fence Line | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002CT3V | #N/A | #N/A | #N/A
[8 empty] | TPY-000001578 - Bacombe Lane Realignment | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | TPY-000001578 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4Y7 - Access to houses off Bacombe Lane | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002J4Y7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJRP - Footpath WEN 6 1 Realignment | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002BJRP | #N/A | #N/A | #N/A
[8 empty] | TPY-000001579 - Ellesborough Road Reinstatement | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | TPY-000001579 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TGPE - Ellesborough Road Reinstatement Drainage System Piped Drain | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002TGPE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TKUS - Ellesborough Road Substation Access East | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002TKUS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TKUT - Ellesborough Road Substation Access West | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002TKUT | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJRS - Footpath WEN 6 2 Realignment | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002BJRS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJRT - Dobbins Lane (WEN 55) Footpath Realignment | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002BJRT | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKT - Wendover Green Tunnel Planting-Plot 1 | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002WUKT | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKU - Wendover Green Tunnel Planting-Plot 2 | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002WUKU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKV - Wendover Green Tunnel Planting-Plot 3 | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002WUKV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKW - Wendover Green Tunnel Planting-Plot 4 | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002WUKW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKX - Wendover Green Tunnel Planting-Plot 5 | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002WUKX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKY - Wendover Green Tunnel Planting-Plot 6 | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002WUKY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKZ - Wendover Green Tunnel Planting-Plot 7 | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002WUKZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUL0 - Wendover Green Tunnel Planting-Plot 8 | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00002WUL0 | #N/A | #N/A | #N/A
[8 empty] | HS2-000033XXL - Bacombe Lane Realignment Drainage System | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-000033XXL | #N/A | #N/A | #N/A
[8 empty] | HS2-00003B5FU - Ellesborough Road Accommodation and Substation Access | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00003B5FU | #N/A | #N/A | #N/A
[8 empty] | HS2-00003B5FV - Dobbins Lane (WEN-55) Footpath Realignment Drainage System | IDR 203.2-3 - Ellesborough Road, Bacombe Lane Realignment, Land Drainage, Landscape Earthworks | IDR 203.2-3 | HS2-00003B5FV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT3H - C2.T.13 Catchment | IDR 203.2-2 - Wendover Green Tunnel South Portal Building | IDR 203.2-2 | HS2-00002CT3H | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT3L - Small Dean North Embankment Noise Barrier Line | IDR 203.2-2 - Wendover Green Tunnel South Portal Building | IDR 203.2-2 | HS2-00002CT3L | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TMEP - Wendover Green Tunnel South Portal Building Fire-fighting water | IDR 203.2-2 - Wendover Green Tunnel South Portal Building | IDR 203.2-2 | HS2-00002TMEP | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TMEQ - Wendover Green Tunnel South Portal Building Telecoms | IDR 203.2-2 - Wendover Green Tunnel South Portal Building | IDR 203.2-2 | HS2-00002TMEQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJRN - Wendover Green Tunnel South Portal Building | IDR 203.2-2 - Wendover Green Tunnel South Portal Building | IDR 203.2-2 | HS2-00002BJRN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EK6N - Wendover Green Tunnel South Portal UTX | IDR 203.2-2 - Wendover Green Tunnel South Portal Building | IDR 203.2-2 | HS2-00002EK6N | #N/A | #N/A | #N/A
[8 empty] | HS2-00002YNH9 - Wendover Green Tunnel South Portal Building Retaining Wall | IDR 203.2-2 - Wendover Green Tunnel South Portal Building | IDR 203.2-2 | HS2-00002YNH9 | #N/A | #N/A | #N/A
[8 empty] | HS2-000000159 - Wendover Green Tunnel | IDR 203.2-1 - Wendover Green Tunnel | IDR 203.2-1 | HS2-000000159 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002Y8VR - Grove Farm Culvert North | IDR 202.5-5 - Grove Farm Culvert Phase 3 - Box Culvert | IDR 202.5-5 | HS2-00002Y8VR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002Y8VP - Grove Farm Culvert Attenuation Tank | IDR 202.5-4 - Grove Farm Culvert Phase 2 - Attenuation Tank | IDR 202.5-4 | HS2-00002Y8VP | 2023-11-14 | 10 - Complete | 2023-11-20
[8 empty] | HS2-00002CT3C - Small Dean Lane Drainage System | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002CT3C | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NA5 - Small Dean Lane Realignment | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-000020NA5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT3K - Small Dean North Embankment Boundary Perimeter Fence Line | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002CT3K | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT3M - Small Dean North Embankment Security Fence Line | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002CT3M | #N/A | #N/A | #N/A
[8 empty] | HS2-00002D88N - Small Dean North Embankment Landscape Earthworks | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002D88N | #N/A | #N/A | #N/A
[8 empty] | HS2-000020NA8 - Wendover Green Tunnel South Portal Access Road | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-000020NA8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJRH - Grove Farm Access Road Realignment | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002BJRH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002VKUX - Bridleway WEN 57 1 Realignment | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002VKUX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT3R - C2.L.15 Catchment | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002CT3R | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKH - Small Dean North Embankment Planting-East Plot 1 | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002WUKH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKJ - Small Dean North Embankment Planting-East Plot 2 | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002WUKJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKK - Small Dean North Embankment Planting-East Plot 3 | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002WUKK | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKL - Small Dean North Embankment Planting-East Plot 4 | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002WUKL | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKM - Small Dean North Embankment Planting-East Plot 5 | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002WUKM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKN - Small Dean North Embankment Planting-West Plot 1 | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002WUKN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKP - Small Dean North Embankment Planting-West Plot 2 | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002WUKP | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKQ - Small Dean North Embankment Planting-West Plot 3 | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002WUKQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKR - Small Dean North Embankment Planting-West Plot 4 | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002WUKR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKS - Small Dean North Embankment Planting-West Plot 5 | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00002WUKS | #N/A | #N/A | #N/A
[8 empty] | HS2-000031G3R - Grove Farm Culvert Inlet System-North | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-000031G3R | #N/A | #N/A | #N/A
[8 empty] | HS2-000031G3S - Grove Farm Culvert Inlet System-South | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-000031G3S | #N/A | #N/A | #N/A
[8 empty] | HS2-00003KLDB - Grove Farm Attenuation Pipe | IDR 202.5-3 - Small Dean Area Highways and Grove Farm Culvert Inlets | IDR 202.5-3 | HS2-00003KLDB | #N/A | #N/A | #N/A
[8 empty] | HS2-000001363 - Grove Farm Accommodation Underbridge | IDR 202.5-2_2 - Small Dean North Embankment - Phase 2 Grove Farm Accommodation Underbridge Piles | IDR 202.5-2_2 | HS2-000001363 | 2024-09-18 | 10 - Complete | 2024-12-17
[8 empty] | HS2-000001023 - Small Dean North Embankment | IDR 202.5-2 - Small Dean North Embankment (Remainder) | IDR 202.5-2 | HS2-000001023 | 2024-12-10 | 10 - Complete | 2024-12-13
[8 empty] | HS2-00002Y8VQ - Grove Farm Culvert South | IDR 202.5-1 - Grove Farm Culvert South | IDR 202.5-1 | HS2-00002Y8VQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT33 - Rocky Lane Drainage System | IDR 202.4-4 - Rocky Lane Highway and Highway Drainage | IDR 202.4-4 | HS2-00002CT33 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT34 - Wendover ATS Access Road | IDR 202.4-4 - Rocky Lane Highway and Highway Drainage | IDR 202.4-4 | HS2-00002CT34 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT36 - Maintenance Access Road to Pond (Off Rocky Lane [P-RAI-0520]) | IDR 202.4-4 - Rocky Lane Highway and Highway Drainage | IDR 202.4-4 | HS2-00002CT36 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020N9Y - Rocky Lane Realignment | IDR 202.4-4 - Rocky Lane Highway and Highway Drainage | IDR 202.4-4 | HS2-000020N9Y | #N/A | #N/A | #N/A
[8 empty] | HS2-00002U7JY - Rocky Lane-Ditch Slab | IDR 202.4-4 - Rocky Lane Highway and Highway Drainage | IDR 202.4-4 | HS2-00002U7JY | 2023-11-09 | 10 - Complete | 2023-11-14
[8 empty] | HS2-000001362 - Rocky Lane Underbridge | IDR 202.4-3 - Rocky Lane Underbridge and Rocky Lane Culvert | IDR 202.4-3 | HS2-000001362 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001361 - Rocky Lane Culvert | IDR 202.4-3 - Rocky Lane Underbridge and Rocky Lane Culvert | IDR 202.4-3 | HS2-000001361 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT2Y - C2.L.12 Catchment | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002CT2Y | 2024-07-09 | 10 - Complete | 2024-07-26
[8 empty] | HS2-00002BVEK - C2.T.5 Catchment | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002BVEK | 2024-07-11 | 10 - Complete | 2024-08-01
[8 empty] | HS2-00002CT32 - C2.T.11 Catchment | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002CT32 | 2024-07-11 | 10 - Complete | 2024-08-01
[8 empty] | HS2-00002CT37 - Small Dean South Embankment Boundary Perimeter Fence Line | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002CT37 | 2024-07-23 | 10 - Complete | 2024-08-08
[8 empty] | HS2-00002CT39 - Small Dean South Embankment Security Fence Line | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002CT39 | 2024-07-23 | 10 - Complete | 2024-08-08
[8 empty] | HS2-00002CT3Q - C2.L.14 Catchment | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002CT3Q | 2024-07-09 | 10 - Complete | 2024-07-26
[8 empty] | HS2-00002EK6M - Wendover Rail Systems Compound UTX | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002EK6M | 2024-07-16 | 10 - Complete | 2024-07-25
[8 empty] | HS2-00002WUK2 - Small Dean South Embankment Planting-East Plot 1 | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002WUK2 | 2024-08-06 | 10 - Complete | 2024-08-08
[8 empty] | HS2-00002WUK3 - Small Dean South Embankment Planting-East Plot 2 | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002WUK3 | 2024-08-06 | 10 - Complete | 2024-08-08
[8 empty] | HS2-00002WUK4 - Small Dean South Embankment Planting-East Plot 3 | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002WUK4 | 2024-08-06 | 10 - Complete | 2024-08-08
[8 empty] | HS2-00002WUK5 - Small Dean South Embankment Planting-East Plot 4 | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002WUK5 | 2024-08-06 | 10 - Complete | 2024-08-08
[8 empty] | HS2-00002WUK6 - Small Dean South Embankment Planting-West Plot 1 | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002WUK6 | 2024-08-06 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00002WUK7 - Small Dean South Embankment Planting-West Plot 2 | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002WUK7 | 2024-08-06 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00002WUK8 - Small Dean South Embankment Planting-West Plot 3 | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002WUK8 | 2024-08-06 | 10 - Complete | 2024-08-09
[8 empty] | HS2-00002WUK9 - Small Dean South Embankment Planting-West Plot 4 | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002WUK9 | 2024-08-06 | 10 - Complete | 2024-08-08
[8 empty] | HS2-00002WUKA - Small Dean South Embankment Planting-West Plot 5 | IDR 202.4-2 - Small Dean South Embankment fencing and landscaping | IDR 202.4-2 | HS2-00002WUKA | 2024-08-06 | 10 - Complete | 2024-08-08
[8 empty] | HS2-000001021 - Small Dean South Embankment | IDR 202.4-1 - Small Dean South Embankment (remainder) | IDR 202.4-1 | HS2-000001021 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVEM - Small Dean South Embankment Landscape Earthworks | IDR 202.4-1 - Small Dean South Embankment (remainder) | IDR 202.4-1 | HS2-00002BVEM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT2Z - Rocky Lane Cutting Boundary Perimeter Fence Line | IDR 202.3-2 - Rocky Lane Cutting Fencing and Landscaping | IDR 202.3-2 | HS2-00002CT2Z | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT31 - Rocky Lane Cutting Security Fence Line | IDR 202.3-2 - Rocky Lane Cutting Fencing and Landscaping | IDR 202.3-2 | HS2-00002CT31 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUJY - Rocky Lane Cutting Planting-East Lineside Plot 1 | IDR 202.3-2 - Rocky Lane Cutting Fencing and Landscaping | IDR 202.3-2 | HS2-00002WUJY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUJZ - Rocky Lane Cutting Planting-West Lineside Plot 1 | IDR 202.3-2 - Rocky Lane Cutting Fencing and Landscaping | IDR 202.3-2 | HS2-00002WUJZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUK0 - Rocky Lane Cutting Planting-East Plot 1 | IDR 202.3-2 - Rocky Lane Cutting Fencing and Landscaping | IDR 202.3-2 | HS2-00002WUK0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUK1 - Rocky Lane Cutting Planting-West Plot 1 | IDR 202.3-2 - Rocky Lane Cutting Fencing and Landscaping | IDR 202.3-2 | HS2-00002WUK1 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001020 - Rocky Lane Cutting | IDR 202.3 - Rocky Lane Cutting & Mitigation Earthworks | IDR 202.3 | HS2-000001020 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BVEJ - Rocky Lane Cutting Landscape Earthworks | IDR 202.3 - Rocky Lane Cutting & Mitigation Earthworks | IDR 202.3 | HS2-00002BVEJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003H07D - Small Dean Viaduct Network Rail Cutting Reinstatement-West | IDR 202.1-3 - Small Dean Viaduct Network Rail Cutting Reinstatement | IDR 202.1-3 | HS2-00003H07D | 2024-11-15 | 10 - Complete | 2024-12-10
[8 empty] | HS2-00003H07E - Small Dean Viaduct Network Rail Cutting Reinstatement-East | IDR 202.1-3 - Small Dean Viaduct Network Rail Cutting Reinstatement | IDR 202.1-3 | HS2-00003H07E | 2024-11-15 | 10 - Complete | 2024-12-10
[8 empty] | HS2-00003J169 - MCJ2 Network Rail Boundary Fencing (East) | IDR 202.1-3 - Small Dean Viaduct Network Rail Cutting Reinstatement | IDR 202.1-3 | HS2-00003J169 | 2024-11-21 | 10 - Complete | 0
[8 empty] | HS2-00003J16A - MCJ2 Network Rail Boundary Fencing (West) | IDR 202.1-3 - Small Dean Viaduct Network Rail Cutting Reinstatement | IDR 202.1-3 | HS2-00003J16A | 2024-11-21 | 10 - Complete | 0
[8 empty] | HS2-00002BJRC - A413 London Road Realignment | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00002BJRC | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT3E - Maintenance Access Road to Pond (P-RAI-0522) | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00002CT3E | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4Y8 - Boswells Farm Access Road Realignment | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00002J4Y8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002C3W6 - A413 London Road Drainage System | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00002C3W6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKB - Small Dean Viaduct Planting-Plot 1 | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00002WUKB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKC - Small Dean Viaduct Planting-Plot 2 | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00002WUKC | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKD - Small Dean Viaduct Planting-Plot 3 | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00002WUKD | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKE - Small Dean Viaduct Planting-Plot 4 | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00002WUKE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKF - Small Dean Viaduct Planting-Plot 5 | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00002WUKF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUKG - Small Dean Viaduct Planting-Plot 6 | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00002WUKG | #N/A | #N/A | #N/A
[8 empty] | HS2-000031CVR - Hale Bridge Parapet Extension | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-000031CVR | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D9CH - Small Dean Viaduct Landscape Terracing (East of A413) | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00003D9CH | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D9CJ - Small Dean Viaduct Landscape Paving (East of A413) | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00003D9CJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D9CK - Small Dean Viaduct Landscape Terracing (West of A413) | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00003D9CK | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D9CL - Small Dean Viaduct Landscape Paving (West of A413) | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00003D9CL | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D9CM - Small Dean Viaduct Landscape Terracing (North) | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00003D9CM | #N/A | #N/A | #N/A
[8 empty] | HS2-00003D9CN - Small Dean Viaduct Landscape Paving (North) | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00003D9CN | #N/A | #N/A | #N/A
[8 empty] | HS2-00003FV0L - Small Dean Viaduct Boundary Perimeter Fencing | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00003FV0L | #N/A | #N/A | #N/A
[8 empty] | HS2-00003FV0M - Small Dean Viaduct Security Fencing | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00003FV0M | #N/A | #N/A | #N/A
[8 empty] | HS2-00003KFQ1 - C2.L.14A Catchment | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00003KFQ1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003LA5B - Small Dean Viaduct (Pier P4) Access Stairs | IDR 202.1-2 - A413 London Road Realignment, Boswells Farm and Highway Drainage, Terracing, Fencing and Landscape Planting | IDR 202.1-2 | HS2-00003LA5B | #N/A | #N/A | #N/A
[8 empty] | HS2-000001022 - Small Dean Viaduct | IDR 202.1-1 - Small Dean Viaduct | IDR 202.1-1 | HS2-000001022 | 2024-07-12 | 99 - Cancelled | 0
[8 empty] | HS2-00002CT2E - C2.L.9 Catchment | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002CT2E | 2024-07-02 | 10 - Complete | 2024-07-16
[8 empty] | HS2-00002CT2Q - Wendover Dean South Embankment Boundary Perimeter Fence Line | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002CT2Q | 2024-07-02 | 10 - Complete | 2024-07-10
[8 empty] | HS2-00002CT2S - Wendover Dean South Embankment Security Fence Line | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002CT2S | 2024-07-02 | 10 - Complete | 2024-07-10
[8 empty] | HS2-00002BVEA - C2.L.10 Catchment | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002BVEA | 2024-07-02 | 10 - Complete | 2024-07-16
[8 empty] | HS2-00002CT2V - Wendover Dean North Embankment Boundary Perimeter Fence Line | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002CT2V | 2024-07-02 | 10 - Complete | 2024-07-10
[8 empty] | HS2-00002CT2X - Wendover Dean North Embankment Security Fence Line | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002CT2X | 2024-07-02 | 10 - Complete | 2024-07-10
[8 empty] | HS2-00002WUJM - Wendover Dean South Embankment Planting-Plot 1 | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002WUJM | 2024-07-23 | 10 - Complete | 2024-07-25
[8 empty] | HS2-00002WUJN - Wendover Dean South Embankment Planting-Plot 2 | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002WUJN | 2024-07-23 | 10 - Complete | 2024-07-25
[8 empty] | HS2-00002WUJP - Wendover Dean South Embankment Planting-Plot 3 | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002WUJP | 2024-07-23 | 10 - Complete | 2024-07-25
[8 empty] | HS2-00002WUJQ - Wendover Dean South Embankment Planting-Plot 4 | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002WUJQ | 2024-07-23 | 10 - Complete | 2024-07-25
[8 empty] | HS2-00002WUJR - Wendover Dean Viaduct Planting-Plot 1 | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002WUJR | 2024-07-23 | 10 - Complete | 2024-07-30
[8 empty] | HS2-00002WUJS - Wendover Dean Viaduct Planting-Plot 2 | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002WUJS | 2024-07-23 | 10 - Complete | 2024-07-26
[8 empty] | HS2-00002WUJU - Wendover Dean North Embankment Planting-East Plot 1 | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002WUJU | 2024-07-23 | 10 - Complete | 2024-07-26
[8 empty] | HS2-00002WUJV - Wendover Dean North Embankment Planting-East Plot 2 | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002WUJV | 2024-07-23 | 10 - Complete | 2024-07-29
[8 empty] | HS2-00002WUJW - Wendover Dean North Embankment Planting-West Plot 1 | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002WUJW | 2024-07-23 | 10 - Complete | 2024-07-29
[8 empty] | HS2-00002WUJX - Wendover Dean North Embankment Planting-West Plot 2 | IDR 202.0-3 - Wendover Dean Fencing and Landscape planting, Land Drainage and GSM-R Radio Compound | IDR 202.0-3 | HS2-00002WUJX | 2024-07-23 | 10 - Complete | 2024-07-29
[8 empty] | HS2-00002BJR0 - Bowood Lane Extension | IDR 202.0-2 - Bowood Lane Extension and Upper Wendover Dean Farm Footpath Realignment | IDR 202.0-2 | HS2-00002BJR0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJR3 - Upper Wendover Dean Farm Footpath and Private Access Realignment | IDR 202.0-2 - Bowood Lane Extension and Upper Wendover Dean Farm Footpath Realignment | IDR 202.0-2 | HS2-00002BJR3 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001017 - Wendover Dean South Embankment | IDR 202.0-1 - Wendover Dean Viaduct, Wendover Dean South and North Embankments | IDR 202.0-1 | HS2-000001017 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001018 - Wendover Dean Viaduct | IDR 202.0-1 - Wendover Dean Viaduct, Wendover Dean South and North Embankments | IDR 202.0-1 | HS2-000001018 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001019 - Wendover Dean North Embankment | IDR 202.0-1 - Wendover Dean Viaduct, Wendover Dean South and North Embankments | IDR 202.0-1 | HS2-000001019 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT27 - Grims Ditch North Retaining Wall | IDR 201.4 - Grims Ditch Retaining Wall | IDR 201.4 | HS2-00002CT27 | 2024-02-16 | 10 - Complete | 2024-02-22
[8 empty] | HS2-00002CT28 - Grims Ditch South Retaining Wall | IDR 201.4 - Grims Ditch Retaining Wall | IDR 201.4 | HS2-00002CT28 | 2024-02-16 | 10 - Complete | 2024-02-22
[8 empty] | HS2-00002BJQU - Dutch Lands Farm to Rushmoor Wood (TLE 2) Footpath Realignment | IDR 201.3-3 - Footpath TLE/2 Accommodation Highway Realignment | IDR 201.3-3 | HS2-00002BJQU | 2023-12-14 | 10 - Complete | 2024-01-12
[8 empty] | HS2-00002CW0U - Dutch Lands Farm to Rushmoor Wood (TLE 2) Drainage System | IDR 201.3-3 - Footpath TLE/2 Accommodation Highway Realignment | IDR 201.3-3 | HS2-00002CW0U | 2024-01-17 | 10 - Complete | 2024-01-19
[8 empty] | HS2-000001285 - Footpath TLE 2 Accommodation Overbridge | IDR 201.3-2 - Footpath TLE/2 Accommodation Overbridge | IDR 201.3-2 | HS2-000001285 | 2025-05-12 | 10 - Complete | 2025-05-22
[8 empty] | HS2-00002G16Z - South Heath Culvert | IDR 201.1 - South Heath Culvert | IDR 201.1 | HS2-00002G16Z | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT2H - Bowood Lane Drainage System | IDR 201.0-6 - Bowood Lane Realignment and Highway Drainage | IDR 201.0-6 | HS2-00002CT2H | 2024-05-01 | 10 - Complete | 2024-05-07
[8 empty] | HS2-00002BJQX - Bowood Lane Realignment | IDR 201.0-6 - Bowood Lane Realignment and Highway Drainage | IDR 201.0-6 | HS2-00002BJQX | 2024-05-01 | 10 - Complete | 2024-05-07
[8 empty] | HS2-000001398 - Bowood Lane Drop Inlet Culvert | IDR 201.0-5 - Bowood Lane Drop Inlet Culvert | IDR 201.0-5 | HS2-000001398 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001286 - Bowood Lane Overbridge | IDR 201.0-2 - Bowood Lane Overbridge | IDR 201.0-2 | HS2-000001286 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001016 - South Heath Cutting | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-000001016 | 2024-11-15 | 10 - Complete | 2024-11-29
[8 empty] | HS2-00002CT2D - C2.L.8 Catchment | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002CT2D | 2024-11-05 | 10 - Complete | 2024-11-29
[8 empty] | HS2-00002CT2G - C2.T.3 Catchment | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002CT2G | 2024-11-04 | 10 - Complete | 2024-11-29
[8 empty] | HS2-00002CT2K - Maintenance Access Road to Pond-0504 | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002CT2K | 2024-11-26 | 10 - Complete | 2024-12-02
[8 empty] | HS2-00002CT2L - South Heath Cutting Boundary Perimeter Fence Line | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002CT2L | 2024-11-26 | 10 - Complete | 0
[8 empty] | HS2-00002CT2N - South Heath Cutting Security Fence Line | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002CT2N | 2024-11-26 | 10 - Complete | 0
[8 empty] | HS2-000020N9Q - Maintenance Access Road to Bowood Lane Drop Inlet Culvert | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-000020N9Q | 2024-11-26 | 10 - Complete | 2024-11-29
[8 empty] | HS2-00002WUJ3 - South Heath Cutting Planting-East Plot 7 | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002WUJ3 | 2024-11-29 | 10 - Complete | 2024-12-05
[8 empty] | HS2-00002WUJ5 - South Heath Cutting Planting-East Plot 9 | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002WUJ5 | 2024-11-28 | 10 - Complete | 2024-12-03
[8 empty] | HS2-00002WUJ6 - South Heath Cutting Planting-East Plot 10 | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002WUJ6 | 2024-11-28 | 10 - Complete | 2024-12-04
[8 empty] | HS2-00002WUJ7 - South Heath Cutting Planting-East Plot 11 | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002WUJ7 | 2024-11-28 | 10 - Complete | 2024-12-04
[8 empty] | HS2-00002WUJ8 - South Heath Cutting Planting-East Plot 12 | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002WUJ8 | 2024-11-28 | 10 - Complete | 2024-12-04
[8 empty] | HS2-00002WUJF - South Heath Cutting Planting-West Plot 7 | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002WUJF | 2024-11-29 | 10 - Complete | 2024-12-05
[8 empty] | HS2-00002WUJG - South Heath Cutting Planting-West Plot 8 | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002WUJG | 2024-11-29 | 10 - Complete | 2024-12-05
[8 empty] | HS2-00002WUJH - South Heath Cutting Planting-West Plot 9 | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002WUJH | 2024-11-28 | 10 - Complete | 2024-12-04
[8 empty] | HS2-00002WUJJ - South Heath Cutting Planting-West Plot 10 | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002WUJJ | 2024-11-28 | 10 - Complete | 2024-12-04
[8 empty] | HS2-00002WUJK - South Heath Cutting Planting-West Plot 11 | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002WUJK | 2024-11-28 | 10 - Complete | 2024-12-04
[8 empty] | HS2-00002WUJL - South Heath Cutting Planting-West Plot 12 | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002WUJL | 2024-11-28 | 10 - Complete | 2024-12-04
[8 empty] | HS2-00002XQ2N - South Heath Cutting Landscape Earthworks-Bowood Lane East | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002XQ2N | 2024-11-15 | 10 - Complete | 2024-11-29
[8 empty] | HS2-00002XQ2P - South Heath Cutting Landscape Earthworks-Bowood Lane West | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002XQ2P | 2024-11-29 | 10 - Complete | 2024-12-03
[8 empty] | HS2-00002Y849 - South Heath Cutting Perturbation Crossover UTX | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00002Y849 | 2024-11-06 | 10 - Complete | 2024-11-27
[8 empty] | HS2-00003JN84 - Access Road to Bowood Lane Radio Compound | IDR 201.0-1 - South Heath Cutting and C2.T.3 | IDR 201.0-1 | HS2-00003JN84 | 2024-11-26 | 10 - Complete | 2024-12-02
[8 empty] | HS2-000020CDA - CSO-01-1101 | IDR 0001 - Multiple WP | IDR 0001 | HS2-000020CDA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWF1 - CFA_09_54 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWF1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWF6 - CFA_09_59 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWF6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWEY - CFA_09_51 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWEY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWF2 - CFA_09_55 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWF2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWF5 - CFA_09_58 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWF5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWF7 - CFA_09_60 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWF7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002PXE6 - South Heath Cutting_Frith Hill_Residence 1 Demolition | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002PXE6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002PXE7 - South Heath Cutting_Frith Hill_Residence 2 Demolition | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002PXE7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWEZ - CFA_09_52 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWEZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWF3 - CFA_09_56 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWF3 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSE4 - CFA_09_54_Elwis Field Farm_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSE4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSE5 - CFA_09_58_Chiltern Cottage_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSE5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSE6 - CFA_09_59_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSE6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSE7 - CFA_09_52_Frith Hill_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSE7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSE8 - CFA_09_56_Orchard Cottage_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSE8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSE9 - CFA_09_60_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSE9 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSEA - CFA_09_55_Weights and Measures_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSEA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWF4 - CFA_09_57 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWF4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSEB - CFA_09_51_Frith Hill_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSEB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002PRX6 - Footpath GMI 13 Diversion | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002PRX6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSEC - CFA_09_53_Frith Hill_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSEC | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSED - CFA_09_57_Bury House Farm_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSED | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWF0 - CFA_09_53 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWF0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT29 - C2.L.2 Catchment | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002CT29 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT2A - C2.L.4 Catchment | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002CT2A | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT2B - C2.L.6 Catchment | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002CT2B | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT2C - C2.L.7 Catchment | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002CT2C | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT2F - C2.T.1 Catchment | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002CT2F | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT2J - Leather Lane Drainage System | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002CT2J | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT2M - South Heath Cutting Noise Barrier Line | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002CT2M | #N/A | #N/A | #N/A
[8 empty] | HS2-00002PRX4 - Maintenance Access Road to Pond C2.T.1-PND-0476 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002PRX4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWEW - CFA_09_07a | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWEW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKWZ - Stockings Wood Ecological Mitigation Site | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002EKWZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJQE - Park Farm Footpath GMI 12 Realignment | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002BJQE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWF8 - CFA_09_61 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWF8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWF9 - CFA_09_62 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWF9 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001281 - Footpath GMI 12 Overbridge | IDR 0001 - Multiple WP | IDR 0001 | HS2-000001281 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSEF - CFA_09_61_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSEF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSEG - CFA_09_62_Mulberry Park Hill_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSEG | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSEH - CFA_09_07a_Mulberry Park Hill_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSEH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKX0 - Havenfield wood Ecological Mitigation Site | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002EKX0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWFA - CFA_09_63 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWFA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWFB - CFA_09_64 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWFB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSEJ - CFA_09_64_Springfield Farm_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSEJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSEK - CFA_09_63_Silver Birches_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSEK | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWFE - CFA_10_02a | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWFE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKX1 - Havenfield Wood Overbridge (Footpath GMI 2) Ecological Mitigation Site | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002EKX1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJQK - GMI 2 1 Footpath East Arm Diversion | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002BJQK | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJQL - GMI 2 1 Footpath West Arm Diversion | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002BJQL | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TMEL - Leather Lane MPATS Telecoms | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002TMEL | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4YZ - Maintenance Access Road to Pond-0485 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002J4YZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWFY - CFA_10_58 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWFY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSEL - CFA_10_58_Hunts Green Chase-North Lodge_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSEL | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJQN - Havenfield Wood Lodge GMI 2 and Accommodation Access Realignment | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002BJQN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKX2 - Leather Lane Ecological Mitigation Site | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002EKX2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSEM - CFA_10_02a_Springfield Farm Hammonds Hall Farm_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSEM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSPJ - CFA_10_02a_Springfield Farm Hammonds Hall Farm_Topsoil Strip Asset_Priority 2 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSPJ | #N/A | #N/A | #N/A
[8 empty] | HS2-000001282 - Footpath GMI 2 Accommodation Overbridge | IDR 0001 - Multiple WP | IDR 0001 | HS2-000001282 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CW0Y - Footpath GMI 2 Drainage System | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002CW0Y | #N/A | #N/A | #N/A
[8 empty] | HS2-000001396 - Havenfield Wood Drop Inlet Culvert | IDR 0001 - Multiple WP | IDR 0001 | HS2-000001396 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020N9C - Maintenance Access Road to Pond-0489 | IDR 0001 - Multiple WP | IDR 0001 | HS2-000020N9C | #N/A | #N/A | #N/A
[8 empty] | HS2-00002BJQQ - Leather Lane Realignment | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002BJQQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4Y6 - Maintenance Access Road to South Heath MPATS | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002J4Y6 | #N/A | #N/A | #N/A
[8 empty] | HS2-000001283 - Leather Lane Overbridge | IDR 0001 - Multiple WP | IDR 0001 | HS2-000001283 | #N/A | #N/A | #N/A
[8 empty] | HS2-000020C7G - South Heath MPATS | IDR 0001 - Multiple WP | IDR 0001 | HS2-000020C7G | #N/A | #N/A | #N/A
[8 empty] | HS2-000001397 - Leather Lane Drop Inlet Culvert | IDR 0001 - Multiple WP | IDR 0001 | HS2-000001397 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT25 - Leather Lane Overbridge-Worksite | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002CT25 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EK6J - Leather Lane South Heath Rail Systems compound (MPATS) UTX | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002EK6J | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TG32 - NRT GSM-R Compound Point 18 5595 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002TG32 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKYA - Hunts Green Farmhouse Listed Building | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002EKYA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002EKYB - Barn North of Hunts Green Farmhouse Listed Building | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002EKYB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT2P - CSO-02-6300P | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002CT2P | #N/A | #N/A | #N/A
[8 empty] | HS2-00002U4N8 - Wendover Dean Radio Compound | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002U4N8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TG35 - NRT GSM-R Compound Point 23 5598T | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002TG35 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CUW5 - Wendover Green Tunnel (South Portal)-Worksite | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002CUW5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TTHA - Wendover Green Tunnel Group Monitoring System | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002TTHA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSF8 - CFA_10_60_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSF8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWG0 - CFA_10_60 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWG0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWGE - CFA_10_74 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWGE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWGG - CFA_10_76 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWGG | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWGH - CFA_10_77 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWGH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSF9 - CFA_10_74_36 Ellesborough Road_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSF9 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSFA - CFA_10_77_30 Ellesborough Road_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSFA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSNJ - CFA_10_74_36 Ellesborough Road_Topsoil Strip Asset_Priority 1 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSNJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSNM - CFA_10_77_30 Ellesborough Road_Topsoil Strip Asset_Priority 1 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSNM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSFB - CFA_10_72_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSFB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSNG - CFA_10_72_Topsoil Strip Asset_Priority 1 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSNG | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSFC - CFA_10_73_Coombe Cottage_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSFC | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSFD - CFA_10_75_34 Ellesborough Road_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSFD | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSFE - CFA_10_76_32 Ellesborough Road_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSFE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSNH - CFA_10_73_Coombe Cottage_Topsoil Strip Asset_Priority 1 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSNH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSNK - CFA_10_75_34 Ellesborough Road_Topsoil Strip Asset_Priority 1 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSNK | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSNL - CFA_10_76_32 Ellesborough Road_Topsoil Strip Asset_Priority 1 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSNL | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWGC - CFA_10_72 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWGC | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWGD - CFA_10_73 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWGD | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWGF - CFA_10_75 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWGF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWFW - CFA_10_56 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWFW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSFF - CFA_10_56_Ellesborough Road_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSFF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSNE - CFA_10_56_Ellesborough Road_Topsoil Strip Asset_Priority 1 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSNE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSFG - CFA_10_78_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSFG | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSNN - CFA_10_78_Topsoil Strip Asset_Priority 1 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSNN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWGJ - CFA_10_78 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWGJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSFH - CFA_10_57_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSFH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSNF - CFA_10_57_Topsoil Strip Asset_Priority 1 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSNF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWFX - CFA_10_57 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWFX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002RWFU - CFA_10_54 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002RWFU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSFJ - CFA_10_54_Corneycroft Farm Ellesborough Road_Topsoil Stripping Asset | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSFJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002QSND - CFA_10_54_Corneycroft Farm Ellesborough Road_Topsoil Strip Asset_Priority 1 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002QSND | #N/A | #N/A | #N/A
[8 empty] | HS2-00002CT47 - Wendover Green Tunnel (North portal) Compound | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002CT47 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002TG36 - NRT GSM-R Compound Point 24 5599T | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002TG36 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUHX - South Heath Cutting Planting-East Plot 1 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002WUHX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUHY - South Heath Cutting Planting-East Plot 2 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002WUHY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUHZ - South Heath Cutting Planting-East Plot 3 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002WUHZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUJ0 - South Heath Cutting Planting-East Plot 4 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002WUJ0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUJ1 - South Heath Cutting Planting-East Plot 5 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002WUJ1 | 2024-11-29 | 10 - Complete | 2024-12-05
[8 empty] | HS2-00002WUJ2 - South Heath Cutting Planting-East Plot 6 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002WUJ2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUJ4 - South Heath Cutting Planting-East Plot 8 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002WUJ4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUJ9 - South Heath Cutting Planting-West Plot 1 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002WUJ9 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUJA - South Heath Cutting Planting-West Plot 2 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002WUJA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUJB - South Heath Cutting Planting-West Plot 3 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002WUJB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUJC - South Heath Cutting Planting-West Plot 4 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002WUJC | #N/A | #N/A | #N/A
[8 empty] | HS2-00002WUJD - South Heath Cutting Planting-West Plot 5 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002WUJD | 2024-11-29 | 10 - Complete | 2024-12-05
[8 empty] | HS2-00002WUJE - South Heath Cutting Planting-West Plot 6 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002WUJE | 2024-11-29 | 10 - Complete | 2024-12-05
[8 empty] | HS2-00002XQ2E - South Heath Cutting Landscape Earthworks-Tunnel | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002XQ2E | #N/A | #N/A | #N/A
[8 empty] | HS2-00002XQ2F - South Heath Cutting Landscape Earthworks-Portal Access Road | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002XQ2F | #N/A | #N/A | #N/A
[8 empty] | HS2-00002XQ2G - South Heath Cutting Landscape Earthworks-GMI 2 East | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002XQ2G | #N/A | #N/A | #N/A
[8 empty] | HS2-00002XQ2H - South Heath Cutting Landscape Earthworks-GMI 2 West | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002XQ2H | #N/A | #N/A | #N/A
[8 empty] | HS2-00002XQ2J - South Heath Cutting Landscape Earthworks-Leather Lane East | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002XQ2J | #N/A | #N/A | #N/A
[8 empty] | HS2-00002XQ2K - South Heath Cutting Landscape Earthworks-Leather Lane West | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002XQ2K | #N/A | #N/A | #N/A
[8 empty] | HS2-00002XQ2L - South Heath Cutting Landscape Earthworks-Cottage Farm South | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002XQ2L | #N/A | #N/A | #N/A
[8 empty] | HS2-00002XQ2M - South Heath Cutting Landscape Earthworks-TLE 2 South | IDR 0001 - Multiple WP | IDR 0001 | HS2-00002XQ2M | #N/A | #N/A | #N/A
[8 empty] | HS2-000033GN0 - Maintenance Access Road to Pond C2.T.1-PND-0476 Drainage System | IDR 0001 - Multiple WP | IDR 0001 | HS2-000033GN0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00003CCJW - Footpath link between PRoW GMI 12 1 and GMI 13 3 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00003CCJW | #N/A | #N/A | #N/A
[8 empty] | HS2-00003CPYW - South Heath Cutting Ditch Slab No.1 | IDR 0001 - Multiple WP | IDR 0001 | HS2-00003CPYW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002J4YY - Footpath SM33 Diversion-upgrade to bridleway (east of HS2) | HP-124 - Warwickshire County Council | HP-124 | HS2-00002J4YY | 2024-11-12 | 10 - Complete | 2024-11-21
[8 empty] | HS2-00002TKV3 - Banbury Road Radio Compound UTX | HP-089 - HS2-00002C5UT - Ladbroke Cutting Group | HP-089 | HS2-00002TKV3 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZ2 - Turweston Embankment GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZ2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZ3 - Turweston Viaduct GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZ3 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZ4 - Helmdon Embankment GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZ4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZ5 - Brackley South Cutting GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZ5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZ6 - Brackley Embankment GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZ6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZ7 - Brackley North Cutting GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZ7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZ8 - Greatworth South Embankment GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZ8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZ9 - Greatworth South Cutting GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZ9 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZA - Greatworth North Embankment GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZB - Greatworth North Cutting GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZC - Greatworth Green Tunnel GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZC | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZD - Thorpe Mandeville Embankment GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZD | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZE - Lower Thorpe Viaduct GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZF - Lower Thorpe South Embankment GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZG - Lower Thorpe South Cutting GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZG | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZH - Lower Thorpe North Embankment GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZH | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZJ - Lower Thorpe North Cutting GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZK - Culworth Embankment GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZK | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZL - Culworth Cutting GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZL | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZM - Edgcote South Embankment GI Work Extents | GI 0007 - C3 South GI Works (Stage Two) | GI 0007 | HS2-00002DRZM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZN - Edgcote Viaduct GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DRZN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZP - Edgcote North Embankment GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DRZP | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZQ - Edgcote Cutting GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DRZQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZR - Chipping Warden Green Tunnel GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DRZR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZS - Aston le Walls Embankment GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DRZS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZT - Highfurlong Brook Viaduct GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DRZT | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZU - Highfurlong Brook Embankment GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DRZU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZV - Lower Boddington Cutting GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DRZV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZW - Lower Boddington Embankment GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DRZW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZX - Boddington Cutting GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DRZX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZY - Oxford Canal South Embankment GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DRZY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZZ - Oxford Canal Viaduct GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DRZZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DS00 - Oxford Canal North Embankment GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DS00 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DS01 - Lower Radbourne South Viaduct GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DS01 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DS02 - Upper Radbourne Embankment GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DS02 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DS03 - Lower Radbourne North Viaduct GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DS03 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DS04 - Lower Radbourne Embankment GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DS04 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DS05 - Ladbroke Grove Cutting GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DS05 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DS06 - Ladbroke Grove Embankment GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DS06 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DS07 - Ladbroke Cutting GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DS07 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DS08 - Southam Embankment GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DS08 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DS09 - Southam Cutting GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DS09 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DS0A - Mill Pond Embankment GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DS0A | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DS0B - River Itchen Viaduct GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DS0B | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DS0C - Leamington Road Embankment GI Work Extents | GI 0006 - C3 North GI Works (Stage Two) | GI 0006 | HS2-00002DS0C | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRXM - South Heath Cutting GI Work Extents | GI 0004 - C2 South GI Works (Stage Two) | GI 0004 | HS2-00002DRXM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRXN - Wendover Dean South Embankment GI Work Extents | GI 0004 - C2 South GI Works (Stage Two) | GI 0004 | HS2-00002DRXN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRXP - Wendover Dean Viaduct GI Work Extents | GI 0004 - C2 South GI Works (Stage Two) | GI 0004 | HS2-00002DRXP | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRXQ - Wendover Dean North Embankment GI Work Extents | GI 0004 - C2 South GI Works (Stage Two) | GI 0004 | HS2-00002DRXQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRXR - Rocky Lane Cutting GI Work Extents | GI 0004 - C2 South GI Works (Stage Two) | GI 0004 | HS2-00002DRXR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRXS - Small Dean South Embankment GI Work Extents | GI 0004 - C2 South GI Works (Stage Two) | GI 0004 | HS2-00002DRXS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRXT - Small Dean Viaduct GI Work Extents | GI 0004 - C2 South GI Works (Stage Two) | GI 0004 | HS2-00002DRXT | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRXU - Small Dean North Embankment GI Work Extents | GI 0004 - C2 South GI Works (Stage Two) | GI 0004 | HS2-00002DRXU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRXV - Wendover Green Tunnel GI Work Extents | GI 0004 - C2 South GI Works (Stage Two) | GI 0004 | HS2-00002DRXV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRXW - Wendover North Cutting GI Work Extents | GI 0004 - C2 South GI Works (Stage Two) | GI 0004 | HS2-00002DRXW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRXX - Stoke Mandeville South Embankment GI Work Extents | GI 0004 - C2 South GI Works (Stage Two) | GI 0004 | HS2-00002DRXX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYJ - Twyford Embankment GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYJ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYK - Twyford Viaduct GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYK | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYL - Cowley Embankment GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYL | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYM - Twyford Cutting GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYM | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYN - Godington East Embankment GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYN | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYP - Godington East Viaduct GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYP | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYQ - Godington West Embankment GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYQ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYR - Godington West Viaduct GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYR | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYS - Chetwode Embankment GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYS | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYT - Chetwode Cutting GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYT | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYU - Barton Hartshorn Embankment GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYU | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYV - Barton to Mixbury Cutting GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYV | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYW - Mixbury Embankment GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYW | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYX - Mixbury Cutting GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYX | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYY - Westbury Embankment GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYZ - Westbury Viaduct GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRYZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZ0 - Grovehill Embankment GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRZ0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRZ1 - Turweston Cutting GI Work Extents | GI 0003 - C2 North GI Works (Stage Two) | GI 0003 | HS2-00002DRZ1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRXY - Aylesbury South Cutting GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRXY | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRXZ - Aylesbury Embankment GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRXZ | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRY0 - Aylesbury North Cutting GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRY0 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRY1 - Oxford Road Embankment GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRY1 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRY2 - Whaddon Hill Cutting GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRY2 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRY3 - Thame Valley South Embankment GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRY3 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRY4 - Thame Valley Viaduct GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRY4 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRY5 - Thame Valley North Embankment GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRY5 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRY6 - Putlowes Cutting GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRY6 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRY7 - Bicester Road Embankment GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRY7 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRY8 - Waddesdon South Cutting GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRY8 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRY9 - Waddesdon Embankment GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRY9 | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYA - Waddesdon North Cutting GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRYA | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYB - Quainton South Embankment GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRYB | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYC - Quainton Cutting GI Work Extents | GI 0002 - C2 Central GI Works (Stage Two) | GI 0002 | HS2-00002DRYC | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYD - Doddershall Embankment GI Work Extents | GI 0001 - C2 Calvert GI Works (Stage Two) | GI 0001 | HS2-00002DRYD | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYE - Woodlands Cutting GI Work Extents | GI 0001 - C2 Calvert GI Works (Stage Two) | GI 0001 | HS2-00002DRYE | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYF - Grendon Underwood Embankment GI Work Extents | GI 0001 - C2 Calvert GI Works (Stage Two) | GI 0001 | HS2-00002DRYF | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYG - Calvert Cutting GI Work Extents | GI 0001 - C2 Calvert GI Works (Stage Two) | GI 0001 | HS2-00002DRYG | #N/A | #N/A | #N/A
[8 empty] | HS2-00002DRYH - Calvert Infrastructure Maintenance Depot GI Work Extents | GI 0001 - C2 Calvert GI Works (Stage Two) | GI 0001 | HS2-00002DRYH | #N/A | #N/A | #N/A
Formulas:
Request Date = MAXIFS(Central_Team!G:G,Central_Team!C:C,TrackerTbl[[#This Row],[UAID_2]])
CompletedDate = INDEX(MainTracker[#Data],MATCH(1,(TrackerTbl[[#This Row],[UAID_2]]=MainTracker[UAID_2])*(TrackerTbl[[#This Row],[Request Date]]=MainTracker[Request sent on (Date)])*1,0),9)
CompletedDate = INDEX(TrackerTbl[#Data],MATCH(Table58[[#This Row],[[Package]]],TrackerTbl[Cleansed_UAID_2],0),7)
Date received = INDEX(TrackerTbl[#Data],MATCH(Table58[[#This Row],[[Package]]],TrackerTbl[Cleansed_UAID_2],0),5)
Date received = INDEX(TrackerTbl[#Data],MATCH(Table58[[#This Row],[[Package, row above]]],TrackerTbl[Cleansed_UAID_2],0),5)
Note on J143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Withdrawn asset